## Slide 1: TGaq Closing Report
Date: 2015-11-12
Authors:

## Slide 2: Abstract
Closing report for TGaq (Pre-Association Discovery) for November 2015, Dallas, TX, USA.

## Slide 3
LB216 Comment Resolution Analysis
  92.66% approval, 400 comments, 72.63% return.
  156 editorial and 215 technical comments remaining open
  Resolved 29 technical comments this week
Discussion topics
    Probe Request/Response query mechanism
    Architecture
    Use of ANQP
Teleconferences
  Roughly 1 every two weeks between now and January 2016 meeting
  1 joint teleconference with ARC
Plans for January 2016
  Continue to work on comment resolutions from LB216