## Slide 1: IEEE 802 JTC1 SC closing report (Nov 2015)
Date: 2015-11-13
Authors:

## Slide 2: Abstract
Closing report for IEEE 802 JTC1 SC for Nov 2015 in Dallas

## Slide 3: The SC did not have a great deal of work this week and only one session was required
Reviewed status of PSDO pipeline
  802 passed FDIS
  802.1BA and 802.1BR passed 60 day pre-ballot
  Responses comments were discussed and will be approved by 802.1 WG
  802.22a, 802.22b will be submitted to FDIS
  802.3bx will be submitted to FDIS soon
Reviewed agenda for SC6 meeting in Mar 2016
  It is likely that IEEE 802 will not have any reps
  Agenda is very light so far
  We will review submitted documents at January meeting

## Slide 4: IEEE 802 has pushed 16 standards completely through the PSDO ratification process …
802 standard | 60 day pre-ballot | 5 month FDIS ballot | Comments resolved
802.11 | 2012 | 2012 | Nov 2013
802.1X | 2013 | 21 Oct 2013 | Jan 2014
802.1AE | 2013 | 21 Oct 2013 | Jan 2014
802.1AB | May 2013 | 18 Dec 2013 | May 2014
802.1AR | May 2013 | 18 Dec 2013 | May 2014
802.1AS | May 2013 | 18 Dec 2013 | May 2014
802.3 | 2013 | 16 Feb 2014 | Not required
802.11aa | Feb 2013 | 28 Jan 2014 | July 2014
802.11ad | Feb 2013 | 28 Jan 2014 | July 2014
802.11ae | Feb 2013 | 28 Jan 2014 | July 2014
802.22 | May 2014 | Feb 2015 | Not required
802.1AEbw | Jan 2014 | Feb 2015 | Apr 2015
802.1AEbn | Jan 2014 | Feb 2015 | Apr 2015
802.3.1 | Oct 2014 | Jun 2015 | Apr 2015
802.11ac | Sep 2014 | Jul 2015 | Jul 2015
802.11af | Sep 2014 | Jul 2015 | Jul 2015

## Slide 5: … and has 9 standards in the pipeline for ratification under the PSDO
IEEE 802 standard | 60 day pre-ballot |  | 5 month FDIS ballot |  | Comments resolved
802 | Passed | Oct 2014 | Passed | 2 Nov 15 | Will be sent in Nov
802.1Xbx | Passed | 19 Mar 15 | Closes | 28 Jan 16 | Sent in Jun 2015
802.1Q-Rev | Passed | 13 Mar 15 | Closes | 28 Jan 16 | Sent in Jun 2015
802.1AX | Passed | 30 May 15 | Closes | 20 Nov 15 | No comments
802.1BA | Passed | 23 Sep 15 | - | - | Will be sent in Nov
802.1BR | Passed | 23 Sep 15 | - | - | Will be sent in Nov
802.22a | In process | - | - | - | -
802.22b | In process | - | - | - | -
802.3bx | In process |  |  |  | 

## Slide 6: The SC will focus in Atlanta on PSDO processes & prep’ing for next SC6 meeting
Continue executing PSDO processes
Prepare for next SC6 meeting