## Sheet1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
10747 | Hamilton, Mark | 1000 | 6 | 10.1.4.3.2 | 100 | 64 | T | Yes | 100 | 64 | 10.1.4.3.2 |  |  | Santosh Abraham |  |  | Something in the state machine doesn't make sense. A non-FILS STA (or a FILS STA after the dot11FILSProbeDelay times out) proceeds to step (c), (d) and then (e), after step (b). But, step (e) says as soon as CCA(busy) is seen (which includes upon the start of reception of any frame), to go to step (h). So, any Probe Response, Beacon, Measurement Pilot or FILS Discovery frame will cause an immediate (at the start of recption) transition to state (h). Thus, states (f) and (g) will never happen. I think step (e) was intended to be like steps (f) and (g), except with the ActiveScannerTimer limited to MinChannelTime instead of MaxChannelTime. Also, if still waiting in step (a) when a Probe Response, et al, comes in, again, the state machine should say to process the Probe Reposne, and if a FILS STA continue listening until MinChannelTime (so, similar to step (b)). | The state machine needs to be drawn out as a state machine, and checked for all the proper transitions and actions. It seems that some of the "steps" in this state flow are really supposed to be happening in parallel, perhaps, for example, which means a considerable restruturing of the "steps". This is too much to go into in a ballot comment, and needs off-line work. | Revised: Adopt changes in doc 16/0145r0 The resolution clarifies step j) in the procedure and would then nicely update the procedure given in REVmc. | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General
10637 | Montemurro, Michael | 1000 | 6 | 10.1.4.3.2 | 101 | 1 | T | Yes | 101 | 1 | 10.1.4.3.2 |  |  | Santosh Abraham |  |  | Why is f) restricted to non-FILS STAs | This behavior should be independent whether the STA is a FILS STA or not. | Reject: There is a difference in behavior for FILS and non-FILS STA. The actions for FILS STA are captured in g) which it includes the actions mentioned in f) along with some exceptions and further actions. Please note, in D6.3, the actions for FILS STA are mentioned in h) | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General
10636 | Montemurro, Michael | 1000 | 6 | 10.1.4.3.2 | 100 | 58 | T | Yes | 100 | 58 | 10.1.4.3.2 |  |  | Santosh Abraham |  |  | What does it mean to send "one or more Probe Request frames". How does the MAC know how to proceed? | Describe what how the MAC and SME interact to execute the primitive. | `Reject: The text is inherited from 802.11-2012 spec. Note: REVmc D5.0 has updated text for this section - please see pg 1564 line 4-9 | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General
10635 | Montemurro, Michael | 1000 | 6 | 10.1.4.3.2 | 100 | 41 | T | Yes | 100 | 41 | 10.1.4.3.2 |  |  | Santosh Abraham |  |  | As written, the "b" condition does not make sense. The MAC executes scanning procedures, but the SME would determine a suitable candidate STA (not AP). | Fix the description to more clearly describe the procedure to reflect proper procedures for a MAC and SME. As is, I can't understand what the actual intent is. | Revised: Adopt changes in doc 16/0143r0 | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General
10569 | EMMELMANN, MARC | 1000 | 6 | 10.47.3.3 | 123 | 62 | T | Yes | 123 | 62 | 10.47.3.3 |  |  | Santosh Abraham |  |  | "If the STA does not receive the FILS Container frame containing an IP assignment within the IP address request timeout period, then the STA may initiate an IP address assignment procedure using mechanisms that are out of scope of this specifica- tion." ---- what happens if the STA initiates an IP address assignment using other mechanisms, gets an IP, and the AP assigns afterwards a (different) IP address? | Insert a clarifying sentence to address the issue | Please adopt changes shown in doc 16/0140r1 Note: the resolution also applies to lines 18-22 on pg 125 | TGai General |  | submission required | Doc on mentor with resolution. |  |  |  | 2016-01-12 15:12 | TGai General
10122 | Malinen, Jouni | 1000 | 6 | 8.4.5.22 | 85 | 35 | T | Yes | 85 | 35 | 8.4.5.22 |  |  | Santosh Abraham |  |  | Incorrect Domain Identifier length is indicated in Figure 8-607d (FILS Domain Information ANQP-element format). These fields are defined as two octet fields in the referenced Figure 8-577n. | On page 85 line 35 (Figure 8-607d), replace the Domain Identifier #1 and #n field lengths "4" with "2". | Accept | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General
10058 | Malinen, Jouni | 1000 | 6 | 10.25.3.2.12 | 117 | 45 | T | No | 117 | 45 | 10.25.3.2.12 |  |  | Santosh Abraham |  |  | Exact value that should be used for the ANQP CAG Version increment does not need to be specified. | Replace "The ANQP CAG Version is a positive number that increases by 1 when" with "The ANQP CAG Version is a positive number and it is incremented when". | Accept | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General
10024 | Inoue, Yasuhiko | 1000 | 6 | 10.47.4 | 124 | 23 | T | Yes | 124 | 23 | 10.47.4 |  |  | Santosh Abraham |  |  | Wrong formula. | Remove ", 0, 15)". | Accept | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General
10002 | McCann, Stephen | 1000 | 6 | 8.4.5.22 | 85 | 29 | T | Yes | 85 | 29 | 8.4.5.22 |  |  | Santosh Abraham |  |  | What is the definition of the "IP Address Type"? Is this the same as the IP Address Data in 8.4.2.180.1? If not, it's not clear how the "IP Address Type " is used within the document and this needs to be defined. | Change "IP Address Type" to "IP Address Data" and add a forward reference to 8.4.2.180.1 | Revised: Adopt changes in doc 16/0139r2 Note: the resolution also applies to section 10.47.4 | TGai General |  | submission required |  |  |  |  | 2015-09-29 07:39 | TGai General