## Slide 1: IEEE 802.11mc Closing Report for January 2016
Date: 2016-01-21
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for January 2016.

## Slide 3: Status
Initial recirculation Sponsor Ballot underway, closes January 26th 2016
Considered available presentations related to comments in initial recirculation ballot
Agenda, includes motions
  https://mentor.ieee.org/802.11/dcn/15/11-15-1522-05-000m-tgmc-agenda-january-2016.pptx
Comment resolution spreadsheet
  https://mentor.ieee.org/802.11/dcn/15/11-15-0532-30-000m-revmc-sponsor-ballot-comments.xls

## Slide 4: TGmc Plan of Record - modified
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process CC input, 11aa, 11ae integration
Dec 2012 – March/May 2013 – 11ad integration
Jan 2013 – First WG Letter ballot - without 11ad – on D1.0
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jan 2015 – D4.0 Recirculation
Form Sponsor Pool: Open Dec 15th or so, close Feb 20, 2015 –good for 6 months (end of July 2015)
Initial Sponsor Ballot 2015-03-27 through 2015-04-26
Jan 2016 Initial SB recirculation
Feb 2016 BRC Ft. Lauderdale meeting
July 2016 – WG/EC Final Approval
September 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: TGmc SB Planning
Slide 5
Initial Sponsor Ballot 2015-03-27 through 2015-04-26 on D4.0
Jan 11-26 2016 Initial SB recirculation D5.0
  Teleconferences, Feb 22-25 2016 BRC Ft. Lauderdale meeting
  2nd recirculation on D6.0: March 2016
April/May 2016
  Comment resolution
  3rd recirculation April/May 2016 D6.0 unchanged or D7.0
  4th recirculation D7.0 unchanged if needed May/June 2016
  Revcom Submission date: 20 May 2016 for June 28-30 Revcom
  EC telecon approval June 2016
July 2016 – WG/EC Final Approval (if not in June 2016)
September 2016 – RevCom/SASB Approval (if not June 2016)
  Revcom Submission date: 05 Aug 2016 for Sept 16 Revcom teleconference
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 5

## Slide 6: Teleconferences and next steps
January -March
  Initial recirculation Sponsor Ballot comment resolution as Comment Resolution Committee
Conference Calls 10am Eastern (2 hours)
  February 5, 19
BRC meeting Feb 22-25, 2016
  Ft. Lauderdale, SR Technologies hosting
  Teleconference facilities will be provided