## Slide 1: Discussion on LRLP Timeline
Date: 2016-03-14
Authors:

## Slide 2: Contents of this Contribution
Review of Timelines for 2 Published Amendments
Review of Timelines for 2 In Process Amendments
LRLP Projected Timeline

## Slide 3: Growth of IoT till 2020
Reference: http://theconnectivist-img.s3.amazonaws.com/wp-content/uploads/2014/05/Unknown.png
(http://www.i-scoop.eu/internet-of-things/)
2020
2018

## Slide 4: 802.11ad Timeline
PAR approved: December 2008
Initial Working Group Letter Ballot: October 2010
Recirculation Working Group Letter Ballot: April 2011
Initial Sponsor Ballot: January 2012
Recirculation Sponsor Ballot: March 2012
Final Working Group Approval: July 2012
RevCom & Standards Board Final Approval: Oct 2012
Reference: http://www.ieee802.org/11/Reports/802.11_Timelines.htm
22 months
6 months
9 months

## Slide 5: 802.11ac Timeline
PAR approved: September 2008
Initial WG Letter Ballot : June 2011
Recirculation WG Letter Ballot: February 2012
Initial Sponsor Ballot: May 2013
Recirculation Sponsor Ballot: August 2013
Final Working Group Approval: November 2013
RevCom & SB approval: December 2013
8 months
33 months
15 months
Reference: http://www.ieee802.org/11/Reports/802.11_Timelines.htm

## Slide 6: 802.11ah Timeline
PAR approved: October 2010
Initial WG Letter Ballot: November 2013
Recirculation WG Letter Ballot: July 2014
Initial Sponsor Ballot: November 2015
Recirculation Sponsor Ballot: March 2016
Final Working Group Approval (predicted): July 2016
RevCom & SB approval (predicted): August 2016
38 months
8 months
Reference: http://www.ieee802.org/11/Reports/802.11_Timelines.htm
16 months

## Slide 7: 802.11ax Predicted Timeline
May 2014
HEW TG (IEEE 802.11ax)
Nov 2014 First TG SFD draft was approved
January 2016 Proposed TG Draft
July 2016
Draft 1.0
WG LB
March 2017
Draft 2.0
Recirculation
March 2019
Publication
March 2016 Draft 0.1 Approval and start of comment collection
May 2013
HEW SG
We are Here
26 months (between TG formation and Draft 1.0)
34 months (between TG formation and Draft 2.0)
Reference: Osama Aboul-Magd, “IEEE 802.11-16/1516r3,” January 2016

## Slide 8: LRLP Projected Timeline
July 2015
Sep 2015
Mar 2016
LRLP TIG approved [1]
LRLP TIG to work on report development
  Technical requirements, use cases
LRLP submits report in Mar 2016
May 2016
LRLP SG starts
Jan 2019
LRLP Draft 2.0
Discussion starts in WFA
LRLP Draft 1.0
July 2018
March 2018
March 2020
LRLP 1st Gen
Nov 2016
LRLP TG formation
Nov 2019
Initial Sponsor
Ballot
LRLP Draft 0.1
20 months
6 months
TG formation
(Sept 2008)
11ac Timeline
Draft 0.1
(Jan 2011)
Draft 1.0
(June 2011)
Draft 2.0
(Feb 2012)
Initial Sponsor
Ballot (May 2013)
33 months
8 months
15 months
9 months

## Slide 9: Discussion on Achieving LRLP Timeline
Efficient execution of LRLP amendment will enable subset of 50 billion devices to be 802.11 enabled by 2020
  LRLP 1st gen timeline of March 2020 will assist in developing battery-operated IoT devices for niche applications with winning edge over competing technologies
Decide on a limited set of features within the Study Group
  Focused PAR description
Delve deep in these limited features to achieve the requirements derived from selective use cases
Good quality of Draft 1.0 can lead to efficient and short comment resolution phase between Draft 1.0 and Draft 2.0 recirculation

## Slide 10: Conclusion
We have reviewed the timelines for published and in-process amendments
  802.11ad timeline
  802.11ac timeline
  802.11ah timeline
  802.11ax predicted timeline
We have presented a projected timeline for LRLP amendment

## Slide 11: References
[1] IEEE 11-15/0775r1: Integrated Long Range Low Power Operation for IoT