## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-16/0553r2
Venue Date: | May 2016
First Author: | Yunsong Yang (Huawei Technologies)
Subject: | LB219 Working Group Ballot Comments for 11aq Draft 4.0
Full Date: | 2016-5-18
Author(s): | Name(s) | Yunsong Yang
| Company | Huawei Technologies
Address
Phone:
Fax:
| email: | yangyunsong@huawei.com
Abstract:
The comment spreasheet for LB219 on the 11aq D4.0, produced after the Wednesday PM1 session.

## Revision History
Revision | Date | Description
0 | 2016-04-25 | Initial export after closing of letter ballot 219
1 | 2016-05-16 | Produced after the Monday PM2 session; updated per discussions on Monday PM1 and PM2 sessions.
2 | 2016-05-18 | Produced after the Wednesday PM1 session; updated per discussions on Wednesday PM1 session.

## LB219 All Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3001 | Adrian Stephens | 219 | 4 |  | 3 | 23 | T | Y | 3.23 | 23 |  |  | V |  |  |  | "Discovery of services offered by a PBSS, BSS, or an external network". A PBSS is a type of BSS, so it is already covered by "a BSS" | Globally replace "PBSS, BSS" by "BSS" (6 instances) | REVISED (GEN: 2016-05-17 00:45:15Z). At P3L23, delete "PBSS, ". And at P3L38, delete "PBSS or". And at P3L40, delete "PBSS or". And at P3L41, delete "PBSS or". And at P4L49, delete "PBSS or". And at P4L56, delete "PBSS or". And at P4L59, delete "PBSS or". | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3002 | Adrian Stephens | 219 | 4 |  | 4 | 17 | E | Y | 4.17 | 17 |  |  |  | Lee Armstrong |  |  | Figure 4-11a contains gratuitous shading, which doesn't reproduce well in the printed copy. | Remove shading. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3003 | Adrian Stephens | 219 | 4 |  |  |  | E | N | [5 empty] | Lee Armstrong |  |  | I have seen at least two instances of "e.g." without a comma. | Please ensure all "e.g." and "i.e." are followed by a comma. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3004 | Adrian Stephens | 219 | 4 |  |  |  | G | Y |  |  |  |  | J |  |  |  | Recent changes add "PCP" all over the place on the assumption that a PCP is "just like an AP". Well, there is a difference, the PCP has no DS - i.e., it is not connected to an infrastructure. So a PCP can advertise its own locally connected services, but not those of anything connected wirelessly to it. | Remove all mention of PCP and PBSS | REJECTED (GEN: 2016-05-17 03:13:07Z). The operation of PAD is not dependent on the presence of DS (i.e., infrastructure). Therefore, the PAD architecture still applies to a PCP and a PBSS. | GEN | 2016-05-18-pm1 | ready for motion | Change all instances of "AP or PCP" to "AP". Note to Editor: There are 35 instances. And at P3L23, delete "PBSS, ". And at P3L38, delete "PBSS or". And at P3L40, delete "PBSS or". And at P3L41, delete "PBSS or". And at P4L49, delete "PBSS or". And at P4L56, delete "PBSS or". And at P4L59, delete "PBSS or". |  |  |  | 2016-05-19 01:56 | GEN
3005 | Adrian Stephens | 219 | 4 |  | 22 | 19 | G | Y | 22.19 | 19 |  |  | V |  |  |  | "Number of Hash Functions field is equal to "0001"" - if this is an integer field, use an integer value, not an ambiguous bitstring/binary representation. | Replace "0001" with "1". | REVISED (GEN: 2016-05-17 00:30:47Z). Change ""0001"" to "binary value of 0001" at the cited location. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3006 | Adrian Stephens | 219 | 4 |  | 28 | 23 | G | Y | 28.23 | 23 |  |  |  | Lee Armstrong |  |  | The dot11Compliances namespace is administered by the 802.11 ANA | Replace the value 6 with <ANA> |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:33 | GEN
3007 | Yongho Seok | 219 | 4 | 11.25a.2 | 20 | 37 | T | N | 20.37 | 37 | 11.25a.2 |  | V |  |  |  | "When dot11UnsolicitedPADActivated is true, an AP or PCP shall advertise services using a Service Hint element or Service Hash element or both in Beacon or Probe Response frames." For the unsolicited PAD procedure of the PCP, the DMG Beacon and Announce frames should also contain the Service Hint element or Service Hash element. | Insert the Service Hint element or Service Hash element into Table 9-41 (DMG Beacon frame body) and Table 9-412 (Announce frame Action field format). Modify the P20 L37 sentence. | REVISED (GEN: 2016-05-17 03:26:00Z). Insert the Service Hint element and Service Hash element into Table 9-41 (DMG Beacon frame body) and Table 9-412 (Announce frame Action field format). Change "When dot11UnsolicitedPADActivated is true, an AP or PCP shall advertise services using a Service Hint element or Service Hash element or both in Beacon or Probe Response frames." to "When dot11UnsolicitedPADActivated is true, an AP shall advertise services using a Service Hint element or Service Hash element or both in Beacon or Probe Response frames." And add "When dot11UnsolicitedPADActivated is true, a PCP shall advertise services using a Service Hint element or Service Hash element or both in DMG Beacon or Announce frames." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3008 | Yongho Seok | 219 | 4 | 9.4.2.27 | 13 | 39 | E | N | 13.39 | 39 | 9.4.2.27 |  |  | Lee Armstrong |  |  | 10.26.3 is a wrong reference | Change 10.26.3 to 11.25a.3. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3009 | Yongho Seok | 219 | 4 | 9.4.2.27 | 13 | 42 | E | N | 13.42 | 42 | 9.4.2.27 |  |  | Lee Armstrong |  |  | 10.26.4 is a wrong reference | Change 10.26.4 to 11.25a.4. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3010 | Mark RISON | 219 | 4 | 9.4.2.216 | 13 | 53 | G | Y | 13.53 | 53 | 9.4.2.216 |  | V |  |  |  | "The Service Hint element contains information a Bloom filter that provides the probabilistic representation of a set of services." This statement is not clear. | Make the statement clearer | REVISED (GEN: 2016-05-17 00:20:16Z). Change "The Service Hint element contains information about a Bloom filter that provides a probabilistic representation of a set of services." to "The Service Hint element contains a Bloom filter that provides a probabilistic representation of a set of services that are available to the BSS." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3011 | Su Khiong Yong | 219 | 4 | 11.25.A3 | 21 | 21 | T | Y | 21.21 | 21 | 11.25.A3 |  | J | Mike Montemurro |  |  | Additional filtering rules should be added to reduce the probe response frames from legacy APs. | Replace line 21-42 on page 21 with the following text When dot11SolicitedPADActivated is true, a non-AP STA sends Probe Request frames with a Service Hash element, which includes one or more service hashes generated from the service name(s) of the service(s) that the non-AP STA is requesting, to an AP or PCP. The Probe Request frames shall have address 1 field sets to PAD Multicast Address (TBD) and address 3 field set to PAD BSSID (TBD). When dot11SolicitedPADActivated is true, an AP or PCP that receives Probe Request frames shall respond with a Probe Response that includes Service Hint element or Service Advertisment element, if the address 1 and address 3 in the Probe Request are the PAD Multicast Address and PAD BSSID address of the STA. If Service Advertisement element is included in the Probe Response frame, the When dot11SolicitedPADActivated is true, an AP or PCP shall verify if there are any services matching those in the received Probe Request frame. The matching of service is based on the service hash value in the Service Hash field of the Service Hash element matches to the corresponding service hash value of the service in which the AP or PCP is offering. If the AP or PCP determines there is one or more matching matched services, the AP or PCP shall respond with a Probe Response frame with the Service Advertisement element containing a Basic Service Information Descriptor field for each matching service. The requesting non-AP STA shall process the Service Advertisement element in the received Probe Response frame to determine if any received service name matches with a service name that the non-AP STA is requesting and the corresponding instance names. If there is a matching matched service name, the non-AP STA may decide to proceed with the PAD ANQP-SD procedure (10.26.4 (PAD ANQP-SD procedure) or authentication and association procedure (10.3 (STA authentication and association)) based on the nature of the service (see examples illustrated in Annex AA.1 (Pre-association discovery usage scenarios)), the details of which are out of the scope of this standard. If Service Hint element is included in the Probe Response frame, the AP or PCP is not required to perform service matching with those services in the received Probe Request frame. The requesting non-AP STA shall determine the bit positions of the Bloom Filter Bit Array field in which the non-AP STA is searching, and verify if there are any matched services based on the matching of the corresponding bit positions of the of the Bloom Filter Bit Array field of the Service Hint element. If there is a matched service, the non-AP STA may determine to proceed with PAD ANQP procedure ( 10.26.4 (PAD ANQP procedure), or authentication and association procedure (10.3 (STA authentication and association)) based on the perceived false positive probability and the nature of the service (see examples illustrated in AA.1 (Preassociation discovery usage scenarios)), the details of which are out of the scope of this standard. | REJECTED (GEN: 2016-05-19 01:04:23Z). The TG members can not reach consensus on a technical resolution to the comment. | GEN | Broadcast Solicited PAD | discussed |  |  |  |  | 2016-05-19 01:55 | GEN
3012 | Stephen McCann | 219 | 4 | 2 | 2 | 25 | E | N | 2.25 | 25 | 2 |  |  | Lee Armstrong |  |  | IETF RFC 6763 is referenced in the amendment and should be added to clause 2. | Add a reference to IETF RFC 6763 |  | GEN | LB219 Editorial | [5 empty] | 2016-05-18 23:38 | GEN
3013 | Stephen McCann | 219 | 4 | 3.1 | 2 | 35 | T | N | 2.35 | 35 | 3.1 |  | A |  |  |  | The definition for UUSID is not used within the amendment | Remove the UUSID definition | ACCEPTED (GEN: 2016-05-17 00:36:26Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3014 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 38 | T | N | 3.38 | 38 | 4.5.9.1 |  | V |  |  |  | PAD is not really a service itself. It's more of a protocol to transport service information | Change the start of the paragraph to read "PAD is a protocol...." or possibly "PAD is an interworking function..." | REVISED (GEN: 2016-05-17 00:48:10Z). Change "PAD is a service" to "PAD is an interworking function". | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3015 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 38 | E | N | 3.38 | 38 | 4.5.9.1 |  | V | Stephen McCann |  |  | Move the references to a network from the last sentence in this paragraph to the first | Change the first sentence of the paragraph to read "PAD is a service provided by a PBSS or BSS (i.e. a network)...". Remove the text "(i.e. a network)" from the last sentence in this paragraph. | REVISED (GEN: 2016-05-19 01:00:45Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 01:01 | GEN
3016 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 40 | T | N | 3.4 | 40 | 4.5.9.1 |  | V |  |  |  | Decide whether the "(non-AP??)" text in this sentence should remain or be removed. | Decide to either keep this text and remove the "??" from the paranthesis or remove all of this text. | REVISED (GEN: 2016-05-17 00:52:13Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3017 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 42 | T | N | 3.42 | 42 | 4.5.9.1 |  | V |  |  |  | Clarify which services are to be obtained, in this final sentence. | Modify the end of the last sentence to "....to associate with to obtain those services." | REVISED (GEN: 2016-05-17 00:54:26Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3018 | Stephen McCann | 219 | 4 | 4.5.9.1.1 | 4 | 6 | E | N | 4.06 | 6 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | The comma should be changed to a full stop | Change the "," to a "." at the end of this sentence |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3019 | Stephen McCann | 219 | 4 | 4.5.9.1.1 | 4 | 7 | T | N | 4.07 | 7 | 4.5.9.1.1 |  | V |  |  |  | Within Figure 4-11a, it's not clear what devices are involved. Is the SIC and SIR associated with a STA, or an AP? | Possibly add "STA" to the SIC box within Figure 4-11a and then add either "STA" or "AP" to the SIR box. | REVISED (GEN: 2016-05-17 00:56:14Z). In Figure 4-11a, add "STA" to the SIC box, and add "AP/PCP" to the SIR box. And delete "PBSS/" from the figure. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3020 | Stephen McCann | 219 | 4 | 4.5.9.1.1 | 4 | 30 | T | N | 4.3 | 30 | 4.5.9.1.1 |  | V |  |  |  | Remove the sentence starting "NOTE: a proxy server", as there is no proxy server anymore in this clause | As per comment | REVISED (GEN: 2016-05-17 00:59:20Z). Change "NOTE- a proxy server" to "NOTE- An SIR". | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3021 | Stephen McCann | 219 | 4 | 4.5.9.1.2 | 4 | 39 | T | N | 4.39 | 39 | 4.5.9.1.2 |  | V |  |  |  | The term "Entities" is a little vague and requires some clarification | Change the start of the sentence to read "Entities operate as proxies and are used to" | REVISED (GEN: 2016-05-17 01:17:59Z). Change Clause 4.5.9.1.2 to "The Service Information Client (SIC) and Registry (SIR), are used to exchange information between higher layer resources above both the non-AP STA and the AP. The PAD and ANQP service discovery procedures operate between the SIC and SIR. The SIC and SIR are used to encapsulate service relevant information (e.g. a service name), and then exchange that information between the SIC and SIR. As shown in Figure 4-11a (Pre-association Discovery Architecture), PAD signaling is opaque to the service relevant information because it is handled by these entities in the STA and AP." | GEN | 2016-05-16-pm2 | ready for motion | Note to Editor: Part of submission 11-16-0606r1. |  |  |  | 2016-05-17 06:54 | GEN
3022 | Stephen McCann | 219 | 4 | 4.5.9.1.3 | 4 | 49 | T | N | 4.49 | 49 | 4.5.9.1.3 |  | V |  |  |  | There are several places where the phrase "services that may be available via the PBSS or BSS" is used within the draft. These should all use the same terminology as defined in clause 4.5.9 | Change the text "The Service Information Registry (SIR) is a logical entity that contains caches of information about services that may be available via the PBSS or BSS" to "The Service Information Registry (SIR) is a logical entity that contains caches of information about services offered by a PBSS or BSS or an external network" Similar changes need to be made to similar text in other parts of the draft | REVISED (GEN: 2016-05-17 01:25:01Z). Change "The Service Information Registry (SIR) is a logical entity that contains caches of information about services that may be available via the PBSS or BSS, for the STA to connect to after it associates with the AP or PCP." to "The Service Information Registry (SIR) contains information about services that may be available to the BSS, for the STA to connect to after it associates with the AP." And change "There is typically one SIR assigned to each ESS and it is a distributed logical entity. It can be reached by each AP and each service within that ESS." to "There is typically one SIR assigned to each ESS. It can be reached by each AP and each service within that ESS." And change, at P4L64, "The Service Information Client (SIC), also shown in Figure 4-11a (Pre-association Discovery Architecture), is a logical entity that initiates STA service discovery." to "The Service Information Client (SIC), also shown in Figure 4-11a (Pre-association Discovery Architecture) initiates STA service discovery." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3023 | Stephen McCann | 219 | 4 | 9.4.2.27 | 13 | 39 | E | N | 13.39 | 39 | 9.4.2.27 |  |  | Lee Armstrong |  |  | The reference needs to be corrected | Change "(10.26.3)" to "(11.25a.3)" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3024 | Stephen McCann | 219 | 4 | 9.4.2.27 | 13 | 41 | E | N | 13.41 | 41 | 9.4.2.27 |  |  | Lee Armstrong |  |  | The reference needs to be corrected | Change "Indicates support for Solicited PAD procedure (10.26.4)" to "Indicates support for PAD ANQP procedure (11.25a.4)" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3025 | Stephen McCann | 219 | 4 | 9.4.2.217 | 15 | 18 | T | N | 15.18 | 18 | 9.4.2.217 |  | A |  |  |  | The term "Basic" is redundant in the sub-frame definition as there is no other sort of Service Information Description frame. | Change all occurances of "Basic Service Information Descriptor" to "Service Information Descriptor" | ACCEPTED (GEN: 2016-05-17 02:45:27Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3026 | Stephen McCann | 219 | 4 | 9.4.5.27 | 16 | 45 | T | N | 16.45 | 45 | 9.4.5.27 |  | J | Stephen McCann |  |  | The format of the Service Information Request and Response ANQP-elements is basically the same. As GAS indicates whether the transported message is either a query or a response already, it should be possible to merge the these ANQP-elements into one single frame, in a similar way to the TDLS ANQP-element in IEEE 802.11 REVmc D5.2 | Commenter will provide a submission to merge the two ANQP-elements together. | REJECTED (GEN: 2016-05-19 00:53:40Z). TGaq members agree to maintain a request and response ANQP-element separately. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:54 | GEN
3027 | Stephen McCann | 219 | 4 | 9.4.5.27 | 17 | 36 | T | N | 17.36 | 36 | 9.4.5.27 |  | V | Stephen McCann |  |  | The Service Information Request ANQP-element doesn't appear to be capable of performing a wild card search for "all services" known to the SIR. The special value of Service Name Length being equal to 0, is rather limiting and confusing. | Change the text so that the Service Name Length is equal to 0xFF when it uses the Service Hash, as opposed to 0. Alternatively add a separate bit to the ANQP-element for this option. | REVISED (GEN: 2016-05-19 00:54:51Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:55 | GEN
3028 | Stephen McCann | 219 | 4 | 11.25a.4 | 21 | 55 | T | N | 21.55 | 55 | 11.25a.4 |  | V | Stephen McCann |  |  | The Service Information ANQP-elements should be capable of being used by themselves, without having to use either unsolicted or solicited PAD beforehand. This is the default behaviour of all the other ANQP-elements. | Remove the word "more" from the sentence "... to obtain more information...". In the last sentence P21L57 of this paragraph, change "the Service Name" to "a Service Name" and "the instance Name" to "a Instance Name". | REVISED (GEN: 2016-05-19 01:00:08Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 01:00 | GEN
3029 | Stephen McCann | 219 | 4 | 11.25.3.2.1 | 19 | 19 | T | N | 19.19 | 19 | 11.25.3.2.1 |  | J | Stephen McCann |  |  | In Table 11-15., merge the two ANQP-elements into one of ANQP-element type "Q, R". | As per comment | REJECTED (GEN: 2016-05-19 00:55:52Z). TGaq members agree to maintain a request and response ANQP-element separately. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:57 | GEN
3030 | Stephen McCann | 219 | 4 | 11.25.3.2.16 | 19 | 59 | T | N | 19.59 | 59 | 11.25.3.2.16 |  | V | Stephen McCann |  |  | This clause seems to be identical to clause 11.25a.4. Merge the two clauses together. | As per comment | REVISED (GEN: 2016-05-19 00:57:35Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:58 | GEN
3031 | Stephen McCann | 219 | 4 | 11.25a.4 | 21 | 49 | T | N | 21.49 | 49 | 11.25a.4 |  | V | Stephen McCann |  |  | The PAD ANQP procedure is another ANQP-element procedure and should be moved into clause 11.25. | Move 11.25.a.4 into section 11.25.3.2.1 and merge with clause 11.25.3.2.16. Rename the new clause "Service Information ANQP procedure", so that it conforms to the other ANQP procedure clauses in REVmc D5.2. Remove all references to PAD ANQP procedures, as they are just ANQP procedures. | REVISED (GEN: 2016-05-19 00:59:31Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 01:00 | GEN
3032 | Stephen McCann | 219 | 4 | 11.25a.4 | 21 | 52 | T | N | 21.52 | 52 | 11.25a.4 |  | V |  |  |  | The sentence "...about a matching service from the AP or PCP" is not correct. The service information does not come from the AP or PCP. | Change the following text "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information Request ANQP-element (see 9.4.5.27 (Service Information Request ANQP-element)) to obtain more information about a matching service from the AP or PCP." to "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information Request ANQP-element (see 9.4.5.27 (Service Information Request ANQP-element)) to obtain more information about a matching service that may be offered by a PBSS, BSS or an external network." | REVISED (GEN: 2016-05-17 03:47:21Z). Change the following text "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information Request ANQP-element (see 9.4.5.27 (Service Information Request ANQP-element)) to obtain more information about a matching service from the AP or PCP." to "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information ANQP-element (see 9.4.5.27 (Service Information ANQP-element)) to obtain more information about a matching service that may be offered by a BSS or an external network." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3033 | Michael Montemurro | 219 | 4 | 4.5.9.1 | 3 | 40 | T | Y | 3.4 | 40 | 4.5.9.1 |  | A |  |  |  | "This information may allow a (non-AP??) STA to choose during network selection..." does not really describe a use case very well, nor does it add to the explanation of what PAD is. | Remove the cited sentence | ACCEPTED (GEN: 2016-05-17 00:53:39Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3034 | Michael Montemurro | 219 | 4 | 4.5.9.1.1 | 4 | 4 | E | Y | 4.04 | 4 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | Add space betweeen ")and" | change ")and" to ") and" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3035 | Michael Montemurro | 219 | 4 | 6.3.3.2.2 | 6 | 44 | T | Y | 6.44 | 44 | 6.3.3.2.2 |  | V | Mike Montemurro |  |  | The scan.request should not be used for Solicited PAD | Remove the parameter as well as the clause 6.3.3.2.3. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:42:51Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed | 11-16-0695 |  |  |  | 2016-05-19 00:43 | GEN
3036 | Michael Montemurro | 219 | 4 | 9.3.3.3 | 11 | 15 | T | Y | 11.15 | 15 | 9.3.3.3 |  | J | Mike Montemurro |  |  | The Service Advertisement is missing from the Beacon frame | Add the Service Advertisement to Beacon frames, otherwise PAD cannot be used with passive scanning procedures). | REJECTED (GEN: 2016-05-19 00:43:58Z). This element has been deleted in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:45 | GEN
3037 | Michael Montemurro | 219 | 4 | 9.3.3.10 | 12 | 7 | T | Y | 12.07 | 7 | 9.3.3.10 |  | V | Mike Montemurro |  |  | Service Hash should not be included in a Probe Request frame. | Remove the parameter and all modificiations to the Probe Request. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:45:25Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:46 | GEN
3038 | Michael Montemurro | 219 | 4 | 9.4.5.1 | 17 | 30 | T | Y | 17.3 | 30 | 9.4.5.1 |  | V | Mike Montemurro |  |  | Include the solicited PAD procedure as an ANQP request/response (or any type of GAS request/response) based on what is currently included in Probe Request/Response) | Add an ANQP protocol (or other GAS protocol) based on current modificiations to the Probe Request/Response to support solicited PAD. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:45:50Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:46 | GEN
3039 | Michael Montemurro | 219 | 4 | 11.25a.3 | 21 | 12 | T | Y | 21.12 | 12 | 11.25a.3 |  | V | Mike Montemurro |  |  | Re-define Solicited PAD procedures to use Public Action frames, or even ANQP/GAS frames. Overloading Active Scanning procedures makes the mechanisms far too complicated. | Add an ANQP protocol (or other GAS protocol) based on current modificiations to the Probe Request/Response to support solicited PAD. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:46:07Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:46 | GEN
3040 | Michael Montemurro | 219 | 4 | 11.25a.5 | 22 | 10 | T | Y | 22.1 | 10 | 11.25a.5 |  | V |  |  |  | It would be better if hashing procedures are described together as subsections to one main section. | Add a new section called PAD Hashing Functions and inclued 11.25a.5 and 11.25a.6 as subsections. | REVISED (GEN: 2016-05-17 03:54:09Z). Swap the sequence of 11.25a.5 and 11.25a.6. Note to Editor: References to these two clauses need to be updated as well. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3041 | Michael Montemurro | 219 | 4 | W1.1 | 30 | 30 | T | Y | 30.3 | 30 | W1.1 |  | V | Mike Montemurro |  |  | The figure should be updated to remove the Solicited PAD procedures with a public action frame, possibly an ANQP element. | Replace the figure based on the updated Solicited PAD procedures that make use of public Action Frames. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:48:37Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:50 | GEN
3042 | Michael Montemurro | 219 | 4 | W1.2 | 32 | 32 | T | Y | 32.32 | 32 | W1.2 |  | V | Mike Montemurro |  |  | The figure should be updated to remove the Solicited PAD procedures with a public action frame, possibly an ANQP element. | Replace the figure based on the updated Solicited PAD procedures that make use of public Action Frames. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:49:36Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:50 | GEN
3043 | stephane baron | 219 | 4 | 4.5.9.1.1 | 4 | 30 | E | N | 4.3 | 30 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | "proxy server" should be replaced by "service information registry" | same as comment |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3044 | stephane baron | 219 | 4 | 11.25a.1 | 20 | 28 | E | N | 20.28 | 28 | 11.25a.1 |  |  | Lee Armstrong |  |  | "logical proxy" should be replaced by "logical registry" | same as comment |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3045 | stephane baron | 219 | 4 | 11.25a.2 | 20 | 52 | T | N | 20.52 | 52 | 11.25a.2 |  | J |  |  |  | Uncolicited case should refer only Beacon. | remove "or Probe Response" | REJECTED (GEN: 2016-05-17 03:38:45Z). Information in the Beacon needs to be the same as in the Probe Response. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3046 | Huizhao Wang | 219 | 4 | 6.3.11.2.2 | 9 | 5 | E | N | 9.05 | 5 | 6.3.11.2.2 |  |  | Lee Armstrong |  |  | Duplicate table | Instead of duplicate the same table, make a reference to the same table on page 7 |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3047 | Huizhao Wang | 219 | 4 | 9.4.2.1 | 13 | 10 | T | N | 13.1 | 10 | 9.4.2.1 |  | V |  |  |  | Fragmentable Flags are missing in Table 9-76 | Please fill this column to indicate whether these Elements are fragmentable or not | REVISED (GEN: 2016-05-17 02:43:39Z). Delete the Fragementable column. Note the baseline document has deleted this column. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3048 | Huizhao Wang | 219 | 4 | 11.25a.6 | 22 | 58 | T | N | 22.58 | 58 | 11.25a.6 |  | J |  |  |  | International UNICODE should be considered in Service Hash Procedure | The defined uppercase/lowercase conversion does not cover UNICODE wither international character in Service Name. In case UNICODE is used, then they should not converted, use them "as is" | REJECTED (GEN: 2016-05-17 03:56:41Z). The text is clear that the conversion of upper cases to lower cases is only for A-Z. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3049 | Yunsong Yang | 219 | 4 | 3.1 | 2 | 36 | T | N | 2.36 | 36 | 3.1 |  | A |  |  |  | The term UUSID is not used anywhere else in the draft. | delete the definition of UUSID. | ACCEPTED (GEN: 2016-05-17 00:36:35Z) | GEN | 2016-05-16-pm2 | ready for motion | Same as CID 3013. |  |  |  | 2016-05-17 06:54 | GEN
3050 | Yunsong Yang | 219 | 4 | 3.2 | 2 | 40 | T | N | 2.4 | 40 | 3.2 |  | A |  |  |  | The definition of Service Hash was originally provided in D3.0 and was removed since D3.1 by error. | In Clause 3.2, insert the following definition (which is copied from D3.0): service hash: A value that is used for representing a service and is formed from a hash of the service name. | ACCEPTED (GEN: 2016-05-17 00:40:41Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3051 | Yunsong Yang | 219 | 4 | 3.2 | 2 | 40 | T | N | 2.4 | 40 | 3.2 |  | V |  |  |  | Since 11aq architecture introduces two new terms of Service Information Registry (SIR) and Service Information Client (SIC), add new definitions of them in Clause 3.2 and add both abbreviations in Clause 3.4. | In Clause 3.2, insert the following definitions (which are copied from Clauses 4.5.9.1.3 and 4.5.9.1.4): Service Information Client: a logical entity that initiates STA service discovery. Service Information Registry: a logical entity that contains caches of information about services that may be available via the PBSS or BSS, for the STA to connect to after it associates with the AP or PCP. And in Clause 3.4, insert the following abbreviations: SIC: Service Information Client SIR: Service Information Registry | REVISED (GEN: 2016-05-17 00:38:11Z) In Clause 3.2, insert the following definitions: Service Information Client: a logical entity that initiates STA service discovery. Service Information Registry: a logical entity that contains caches of information about services that may be available via the BSS, for the STA to connect to after it associates with the AP. And in Clause 3.4, insert the following abbreviations: SIC: Service Information Client SIR: Service Information Registry | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3052 | Yunsong Yang | 219 | 4 | 4.5.9.1.3 | 4 | 59 | T | Y | 4.59 | 59 | 4.5.9.1.3 |  | V |  |  |  | This sentence is very generic. Without describing for what purpose(s) the SIR communicates with the ANQP Server, this sentence doesn't add much useful information. | Either add the description of why the SIR communicates with the ANQP service or delete this sentence. | REVISED (GEN: 2016-05-17 02:07:31Z). Change "The SIR communicates with the ANQP Server that is also available via the PBSS or BSS." to "The SIR communicates with the ANQP Server to respond to PAD ANQP requests." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3053 | Yunsong Yang | 219 | 4 | 9.4.5.28 | 18 | 46 | T | Y | 18.46 | 46 | 9.4.5.28 |  | V | Stephen McCann |  |  | Both instances of "Query Request" in this sentence should be "Query Response". | As commented. | REVISED (GEN: 2016-05-19 00:55:36Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:56 | GEN
3054 | Yunsong Yang | 219 | 4 | 11.25.3.2.1 | 19 | 64 | T | Y | 19.64 | 64 | 11.25.3.2.1 |  | A | Stephen McCann |  |  | According to Clause 9.4.5.27, either the service name or the service hash may be placed in the Service Name field within this ANQP-element. But since Clause 11 is about the procedures, the "service name" here is not referring to the Service Name field, rather the content in that field. Therefore, both possible contents in that field should be mentioned here, recognizing that this only applies to ANQP-based request. | Change "A service name may be placed with the request." to "A service name or a service hash generated from the service name may be placed within such an ANQP request." | ACCEPTED (GEN: 2016-05-19 00:58:51Z). | GEN | PAD ANQP | discussed | Text will be in doc. 11-16-0695r3. |  |  |  | 2016-05-19 00:59 | GEN
3055 | Yunsong Yang | 219 | 4 | 11.25a.1 | 20 | 22 | E | Y | 20.22 | 22 | 11.25a.1 |  |  | Lee Armstrong |  |  | Both instances of "ANQP-SD" on this line should be "PAD ANQP". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3056 | Yunsong Yang | 219 | 4 | 11.25a.1 | 20 | 28 | T | Y | 20.28 | 28 | 11.25a.1 |  | A |  |  |  | Is "a logical proxy" here the same as the SIR as described in 4.5.9.1.3. If yes, it is better to say so. | Replace "a logical proxy," with "the Service Information Registry as described in 4.5.9.1.3 (Service Information Registry)," | ACCEPTED (GEN: 2016-05-17 02:59:35Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3057 | Yunsong Yang | 219 | 4 | 11.25a.2 | 20 | 65 | T | Y | 20.65 | 65 | 11.25a.2 |  | A |  |  |  | "step 1" should be "step 2" since clearly the bit positions are determined in step 2. | Replace "step 1" with "step 2". | ACCEPTED (GEN: 2016-05-17 03:40:49Z). | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3058 | Yunsong Yang | 219 | 4 | 11.25a.2 | 21 | 1 | E | N | 21.01 | 1 | 11.25a.2 |  |  | Lee Armstrong |  |  | "If" in the sentence is no needed. | Replace "If the" with "The". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3059 | Yunsong Yang | 219 | 4 | 11.25a.2 | 21 | 2 | E | N | 21.02 | 2 | 11.25a.2 |  |  | Lee Armstrong |  |  | "ANQP-SD" should be "PAD ANQP". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3060 | Yunsong Yang | 219 | 4 | W1.1 | 29 | 41 | E | N | 29.41 | 41 | W1.1 |  |  | Lee Armstrong |  |  | "Based on" should be "If". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3061 | Yunsong Yang | 219 | 4 | W1.1 | 30 | 36 | E | N | 30.36 | 36 | W1.1 |  |  | Lee Armstrong |  |  | "Based on" should be "If". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3062 | Ahmadreza Hedayat | 219 | 4 | 4.5.9.1 | 3 | 40 | T | Y | 3.4 | 40 | 4.5.9.1 |  | V |  |  |  | This information may allow a (non-AP??) STA to choose during network selection, which PBSS or BSS (i.e. a network) to associate with to obtain services. | This information may allow a non-AP STA to choose during network selection, which PBSS or BSS to associate with to obtain services. | REVISED (GEN: 2016-05-17 00:53:18Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3063 | Ahmadreza Hedayat | 219 | 4 | 4.5.9.1.1 | 4 | 3 | E | Y | 4.03 | 3 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | ... Client (SIC)and a Service Information Registry (SIR). | ... Client (SIC) and a Service Information Registry (SIR). |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3064 | Jouni Malinen | 219 | 4 | 4.5.9.1 | 3 | 40 | T | Y | 3.4 | 40 | 4.5.9.1 |  | V |  |  |  | "(non-AP??)" does not belong in the standard.. If there is no conclusion on whether the "non-AP" part should be included here, it is fine to leave it out and just say "STA". | On page 3 line 40, replace "(non-AP??) STA" with "STA". | REVISED (GEN: 2016-05-17 00:52:48Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3065 | Jouni Malinen | 219 | 4 | 4.5.9.1.1 | 6 | 17 | E | Y | 6.17 | 17 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | Typos in a figure ("solcited" vs. "solicited"). | In Figure 4-11a (page 6 lines 15-16), replace "Unsolicted" with "Unsolicited" and "Solicted" with "Solicited". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3066 | Jouni Malinen | 219 | 4 | 9.4.2.27 | 13 | 41 | E | Y | 13.41 | 41 | 9.4.2.27 |  |  | Lee Armstrong |  |  | Incorrect procedure name in Table 9-134 (copy-paste error from the previous row?). | On page 13 line 41 (Table 9-134 "PAD ANQP" row), replace "Indicates support for Solicited PAD procedure" with "Indicates support for PAD ANQP procedure". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3067 | Jouni Malinen | 219 | 4 | 9.4.2.217 | 15 | 53 | E | Y | 15.53 | 53 | 9.4.2.217 |  |  | Lee Armstrong |  |  | Wrong word or typo? | On page 15 line 53, replace "For example, of service name of print service is" with "For example, the service name of print service is" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3068 | Jouni Malinen | 219 | 4 | 9.4.5.1 | 16 | 35 | E | N | 16.35 | 35 | 9.4.5.1 |  |  | Lee Armstrong |  |  | Inconsistent style in editing instruction. | On page 16 line 35, replace "Inserting new rows" with "Insert new rows". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3069 | Jouni Malinen | 219 | 4 | 11.25a.1 | 20 | 22 | E | N | 20.22 | 22 | 11.25a.1 |  |  | Lee Armstrong |  |  | Couple of leftover ANQP-SD terms remain. This was replaced with standard ANQP and the new term used for the procedure in P802.11aq seems to be "PAD ANQP procedure". | On page 20 line 22, replace "ANQP-SD procedures" with "PAD ANQP procedures" (twice). On page 21 line 2, replace "ANQP-SD procedure" with "PAD ANQP procedure". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3070 | Jouni Malinen | 219 | 4 | 11.25a.3 | 21 | 22 | T | Y | 21.22 | 22 | 11.25a.3 |  | V | Mike Montemurro |  |  | Solicited PAD procedure does not describe clearly when the AP replies to a Probe Request frame based on whether there are matching services. Some text for this was added in 11.25a.3 (Solicited PAD procedure; the second paragraph there). However, "it shall respond" is only describing a case where the AP replies. There is no "otherwise, it shall not reply" type of statement indicating when this does not happen. In addition, this is not really the correct clause for describing rules on when a STA replies to a Probe Request frame. Without the AP rules being clearly described, the solicited PAD procedure can cause significant harm to networks by increasing the number of unnecessary management frames. | Update 11.1.4.3.4 (Criteria for sending a probe response) to indicate clearly when an AP does not reply to a Probe Request frame based on there being no match to the requested service. | REVISED (GEN: 2016-05-19 00:46:38Z). The Solicited PAD has been moved to a Public Action frame with the acceptance of document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:48 | GEN
3071 | Jouni Malinen | 219 | 4 |  |  |  | T | Y |  |  |  |  | V | Mike Montemurro |  |  | Regarding CID 2143 in the previous LB, it does not sound justifiable to ignore the issue which the group seemed to agree to existing based on the resolution. If the group cannot come to a conclusion on how to resolve the comment, I can propose a different way of getting this issue resolved: remove the Solicited PAD procedure completely. That said, I'd still accept a mechanism that implements the Solicited PAD procedure in a manner that does not cause significant increase in the number of undesired management frames. I don't think it is acceptable to introduce new mechanism using Probe Request frames in a manner that makes existing devices reply to them in case where no such response is desired. CID 2143 listed number of ways of doing this more properly. | Remove the Solicited PAD procedure from P802.11aq. | REVISED (GEN: 2016-05-19 00:41:22Z). Incorporate changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:42 | GEN

## 2016-05-16-pm2
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3033 | Michael Montemurro | 219 | 4 | 4.5.9.1 | 3 | 40 | T | Y | 3.4 | 40 | 4.5.9.1 |  | A |  |  |  | "This information may allow a (non-AP??) STA to choose during network selection..." does not really describe a use case very well, nor does it add to the explanation of what PAD is. | Remove the cited sentence | ACCEPTED (GEN: 2016-05-17 00:53:39Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3005 | Adrian Stephens | 219 | 4 |  | 22 | 19 | G | Y | 22.19 | 19 |  |  | V |  |  |  | "Number of Hash Functions field is equal to "0001"" - if this is an integer field, use an integer value, not an ambiguous bitstring/binary representation. | Replace "0001" with "1". | REVISED (GEN: 2016-05-17 00:30:47Z). Change ""0001"" to "binary value of 0001" at the cited location. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3007 | Yongho Seok | 219 | 4 | 11.25a.2 | 20 | 37 | T | N | 20.37 | 37 | 11.25a.2 |  | V |  |  |  | "When dot11UnsolicitedPADActivated is true, an AP or PCP shall advertise services using a Service Hint element or Service Hash element or both in Beacon or Probe Response frames." For the unsolicited PAD procedure of the PCP, the DMG Beacon and Announce frames should also contain the Service Hint element or Service Hash element. | Insert the Service Hint element or Service Hash element into Table 9-41 (DMG Beacon frame body) and Table 9-412 (Announce frame Action field format). Modify the P20 L37 sentence. | REVISED (GEN: 2016-05-17 03:26:00Z). Insert the Service Hint element and Service Hash element into Table 9-41 (DMG Beacon frame body) and Table 9-412 (Announce frame Action field format). Change "When dot11UnsolicitedPADActivated is true, an AP or PCP shall advertise services using a Service Hint element or Service Hash element or both in Beacon or Probe Response frames." to "When dot11UnsolicitedPADActivated is true, an AP shall advertise services using a Service Hint element or Service Hash element or both in Beacon or Probe Response frames." And add "When dot11UnsolicitedPADActivated is true, a PCP shall advertise services using a Service Hint element or Service Hash element or both in DMG Beacon or Announce frames." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3010 | Mark RISON | 219 | 4 | 9.4.2.216 | 13 | 53 | G | Y | 13.53 | 53 | 9.4.2.216 |  | V |  |  |  | "The Service Hint element contains information a Bloom filter that provides the probabilistic representation of a set of services." This statement is not clear. | Make the statement clearer | REVISED (GEN: 2016-05-17 00:20:16Z). Change "The Service Hint element contains information about a Bloom filter that provides a probabilistic representation of a set of services." to "The Service Hint element contains a Bloom filter that provides a probabilistic representation of a set of services that are available to the BSS." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3013 | Stephen McCann | 219 | 4 | 3.1 | 2 | 35 | T | N | 2.35 | 35 | 3.1 |  | A |  |  |  | The definition for UUSID is not used within the amendment | Remove the UUSID definition | ACCEPTED (GEN: 2016-05-17 00:36:26Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3014 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 38 | T | N | 3.38 | 38 | 4.5.9.1 |  | V |  |  |  | PAD is not really a service itself. It's more of a protocol to transport service information | Change the start of the paragraph to read "PAD is a protocol...." or possibly "PAD is an interworking function..." | REVISED (GEN: 2016-05-17 00:48:10Z). Change "PAD is a service" to "PAD is an interworking function". | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3016 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 40 | T | N | 3.4 | 40 | 4.5.9.1 |  | V |  |  |  | Decide whether the "(non-AP??)" text in this sentence should remain or be removed. | Decide to either keep this text and remove the "??" from the paranthesis or remove all of this text. | REVISED (GEN: 2016-05-17 00:52:13Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3017 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 42 | T | N | 3.42 | 42 | 4.5.9.1 |  | V |  |  |  | Clarify which services are to be obtained, in this final sentence. | Modify the end of the last sentence to "....to associate with to obtain those services." | REVISED (GEN: 2016-05-17 00:54:26Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3019 | Stephen McCann | 219 | 4 | 4.5.9.1.1 | 4 | 7 | T | N | 4.07 | 7 | 4.5.9.1.1 |  | V |  |  |  | Within Figure 4-11a, it's not clear what devices are involved. Is the SIC and SIR associated with a STA, or an AP? | Possibly add "STA" to the SIC box within Figure 4-11a and then add either "STA" or "AP" to the SIR box. | REVISED (GEN: 2016-05-17 00:56:14Z). In Figure 4-11a, add "STA" to the SIC box, and add "AP/PCP" to the SIR box. And delete "PBSS/" from the figure. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3020 | Stephen McCann | 219 | 4 | 4.5.9.1.1 | 4 | 30 | T | N | 4.3 | 30 | 4.5.9.1.1 |  | V |  |  |  | Remove the sentence starting "NOTE: a proxy server", as there is no proxy server anymore in this clause | As per comment | REVISED (GEN: 2016-05-17 00:59:20Z). Change "NOTE- a proxy server" to "NOTE- An SIR". | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3021 | Stephen McCann | 219 | 4 | 4.5.9.1.2 | 4 | 39 | T | N | 4.39 | 39 | 4.5.9.1.2 |  | V |  |  |  | The term "Entities" is a little vague and requires some clarification | Change the start of the sentence to read "Entities operate as proxies and are used to" | REVISED (GEN: 2016-05-17 01:17:59Z). Change Clause 4.5.9.1.2 to "The Service Information Client (SIC) and Registry (SIR), are used to exchange information between higher layer resources above both the non-AP STA and the AP. The PAD and ANQP service discovery procedures operate between the SIC and SIR. The SIC and SIR are used to encapsulate service relevant information (e.g. a service name), and then exchange that information between the SIC and SIR. As shown in Figure 4-11a (Pre-association Discovery Architecture), PAD signaling is opaque to the service relevant information because it is handled by these entities in the STA and AP." | GEN | 2016-05-16-pm2 | ready for motion | Note to Editor: Part of submission 11-16-0606r1. |  |  |  | 2016-05-17 06:54 | GEN
3022 | Stephen McCann | 219 | 4 | 4.5.9.1.3 | 4 | 49 | T | N | 4.49 | 49 | 4.5.9.1.3 |  | V |  |  |  | There are several places where the phrase "services that may be available via the PBSS or BSS" is used within the draft. These should all use the same terminology as defined in clause 4.5.9 | Change the text "The Service Information Registry (SIR) is a logical entity that contains caches of information about services that may be available via the PBSS or BSS" to "The Service Information Registry (SIR) is a logical entity that contains caches of information about services offered by a PBSS or BSS or an external network" Similar changes need to be made to similar text in other parts of the draft | REVISED (GEN: 2016-05-17 01:25:01Z). Change "The Service Information Registry (SIR) is a logical entity that contains caches of information about services that may be available via the PBSS or BSS, for the STA to connect to after it associates with the AP or PCP." to "The Service Information Registry (SIR) contains information about services that may be available to the BSS, for the STA to connect to after it associates with the AP." And change "There is typically one SIR assigned to each ESS and it is a distributed logical entity. It can be reached by each AP and each service within that ESS." to "There is typically one SIR assigned to each ESS. It can be reached by each AP and each service within that ESS." And change, at P4L64, "The Service Information Client (SIC), also shown in Figure 4-11a (Pre-association Discovery Architecture), is a logical entity that initiates STA service discovery." to "The Service Information Client (SIC), also shown in Figure 4-11a (Pre-association Discovery Architecture) initiates STA service discovery." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3001 | Adrian Stephens | 219 | 4 |  | 3 | 23 | T | Y | 3.23 | 23 |  |  | V |  |  |  | "Discovery of services offered by a PBSS, BSS, or an external network". A PBSS is a type of BSS, so it is already covered by "a BSS" | Globally replace "PBSS, BSS" by "BSS" (6 instances) | REVISED (GEN: 2016-05-17 00:45:15Z). At P3L23, delete "PBSS, ". And at P3L38, delete "PBSS or". And at P3L40, delete "PBSS or". And at P3L41, delete "PBSS or". And at P4L49, delete "PBSS or". And at P4L56, delete "PBSS or". And at P4L59, delete "PBSS or". | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3032 | Stephen McCann | 219 | 4 | 11.25a.4 | 21 | 52 | T | N | 21.52 | 52 | 11.25a.4 |  | V |  |  |  | The sentence "...about a matching service from the AP or PCP" is not correct. The service information does not come from the AP or PCP. | Change the following text "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information Request ANQP-element (see 9.4.5.27 (Service Information Request ANQP-element)) to obtain more information about a matching service from the AP or PCP." to "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information Request ANQP-element (see 9.4.5.27 (Service Information Request ANQP-element)) to obtain more information about a matching service that may be offered by a PBSS, BSS or an external network." | REVISED (GEN: 2016-05-17 03:47:21Z). Change the following text "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information Request ANQP-element (see 9.4.5.27 (Service Information Request ANQP-element)) to obtain more information about a matching service from the AP or PCP." to "When dot11UnsolicitedPADActivated or dot11SolicitedPADActivated is true, a non-AP STA may send an ANQP request with a Service Information ANQP-element (see 9.4.5.27 (Service Information ANQP-element)) to obtain more information about a matching service that may be offered by a BSS or an external network." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3064 | Jouni Malinen | 219 | 4 | 4.5.9.1 | 3 | 40 | T | Y | 3.4 | 40 | 4.5.9.1 |  | V |  |  |  | "(non-AP??)" does not belong in the standard.. If there is no conclusion on whether the "non-AP" part should be included here, it is fine to leave it out and just say "STA". | On page 3 line 40, replace "(non-AP??) STA" with "STA". | REVISED (GEN: 2016-05-17 00:52:48Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3040 | Michael Montemurro | 219 | 4 | 11.25a.5 | 22 | 10 | T | Y | 22.1 | 10 | 11.25a.5 |  | V |  |  |  | It would be better if hashing procedures are described together as subsections to one main section. | Add a new section called PAD Hashing Functions and inclued 11.25a.5 and 11.25a.6 as subsections. | REVISED (GEN: 2016-05-17 03:54:09Z). Swap the sequence of 11.25a.5 and 11.25a.6. Note to Editor: References to these two clauses need to be updated as well. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3045 | stephane baron | 219 | 4 | 11.25a.2 | 20 | 52 | T | N | 20.52 | 52 | 11.25a.2 |  | J |  |  |  | Uncolicited case should refer only Beacon. | remove "or Probe Response" | REJECTED (GEN: 2016-05-17 03:38:45Z). Information in the Beacon needs to be the same as in the Probe Response. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3047 | Huizhao Wang | 219 | 4 | 9.4.2.1 | 13 | 10 | T | N | 13.1 | 10 | 9.4.2.1 |  | V |  |  |  | Fragmentable Flags are missing in Table 9-76 | Please fill this column to indicate whether these Elements are fragmentable or not | REVISED (GEN: 2016-05-17 02:43:39Z). Delete the Fragementable column. Note the baseline document has deleted this column. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3048 | Huizhao Wang | 219 | 4 | 11.25a.6 | 22 | 58 | T | N | 22.58 | 58 | 11.25a.6 |  | J |  |  |  | International UNICODE should be considered in Service Hash Procedure | The defined uppercase/lowercase conversion does not cover UNICODE wither international character in Service Name. In case UNICODE is used, then they should not converted, use them "as is" | REJECTED (GEN: 2016-05-17 03:56:41Z). The text is clear that the conversion of upper cases to lower cases is only for A-Z. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3049 | Yunsong Yang | 219 | 4 | 3.1 | 2 | 36 | T | N | 2.36 | 36 | 3.1 |  | A |  |  |  | The term UUSID is not used anywhere else in the draft. | delete the definition of UUSID. | ACCEPTED (GEN: 2016-05-17 00:36:35Z) | GEN | 2016-05-16-pm2 | ready for motion | Same as CID 3013. |  |  |  | 2016-05-17 06:54 | GEN
3050 | Yunsong Yang | 219 | 4 | 3.2 | 2 | 40 | T | N | 2.4 | 40 | 3.2 |  | A |  |  |  | The definition of Service Hash was originally provided in D3.0 and was removed since D3.1 by error. | In Clause 3.2, insert the following definition (which is copied from D3.0): service hash: A value that is used for representing a service and is formed from a hash of the service name. | ACCEPTED (GEN: 2016-05-17 00:40:41Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3051 | Yunsong Yang | 219 | 4 | 3.2 | 2 | 40 | T | N | 2.4 | 40 | 3.2 |  | V |  |  |  | Since 11aq architecture introduces two new terms of Service Information Registry (SIR) and Service Information Client (SIC), add new definitions of them in Clause 3.2 and add both abbreviations in Clause 3.4. | In Clause 3.2, insert the following definitions (which are copied from Clauses 4.5.9.1.3 and 4.5.9.1.4): Service Information Client: a logical entity that initiates STA service discovery. Service Information Registry: a logical entity that contains caches of information about services that may be available via the PBSS or BSS, for the STA to connect to after it associates with the AP or PCP. And in Clause 3.4, insert the following abbreviations: SIC: Service Information Client SIR: Service Information Registry | REVISED (GEN: 2016-05-17 00:38:11Z) In Clause 3.2, insert the following definitions: Service Information Client: a logical entity that initiates STA service discovery. Service Information Registry: a logical entity that contains caches of information about services that may be available via the BSS, for the STA to connect to after it associates with the AP. And in Clause 3.4, insert the following abbreviations: SIC: Service Information Client SIR: Service Information Registry | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3052 | Yunsong Yang | 219 | 4 | 4.5.9.1.3 | 4 | 59 | T | Y | 4.59 | 59 | 4.5.9.1.3 |  | V |  |  |  | This sentence is very generic. Without describing for what purpose(s) the SIR communicates with the ANQP Server, this sentence doesn't add much useful information. | Either add the description of why the SIR communicates with the ANQP service or delete this sentence. | REVISED (GEN: 2016-05-17 02:07:31Z). Change "The SIR communicates with the ANQP Server that is also available via the PBSS or BSS." to "The SIR communicates with the ANQP Server to respond to PAD ANQP requests." | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3056 | Yunsong Yang | 219 | 4 | 11.25a.1 | 20 | 28 | T | Y | 20.28 | 28 | 11.25a.1 |  | A |  |  |  | Is "a logical proxy" here the same as the SIR as described in 4.5.9.1.3. If yes, it is better to say so. | Replace "a logical proxy," with "the Service Information Registry as described in 4.5.9.1.3 (Service Information Registry)," | ACCEPTED (GEN: 2016-05-17 02:59:35Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3057 | Yunsong Yang | 219 | 4 | 11.25a.2 | 20 | 65 | T | Y | 20.65 | 65 | 11.25a.2 |  | A |  |  |  | "step 1" should be "step 2" since clearly the bit positions are determined in step 2. | Replace "step 1" with "step 2". | ACCEPTED (GEN: 2016-05-17 03:40:49Z). | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3062 | Ahmadreza Hedayat | 219 | 4 | 4.5.9.1 | 3 | 40 | T | Y | 3.4 | 40 | 4.5.9.1 |  | V |  |  |  | This information may allow a (non-AP??) STA to choose during network selection, which PBSS or BSS (i.e. a network) to associate with to obtain services. | This information may allow a non-AP STA to choose during network selection, which PBSS or BSS to associate with to obtain services. | REVISED (GEN: 2016-05-17 00:53:18Z). Remove the cited sentence. | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN
3025 | Stephen McCann | 219 | 4 | 9.4.2.217 | 15 | 18 | T | N | 15.18 | 18 | 9.4.2.217 |  | A |  |  |  | The term "Basic" is redundant in the sub-frame definition as there is no other sort of Service Information Description frame. | Change all occurances of "Basic Service Information Descriptor" to "Service Information Descriptor" | ACCEPTED (GEN: 2016-05-17 02:45:27Z) | GEN | 2016-05-16-pm2 | ready for motion |  |  |  |  | 2016-05-17 06:54 | GEN

## 2016-05-18-pm1
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3004 | Adrian Stephens | 219 | 4 |  |  |  | G | Y |  |  |  |  | J |  |  |  | Recent changes add "PCP" all over the place on the assumption that a PCP is "just like an AP". Well, there is a difference, the PCP has no DS - i.e., it is not connected to an infrastructure. So a PCP can advertise its own locally connected services, but not those of anything connected wirelessly to it. | Remove all mention of PCP and PBSS | REJECTED (GEN: 2016-05-17 03:13:07Z). The operation of PAD is not dependent on the presence of DS (i.e., infrastructure). Therefore, the PAD architecture still applies to a PCP and a PBSS. | GEN | 2016-05-18-pm1 | ready for motion | Change all instances of "AP or PCP" to "AP". Note to Editor: There are 35 instances. And at P3L23, delete "PBSS, ". And at P3L38, delete "PBSS or". And at P3L40, delete "PBSS or". And at P3L41, delete "PBSS or". And at P4L49, delete "PBSS or". And at P4L56, delete "PBSS or". And at P4L59, delete "PBSS or". |  |  |  | 2016-05-19 01:56 | GEN

## LB219 Editorial
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3046 | Huizhao Wang | 219 | 4 | 6.3.11.2.2 | 9 | 5 | E | N | 9.05 | 5 | 6.3.11.2.2 |  |  | Lee Armstrong |  |  | Duplicate table | Instead of duplicate the same table, make a reference to the same table on page 7 |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3003 | Adrian Stephens | 219 | 4 |  |  |  | E | N | [5 empty] | Lee Armstrong |  |  | I have seen at least two instances of "e.g." without a comma. | Please ensure all "e.g." and "i.e." are followed by a comma. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3006 | Adrian Stephens | 219 | 4 |  | 28 | 23 | G | Y | 28.23 | 23 |  |  |  | Lee Armstrong |  |  | The dot11Compliances namespace is administered by the 802.11 ANA | Replace the value 6 with <ANA> |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:33 | GEN
3008 | Yongho Seok | 219 | 4 | 9.4.2.27 | 13 | 39 | E | N | 13.39 | 39 | 9.4.2.27 |  |  | Lee Armstrong |  |  | 10.26.3 is a wrong reference | Change 10.26.3 to 11.25a.3. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3009 | Yongho Seok | 219 | 4 | 9.4.2.27 | 13 | 42 | E | N | 13.42 | 42 | 9.4.2.27 |  |  | Lee Armstrong |  |  | 10.26.4 is a wrong reference | Change 10.26.4 to 11.25a.4. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3012 | Stephen McCann | 219 | 4 | 2 | 2 | 25 | E | N | 2.25 | 25 | 2 |  |  | Lee Armstrong |  |  | IETF RFC 6763 is referenced in the amendment and should be added to clause 2. | Add a reference to IETF RFC 6763 |  | GEN | LB219 Editorial | [5 empty] | 2016-05-18 23:38 | GEN
3018 | Stephen McCann | 219 | 4 | 4.5.9.1.1 | 4 | 6 | E | N | 4.06 | 6 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | The comma should be changed to a full stop | Change the "," to a "." at the end of this sentence |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3023 | Stephen McCann | 219 | 4 | 9.4.2.27 | 13 | 39 | E | N | 13.39 | 39 | 9.4.2.27 |  |  | Lee Armstrong |  |  | The reference needs to be corrected | Change "(10.26.3)" to "(11.25a.3)" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3024 | Stephen McCann | 219 | 4 | 9.4.2.27 | 13 | 41 | E | N | 13.41 | 41 | 9.4.2.27 |  |  | Lee Armstrong |  |  | The reference needs to be corrected | Change "Indicates support for Solicited PAD procedure (10.26.4)" to "Indicates support for PAD ANQP procedure (11.25a.4)" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3034 | Michael Montemurro | 219 | 4 | 4.5.9.1.1 | 4 | 4 | E | Y | 4.04 | 4 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | Add space betweeen ")and" | change ")and" to ") and" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3002 | Adrian Stephens | 219 | 4 |  | 4 | 17 | E | Y | 4.17 | 17 |  |  |  | Lee Armstrong |  |  | Figure 4-11a contains gratuitous shading, which doesn't reproduce well in the printed copy. | Remove shading. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3044 | stephane baron | 219 | 4 | 11.25a.1 | 20 | 28 | E | N | 20.28 | 28 | 11.25a.1 |  |  | Lee Armstrong |  |  | "logical proxy" should be replaced by "logical registry" | same as comment |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3069 | Jouni Malinen | 219 | 4 | 11.25a.1 | 20 | 22 | E | N | 20.22 | 22 | 11.25a.1 |  |  | Lee Armstrong |  |  | Couple of leftover ANQP-SD terms remain. This was replaced with standard ANQP and the new term used for the procedure in P802.11aq seems to be "PAD ANQP procedure". | On page 20 line 22, replace "ANQP-SD procedures" with "PAD ANQP procedures" (twice). On page 21 line 2, replace "ANQP-SD procedure" with "PAD ANQP procedure". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3055 | Yunsong Yang | 219 | 4 | 11.25a.1 | 20 | 22 | E | Y | 20.22 | 22 | 11.25a.1 |  |  | Lee Armstrong |  |  | Both instances of "ANQP-SD" on this line should be "PAD ANQP". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3058 | Yunsong Yang | 219 | 4 | 11.25a.2 | 21 | 1 | E | N | 21.01 | 1 | 11.25a.2 |  |  | Lee Armstrong |  |  | "If" in the sentence is no needed. | Replace "If the" with "The". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3059 | Yunsong Yang | 219 | 4 | 11.25a.2 | 21 | 2 | E | N | 21.02 | 2 | 11.25a.2 |  |  | Lee Armstrong |  |  | "ANQP-SD" should be "PAD ANQP". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3060 | Yunsong Yang | 219 | 4 | W1.1 | 29 | 41 | E | N | 29.41 | 41 | W1.1 |  |  | Lee Armstrong |  |  | "Based on" should be "If". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3061 | Yunsong Yang | 219 | 4 | W1.1 | 30 | 36 | E | N | 30.36 | 36 | W1.1 |  |  | Lee Armstrong |  |  | "Based on" should be "If". | As commented. |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3063 | Ahmadreza Hedayat | 219 | 4 | 4.5.9.1.1 | 4 | 3 | E | Y | 4.03 | 3 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | ... Client (SIC)and a Service Information Registry (SIR). | ... Client (SIC) and a Service Information Registry (SIR). |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3065 | Jouni Malinen | 219 | 4 | 4.5.9.1.1 | 6 | 17 | E | Y | 6.17 | 17 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | Typos in a figure ("solcited" vs. "solicited"). | In Figure 4-11a (page 6 lines 15-16), replace "Unsolicted" with "Unsolicited" and "Solicted" with "Solicited". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3066 | Jouni Malinen | 219 | 4 | 9.4.2.27 | 13 | 41 | E | Y | 13.41 | 41 | 9.4.2.27 |  |  | Lee Armstrong |  |  | Incorrect procedure name in Table 9-134 (copy-paste error from the previous row?). | On page 13 line 41 (Table 9-134 "PAD ANQP" row), replace "Indicates support for Solicited PAD procedure" with "Indicates support for PAD ANQP procedure". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3067 | Jouni Malinen | 219 | 4 | 9.4.2.217 | 15 | 53 | E | Y | 15.53 | 53 | 9.4.2.217 |  |  | Lee Armstrong |  |  | Wrong word or typo? | On page 15 line 53, replace "For example, of service name of print service is" with "For example, the service name of print service is" |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3068 | Jouni Malinen | 219 | 4 | 9.4.5.1 | 16 | 35 | E | N | 16.35 | 35 | 9.4.5.1 |  |  | Lee Armstrong |  |  | Inconsistent style in editing instruction. | On page 16 line 35, replace "Inserting new rows" with "Insert new rows". |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN
3043 | stephane baron | 219 | 4 | 4.5.9.1.1 | 4 | 30 | E | N | 4.3 | 30 | 4.5.9.1.1 |  |  | Lee Armstrong |  |  | "proxy server" should be replaced by "service information registry" | same as comment |  | GEN | LB219 Editorial | [5 empty] | 2016-05-17 00:02 | GEN

## Solicited PAD
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3071 | Jouni Malinen | 219 | 4 |  |  |  | T | Y |  |  |  |  | V | Mike Montemurro |  |  | Regarding CID 2143 in the previous LB, it does not sound justifiable to ignore the issue which the group seemed to agree to existing based on the resolution. If the group cannot come to a conclusion on how to resolve the comment, I can propose a different way of getting this issue resolved: remove the Solicited PAD procedure completely. That said, I'd still accept a mechanism that implements the Solicited PAD procedure in a manner that does not cause significant increase in the number of undesired management frames. I don't think it is acceptable to introduce new mechanism using Probe Request frames in a manner that makes existing devices reply to them in case where no such response is desired. CID 2143 listed number of ways of doing this more properly. | Remove the Solicited PAD procedure from P802.11aq. | REVISED (GEN: 2016-05-19 00:41:22Z). Incorporate changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:42 | GEN
3070 | Jouni Malinen | 219 | 4 | 11.25a.3 | 21 | 22 | T | Y | 21.22 | 22 | 11.25a.3 |  | V | Mike Montemurro |  |  | Solicited PAD procedure does not describe clearly when the AP replies to a Probe Request frame based on whether there are matching services. Some text for this was added in 11.25a.3 (Solicited PAD procedure; the second paragraph there). However, "it shall respond" is only describing a case where the AP replies. There is no "otherwise, it shall not reply" type of statement indicating when this does not happen. In addition, this is not really the correct clause for describing rules on when a STA replies to a Probe Request frame. Without the AP rules being clearly described, the solicited PAD procedure can cause significant harm to networks by increasing the number of unnecessary management frames. | Update 11.1.4.3.4 (Criteria for sending a probe response) to indicate clearly when an AP does not reply to a Probe Request frame based on there being no match to the requested service. | REVISED (GEN: 2016-05-19 00:46:38Z). The Solicited PAD has been moved to a Public Action frame with the acceptance of document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:48 | GEN
3042 | Michael Montemurro | 219 | 4 | W1.2 | 32 | 32 | T | Y | 32.32 | 32 | W1.2 |  | V | Mike Montemurro |  |  | The figure should be updated to remove the Solicited PAD procedures with a public action frame, possibly an ANQP element. | Replace the figure based on the updated Solicited PAD procedures that make use of public Action Frames. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:49:36Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:50 | GEN
3041 | Michael Montemurro | 219 | 4 | W1.1 | 30 | 30 | T | Y | 30.3 | 30 | W1.1 |  | V | Mike Montemurro |  |  | The figure should be updated to remove the Solicited PAD procedures with a public action frame, possibly an ANQP element. | Replace the figure based on the updated Solicited PAD procedures that make use of public Action Frames. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:48:37Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:50 | GEN
3039 | Michael Montemurro | 219 | 4 | 11.25a.3 | 21 | 12 | T | Y | 21.12 | 12 | 11.25a.3 |  | V | Mike Montemurro |  |  | Re-define Solicited PAD procedures to use Public Action frames, or even ANQP/GAS frames. Overloading Active Scanning procedures makes the mechanisms far too complicated. | Add an ANQP protocol (or other GAS protocol) based on current modificiations to the Probe Request/Response to support solicited PAD. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:46:07Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:46 | GEN
3038 | Michael Montemurro | 219 | 4 | 9.4.5.1 | 17 | 30 | T | Y | 17.3 | 30 | 9.4.5.1 |  | V | Mike Montemurro |  |  | Include the solicited PAD procedure as an ANQP request/response (or any type of GAS request/response) based on what is currently included in Probe Request/Response) | Add an ANQP protocol (or other GAS protocol) based on current modificiations to the Probe Request/Response to support solicited PAD. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:45:50Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:46 | GEN
3037 | Michael Montemurro | 219 | 4 | 9.3.3.10 | 12 | 7 | T | Y | 12.07 | 7 | 9.3.3.10 |  | V | Mike Montemurro |  |  | Service Hash should not be included in a Probe Request frame. | Remove the parameter and all modificiations to the Probe Request. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:45:25Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:46 | GEN
3036 | Michael Montemurro | 219 | 4 | 9.3.3.3 | 11 | 15 | T | Y | 11.15 | 15 | 9.3.3.3 |  | J | Mike Montemurro |  |  | The Service Advertisement is missing from the Beacon frame | Add the Service Advertisement to Beacon frames, otherwise PAD cannot be used with passive scanning procedures). | REJECTED (GEN: 2016-05-19 00:43:58Z). This element has been deleted in document 11-16-0695r3. | GEN | Solicited PAD | discussed |  |  |  |  | 2016-05-19 00:45 | GEN
3035 | Michael Montemurro | 219 | 4 | 6.3.3.2.2 | 6 | 44 | T | Y | 6.44 | 44 | 6.3.3.2.2 |  | V | Mike Montemurro |  |  | The scan.request should not be used for Solicited PAD | Remove the parameter as well as the clause 6.3.3.2.3. The commentor will provide an alternative contribution for solicited PAD. | REVISED (GEN: 2016-05-19 00:42:51Z). Incorporate the changes in document 11-16-0695r3. | GEN | Solicited PAD | discussed | 11-16-0695 |  |  |  | 2016-05-19 00:43 | GEN

## PAD ANQP
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3054 | Yunsong Yang | 219 | 4 | 11.25.3.2.1 | 19 | 64 | T | Y | 19.64 | 64 | 11.25.3.2.1 |  | A | Stephen McCann |  |  | According to Clause 9.4.5.27, either the service name or the service hash may be placed in the Service Name field within this ANQP-element. But since Clause 11 is about the procedures, the "service name" here is not referring to the Service Name field, rather the content in that field. Therefore, both possible contents in that field should be mentioned here, recognizing that this only applies to ANQP-based request. | Change "A service name may be placed with the request." to "A service name or a service hash generated from the service name may be placed within such an ANQP request." | ACCEPTED (GEN: 2016-05-19 00:58:51Z). | GEN | PAD ANQP | discussed | Text will be in doc. 11-16-0695r3. |  |  |  | 2016-05-19 00:59 | GEN
3053 | Yunsong Yang | 219 | 4 | 9.4.5.28 | 18 | 46 | T | Y | 18.46 | 46 | 9.4.5.28 |  | V | Stephen McCann |  |  | Both instances of "Query Request" in this sentence should be "Query Response". | As commented. | REVISED (GEN: 2016-05-19 00:55:36Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:56 | GEN
3031 | Stephen McCann | 219 | 4 | 11.25a.4 | 21 | 49 | T | N | 21.49 | 49 | 11.25a.4 |  | V | Stephen McCann |  |  | The PAD ANQP procedure is another ANQP-element procedure and should be moved into clause 11.25. | Move 11.25.a.4 into section 11.25.3.2.1 and merge with clause 11.25.3.2.16. Rename the new clause "Service Information ANQP procedure", so that it conforms to the other ANQP procedure clauses in REVmc D5.2. Remove all references to PAD ANQP procedures, as they are just ANQP procedures. | REVISED (GEN: 2016-05-19 00:59:31Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 01:00 | GEN
3030 | Stephen McCann | 219 | 4 | 11.25.3.2.16 | 19 | 59 | T | N | 19.59 | 59 | 11.25.3.2.16 |  | V | Stephen McCann |  |  | This clause seems to be identical to clause 11.25a.4. Merge the two clauses together. | As per comment | REVISED (GEN: 2016-05-19 00:57:35Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:58 | GEN
3029 | Stephen McCann | 219 | 4 | 11.25.3.2.1 | 19 | 19 | T | N | 19.19 | 19 | 11.25.3.2.1 |  | J | Stephen McCann |  |  | In Table 11-15., merge the two ANQP-elements into one of ANQP-element type "Q, R". | As per comment | REJECTED (GEN: 2016-05-19 00:55:52Z). TGaq members agree to maintain a request and response ANQP-element separately. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:57 | GEN
3028 | Stephen McCann | 219 | 4 | 11.25a.4 | 21 | 55 | T | N | 21.55 | 55 | 11.25a.4 |  | V | Stephen McCann |  |  | The Service Information ANQP-elements should be capable of being used by themselves, without having to use either unsolicted or solicited PAD beforehand. This is the default behaviour of all the other ANQP-elements. | Remove the word "more" from the sentence "... to obtain more information...". In the last sentence P21L57 of this paragraph, change "the Service Name" to "a Service Name" and "the instance Name" to "a Instance Name". | REVISED (GEN: 2016-05-19 01:00:08Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 01:00 | GEN
3027 | Stephen McCann | 219 | 4 | 9.4.5.27 | 17 | 36 | T | N | 17.36 | 36 | 9.4.5.27 |  | V | Stephen McCann |  |  | The Service Information Request ANQP-element doesn't appear to be capable of performing a wild card search for "all services" known to the SIR. The special value of Service Name Length being equal to 0, is rather limiting and confusing. | Change the text so that the Service Name Length is equal to 0xFF when it uses the Service Hash, as opposed to 0. Alternatively add a separate bit to the ANQP-element for this option. | REVISED (GEN: 2016-05-19 00:54:51Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:55 | GEN
3026 | Stephen McCann | 219 | 4 | 9.4.5.27 | 16 | 45 | T | N | 16.45 | 45 | 9.4.5.27 |  | J | Stephen McCann |  |  | The format of the Service Information Request and Response ANQP-elements is basically the same. As GAS indicates whether the transported message is either a query or a response already, it should be possible to merge the these ANQP-elements into one single frame, in a similar way to the TDLS ANQP-element in IEEE 802.11 REVmc D5.2 | Commenter will provide a submission to merge the two ANQP-elements together. | REJECTED (GEN: 2016-05-19 00:53:40Z). TGaq members agree to maintain a request and response ANQP-element separately. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 00:54 | GEN
3015 | Stephen McCann | 219 | 4 | 4.5.9.1 | 3 | 38 | E | N | 3.38 | 38 | 4.5.9.1 |  | V | Stephen McCann |  |  | Move the references to a network from the last sentence in this paragraph to the first | Change the first sentence of the paragraph to read "PAD is a service provided by a PBSS or BSS (i.e. a network)...". Remove the text "(i.e. a network)" from the last sentence in this paragraph. | REVISED (GEN: 2016-05-19 01:00:45Z). Incorporate the changes in document 11-16-0695r3. | GEN | PAD ANQP | discussed |  |  |  |  | 2016-05-19 01:01 | GEN

## Broadcast Solicited PAD
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
3011 | Su Khiong Yong | 219 | 4 | 11.25.A3 | 21 | 21 | T | Y | 21.21 | 21 | 11.25.A3 |  | J | Mike Montemurro |  |  | Additional filtering rules should be added to reduce the probe response frames from legacy APs. | Replace line 21-42 on page 21 with the following text When dot11SolicitedPADActivated is true, a non-AP STA sends Probe Request frames with a Service Hash element, which includes one or more service hashes generated from the service name(s) of the service(s) that the non-AP STA is requesting, to an AP or PCP. The Probe Request frames shall have address 1 field sets to PAD Multicast Address (TBD) and address 3 field set to PAD BSSID (TBD). When dot11SolicitedPADActivated is true, an AP or PCP that receives Probe Request frames shall respond with a Probe Response that includes Service Hint element or Service Advertisment element, if the address 1 and address 3 in the Probe Request are the PAD Multicast Address and PAD BSSID address of the STA. If Service Advertisement element is included in the Probe Response frame, the When dot11SolicitedPADActivated is true, an AP or PCP shall verify if there are any services matching those in the received Probe Request frame. The matching of service is based on the service hash value in the Service Hash field of the Service Hash element matches to the corresponding service hash value of the service in which the AP or PCP is offering. If the AP or PCP determines there is one or more matching matched services, the AP or PCP shall respond with a Probe Response frame with the Service Advertisement element containing a Basic Service Information Descriptor field for each matching service. The requesting non-AP STA shall process the Service Advertisement element in the received Probe Response frame to determine if any received service name matches with a service name that the non-AP STA is requesting and the corresponding instance names. If there is a matching matched service name, the non-AP STA may decide to proceed with the PAD ANQP-SD procedure (10.26.4 (PAD ANQP-SD procedure) or authentication and association procedure (10.3 (STA authentication and association)) based on the nature of the service (see examples illustrated in Annex AA.1 (Pre-association discovery usage scenarios)), the details of which are out of the scope of this standard. If Service Hint element is included in the Probe Response frame, the AP or PCP is not required to perform service matching with those services in the received Probe Request frame. The requesting non-AP STA shall determine the bit positions of the Bloom Filter Bit Array field in which the non-AP STA is searching, and verify if there are any matched services based on the matching of the corresponding bit positions of the of the Bloom Filter Bit Array field of the Service Hint element. If there is a matched service, the non-AP STA may determine to proceed with PAD ANQP procedure ( 10.26.4 (PAD ANQP procedure), or authentication and association procedure (10.3 (STA authentication and association)) based on the perceived false positive probability and the nature of the service (see examples illustrated in AA.1 (Preassociation discovery usage scenarios)), the details of which are out of the scope of this standard. | REJECTED (GEN: 2016-05-19 01:04:23Z). The TG members can not reach consensus on a technical resolution to the comment. | GEN | Broadcast Solicited PAD | discussed |  |  |  |  | 2016-05-19 01:55 | GEN