## Slide 1: TGak May Closing Report
Date: 2016-05-19
Authors:

## Slide 2: Abstract
Closing Report of IEEE 802.11 Task Group ak at the IEEE 802.11 Meeting, March 2016, held at the Hilton Waikoloa, Big Island, Hawai‘i.

## Slide 3: TGak Closing Report
Accomplishments
  Met jointly:
    With 802.11 ARC SC Thursday AM1.
  Generated Draft D2.1 and D2.2 which have been posted.
  TGak has resolved 227 of our 346 comments from recirculation LB218 and all unresolved comments have been assigned to someone.
  An annotated agenda is in 11-16/0513.
  The minutes will be in 11-16/0749.

## Slide 4: TGak Closing Report
Teleconferences
  Decided to hold 1 ½ hour teleconferences, to be joint with 802.1Qbz if mutually convenient, on Monday, June 6th, 13th, and 20th, and July 11th, all at 10am Eastern US time.
July 2016 Plans
  Resolve comments from WG recirculation ballot.
  Joint meeting with 802.11 ARC SC and 802.1 TSN.