## Slide 1: IEEE 802.11mc Closing Report for July 2016
Date: 2016-07-28
Authors:

## Slide 2: Abstract
This document contains the TGmc closing report for July 2016.

## Slide 3: Status
Sponsor Ballot Comment resolution
  334 comments received and resolved (second recirc SB, 93% approval) on P802.11REVmc D6.0.
  Approved motion for SB recirculation on D7.0
Agenda, includes motions
  https://mentor.ieee.org/802.11/dcn/16/11-16-0785-11-000m-tgmc-agenda-july-2016.pptx
Comment resolution spreadsheet
  11-15-532

## Slide 4: TGmc Plan of Record - modified
Slide 4
20 July 2012 – 12 Sept 2012 – Call for Comment/Input
29-30 Aug 2012 – NesCom, SASB PAR Approval
Sept 2012 – Begin to process CC input, 11aa, 11ae integration
Dec 2012 – March/May 2013 – 11ad integration
Jan 2013 – First WG Letter ballot - without 11ad – on D1.0
Sept 2013 – Letter ballot on D2.0
Dec 2013 – May 2014 – 11ac, 11af integration – D3.0 in May 2014
July 2014 – Mandatory Draft Review
Jan 2015 – D4.0 Recirculation
Form Sponsor Pool: Open Dec 15th or so, close Feb 20, 2015 –good for 6 months (end of July 2015)
D4.0 Initial Sponsor Ballot 2015-03-27 through 2015-04-26
D5.0 Jan 2016 Initial SB recirculation
D6.0 Second Recirculation 2016-06-07 through 2016-06-30
D7.0 August/September Third/Fourth (unchanged) Recirculation
October 2016 – WG/EC Final Approval Oct 4th telecon
December 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 4

## Slide 5: TGmc SB Planning
Slide 5
June 2016
  2rd recirculation D6.0 2016-06-07 to 2016-06-30
July 2016
  Comment resolution on D6.0
August/Sept 2016
  July 30 – Aug 15 editing and review of editing
  3th recirculation D7.0 August 15-25
  On or before Sept 9: Complete comment resolution (goal: unchanged draft)
  4th recirculation D7.0 unchanged Sept 10 - 20: 10 day recirculation of unchanged draft
October 4th: EC teleconference approval – request unconditional approval for TGmc
  October 17th deadline for submission to Revcom
December 2016 – RevCom/SASB Approval
Notes: doc.: IEEE 802.11-10/0503r4
May 2010
        Michael Montemurro, Research in Motion
Page 5

## Slide 6: July – September 2016 Meeting Planning
Objectives:
  Complete 3rd Sponsor Ballot comment resolution, Initiate 4th recirculation
  Prepare Report to EC for Unconditional approval (Oct 4th teleconference),
  Sept 2016 WG approval for proceeding to RevCom
Conference calls 10am Eastern 2 hours
  August 12, 2 hours if needed; other calls scheduled with 10 day notice
Ballot Resolution Committee meeting –
  None currently scheduled
Availability of 11mc in the IEEE store
  D6.0 is available (add D7.0 after SB approval), see http://www.techstreet.com/ieee/products/1867583
Forward to ISO JTC1/SC6 WG1
  D5.0 forwarded; D6.0 & D7.0 will be forwarded upon SB approval