## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-16/1203r06
Venue Date: | September 2016
First Author: | Marc Emmelmann
Subject: | Comments from 4th Recirculation SB on TGai D10.0
Full Date: | 2016-09-15
Author(s): | Marc Emmelmann
| Company: | self
Address
Phone:
Fax:
| email: | emmelmann@ieee.org
Abstract:
Comments from 4th Recirculatoin SB on TGai D10.0

## 4th SB Recirc -- All Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
31101 | Hamilton, Mark | 5000 | 10 | 9.3.3.9 | 43 | 30 | T | Yes | 43 | 30 | 9.3.3.9 |  | A |  |  | 360 | Key Delivery "Order" column should be 40, not 49. | Change "49" to "40" | Accept | EDITOR | 2016-09-11-Editor | Approved |  |  |  |  | 2016-09-13 06:31 | TGai General
31102 | Hamilton, Mark | 5000 | 10 | 12.7.1.7.2 | 132 | 3 | T | Yes | 132 | 3 | 12.7.1.7.2 |  | V |  |  | 361 | Changes here don't relate to the baseline, anymore. | Remove these changes (and the "ed note"). Changes should be made in 12.7.1.2 to introduce these new AKMs. | Revise. Incorporate text changes in 11-16/1151r5 (https://mentor.ieee.org/802.11/dcn/16/11-16-1151-05-00ai-kdf-prf-pkex.docx) for CIDs 31228, 31112, and 31102. | EDITOR | 2016-09-13-AM1 | Approved |  |  |  |  | 2016-09-13 08:22 | TGai General
31103 | Hamilton, Mark | 5000 | 10 | 12.7.2 | 133 | 15 | E | Yes | 133 | 15 | 12.7.2 |  | V |  |  | 361 | The deletion of the period here (to match REVmc better?) now makes this sentence not read correctly. | Change the start of the sentence to, "Key MIC (bit 8), when the negotiated AKM is not an AEAD cipher, is set to 1 if ..." | Revise. Replace this item in 12.7.2 (page 131 lines 24-27) with: "Key MIC (bit 8) is set to 1 if not using an AEAD cipher and a MIC is in this EAPOL-Key frame, and is set to 0 otherwise." showing the modification to the baseline. | EDITOR | 2016-09-13-AM1 | Approved |  |  |  |  | 2016-09-13 08:22 | TGai General
31104 | Hamilton, Mark | 5000 | 10 | C.3 | 166 | 62 | T | No | 166 | 62 | C.3 |  | V |  |  | 361 | The renaming of this attribute to "FILSImplemented" is odd and confusing, and not consistent with the usage directions coming from ARC SC discussions (see 11-15/0355 for a work-in-progress). If there are both <xxx>Implemented and <xxx> Activated, they should relate to each other, and relate to the same feature(s). In the 11ai Draft 10.0, FILSImplemented is used to manage the use of Differential Initial Link Setup elements, and FILSActivated is used to manage the use of everything else "FILS". The latter makes sense. The former does not. Further, from the PICS, it seems that this feature (Differential Initial Link Setup) is only valid if CFFILS is true, but the body text does not cover this. | Rename "FILSImplemented" to something else (I gather "DILSImplemented" was not acceptable). Add text in 11.47.5.2 to indicate that this attribute can be true on STAs that have FILSActivated true. | REVISED (TGai General: 2016-09-12 10:30:04Z) - Globally Replace "dot11FILSImplemented" with "dot11DILSImplemented" throughout P802.11ai. (5 instances) | EDITOR | 2016-09-13-AM1 | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. It looks like dot11DILSImplemented was renamed to dot11FILSImplemented in D10.0. There does not seem to be a comment requesting this change, so maybe this was done as an editorial fix to an assumed typo (FILS vs. DILS). However, this MIB variable was on purpose called dot11DILSImplemented since it identifies whether the STA implements support for DILS (not FILS). |  |  |  | 2016-09-13 16:42 | EDITOR
31105 | Perry, Lisa | 5000 | 10 |  |  |  | G | No |  |  |  |  | J |  |  | 360 | This draft meets all editorial requirements. |  | Reject. The comment does not identify a technical remidy but is provided by IEEE editorial staff to indicate that the draft meets all editorial requirements. | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31106 | EMMELMANN, MARC | 5000 | 10 | 9.3.3.9 | 43 | 30 | E | No | 43 | 30 | 9.3.3.9 |  | A |  |  | 360 | An editorial glitch occurred when aligning the Tgai draft with the REVmc D8.0 baseline. The order numbers were to be moved (upwards) but they all should have been consequitive numbers. Key Delivery "Order" column should be 40, not 49. It looks like a type (9 and 0 are next to each other on the keyboard) and making the number 49 is an editorial glitch that caused an unintended change | Change 49 to 40 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31107 | EMMELMANN, MARC | 5000 | 10 | 9.4.1.9 | 51 | 42 | E | Yes | 51 | 42 | 9.4.1.9 |  | A |  |  | 360 | Editorial glitch: while updating Tgai D10.0 to the REVmc D8.0 baseline, numbers assigned by ANA should not have been updated. But the formerly correct status code (as 112) was updtated to 108 | Revert the change, i.e.: Replace 108 with 112 | Accept | EDITOR | 2016-09-11-Editor | Approved |  |  |  |  | 2016-09-13 06:31 | TGai General
31108 | EMMELMANN, MARC | 5000 | 10 | 9.4.1.9 | 51 | 43 | E | Yes | 51 | 43 | 9.4.1.9 |  | A |  |  | 360 | Editorial glitch: while updating Tgai D10.0 to the REVmc D8.0 baseline, numbers assigned by ANA should not have been updated. But the formerly correct status code (as 113) was updtated to 109 | Revert the change, i.e.: Replace 109 with 113 | Accept | EDITOR | 2016-09-11-Editor | Approved |  |  |  |  | 2016-09-13 06:31 | TGai General
31109 | EMMELMANN, MARC | 5000 | 10 | 1 | 1 | 1 | E | No | 1 | 1 | 1 |  | J |  |  | 360 | Status Code 114 is assigned by ANA to Tgai but is not used in the draft (search for 114 did not return anything, neither in the redline nor in the clean D10.0). But the ANA database does not contain information that this status code is not used. | Send an update request to ANA to indicate for status code 114 that it is not used. | Reject. The comment does not identify a technical remidy of the draft. The 2nd Editor sent a corresponding request to ANA | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31110 | EMMELMANN, MARC | 5000 | 10 | 1 | 1 | 1 | E | No | 1 | 1 | 1 |  | J |  |  | 360 | Status Code 115 is assigned by ANA to Tgai but is not used in the draft (search for 114 did not return anything, neither in the redline nor in the clean D10.0). But the ANA database does not contain information that this status code is not used. | Send an update request to ANA to indicate for status code 115 that it is not used. | Reject. The comment does not identify a technical remidy of the draft. The 2nd Editor sent a corresponding request to ANA | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31111 | EMMELMANN, MARC | 5000 | 10 | 1 | 1 | 1 | E | No | 1 | 1 | 1 |  | J |  |  | 360 | Note: Search in Redline Tgai D10.0 against D9.0: could not find 107, so we did not use the ANA number assigned to Tgah could not find 109, so we did not use the ANA number assigned to Tgah could not find 111, so we did not use the ANA number assigned to Tgah could not find 111, so we did not use the ANA number assigned to Tgah This comment is intended to provide feedback to the Editors, i.e. providing a positive confirmation that the usage of ANA assigned numbers has been. Checked. No actions required. Please reject this comment as part of the comment resolution process. | No actions required. Please reject this comment but make the editors aware of it. | Reject: The comment does not identify a technical remedy. | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31112 | EMMELMANN, MARC | 5000 | 10 | 12.7.1.7.2 | 130 | 3 | E | No | 130 | 3 | 12.7.1.7.2 |  | V |  |  | 361 | Changes here don't relate to the baseline, anymore. | Remove these changes (and the "ed note"). Changes should be made in 12.7.1.2 to introduce these new AKMs. | Revise. Incorporate text changes in 11-16/1151r5 (https://mentor.ieee.org/802.11/dcn/16/11-16-1151-05-00ai-kdf-prf-pkex.docx) for CIDs 31228, 31112, and 31102. | EDITOR | 2016-09-13-AM1 | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31113 | EMMELMANN, MARC | 5000 | 10 | 12.7.2 | 131 | 24 | E | No | 131 | 24 | 12.7.2 |  | V |  |  | 361 | When bringing in the baseline REVmc D8.0, the sentence does only cover the case if AKM negotiated is not 00-0F-AC:14, 00-0F-AC:15, 00-0F-AC:16, or 00-0F-AC:17. But it it does not specify the value of the subfield if AKM negotiated is 00-0F-AC:14, 00-0F-AC:15, 00-0F-AC:16, or 00-0F-AC:17 | Add at the end of the sentence "When AKM negotiated is 00-0F-AC:14, 00-0F-AC:15, 00-0F-AC:16, or 00-0F-AC:17, the subfield is set to ...... | Revise. Replace this item in 12.7.2 (page 131 lines 24-27) with: "Key MIC (bit 8) is set to 1 if not using an AEAD cipher and a MIC is in this EAPOL-Key frame, and is set to 0 otherwise." showing the modification to the baseline. | EDITOR | 2016-09-13-AM1 | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31114 | EMMELMANN, MARC | 5000 | 10 | 6.3.3.3.1 | 14 | 45 | E | No | 14 | 45 | 6.3.3.3.1 |  | A |  |  | 360 | "This primitive returns the descriptions of the set of BSS(s) detected by the scan process." is the text in Tgai D10.0. The baseline REVmc D8.0 does not have the () at BSS(s) | Delete () at BSS(s) to align with baseline text | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31115 | EMMELMANN, MARC | 5000 | 10 | 6.3.7.2.2 | 22 | 49 | E | No | 22 | 49 | 6.3.7.2.2 |  | A |  |  | 360 | The parameters in MLME-ASSOCIATE.request do not match with the parameters in the baseline. The additions from Tgai are o.k., but the baseline text is not aligned: CapabilityInformation -- not included in baseline any more SMPowerSave is in baseline but not in TGai HT Capabilities is in TGai but not in baseline Extended Capabilites -- is in TGai but not in baseline 20/40 BSS Coexistence -- is in TGai but not in baseline VHT Capabilities -- is in TGai but not in baseline | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31116 | EMMELMANN, MARC | 5000 | 10 | 6.3.7.3.2 | 23 | 48 | E | No | 23 | 48 | 6.3.7.3.2 |  | A |  |  | 360 | The parameters of MLME-ASSOCIA TE.confirm do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned. SupportedRates is in Tgai but not any more in baseline RCPI.request should read "RCPI of request" RSNI.request should read "RSNI of request" RCPI.response should read RCPI of Response RSNI.response should read RSNI of Response HT Capabilities is in TGai but not any more in REVmc baseline D8.0 VHT Capabilities is in TGai but not any more in baseline | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31117 | EMMELMANN, MARC | 5000 | 10 | 6.3.7.4.2 | 24 | 62 | E | No | 24 | 62 | 6.3.7.4.2 |  | A |  |  | 360 | The parameters of MLME-ASSOCIATE.indication do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned. Supported Rates -- is in Tgai but not any more in baseline OperationalRateSet -- is in baseline but not in TGai BSSMembershipSelectorSet -- is in baseline but not in TGai | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31118 | EMMELMANN, MARC | 5000 | 10 | 6.3.7.5.2 | 26 | 11 | E | No | 26 | 11 | 6.3.7.5.2 |  | A |  |  | 360 | The parameters of MLME-ASSOCIATE.response( do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned. CapabilityInformation -- is in Tgai but not any more in baseline EDCA ParameterSet -- is in Tgai but not any more in baseline DSERegisteredLocation -- is in TGai but not any more in baseline HT Capabilities -- is in TGai but not in baseline Extended Capabilities -- is in TGai but not in baseline 20/40 BSS Coexistence -- is in TGai but not in baseline QMFPolicy -- is in TGai but not in baseline DMG Capabilities -- is in TGai but not in baseline Multi-band local -- is in TGai but not in baseline VHT Capabilities -- is in TGai but not in baseline | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31119 | EMMELMANN, MARC | 5000 | 10 | 6.3.8.2.2 | 27 | 46 | E | No | 27 | 46 | 6.3.8.2.2 |  | A |  |  | 360 | The parameters of MLME-REASSOCIATE.request( do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned. CapabilityInformation -- is in Tgai but not in baseline HT Capabilities -- is in Tgai but not in baseline Extended Capabilities -- is in TGai but not in baseline 20/40 BSS Coexistence -- is in TGai but not in baseline VHT Capabilities -- is in TGai but not in baseline SM Power Save -- is in baseline but not in TGai | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31120 | EMMELMANN, MARC | 5000 | 10 | 6.3.8.3.2 | 28 | 49 | E | No | 28 | 49 | 6.3.8.3.2 |  | A |  |  | 360 | The parameters of MLME-REASSOCIA TE.confirm do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned. Supported Rates -- is in Tgai but not in baseline RCPI.request should read "RCPI of Request" RSNI.request should read "RSNI of request" RCPI.response should read "RCPI of response" RSNI.response should read "RSNI of Response" HT Capabilities -- is in TGai but not in baseline VHT Capabilities -- is in TGai but not in baseline | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31121 | EMMELMANN, MARC | 5000 | 10 | 6.3.8.4.2 | 29 | 1 | E | No | 29 | 1 | 6.3.8.4.2 |  | A |  |  | 360 | The parameters of MLME-REASSOCIA TE.confirm do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned. OperationalRateSet -- is in baseline but not in TGai SupportedRates -- is in Tgai but not in baseline BSSMembershipSelectorSet -- is in baseline but not in TGai | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31122 | EMMELMANN, MARC | 5000 | 10 | 6.3.8.5.2 | 31 | 33 | E | No | 31 | 33 | 6.3.8.5.2 |  | A |  |  | 360 | The parameters of MLME-REASSOCIA TE.response do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned CapabilityInformation -- is in Tgai but not in baseline EDCAParameterSet -- is in Tgai but not in baseline DSERegisteredLocation -- is in TGai but not in baseline HT Capabilities -- is in TGai but not in baseline Extended Capabilities -- is in TGai but not in baseline 20/40 BSS Coexistence -- is in TGai but not in baseline DMG Capabilities -- is in TGai but not in baseline Mulit-band local -- is in TGai but not in baseline MMS -- is in TGai but not in baseline VHT Capabilities -- is in TGai but not in baseline | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31123 | EMMELMANN, MARC | 5000 | 10 | 6.3.11.2.2 | 33 | 12 | E | No | 33 | 12 | 6.3.11.2.2 |  | A |  |  | 360 | The parameters of MLME-START.request do not match with the baseline text. The additions from Tgai are o.k., but the baseline text is not aligned NAVSyncDelay -- is in baseline but not in TGai ProbeDelay -- is in Tgai but not in baseline | Align the baseline text in Tgai D10.0 with REVmc D8.0 | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31124 | EMMELMANN, MARC | 5000 | 10 | 6.3.105 | 35 | 4 | E | No | 35 | 4 | 6.3.105 |  | A |  |  | 360 | Editorial instructions still contain a reference to a submission. | Delete that reference | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31125 | EMMELMANN, MARC | 5000 | 10 | 9.3.3.3 | 40 | 9 | E | No | 40 | 9 | 9.3.3.3 |  | A |  |  | 360 | Table 9-27: Tgai inserts new entires into the table. Tgai draft start with "order 66" for the first newly inserted entry; but the baseline already occupies entries up to order number 67 | Change the order numbers in Tgai draft to start with 68 (= first free order number). | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31126 | EMMELMANN, MARC | 5000 | 10 | 9.4.1.9 | 51 | 35 | E | No | 51 | 35 | 9.4.1.9 |  | A |  |  | 360 | An editorial instructions is missing that the entry for the reserved values needs to be adjusted. | Extend the editorial instructions to state that the values reserved need to be adjusted correspondingly. | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31127 | EMMELMANN, MARC | 5000 | 10 | 9.4.1.11 | 51 | 51 | E | No | 51 | 51 | 9.4.1.11 |  | A |  |  | 360 | An editorial instructions is missing that the entry for the reserved values needs to be adjusted. | Extend the editorial instructions to state that the values reserved need to be adjusted correspondingly. | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31128 | EMMELMANN, MARC | 5000 | 10 | 9.4.2.27 | 56 | 23 | E | No | 56 | 23 | 9.4.2.27 |  | V |  |  | 364 | Table 9-134 in Tgai draft: Cls. 9.4.2.27 does not contain a Table 9.135. The table number should be 9-135. Also, the table title is wrong. The baseline calls the table "Extended Capabilities field" whereas Tgai calls the table "Capabilities Field" Missing editorial note that the values for the Reserved entry in the table need to be adjusted. | fix table number to match REVmc D8.0; adjust table title as well; extend editoiral instructions | CID 31128: : Revised: Correct the table number to be 9-135, change the table title to match baseline, change the Reserved row in the baseline from "72, 75 - n" to "75 - n". | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-15 10:30 | EDITOR
31129 | EMMELMANN, MARC | 5000 | 10 | 9.4.2.171.1 | 57 | 27 | E | No | 57 | 27 | 9.4.2.171.1 |  | V |  |  | 366 | Figure 9-581 does not show any changes as compared to the base line. Is this intended? If so, why do we have to include the figure? Note: it is possible that the figure is included as ther might be an inserted new sentence just below the figure; but that sentence is not underlined | Assure that there is no intended change to the figure; if the figure is not intended to be changed, do not include the figure in Tgai draft. | Revised: The Baseline figure is not to be changed. Remove the Figure from the Tgai. | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-15 10:31 | EDITOR
31130 | EMMELMANN, MARC | 5000 | 10 | 9.4.2.171.1 | 57 | 38 | E | No | 57 | 38 | 9.4.2.171.1 |  | V |  |  | 360 | The sentence starting at L38 is not in the baseline but it is not underlinded in Tgai draft hence not indicating an insertion here | Underline the sentence | Revised. Delete the sentence cited in the comment | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31131 | EMMELMANN, MARC | 5000 | 10 | 9.4.2.171.1 | 57 | 44 | E | No | 57 | 44 | 9.4.2.171.1 |  | V |  |  | 366 | Figure 9-582 does not show any changes as compared to the base line. Is this intended? If so, why do we have to include the figure? Note: it is possible that the figure is included as ther might be an inserted new sentence just above the figure; but that sentence is not underlined | Assure that there is no intended change to the figure; if the figure is not intended to be changed, do not include the figure in Tgai draft. | Revised: The Baseline figure is not to be changed. Remove the Figure from the TGai. | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-15 10:32 | EDITOR
31132 | EMMELMANN, MARC | 5000 | 10 | 9.4.2.171.1 | 58 | 49 | E | No | 58 | 49 | 9.4.2.171.1 |  | A |  |  | 360 | Missing "The" at the beginning of the sentence to match text in baseline | Insert "The" at beginning of sentence | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31133 | EMMELMANN, MARC | 5000 | 10 | 9.4.2.175 | 59 | 46 | E | No | 59 | 46 | 9.4.2.175 |  | A |  |  | 360 | The editorial instruction says "insert NEW subclauses" and then, the subclauses start with 9.4.2.175. But the baseline does already contain a subclause 9.4.2.175. | Increase the subclause number of the newly inserted subclauses to start with 9.4.2.176. Pay attention that the numbers for all new subclauses need to be increased in the following. | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31134 | EMMELMANN, MARC | 5000 | 10 | 9.4.5.23 | 77 | 37 | E | No | 77 | 37 | 9.4.5.23 |  | A |  |  | 360 | The editorial instruction says "insert NEW subclauses" and then, the subclauses start with 9.4.5.23. But the baseline does already contain a subclause 9.4.5.23. | Adjust the subclause number to 9.4.5.24 (which is the first free subclause number in the baseline) Increase following new subclause numbers as well, i.e. for all subclauses 9.4.5.23 ff | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31135 | EMMELMANN, MARC | 5000 | 10 | 11.1.4.1 | 95 | 31 | E | No | 95 | 31 | 11.1.4.1 |  | A |  |  | 360 | Missing underline of word "procedures" which is inserted by Tgai | underlind "procedures" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31136 | EMMELMANN, MARC | 5000 | 10 | 11.1.4.1 | 96 | 12 | E | No | 96 | 12 | 11.1.4.1 |  | A |  |  | 360 | "or actively": the or does not need to be underlinded | do not underline the "or" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31137 | EMMELMANN, MARC | 5000 | 10 | 11.1.4.3.2 | 98 | 27 | E | No | 98 | 27 | 11.1.4.3.2 |  | A |  |  | 360 | Tgai intendes to delete the entire paragraph. So the delted text should match REVmc, but it still contains (underlined) text | Remove the underlined text from thr paragraph | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31138 | EMMELMANN, MARC | 5000 | 10 | 11.3.1 | 103 | 33 | E | No | 103 | 33 | 11.3.1 |  | A |  |  | 360 | Wrong cls. Number. Does not match baseline. Should be 11.3.2 instead | Change clause number to 11.3.2 Change as well the cls. Numbers of the following subclauses to accomodate for this increase in cls. Numbering | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31139 | EMMELMANN, MARC | 5000 | 10 | 11.3.1 | 103 | 35 | E | No | 103 | 35 | 11.3.1 |  | V |  |  | 360 | Wrong editorial instructions. The figure to be changed is numbered 11-13 in the baseline | Adjust editorial instructions | Revised. The editorial instructions are adjusted. | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31140 | EMMELMANN, MARC | 5000 | 10 | 11.3.5.1 | 107 | 3 | E | No | 107 | 3 | 11.3.5.1 |  | V |  |  | 361 | There is a descrepancy between the baseline and Tgai draft. The baseline reads: "Successful reassociation when not in State 1 sets the STA's state to State 2 ..." Tgai reads: "Successful reassociation set the non-FILS STAs state to State 3 ... There are several issue which might not be only editoria: unsuccessfull is now successfull The State 1 statement is missing. There has to be a precice editorial instruction here. It looks like the 2nd sentence (starting in L1P107 with "Unseccessful ...." is not underlined though inserted by TGai | Make the changes clear. | Revised. On page 107 line 8 replace "Successful reassociation sets a FILS STA’s state to State 4 and enables it to exchange Class 3 frames." with "Successful reassociation sets a FILS STA’s state to State 4 (with respect to the AP or PCP that was sent the Reassociation Request frame) and enables it to exchange Class 3 frames." | EDITOR | 2016-09-13-AM1 | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31141 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.1.1 | 121 | 41 | E | No | 121 | 41 | 12.6.1.1.1 |  | A |  |  | 360 | the "or" should not be underlined at the end of the marked insertion | Do not underline the "or" at the end of the inserted text | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31142 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.1.1 | 121 | 54 | E | No | 121 | 54 | 12.6.1.1.1 |  | A |  |  | 360 | "handshake, FT authentication" The baseline as a "or" in front of "FT authentication" which is removed by Tgai. | insert "or" (and make it strke-through) in front of "FT authentication" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31143 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.1.1 | 121 | 57 | E | No | 121 | 57 | 12.6.1.1.1 |  | A |  |  | 360 | "handshake, successful 4-way handshake, successful FT" The first "successful" is underlined but exists in the baseline; the second one is not underlinded but is inserted by Tgai. | Remove underline of first "successful" and underline the second one | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31144 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.1.1 | 121 | 58 | E | No | 121 | 58 | 12.6.1.1.1 |  | V |  |  | 360 | "4-way handshake, the Reassociation Response " The baseline has a "or" after the comma which is not shown. | Insert or after "," | Revised: insert "or" in strkethrough to indicate deletion by Tgai | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31145 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.3.2 | 124 | 11 | E | No | 124 | 11 | 12.6.1.3.2 |  | A |  |  | 360 | Sentence under (a): Period at end of line already in baseline; no need to underline | remove underline | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31146 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.3.2 | 125 | 11 | E | No | 125 | 11 | 12.6.1.3.2 |  | A |  |  | 360 | "A STA can cache": baseline reads "A STA (AP) can cache". | insert "(AP) to match baseline | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31147 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.3.2 | 125 | 11 | E | No | 125 | 11 | 12.6.1.3.2 |  | A |  |  | 360 | "PMKSAs" -- change already done in baseline. No need to underline "SA" in the word | remove underline | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31148 | EMMELMANN, MARC | 5000 | 10 | 12.6.1.3.2 | 125 | 14 | E | No | 125 | 14 | 12.6.1.3.2 |  | A |  |  | 360 | "PMKSAs" -- change already done in baseline. No need to underline "SA" in the word | remove underline | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31149 | EMMELMANN, MARC | 5000 | 10 | 12.6.10.3 | 126 | 48 | E | No | 126 | 48 | 12.6.10.3 |  | A |  |  | 360 | Tgai reads: "The PMK in the PMKSA" The baseline reads: "The PMKSA in the PMKSA" Tgai intended to correct this error in the baseline, i.e. delete "SA" from first acronym but did not show this deltion. | Add "SA" in strikethrough to the "PMK" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31150 | EMMELMANN, MARC | 5000 | 10 | 12.7.6.3 | 133 | 23 | E | No | 133 | 23 | 12.7.6.3 |  | A |  |  | 360 | "message 2" is underlined but already in the baseline | remove underline from "message 2" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31151 | EMMELMANN, MARC | 5000 | 10 | 12.7.6.3 | 133 | 29 | E | No | 133 | 29 | 12.7.6.3 |  | A |  |  | 360 | "message 2" is underlined but already in the baseline | remove underline from "message 2" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31152 | EMMELMANN, MARC | 5000 | 10 | 9.4.1.11 | 51 | 51 | E | Yes | 51 | 51 | 9.4.1.11 |  | A |  |  | 360 | Editorial glitch: while updating Tgai to the newest baseline, the code in Tabel 9-47 was adjusted even though it should have not as it it controlled by ANA. The code should not be "22" but "26" instead. | Change 22 to 26 | Accept | EDITOR | 2016-09-11-Editor | Approved |  |  |  |  | 2016-09-13 06:31 | TGai General
31153 | Malinen, Jouni | 5000 | 10 | 9.4.2.25.3 | 55 | 63 | E | No | 55 | 63 | 9.4.2.25.3 |  | A |  |  | 360 | Inconsistent spelling of SHA-384. | In Table 9-133 (page 55 line 63), replace "SHA 384" with "SHA-384". | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31154 | Malinen, Jouni | 5000 | 10 | 12.7.1.3 | 128 | 12 | E | No | 128 | 12 | 12.7.1.3 |  | A |  |  | 360 | Missing space in baseline text (REVmc is fine, i.e., this is just an editorial issue in P802.11ai). | On page 128 line 12, replace "PRF-704to" with "PRF-704 to". | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31155 | Malinen, Jouni | 5000 | 10 | 9.4.2.25.3 | 55 | 41 | E | No | 55 | 41 | 9.4.2.25.3 |  | A |  |  | 360 | Inconsistent spelling of "AES SIV" in Table 9-133. | On page 55 line 41, replace "AES SIV-256" with "AES-SIV-256". | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31156 | Malinen, Jouni | 5000 | 10 | 9.4.2.25.3 | 55 | 41 | E | No | 55 | 41 | 9.4.2.25.3 |  | A |  |  | 360 | Inconsistent spelling of "SHA-256" in Table 9-133. | On page 55 line 41, replace "SHA 256" with "SHA-256". | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31157 | Fang, Ping | 5000 | 10 | 4.10.3.6.1 | 8 | 54 | E | No | 8 | 54 | 4.10.3.6.1 |  | J |  |  | 360 | Delete "Insert new subclause as follows:" | As per comment | Reject: The editorial instruction is not strictly required but adds redundancy. The draft has been reviewed by IEEE editorial team and was marked as "meets all editorial requirements" | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31158 | Fang, Ping | 5000 | 10 | 4.10.3.6.2 | 9 | 38 | E | No | 9 | 38 | 4.10.3.6.2 |  | J |  |  | 360 | Delete "Insert new subclause as follows:" | As per comment | Reject: The editorial instruction is not strictly required but adds redundancy. The draft has been reviewed by IEEE editorial team and was marked as "meets all editorial requirements" | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31159 | Fang, Ping | 5000 | 10 | 6.3.3.2.2 | 14 | 1 | E | No | 14 | 1 | 6.3.3.2.2 |  | A |  |  | 360 | Insert rows (ignoring the header row) in the table as follows: to "Insert rows (ignoring the header row) in the table before the row of VendorSpecificInfo as follows:" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31160 | Fang, Ping | 5000 | 10 | 6.3.7.2.2 | 22 | 42 | E | No | 22 | 42 | 6.3.7.2.2 |  | J |  |  | 360 | "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table as follows:" to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31161 | Fang, Ping | 5000 | 10 | 6.3.7.3.2 | 23 | 44 | E | No | 23 | 44 | 6.3.7.3.2 |  | J |  |  | 360 | Change the primitive parameter list and insert new rows (ignoring the header row) in the associated table as follows: to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31162 | Fang, Ping | 5000 | 10 | 6.3.7.4.2 | 24 | 59 | E | No | 24 | 59 | 6.3.7.4.2 |  | J |  |  | 360 | Change the primitive parameter list and insert new rows (ignoring the header row) in the associated table as follows: to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31163 | Fang, Ping | 5000 | 10 | 6.3.7.5.2 | 26 | 7 | E | No | 26 | 7 | 6.3.7.5.2 |  | J |  |  | 360 | Change the primitive parameter list and insert new rows (ignoring the header row) in the associated table as follows: to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31164 | Fang, Ping | 5000 | 10 | 6.3.8.2.2 | 27 | 42 | E | No | 27 | 42 | 6.3.8.2.2 |  | J |  |  | 360 | Change the primitive parameter list and insert new rows (ignoring the header row) in the associated table as follows: to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31165 | Fang, Ping | 5000 | 10 | 6.3.8.3.2 | 28 | 43 | E | No | 28 | 43 | 6.3.8.3.2 |  | J |  |  | 360 | Change the primitive parameter list and insert new rows (ignoring the header row) in the associated table as follows: to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31166 | Fang, Ping | 5000 | 10 | 6.3.8.4.2 | 29 | 64 | E | No | 29 | 64 | 6.3.8.4.2 |  | J |  |  | 360 | Change the primitive parameter list and insert new rows (ignoring the header row) in the associated table as follows: to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31167 | Fang, Ping | 5000 | 10 | 6.3.8.5.2 | 31 | 41 | E | No | 31 | 41 | 6.3.8.5.2 |  | J |  |  | 360 | Change the primitive parameter list and insert new rows (ignoring the header row) in the associated table as follows: to "Change the primitive parameter list and insert new rows (ignoring the header row) to the associated table before the row of VendorSpecificInfo as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31168 | Fang, Ping | 5000 | 10 | 6.3.11.2.2 | 34 | 24 | E | No | 34 | 24 | 6.3.11.2.2 |  | A |  |  | 360 | Underline the text "This element is present when dot11FILSActivated is true and the AP is a member of a Multiple BSSID Set with two or more members." | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31169 | Fang, Ping | 5000 | 10 | 6.3.11.2.2 | 34 | 38 | E | No | 34 | 38 | 6.3.11.2.2 |  | A |  |  | 360 | "Insert new row (ignoring the header row) in the table as follows:" to "Insert new row (ignoring the header row) in the table before the row of VendorSpecificInfo as follows:" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31170 | Fang, Ping | 5000 | 10 | 6.3.11.2.2 | 35 | 4 | E | No | 35 | 4 | 6.3.11.2.2 |  | A |  |  | 360 | delete "[16/0981r1]" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31171 | Fang, Ping | 5000 | 10 | 9.3.3.3 | 40 | 1 | E | No | 40 | 1 | 9.3.3.3 |  | J |  |  | 360 | "Insert new rows/elements before the last order in the table as follows" change to "Insert new rows/elements(ignoring the header row) before the last row in the table as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31172 | Fang, Ping | 5000 | 10 | 9.3.3.3 | 40 | 9 | E | No | 40 | 9 | 9.3.3.3 |  | A |  |  | 360 | Change the order in Table 9-27 from 68 according to Revmc 8.0, "66" change to "68", "67" change to "69", "68" change to "70", "69" change to "71". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31173 | Fang, Ping | 5000 | 10 | 9.3.3.9 | 43 | 3 | E | No | 43 | 3 | 9.3.3.9 |  | J |  |  | 360 | "Insert the following new rows (ignoring the header row) in the table as follows:" change to "Insert the following new rows (ignoring the header row) before the last row in the table as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31174 | Fang, Ping | 5000 | 10 | 9.3.3.10 | 44 | 4 | E | No | 44 | 4 | 9.3.3.10 |  | J |  |  | 360 | "Insert new rows/elements (ignoring the header row) to the table as follows:" change to "Insert the following new rows (ignoring the header row) before the last row in the table as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31175 | Fang, Ping | 5000 | 10 | 9.3.3.11 | 44 | 37 | E | No | 44 | 37 | 9.3.3.11 |  | A |  |  | 360 | underline "otherwise not present." | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31176 | Fang, Ping | 5000 | 10 | 9.3.3.11 | 44 | 42 | E | No | 44 | 42 | 9.3.3.11 |  | J |  |  | 360 | "Insert new rows (ignoring the header row) in the table as follows:" change to "Insert the following new rows (ignoring the header row) before the Last-1 row in the table as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31177 | Fang, Ping | 5000 | 10 | 9.3.3.12 | 46 | 51 | E | No | 46 | 51 | 9.3.3.12 |  | J |  |  | 360 | "Insert the following rows (excluding header row) as follow:" change to "Insert the following new rows (ignoring the header row) before the last row in the table as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31178 | Fang, Ping | 5000 | 10 | 9.3.3.12 | 48 | 1 | E | No | 48 | 1 | 9.3.3.12 |  | J |  |  | 360 | "Insert new rows (ignoring the header row) to the table as follows:" change to "Insert new rows (ignoring the header row) to the end of the table as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31179 | Fang, Ping | 5000 | 10 | 9.3.3.12 | 49 | 50 | E | No | 49 | 50 | 9.3.3.12 |  | A |  |  | 360 | missing one bottom line for the table | Add bottom line for the table | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31180 | Fang, Ping | 5000 | 10 | 9.4.1.9 | 51 | 41 | E | No | 51 | 41 | 9.4.1.9 |  | A |  |  | 360 | in Table 9-46 Status codes, Status codes for FILS_AUTHENTICATION_FAILURE is "108", should be changed to "112"; (In ANA and D9.0, it is "112". ) | Chagne "108" to "112" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31181 | Fang, Ping | 5000 | 10 | 9.4.1.9 | 51 | 45 | E | No | 51 | 45 | 9.4.1.9 |  | A |  |  | 360 | in Table 9-46 Status codes, Status codes for UNKNOWN_AUTHENTICATION_SERVER is "109", should be changed to "113";(In ANA and D9.0, it is "113". ) | Chagne "109" to "113" | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31182 | Fang, Ping | 5000 | 10 | 9.4.1.11 | 51 | 53 | E | No | 51 | 53 | 9.4.1.11 |  | J |  |  | 360 | "Insert the new row (ignoring the header row) to the table as follows:" change to "Insert the new row (ignoring the header row) to the table after row Code of 21 as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31183 | Fang, Ping | 5000 | 10 | 9.4.1.11 | 51 | 63 | E | No | 51 | 63 | 9.4.1.11 |  | A |  |  | 360 | in Table 9-47, Code for FILS is "22", should be changed from "22" to "26". (In ANA, Code is "26" and in Draft 9.0 is "26". ) | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31184 | Fang, Ping | 5000 | 10 | 9.4.2.1 | 53 | 6 | E | No | 53 | 6 | 9.4.2.1 |  | J |  |  | 360 | "Insert new column and rows (ignoring the header row) to the table as follows and within the new >Fragmentable< column insert >No< for those elements not shown below:" change to "Insert new column and rows (ignoring the header row) to the table as follows, and make appropriate adjustment to value of >Reserved< and >Reserved for elements using the Element ID Extension field<, and within the new >Fragmentable<column insert >No< for those elements not shown below: | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31185 | Fang, Ping | 5000 | 10 | 9.4.2.1 | 54 | 58 | E | No | 54 | 58 | 9.4.2.1 |  | A |  |  | 360 | "Change the third to last paragraph of 9.4.2.1 as follows:" change to "Change the third paragraph of 9.4.2.1 as follows:" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31186 | Fang, Ping | 5000 | 10 | 9.4.2.25.3 | 55 | 27 | E | No | 55 | 27 | 9.4.2.25.3 |  | J |  |  | 360 | "Insert new rows (ignoring the header row) in the table as follows:" change to "Insert new rows (ignoring the header row) in the table after the row of Suite Type of 13 as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31187 | Fang, Ping | 5000 | 10 | 9.4.2.27 | 56 | 17 | E | No | 56 | 17 | 9.4.2.27 |  | V |  |  | 360 | "Insert a new row (ignoring the header row) as follows:" change to "Insert a new row (ignoring the header row) after the row of Bit of 71 as follows, and make appropriate adjustment to value of >Reserved<" | As per comment | Revised: add information to the editorial instruction stating that the value of Reserved has to be adjusted. | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31188 | Fang, Ping | 5000 | 10 | 9.4.2.171.1 | 57 | 57 | E | No | 57 | 57 | 9.4.2.171.1 |  | A |  |  | 360 | remove "/", it is not in the base line text. | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31189 | Fang, Ping | 5000 | 10 | 9.4.2.171.2 | 59 | 42 | E | No | 59 | 42 | 9.4.2.171.2 |  | A |  |  | 360 | remove "-" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31190 | Fang, Ping | 5000 | 10 | 9.4.2.175 | 59 | 46 | E | No | 59 | 46 | 9.4.2.175 |  | A |  |  | 360 | "9.4.2.175 Association Delay Info element" change to "9.4.2.176 Association Delay Info element" (In Revmc D8.0, 9.4.2.175 is already used) | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31191 | Fang, Ping | 5000 | 10 | 9.4.2.176 | 60 | 5 | E | No | 60 | 5 | 9.4.2.176 |  | A |  |  | 360 | "9.4.2.176 CAG Number elemen"t change to "9.4.2.177 CAG Number element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31192 | Fang, Ping | 5000 | 10 | 9.4.2.177 | 61 | 1 | E | No | 61 | 1 | 9.4.2.177 |  | A |  |  | 360 | "9.4.2.177 FILS Request Parameters element" change to "9.4.2.178 FILS Request Parameters element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31193 | Fang, Ping | 5000 | 10 | 9.4.2.178 | 64 | 1 | E | No | 64 | 1 | 9.4.2.178 |  | A |  |  | 360 | "9.4.2.178 FILS Key Confirmation element" change to "9.4.2.179 FILS Key Confirmation element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31194 | Fang, Ping | 5000 | 10 | 9.4.2.179 | 64 | 27 | E | No | 64 | 27 | 9.4.2.179 |  | A |  |  | 360 | "9.4.2.179 FILS Session element" change to "9.4.2.180 FILS Session element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31195 | Fang, Ping | 5000 | 10 | 9.4.2.180 | 64 | 51 | E | No | 64 | 51 | 9.4.2.180 |  | A |  |  | 360 | "9.4.2.180 FILS Public Key element" change to "9.4.2.181 FILS Public Key element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31196 | Fang, Ping | 5000 | 10 | 9.4.2.181 | 65 | 17 | E | No | 65 | 17 | 9.4.2.181 |  | A |  |  | 360 | "9.4.2.181 AP Configuration Sequence Number (AP-CSN) element" change to "9.4.2.182 AP Configuration Sequence Number (AP-CSN) element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31197 | Fang, Ping | 5000 | 10 | 9.4.2.182 | 65 | 44 | E | No | 65 | 44 | 9.4.2.182 |  | A |  |  | 360 | "9.4.2.182 FILS Indication element" change to "9.4.2.183 FILS Indication element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31198 | Fang, Ping | 5000 | 10 | 9.4.2.183 | 68 | 1 | E | No | 68 | 1 | 9.4.2.183 |  | A |  |  | 360 | "9.4.2.183 FILS HLP Container element" change to "9.4.2.184 FILS HLP Container element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31199 | Fang, Ping | 5000 | 10 | 9.4.2.184 | 68 | 33 | E | No | 68 | 33 | 9.4.2.184 |  | A |  |  | 360 | "9.4.2.184 FILS IP Address Assignment element" change to "9.4.2.185 FILS IP Address Assignment element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31200 | Fang, Ping | 5000 | 10 | 9.4.2.184.1 | 68 | 36 | E | No | 68 | 36 | 9.4.2.184.1 |  | A |  |  | 360 | "9.4.2.184.1 General" change to "9.4.2.185.1 General" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31201 | Fang, Ping | 5000 | 10 | 9.4.2.184.2 | 69 | 1 | E | No | 69 | 1 | 9.4.2.184.2 |  | A |  |  | 360 | "9.4.2.184.2 IP Address Data field for request" change to "9.4.2.185.2 IP Address Data field for request" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31202 | Fang, Ping | 5000 | 10 | 9.4.2.184.3 | 70 | 18 | E | No | 70 | 18 | 9.4.2.184.3 |  | A |  |  | 360 | "9.4.2.184.3 IP Address Data field for response" change to "9.4.2.185.3 IP Address Data field for response" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31203 | Fang, Ping | 5000 | 10 | 9.4.2.185 | 73 | 1 | E | No | 73 | 1 | 9.4.2.185 |  | A |  |  | 360 | "9.4.2.185 Key Delivery element" change to "9.4.2.186 Key Delivery element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31204 | Fang, Ping | 5000 | 10 | 9.4.2.186 | 73 | 29 | E | No | 73 | 29 | 9.4.2.186 |  | A |  |  | 360 | "9.4.2.186 Differentiated Initial Link Setup element" change to "9.4.2.187 Differentiated Initial Link Setup element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31205 | Fang, Ping | 5000 | 10 | 9.4.2.187 | 75 | 36 | E | No | 75 | 36 | 9.4.2.187 |  | A |  |  | 360 | "9.4.2.187 FILS Wrapped Data element" change to "9.4.2.188 FILS Wrapped Data element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31206 | Fang, Ping | 5000 | 10 | 9.4.2.188 | 75 | 61 | E | No | 75 | 61 | 9.4.2.188 |  | A |  |  | 360 | "9.4.2.188 Fragment element" change to "9.4.2.189 Fragment element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31207 | Fang, Ping | 5000 | 10 | 9.4.2.189 | 76 | 27 | E | No | 76 | 27 | 9.4.2.189 |  | A |  |  | 360 | "9.4.2.189 FILS Nonce element" change to "9.4.2.190 FILS Nonce element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31208 | Fang, Ping | 5000 | 10 | 9.4.5.23 | 77 | 37 | E | No | 77 | 37 | 9.4.5.23 |  | A |  |  | 360 | "9.4.5.23 Query AP List ANQP-element" change to "9.4.5.24 Query AP List ANQP-element" (In Revmc D8.0, 9.4.5.23 is already used) | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31209 | Fang, Ping | 5000 | 10 | 9.4.5.24 | 78 | 28 | E | No | 78 | 28 | 9.4.5.24 |  | A |  |  | 360 | "9.4.5.24 AP List Response ANQP-element" change to "9.4.5.25 AP List Response ANQP-element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31210 | Fang, Ping | 5000 | 10 | 9.4.5.25 | 79 | 1 | E | No | 79 | 1 | 9.4.5.25 |  | A |  |  | 360 | "9.4.5.25 FILS Realm Information ANQP-element" change to "9.4.5.26 FILS Realm Information ANQP-element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31211 | Fang, Ping | 5000 | 10 | 9.4.5.26 | 79 | 24 | E | No | 79 | 24 | 9.4.5.26 |  | A |  |  | 360 | "9.4.5.26 CAG ANQP-element" change to "9.4.5.27 CAG ANQP-element" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31212 | Fang, Ping | 5000 | 10 | 9.6.16.7.2 | 88 | 57 | E | No | 88 | 57 | 9.6.16.7.2 |  | J |  |  | 360 | delete "Insert new subclauses as follows:" | As per comment | Reject: The editorial instruction is not strictly required but adds redundancy. The draft has been reviewed by IEEE editorial team and was marked as "meets all editorial requirements" | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31213 | Fang, Ping | 5000 | 10 | 11.1.4.1 | 95 | 31 | E | No | 95 | 31 | 11.1.4.1 |  | A |  |  | 360 | underline "procedures" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31214 | Fang, Ping | 5000 | 10 | 11.1.4.3.2 | 96 | 65 | E | No | 96 | 65 | 11.1.4.3.2 |  | A |  |  | 360 | remove the "_" at the end of the sentence | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31215 | Fang, Ping | 5000 | 10 | 11.1.4.3.2 | 97 | 44 | E | No | 97 | 44 | 11.1.4.3.2 |  | A |  |  | 360 | remove underline for "for non-DMG STAs" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31216 | Fang, Ping | 5000 | 10 | 11.3.1 | 103 | 33 | E | No | 103 | 33 | 11.3.1 |  | A |  |  | 360 | change "11.3.1 State transition diagram for nonmesh STAs" to "11.3.2 State transition diagram for nonmesh STAs" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31217 | Fang, Ping | 5000 | 10 | 11.3.2 | 104 | 56 | E | No | 104 | 56 | 11.3.2 |  | A |  |  | 360 | change "11.3.2 Frame filtering based on STA state" to "11.3.3 Frame filtering based on STA state" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31218 | Fang, Ping | 5000 | 10 | 11.3.3 | 105 | 10 | E | No | 105 | 10 | 11.3.3 |  | A |  |  | 360 | change "11.3.3 Authentication and deauthentication" to "11.3.4 Authentication and deauthentication" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31219 | Fang, Ping | 5000 | 10 | 11.47.2.2 | 113 | 51 | E | No | 113 | 51 | 11.47.2.2 |  | J |  |  | 360 | delete "Insert new subclauses as follows:". | As per comment | Reject: The editorial instruction is not strictly required but adds redundancy. The draft has been reviewed by IEEE editorial team and was marked as "meets all editorial requirements" | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31220 | Fang, Ping | 5000 | 10 | 11.47.5.2 | 118 | 32 | E | No | 118 | 32 | 11.47.5.2 |  | J |  |  | 360 | delete "Insert new subclause as follows:" | As per comment | Reject: The editorial instruction is not strictly required but adds redundancy. The draft has been reviewed by IEEE editorial team and was marked as "meets all editorial requirements" | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31221 | Fang, Ping | 5000 | 10 | 12.6.1.1.1 | 121 | 43 | E | No | 121 | 43 | 12.6.1.1.1 |  | A |  |  | 360 | delete underline for "or". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31222 | Fang, Ping | 5000 | 10 | 12.6.1.1.1 | 121 | 54 | E | No | 121 | 54 | 12.6.1.1.1 |  | A |  |  | 360 | in baseline text of Revmc D8.0, "or FT authentication sequence.", add strikethrough for "or". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31223 | Fang, Ping | 5000 | 10 | 12.6.1.1.1 | 121 | 57 | E | No | 121 | 57 | 12.6.1.1.1 |  | A |  |  | 360 | delelte underline for the second "successful", add underline for the third "successful". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31224 | Fang, Ping | 5000 | 10 | 12.6.1.1.1 | 121 | 58 | E | No | 121 | 58 | 12.6.1.1.1 |  | A |  |  | 360 | in baseline text of Revmc D8.0, "or the Reassociation Response frame of the fast BSS transition protocol", add strikethrough for "or". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31225 | Fang, Ping | 5000 | 10 | 12.6.1.1.6 | 123 | 29 | E | No | 123 | 29 | 12.6.1.1.6 |  | A |  |  | 360 | remove "-" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31226 | Fang, Ping | 5000 | 10 | 12.6.1.3.2 | 125 | 11 | E | No | 125 | 11 | 12.6.1.3.2 |  | A |  |  | 360 | replace "STA" with "STA(AP)" according to baseline text in Revmc D8.0, and remove underline for SAs. | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31227 | Fang, Ping | 5000 | 10 | 12.7.1.7.1 | 130 | 6 | E | No | 130 | 6 | 12.7.1.7.1 |  | A |  |  | 360 | delete "(ed note, we should probably delete this subclause from our draft to better match the changes made in REVmc)" | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31228 | Fang, Ping | 5000 | 10 | 12.7.1.7.2 | 130 | 12 | E | No | 130 | 12 | 12.7.1.7.2 |  | V |  |  | 361 | the baseline text in Revmc D8.0 is now "The KDF is a variant of the pseudorandom function (PRF) defined in 12.7.1.2 (PRF) and is defined as follows:", the group need to decide whether the change is still needed or not. | Delete the change | Revise. Incorporate text changes in 11-16/1151r5 (https://mentor.ieee.org/802.11/dcn/16/11-16-1151-05-00ai-kdf-prf-pkex.docx) for CIDs 31228, 31112, and 31102. | EDITOR | 2016-09-13-AM1 | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31229 | Fang, Ping | 5000 | 10 | 12.7.3 | 132 | 8 | E | No | 132 | 8 | 12.7.3 |  | J |  |  | 360 | change "Insert new rows (ignoring the header row) in the table as follows:" to "Insert new rows (ignoring the header row) at the end of the table as follows:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31230 | Fang, Ping | 5000 | 10 | 12.7.6.3 | 133 | 23 | E | No | 133 | 23 | 12.7.6.3 |  | A |  |  | 360 | remove underline for "message 2". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31231 | Fang, Ping | 5000 | 10 | 12.7.6.3 | 133 | 29 | E | No | 133 | 29 | 12.7.6.3 |  | A |  |  | 360 | remove underline for "message 2". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31232 | Fang, Ping | 5000 | 10 | B.4.3 | 163 | 32 | E | No | 163 | 32 | B.4.3 |  | A |  |  | 360 | remove "[CID 20003]". | As per comment | Accept | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31233 | Fang, Ping | 5000 | 10 | C.3 | 165 | 60 | E | No | 165 | 60 | C.3 |  | V |  |  | 367 | change "In the Major Section of the Annex, insert the following comment to the end of SMT attributes:" to "In the Major Section of the Annex, insert the following text before the line of "{ dot11smt 36 }" | As per comment | REVISED (EDITOR: 2016-09-14 12:29:53Z) - Revised. Change "In the Major Section of the Annex, insert the following comment to the end of SMT attributes:" to “Insert the following text before this entry ' -- dot11STALCIConfigTable ::= { dot11smt 36 }‘in the dot11smt attribute.“ | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-15 10:33 | EDITOR
31234 | Fang, Ping | 5000 | 10 | C.3 | 166 | 27 | E | No | 166 | 27 | C.3 |  | V |  |  | 361 | "simultaneousAuthEquals(4)", 4 is already used in baseline text, need to verify whether should change line 23~26, 1 to 0, 2 to 1, 3 to 2, 4 to 3. | As per comment | Revised. Use dot11AuthenticationAlgorithm values 5-7 instead of 4-6 for the new FILS values and fix the baseline text for previously used values with following changes on page 166: line 27 replace "(4)" with "(5)", line 28 replace "(5)" with "(6)", line 29 replace "(6)" with "(7)", lines 39-42 increment each value by one (1..4) to match baseline in REVmc, lines 43-45 increment each value by one (5..7) for the new FILS values. | EDITOR | 2016-09-13-AM1 | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31235 | Fang, Ping | 5000 | 10 | C.3 | 166 | 51 | E | No | 166 | 51 | C.3 |  | J |  |  | 360 | "Insert the following new group at the end of Groups - units of conformance RSN section.:" change to "Insert the following new group at the end of Groups - units of compliance - RSN section.:" | As per comment | Reject: IEEE editorial staff reviewed the draft and did not report any ambigeous editorial instructions. The Tgai Editor and the group do not see any ambiguity in the editorial instruction in the draft that require a change | EDITOR | 2016-09-11-Editor | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. |  |  |  | 2016-09-13 16:42 | EDITOR
31236 | RISON, Mark | 5000 | 10 |  |  |  | G | Yes |  |  |  |  | J |  |  | 363 | I believe that some of the "out of scope" resolutions to comments in the previous round are in error (note that a comment is in scope if it "Is in a recirculation, and relates to text that is the target of an unsatisfied "must be satisfied" comment from a current "no" voter"; see 13/0230): 5.6. CID31008 "it's not the value that is present or not present, it's the parameter" 5.6.1. Reject. 5.6.2. Out of scope. See CID 20062-20068. 5.9. CID31014 "When all channels in the ChannelList have been scanned, and the ReportingOption of the MLME-SCAN.request primitive is AT_END or not present, the MLME shall issue an MLME-SCAN.confirm primitive with one or more of BSSDescriptionSet, BSSDescriptionFromFDSet, or BSSDescriptionFromMeasurementPilotSet containing all of the information gathered during the scan." -- the ResultCode is not specified" 5.9.1. Reject. 5.9.2. Out of scope. See CID 20072. 5.11. CID31011 "and the scanning FILS STA detects a BSS whose MLME-SCAN.confirm primitive has not been issued during the ongoing scan," -- the "whose MLME-SCAN ..." bit is not clear and under the plausible interpretation "have sent a .confirm with that BSSID" is wrong (e.g. you want to issue a new SCAN.cfm if some parameters have changed). It also imposes a potentially unbound storage requirement on the STA" 5.11.1. Straw poll 5.11.1.1.1. in favor of making a text change? 5.11.1.1.2. Y/N: 1/3 5.11.2. Reject. 5.11.3. Out of scope. See CID 10647, 20072. 5.13. CID31012 ""If a FILS STA has the ReportingOption parameter in the MLME-SCAN.request primitive not equal to IMMEDIATE or CHANNEL_SPECIFIC, then the STA shall follow the procedures indicated in 11.1.4.1" -- but 11.47.2.2 then only describes IMMEDIATE (at 115.37), not CHANNEL_SPECIFIC" 5.13.1. Straw poll 5.13.1.1.1. in favor of making a text change? 5.13.1.1.2. Y/N: 0/5 5.13.2. Reject. 5.13.3. Out of scope. See CID 20071. 5.14. CID31027 ""Multiple MLME-SCAN.confirm primitives can be issued when the value of the ReportingOption parameter in the MLME-SCAN.request primitive is CHANNEL_SPECIFIC or IMMEDIATE. When the value of the ReportingOption parameter value is AT_END, or the ReportingOption parameter is not present, a single MLME-SCAN.confirm primitive is issued."" -- a parameter does not have a value if it is not present" 5.14.1. Reject. 5.14.2. Out of scope. See CID 20062-20068. 5.16. CID31022 ""The IPv6 Gateway MAC address is the MAC address of the IPv6 default gateway." -- this statement is missing for IPv4. Also the article is inconsistent with the absence of the articles in surrounding text" 5.16.1. Straw poll 5.16.1.1.1. in favor of making a text change? 5.16.1.1.2. Y/N: 0/5 5.16.2. Reject. 5.16.3. Out of scope. See CID 10654, 20083. 5.20. CID31035 "Ref CID 20091. The resolution of this comment seems to have gone in the direction of getting rid of the "shall"s, but everything in this subclause is normative (this is not Clause 9)" 5.20.1. Straw poll 5.20.1.1.1. in favor of making a text change? 5.20.1.1.2. Y/N: 1/4 5.20.2. Reject. 5.20.3. Out of scope. See CID 20091. 5.21. CID31030 "Ref CIDs 20064/20065. A parameter (here ReportingOption) does not have a value if it is not present" 5.21.1. Reject. 5.21.2. Out of scope. See CID 20064, 20065. 5.22. CID31029 "Ref CIDs 20064/20065. A parameter (here ReportingOption) does not have a value if it is not present" 5.22.1. Reject. 5.22.2. Out of scope. See CID 20064, 20065. 5.23. CID31010 "Ref CID 20072. The ReportingOption == IMMEDIATE case is not covered. In this case an MLME-SCAN.confirm still needs to be returned, per 6.3.3.3.3" 5.23.1. Straw poll 5.23.1.1.1. in favor of making a text change? 5.23.1.1.2. Y/N: 0/4 5.23.2. Reject. 5.23.3. Out of scope. See CID 20072. | Accept the proposed changes for the CIDs identified in this comment (CIDs 3xxxx) as having been incorrectly rejected as being out of scope. | REJECTED (TGai General: 2016-09-13 08:22:58Z) - Rejected. Only two of the cited CID 3xxxx comments were rejected based on being "out-of-scope". Those two comments (CID 31029 and 31030) pile up on two comments (CID 20064 and 20065) that were invalid comments since they failed to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | EDITOR | 2016-09-11-Technical | Approved | TODO Ad-hoc notes: Taken into account how many changes we are going to be doing in the next draft, I'd go ahead and apply the clear cleanup changes in the previous rejected comments.. That would be a revised resolution for this CID 31236 listing all the changes from the identified CID3xxxx comments. TODO: need to figure out the exact changes and confirm that none of the identified comments need to be removed due to unacceptable proposed changes. |  |  |  | 2016-09-13 08:23 | TGai General
31237 | Seok, Yongho | 5000 | 10 | 11.47.1 | 111 | 45 | T | No | 111 | 45 | 11.47.1 |  | A |  |  | 361 | "dot11QosCapabilityImplemented" is not defined anywhere including IEEE 802.11 REVmc. Probably, it shall be changed to "dot11QosOptionImplemented". | As per comment. | ACCEPTED (TGai General: 2016-09-12 10:29:22Z) | EDITOR | 2016-09-13-AM1 | Approved | EDITOR: 2016-09-13 16:42:14Z - Comments that have "Part of No Vote == N" cannot be unsatisfied. Ad-hoc notes: The comment is correct about dot11QosCapabilityImplemented not existing and the proposed change (use dot11QosOptionImplemented) seems to cover what this sentence is trying to say, i.e., indicate that the STA implements QoS. |  |  |  | 2016-09-13 16:42 | EDITOR

## Revision History
Revision | Date | Description
0 | 2016-09-11 | Initial export from DB
1 | 2016-09-12 | Update with proposed comment resolutions for technical comments
2 | 2016-09-13 | Import of comment resolutions from https://mentor.ieee.org/802.11/dcn/16/11-16-1235-02-00ai-proposed-resolution-editorial-issues.xlsx
3 | 2016-09-13 | Motion tab for rdy4motion resolutions from AM1
4 | 2016-09-13 | All comments resolved and resolution motioned. Exporting ..
5 | 2016-09-13 | Update with comment resolutions from CID-specific motions
6 | 2016-09-14 | Update with comment resolutions from CID-specific motions