## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/0613r3
Venue Date: | May 2017
First Author: | Jiamin CHEN, Huawei/HiSilicon
Subject: | Comments from TGaj initial sponsor ballot
Full Date: | 2017-05-10
Author(s): | Name(s) | Jiamin CHEN | Shiwen He
| Affiliation | Huawei/HiSilicon | SEU
Address
Phone:
Fax:
| email: | jiamin.chen@mail01.huawei.com | shiwenhe@seu.edu.cn
Abstract:
This document contains comments received from the initial sponsor ballot on 802.11aj D5.0. This document is periodically updated to reflect the status of those comments.

## Comments
CID | Commenter | SB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
801 | Chen, Jiamin | 1 | 5 | 11.50.4 | 160 | 21 | E | No | 160 | 21 | 11.50.4 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "A recipient CMMG STA in the BSS STA that has dot11SpectrumManagementRequired ..." Typo, remove the extra "STA". | Change to "A recipient CMMG STA in the BSS that has dot11SpectrumManagementRequired ..." Ditto at P160L49. | Accepted.
802 | Chen, Jiamin | 1 | 5 | 11.50.4 | 159 | 43 | E | No | 159 | 43 | 11.50.4 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | " The value of the New Channel Number field is set to the value that dot11CurrentPrimaryChannel have after the switch." Typo, should be "has" not "have". | Change to "The value of the New Channel Number field is set to the value that dot11CurrentPrimaryChannel has after the switch." | Accepted.
803 | Chen, Jiamin | 1 | 5 | 11.49.2 | 155 | 49 | T | No | 155 | 49 | 11.49.2 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | Two or more 1.08 GHz and/or 2.16 GHz channels may be occupied when a new BSS comes. Illustrate a number of possible use cases for the DCT procedure. | As comment. | Revised. Propose to insert following txt and figure into the draft: Figure 11-53b Examples of using DCT procedure “Figure 11-53b illustrates a number of use cases for DCT procedure: — In case 1, 2 and 3, a CDMG AP or PCP that intends to start a new BSS can request one of the two BSSs operating on two occupied 1.08 GHz channels to move to one of the two idle channels. Case1 for example, the BSS operating on channel 6 can move to channel 7; or the BSS operating on channel 7 can move to channel 5. Then a 2.16GHz channel 2 or 3 is idle and the CDMG AP or PCP can start its BSS on it. — In case 4 and 5, the CDMG AP or PCP that intends to start a new BSS can request one or two BSSs operating on a 2.16 GHz channel to move to operate on a 1.08 GHz channel. Case 4 for example, the BSS operating on the channel 2 (2.16 GHz) can move to the channel 8 (1.08 GHz). Then the 2.16 GHz channel 2 is idle and the CDMG AP or PCP can start its BSS on it.”
804 | Chen, Jiamin | 1 | 5 | 11.2.3.21 | 152 | 19 | E | No | 152 | 19 | 11.2.3.21 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "A CMMG AP may allow non-AP CMMG STAs in TXOP power save mode to enter the Doze state during a TXOP. " Should be "doze state". | "A CMMG AP may allow non-AP CMMG STAs in TXOP power save mode to enter the doze state during a TXOP." Do the same changes throughout the draft where applicable. | Accepted.
805 | Chen, Jiamin | 1 | 5 | 11.2.3.21 | 153 | 35 | T | No | 153 | 35 | 11.2.3.21 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "... but the COLOR in the RXVECTOR parameter does not match the COLOR indicated by the AP to which the STA is associated." Reword. | Suggest to change to "... but the RXVECTOR parameter COLOR does not match the COLOR indicated by the AP to which the STA is associated." | Accepted.
806 | Chen, Jiamin | 1 | 5 | 10.64.3 | 146 | 49 | G | No | 146 | 49 | 10.64.3 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "..., to request the AP or PCP to shift its operating channel to one of the 1.08 GHz channels (e.g. Channel 5) within its original 2.16 GHz. ..." Incomplete statement at the end of the sentence. | Change to "..., to request the AP or PCP to shift its operating channel to one of the 1.08 GHz channels (e.g. Channel 5) within its original 2.16 GHz channel...." | Accepted.
807 | Chen, Jiamin | 1 | 5 | 10.64.2.2 | 141 | 54 | G | No | 141 | 54 | 10.64.2.2 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "During the BTI on the 2.16 GHz channel, the AP or PCP shall transmit a DMG Beacon frame containing the Dynamic Bandwidth Control element that information on the operating status of the BSS through the DBC Control field and Channel Number field...." May be syntax error. | Change to "During the BTI on the 2.16 GHz channel, the AP or PCP shall transmit a DMG Beacon frame containing the Dynamic Bandwidth Control element that includes information on the operating status of the BSS through the DBC Control field and Channel Number field. " | Accepted.
808 | Chen, Jiamin | 1 | 5 | 10.39a.1 | 138 | 27 | E | No | 138 | 27 | 10.39a.1 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "...can be used to obtain Link Margin information," Should be "link margin information" i.e., lowercase the initial letter because it is not a frame or field name here. | Change to "...can be used to obtain link margin information,". | Accepted.
809 | Chen, Jiamin | 1 | 5 | 10.38.9 | 136 | 5 | G | No | 136 | 5 | 10.38.9 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "An enhanced beam tracking initiator requesting Transmit enhanced beam tracking shall set the..." Should be "enhanced transmit beam tracking" here. | Change to "An enhanced beam tracking initiator requesting enhanced transmit beam tracking shall set the..." | Accepted.
810 | Chen, Jiamin | 1 | 5 | 10.37a.6 | 133 | 21 | T | No | 133 | 21 | 10.37a.6 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "If the SPSH in the CDMG AP or PCP Cluster subfield..." Wrong subfield name.Should be "SPSH in a CDMG AP or PCP Cluster subfield" as defined in 9.4.2.222.3. | Further suggestion is to change the subfield name to "SPSH in CDMG Cluster". | Accepted.
811 | Chen, Jiamin | 1 | 5 |  | 130 | 48 | E | No | 130 | 48 |  |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "If the AP or PCP cannot detects the presence of " Typo here. | Change to "If the AP or PCP cannot detect the presence of ". | Accepted.
812 | Chen, Jiamin | 1 | 5 | 10.37.3.4 | 122 | 55 | E | No | 122 | 55 | 10.37.3.4 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "If the non-AP and non-PCP STA is the source CMMG STA of an SP and if the non-AP and non-PCP determines that it needs to perform a TXSS before continuing to transmit to the destination CMMG STA of the SP,..." Missing "STA", should be "the non-AP and non-PCP STA". | Change to "If the non-AP and non-PCP STA is the source CMMG STA of an SP and if the non-AP and non-PCP STA determines that it needs to perform a TXSS before continuing to transmit to the destination CMMG STA of the SP,..." | Accepted.
813 | Chen, Jiamin | 1 | 5 | 10.36.11 | 121 | 64 | E | No | 121 | 64 | 10.36.11 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "If the NoPrimaryChannel field in the BF Control field is equal to 1..." It should be "NoPrimaryChannel subfield". | Change to "If the NoPrimaryChannel subfield in the BF Control field is equal to 1..." | Accepted.
814 | Chen, Jiamin | 1 | 5 | 10.36.11 | 121 | 47 | T | No | 121 | 47 | 10.36.11 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "..., the CDMG STA shall respond with a DELTS frame to the AP or PCP with the Reason Code field (9.4.1.7 (Reason Code field)) set to 68 to indicate the alternative channel is occupied upon the reception of a DMG CTS-to-self frame from the AP or PCP during the ATI." The specific value, which is defined in 9.4.1.7 (Reason Code field)to indicate the alternative channel is occupied, may be changed during the development of 802.11 spec and the value mentioned here might not be timely updated. It is difficult for editor to check and update the values that might be mentioned throughout the draft. So not to mention the spcific value here. | Remove the specific value and change to "..., the CDMG STA shall respond with a DELTS frame to the AP or PCP with the Reason Code field set to the value defined in 9.4.1.7 (Reason Code field) that indicate the alternative channel is occupied upon the reception of a DMG CTS-to-self frame from the AP or PCP during the ATI." Ditto at P121L50/L53. | Accepted.
815 | Chen, Jiamin | 1 | 5 | 10.36.10 | 118 | 32 | E | No | 118 | 32 | 10.36.10 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "...the variable NAV_CHANNEL indicated the channel that the Duration field is received," Should use present tense rather than past tense here. | Change to "indicates" | Accepted.
816 | Chen, Jiamin | 1 | 5 | 10.36.10 | 118 | 31 | E | No | 118 | 31 | 10.36.10 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "...and has associated variables NAV_RTSCANCELABLE, NAV_DTSCANCELABLE and NAV_CHANNEL which is only used by CMMG STAs,..." Use of "which" should generally be preceded by a comma or preposition. | Change "which" to "that". | Accepted.
817 | Chen, Jiamin | 1 | 5 | 10.36.6.6.4 | 116 | 39 | T | No | 116 | 39 | 10.36.6.6.4 |  | V | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "CMMG STAs shall also include the Interferer Channel Bandwidth subfield in the report, and the Interferer Channel Bandwidth subfield shall be set to the CHBAND of the NAV timer." What is "CHBAND"? | Define or explain what is "CHBAND". | Revised. Change to "CMMG STAs shall also include the Interferer Channel Bandwidth subfield in the report, and the Interferer Channel Bandwidth subfield shall be set to the CH_BANDWIDTH of the NAV timer."
818 | Chen, Jiamin | 1 | 5 | 10.36.6.6.2a | 115 | 8 | E | No | 115 | 8 | 10.36.6.6.2a |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "...after an SIFS interval." 1. In reference to 802.11-2016, use "a SIFS" rather than "an SIFS". 2. According to the 802.11 style guide, a SIFS indicates a Short Interframe Space and is already a noun phrase. There is no need to follow with "spacing/interval/period". | Change "an SIFS" to "a SIFS" and remove "interval". Similarly change "SIFS period" to "SIFS". Do the same throughout the draft. | Accepted.
819 | Chen, Jiamin | 1 | 5 | 10.36.6.6.2a | 114 | 36 | E | No | 114 | 36 | 10.36.6.6.2a |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "...otherwise, the CDMG AP or PCP shall set the Protected Period subfield to 0 to indicate the source and destination CDMG STAs do not have to establish a protected period for the SP." Missed "that" after "indicate". Ditto at P114L33/L55/L62, P51L24, P121L47. | "...otherwise, the CDMG AP or PCP shall set the Protected Period subfield to 0 to indicate that the source and destination CDMG STAs do not have to establish a protected period for the SP." Do the same changes at P114L33/L55/L62, P51L24, P121L47. | Accepted.
820 | Chen, Jiamin | 1 | 5 | 10.36.6.6.2 | 113 | 50 | E | No | 113 | 50 | 10.36.6.6.2 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "...its NAV timers corresponding to this channel are not equal to zero." According to the 802.11 Style Guide, values are shown as digits when representing the value of fields. | Change to "...its NAV timers corresponding to this channel are not equal to 0." | Accepted.
821 | Chen, Jiamin | 1 | 5 | 10.36.6.6.1 | 112 | 54 | T | No | 112 | 54 | 10.36.6.6.1 |  | V | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "In the CMMG band, the SP can have different bandwidth, 540MH or 1080 MHz, so another intent of CMMG protected period is to use dynamic bandwidth operation to negotiate a bandwidth can be use in this SP." The description is not clear, may have syntax problem. | Reword. | Revised. Change to "In the CMMG protected period that have 540MHz or 1080 MHz bandwidth, the STA can use dynamic bandwidth operation to negotiate a bandwidth that can be use in this SP."
822 | Chen, Jiamin | 1 | 5 | 10.31.4 | 101 | 39 | T | No | 101 | 39 | 10.31.4 |  | V | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | There is no definition for the +CMMGC frame. | Define it in reference to the definition of the +HTC frame in 9.2.2. | Revised. Change to "In an MFB response solicited by an MRQ that was not carried in a NDP Announcement frame, the MFB is computed based on RXVECTOR parameters CH_BANDWIDTH, NUM_STS, BEAMFORMED, and STBC of the received PPDU that carried the MRQ and might additionally be based on other factors that are not part of the RXVECTOR. The NUM_STS subfield of the MFB subfield of the CMMG Control field shall be set to an equal or smaller value than the RXVECTOR parameter NUM_STS of the received PPDU that triggered the MRQ."
823 | Chen, Jiamin | 1 | 5 | 10.22.2.5 | 97 | 32 | T | No | 97 | 32 | 10.22.2.5 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | The rules for the EDCA channel access in a CMMG BSS are defined in 10.22.2.12. No need to have related description in 10.22.2.5. | Remove proposed changes to 10.22.2.5. | Accepted.
824 | Chen, Jiamin | 1 | 5 | 10.2 | 95 | 8 | E | No | 95 | 8 | 10.2 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "Table 10-9 Settings for the TXVECTOR parameter PARTIAL_AID for CMMG STAs for VHT STAs". Typo and remove "...for CMMG STAs...". | Per comment. | Accepted.
825 | Chen, Jiamin | 1 | 5 | 9.6.31.3 | 84 | 54 | E | No | 84 | 54 | 9.6.31.3 |  | V | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "The Noncompressed Beamforming frame is ...". Incomplete frame name, should be "The CMMG Noncompressed Beamforming frame is ...". Ditto at P85L27 | Per comment. | Revised. This subsection is removed following suggestions of CID 860 in DOC: 11-17-0635-02-00aj.
826 | Chen, Jiamin | 1 | 5 | 9.4.2.132 | 43 | 56 | E | No | 43 | 56 | 9.4.2.132 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | Typo. Change "The Truncation Type subfield is equal to 0w." to " The Truncation Type subfield is equal to 0." | Fix it. | Accepted.
827 | Chen, Jiamin | 1 | 5 | 9.4.1.47 | 32 | 1 | T | No | 32 | 1 | 9.4.1.47 |  | V | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | Usually one subclause contains one definition for one field. Insert a new subclause for the CMMG Parameters field. | Per comment. | Revised. Insert the following subclauses, 9.4.1.47a after 9.4.1.47 as follows: 9.4.1.47a CMMG Parameters field The definition of the CMMG parameters field is the same as the definition of the DMG parameters field.
828 | Chen, Jiamin | 1 | 5 | 9.3.4.2 | 29 | 29 | E | No | 29 | 29 | 9.3.4.2 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | This is a subfield rather than a field. Change "the SPSH Measurement Enabled field" to "the SPSH Measurement Enabled subfield". | Per comment. | Accepted.
829 | Chen, Jiamin | 1 | 5 | 9.2.4.6a | 26 | 55 | T | No | 26 | 55 | 9.2.4.6a |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | The subfield name in the CMMG Control field is wrong. Change "The AC Constraint subfield of the CMMG Control field" to "The CMMG AC Constraint subfield of the CMMG Control field" | Per comment. | Accepted.
830 | Chen, Jiamin | 1 | 5 | 9.2.4.6a | 24 | 19 | E | No | 24 | 19 | 9.2.4.6a |  | V | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | The CMMG NDP Announcement subfield is 1 bit and the RDG/More PPDU subfield is 2 bits in Length. So the bit labels above them are wrong. | Fix it. | Revised. Fixed the errors.
831 | Chen, Jiamin | 1 | 5 | 4.3.27 | 6 | 6 | G | No | 6 | 6 | 4.3.27 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "... allows it to operate in an Infrastructure BSS, in an IBSS, and in a PBSS." Change to "...allows it to operate in an Infrastructure BSS, in an IBSS, or in a PBSS. " | Per comment. | Accepted.
832 | Chen, Jiamin | 1 | 5 | 4.3.27 | 5 | 46 | E | No | 5 | 46 | 4.3.27 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "Normal Guard Interval" -> "Normal guard interval" | Per comment. | Accepted.
833 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 15 | E | No | 5 | 15 | 4.3.26 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "...Clause 24 (China directional multi-gigabit (CDMG) PHY specification)..." Wrong font size, use size 10. | Per comment. | Accepted.
834 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 13 | G | No | 5 | 13 | 4.3.26 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "In addition to DMG features, a CDMG STA supports DMG features as described in 4.3.21 (DMG STA)." Remove "In addition to DMG features,..." | Per comment. | Revised. Change to “The IEEE Std 802.11 CDMG STA is a DMG STA that supports CDMG operation on Chinese 60 GHz frequency band when dot11CDMGOptionImplemented is true. In addition to CDMG features, a CDMG STA supports DMG features as described in 4.3.21 (DMG STA).”
835 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 12 | G | No | 5 | 12 | 4.3.26 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | Change "...CDMG operation on Chinese 60 GHz frequency band..." to " CDMG operation in Chinese 60 GHz frequency band " | Per comment. | Accepted.
836 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 12 | G | No | 5 | 12 | 4.3.26 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | Change "The IEEE Std 802.11 CDMG STA is a DMG STA that..." to " The IEEE 802.11 CDMG STA is a IEEE 802.11 DMG STA that...". Remove "Std" in reference to 802.11-2016. Ditto in line 33, 62. | Per comment. | Accepted.
837 | Chen, Jiamin | 1 | 5 | 9.2.3 | 23 | 27 | T | No | 23 | 27 | 9.2.3 |  | V | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | No need to define an additional MAC frame format for CMMG STAs for only a minor difference with the existing frame format. | Add the CMMG Control field with a length of "0 or 4" as a new field to the MAC frame format in reference to the "HT Control" field. Add related description in the first paragraph of 9.2.3. | Revised. Change the first paragraph as follows: The MAC frame format comprises a set of fields that occur in a fixed order in all frames. Figure 9-1 depicts the general MAC frame format. The first three fields (Frame Control, Duration/ID, and Address 1) and the last field (FCS) in Figure 9-1 constitute the minimal frame format and are present in all frames, including reserved types and subtypes. The fields Address 2, Address 3, Sequence Control, Address 4, QoS Control, HT Control, CMMG Control, and Frame Body are present only in certain frame types and subtypes. Each field is defined in 9.2.4. The format of each of the individual subtypes of each frame type is defined in 9.3. The components of management frame bodies are defined in 9.4. The formats of Action frames are defined in 9.6. Delete the new inserted Figure 9-1a.
838 | Li, Dejian | 1 | 5 | 10.64.2.2 | 141 | 1 | T | No | 141 | 1 | 10.64.2.2 |  | A | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | Channel number 5,6,7,8 have been changed to 35,36,37,38 in annex E. | Change the channel number 5,6,7,8 to 35,36,37,38 throughout the 11aj D5.0, respectively. | Accepted.
839 | Li, Dejian | 1 | 5 | 10.37a.2.2 | 129 | 25 | T | No | 129 | 25 | 10.37a.2.2 |  | V | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | It is not clear for the purpose of the step f | Change to "The AP or PCP shall join the S-AP's cluster at the selected cluster time offset on the channel of the S-AP and transmit DMG Beacon frames with the AP or PCP Clustering Control field." | Revised. Discussion: It is not clear for the purpose of the step f). The suggested remedy can make the step f more clear. Proposed resolution: Revised Change the last bullet f) as follows "f) The AP or PCP shall join the cluster of S-AP at the selected cluster time offset on the channel of the S-AP and transmit DMG Beacon frames with the AP or PCP Clustering Control field." 9.4.2.132 Extended Schedule element For a CDMG PCP, the PCP Active subfield is set to 1 at least in the following cases: — The PCP transmitting the field is the source or destination of the CBAP or SP. — The Truncatable subfield is equal to 1 and the Truncation Type subfield is equal to 0. — The Extendable subfield is equal to 1. — The subfield is transmitted by an AP. 10.36.8.2 CDMG dynamic truncation of service period A CDMG AP or PCP should determine the Truncatable subfield and the Truncation Type subfields according to the allocation type requirements of the STAs in its BSS, in order to satisfy the channel access requirements of the STAs using the potential released time of SPs. Since the remaining time in the SP released as a CBAP might cause interference to other STAs during SPSH, the CDMG AP or PCP shall set the Truncation Type field to 0 for the SPs that are under SPSH state to indicate that the CDMG STA returns the time left in the SP to the AP or PCP. The CDMG AP or PCP may also set the Truncation Type field to 0 for an SP in order to mitigate interference to other STAs of a adjacent BSS based on the schedule information of the adjacent BSS.
840 | Li, Dejian | 1 | 5 | 10.37a.2.2 | 128 | 61 | T | No | 128 | 61 | 10.37a.2.2 |  | V | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | It is not clear what is "the current cluster" | Change "the current cluster" to "the current S-AP's cluster" | Revised. Discussion: Do as the suggested remedy. Proposed resolution: Revised Change bullet c) to c) The CDMG AP or PCP should determine whether to join the current S-AP’s cluster or other S-AP(s)’s cluster based on the signal quality, the states of Beacon SPs during a BI indicated by the Available Cluster Offset Bitmap field in the ECPAC Policy element of the S-AP or the member APs or member PCPs of the current S-AP’s cluster, and other S-AP(s)’s cluster information. If the AP or PCP elects to join the current cluster, proceed to step d); …
841 | Li, Dejian | 1 | 5 | 9.4.2.147 | 45 | 45 | T | No | 45 | 45 | 9.4.2.147 |  | A | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | In 802.11ad, we use the term "ECPAC", which denotes "Extended Centralized PCP or AP Cluster". However, in 802.11-2016, we use the term ECAPC (Extended Centralized AP or PCP Cluster). We need to align this definition with 802.11-2016 | Change all the "ECPAC" to "ECAPC" throughout the 11aj D5.0. | Accepted.
842 | Li, Dejian | 1 | 5 | 10.64.1 | 140 | 32 | T | No | 140 | 32 | 10.64.1 |  | A | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | It is not clear in "A pair of CDMG BSSs operating on the adjacent 1.08 GHz channels (e.g. Channel 5 and Channel 6) within a 2.16 GHz channel (i.e. Channel 2) should maintain synchronization with each other". | It is not appropriate to say "a pair of BSSs" should maintain synchronization with each other. Change "a pair of BSSs" to "a pair of APs or PCPs". | Accepted.
843 | Li, Dejian | 1 | 5 | Abstract | ii | 3 | E | No | ii | 3 | Abstract |  | A | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | Grammer mistake in "at around 60 GHz" and "at around 45 GHz" | Change to "around 60 GHz" and "around 45 GHz" | Accepted.
844 | Li, Dejian | 1 | 5 | 24.3.6.1 | 170 | 65 | E | No | 170 | 65 | 24.3.6.1 |  | A | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | Typo in letter "F" | Delete the letter "F" | Accepted.
845 | Li, Dejian | 1 | 5 | 9.4.2.132 | 42 | 50 | E | No | 42 | 50 | 9.4.2.132 |  | V | Dejian Li | 11-17/0792r1 | motion 1 in 11-17/0539r3 | typo in "Figure 9-517--Allocation field format" | Change to "Figure 9-517--Allocation Control field format". So does P43L9. | Revised. Discussion: Do as the suggested remedy. Proposed resolution: Revised Change the title of 9-517 and 9-517a as follows:(see details in 11-17/0792r1). Change the table title to "Figure 9-518a- Allocation Control field format (CDMG)"
846 | Li, Dejian | 1 | 5 | 9.4.2.132 | 43 | 56 | E | No | 43 | 56 | 9.4.2.132 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | typo in "The Truncation Type subfield is equal to 0w." | change to "The Truncation Type subfield is equal to 0." | Accepted.
847 | Goodall, David | 1 | 5 | 10.64.5 | 148 | 63 | T | Yes | 148 | 63 | 10.64.5 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | If the authentication algorithm is other than 'Open' then an authentication frame exchange may also be required as part of the join. | Perhaps just leave that sentence out. | Revised. Association is only a part of the procedure to join a BSS. The purpose of the txt here is to indicate that a DMG STA can technically request to join a CDMG BSS. The DMG STA definitely shall follow the rules and procedures to join a BSS, which are defined in 802.11 spec elsewhere. So no need to mention the detailed information about how to join a BSS here. Proposed changes are as follows: “…A DMG STA can request to join a CDMG BSS. If the DMG STA successfully joins the CDMG BSS, the CDMG AP or PCP of the BSS shall schedule SPs and/or CBAPs for the DMG STA on the 2.16 GHz channel....”
848 | Goodall, David | 1 | 5 | 10.64.2.2 | 142 | 7 | T | Yes | 142 | 7 | 10.64.2.2 |  | V | Dejian Li | 11-17/0791r1 | motion 1 in 11-17/0539r3 | Is the guard interval mentioned in this sentence a PHY layer guard interval or an interframe space? | Please clarify. | Revised. The guard interval here is an interframe space. We need to add description to clarify it is a frame interspace here. Proposed resolution: Revised 10.64.2.2 CDMG BSS operating on a 1.08 GHz channel Change the mentioned paragraph as follows: A guard interval (GI) that is an interframe space follows a NP/BHI on the 2.16 GHz channel as shown in Figure 10-89a (Example of an AP or PCP starts its infrastructure BSS or PBSS on Channel 5 by transmitting DMG Beacon frames on both Channel 2 and Channel 5) and Figure 10-89b (Example of a CDMG AP or PCP starts its infrastructure BSS or PBSS on Channel 5 through transmitting DMG Beacon frames on Channel 2 only) for CDMG STAs to switch from transmitting and receiving frames on the 2.16 GHz channel to transmitting and receiving frames on the 1.08 GHz channel. The determination of the length of the GI is implementation dependent. At the end of the GI (or the NP/BHI if the GI is not present), the AP or PCP shall be ready to transmit or receive frames on the 1.08 GHz channel indicated by the Channel Number field of the Dynamic Bandwidth Control element.
849 | Goodall, David | 1 | 5 | 9.6.30.7 | 83 | 8 | E | No | 83 | 8 | 9.6.30.7 |  | v | Dejian Li | 11-17/0791r1 | motion 1 in 11-17/0539r3 | The title of the section needs to be more specific, i.e. "Allocation Response frame format" doesn't indicate what the response is for. | Specify what the response is for. | Revised. The Allocation Response frame is already in the category of CDMG Action frame, which is used only for CDMG STAs (11aj). To further avoid potential conflicts and confusion, change the name of this frame to “CDMG Allocation Response frame”. In this way, people will all know “CDMG Allocation Response frame” is just used for CDMG STAs. Proposed resolution: Revised Change all the “Allocation Response frame” to “CDMG Allocation Response frame” throughout the 11aj D5.0 spec .
850 | Goodall, David | 1 | 5 | 9.6.30.6 | 82 | 52 | E | No | 82 | 52 | 9.6.30.6 |  | V | Dejian Li | 11-17/0791r1 | motion 1 in 11-17/0539r3 | The title of the section needs to be more specific, i.e. "Allocation Request frame format" doesn't indicate what the request is for. | Specify what the request is for. | Revised. The Allocation Request frame is already in the category of CDMG Action frame, which is used only for CDMG STAs (11aj). To further avoid potential conflicts and confusion, change the name of this frame to “CDMG Allocation Request frame”. In this way, people will all know “CDMG Allocation Request frame” is just used for CDMG STAs. Proposed resolution: Revised Change all the “Allocation Request frame” to “CDMG Allocation Request frame” throughout the 11aj D5.0 spec .
851 | Lepp, James | 1 | 5 | 4.3.27 | 5 | 62 | E | No | 5 | 62 | 4.3.27 |  | A | Shiwen He | 11-17/0622r2 | motion 1 in 11-17/0539r3 | "IEEE Std 802.11" only needs to be used once on line 33. Can just call it a CMMG STA the second time around on line 62. | Remove IEEE Std 802.11 on line 62 | Accepted.
852 | Kasher, Assaf | 1 | 5 | 25.2.2. | 192 | 39 | T | Yes | 192 | 39 | 25.2.2. |  | V | Shiwen He | 11-17/0639r2 | motion 1 in 11-17/0539r3 | MIMO MCS are defined, however, there is no discussion (in clause 10 how beamforming training is done in the case of several MIMO antenna arrays | Explain how beamforming training works in this case. | Revised. MIMO MCS is only used for a transmission that uses an omnidirectional antenna pattern or quasiomni antenna pattern. It also means that the beamforming training is not a necessary step for MIMO MCS mechanism. Therefore, The beamforming training that works in the case of several MIMO antenna arrays is not defined in IEEE 802.11aj draft. — Support MIMO transmission (SC mode and OFDM mode with omnidirectional antenna pattern or quasiomni antenna pattern transceiver)
853 | Kasher, Assaf | 1 | 5 | 25.3 | 196 | 52 | T | Yes | 196 | 52 | 25.3 |  | J | Shiwen He | 11-17/0639r2 | motion 1 in 11-17/0539r3 | Channelization, (what channels CMMG operates in is not clearly defined in the PHY clause) | Add definition\clarify | Rejected. The channelization is clearly described in 25.10 and 25.11.
854 | Kasher, Assaf | 1 | 5 | 25.3.5.2 | 203 | 62 | T | Yes | 203 | 62 | 25.3.5.2 |  | V | Shiwen He | 11-17/0639r2 | motion 1 in 11-17/0539r3 | Sequences of length 256 are too long at the sample rate of 540MHz with maximum frequency offset of 20ppm. 40ppm (between two statios) at 45GHz translates to 1.8MHz. A full cycle at 1.8MHz as 0.55usec, just slightly longer than the 0.47usec of the sequence. This means that integration of a full sequence will use inverse phase for half the sequence, lowering the correlator output | shorten the sequence, or justify the length | Revised. The length of the sequence is adjusted to be 32. 25.3.5.2.1 STF of control mode The Short Training field is composed of 50 repetitions of the sequence Z(n) of length 32. The sequences Z(n) is defined in 25.8 (ZCZ sequence). 25.3.5.2.2 STF of SC and OFDM mode The Short Training fields of SC and OFDM modes share the same definition. The common Short Training field is composed of 17 repetitions of the sequence Z(n) of length 32. The sequences Z(n) is defined in 25.8 (ZCZ sequence).
855 | Kasher, Assaf | 1 | 5 | 25.3.5.2 | 203 | 62 | T | No | 203 | 62 | 25.3.5.2 |  | V | Shiwen He | 11-17/0639r2 | motion 1 in 11-17/0539r3 | The length of the control PHY preamble is equal to that of a the SC and OFDM PHY. This does not makes sense as the operate in signficantly different SNRs. | Lengthen the control PHY preamble and shorten the OFDM and SC | Revised. The control PHY preamble is adjusted to include 50 repetitions of the sequence Z(n) of length 32, however, the length of the sc and ofdm preabmle is adjusted to include 17 repetitions of the sequence Z(n) of length 32. 25.3.5.2.1 STF of control mode The Short Training field is composed of 50 repetitions of the sequence Z(n) of length 32. The sequences Z(n) is defined in 25.8 (ZCZ sequence). 25.3.5.2.2 STF of SC and OFDM mode The Short Training fields of SC and OFDM modes share the same definition. The common Short Training field is composed of 17 repetitions of the sequence Z(n) of length 32. The sequences Z(n) is defined in 25.8 (ZCZ sequence).
856 | Kasher, Assaf | 1 | 5 | 25.2.3 | 193 | 24 | E | No | 193 | 24 | 25.2.3 |  | V | Shiwen He | 11-17/0635r2 | motion 1 in 11-17/0539r3 | Channel matrices should have only one type. Compression is part of the MAC packet format and of no business of the PHY | Simplify the interface to a single format of channel matrix matrix | Revised. In Table 25-1, the row of CHAN_MAT_TYPE is removed and the CHAN_MAT only include one type, i.e., compressed feedback. The noncompressed related contents are removed from the draft. See 11-17/0635r2 for details.
857 | Kasher, Assaf | 1 | 5 | 25.2.2 | 192 | 41 | E | No | 192 | 41 | 25.2.2 |  | V | Shiwen He | 11-17/0635r2 | motion 1 in 11-17/0539r3 | It is not clear why the expansion matrices are transmitted in 3 methods from the MAC. The expansion matrix, should be computed by the MAC and sent in a single format to the PHY | Simplify the interface to a single format of expension matrix | Revised. In Table 25-1, the row of EXPANSION_MAT_TYPE is removed and the EXPANSION_MAT only include one type, i.e., compressed feedback. Removed non compressed related items from the draft. See 11-17/0635r2 for details.
858 | Kasher, Assaf | 1 | 5 | 9.4.2.232.2 | 58 | 46 | T | Yes | 58 | 46 | 9.4.2.232.2 |  | V | Shiwen He | 11-17/0635r2 | motion 1 in 11-17/0539r3 | CMMG antenna is used but not defined | Define what is a CMMG antenna (is related to an omni antenan or to an TX/RX chain) | Revised. This is a typos. CMMG antenna is refered to DMG antenna. CMMG STA uses the DMG antenna. Change related subfields name accordingly. See 11-17/0635r2 for details.
859 | Kasher, Assaf | 1 | 5 | 10.38.9 | 135 | 32 | T | Yes | 135 | 32 | 10.38.9 |  | V | Dejian Li | 11-17/0791r1 | motion 1 in 11-17/0539r3 | It is not clear in what frames is the SSW report element carried, and in what place in the mentioned flows (SLS, BRP) is it sent. | Describe when and how is the SSW report element sent in the SLS and BRP phases. | Revised. Discussion: SSW Report element is included in the BRP frame(s) during the first BRP phase after the SLS. Proposed resolution: Revised 9.6.22.3 BRP frame format Insert the following new row at the end of Table 9-417: Table 9-417—BRP frame Action field format Order Information ... ... 7 Enhanced Beam Tracking element 8 SSW report element Insert the following new row at the end of 9.6.22.3: The SSW report element is defined in 9.4.2.225 (SSW Report element). 10.38.9 CDMG enhanced beam tracking Change the third paragraph as follows: The initial alternative link of the peer STA under enhanced beam tracking is configured in the BRP phase. Specifically, in the first BRP phase after the SLS, the initiator STA returns the sector and antenna IDs of the alternative link to the responder STA, via transmitting the SSW Report element or the Enhanced Beam Tracking element in the BRP frame(s). The responder STA specifies the alternative TX AWV according to the received Report Info field or the Peer TX Antenna Parameter field. The alternative link is not used for the current data transmission.
860 | Kasher, Assaf | 1 | 5 | 9.4.1.63 | 35 | 1 | T | Yes | 35 | 1 | 9.4.1.63 |  | V | Shiwen He | 11-17/0635r2 | motion 1 in 11-17/0539r3 | There are two methods for CSI feedback. This will lead to interoperabiolity nightmare as it has led in 802.11n. One method should be chosen as it has been in 802.11ac | Chose the compressed beamforming report and remove other methods | Revised. The subsection of 9.4.1.63 CMMG Noncompressed Beamforming Report field is removed. The related descriptions, tables and subfields are also removed. See 11-17/0635r2 for details.
861 | Goldhamer, Mariana | 1 | 5 |  |  |  | G | No |  |  |  |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | DCT means "Discrete Cosine Transform" and is very confusing having the same acronym for another function | Change "Transfer" in "Dynamic Channel Transfer" to "Switch" | Revised. Change “Dynamic Channel Transfer” to “Dynamic Channel Selection (DCS)”.
862 | Goldhamer, Mariana | 1 | 5 |  |  |  | G | Yes |  |  |  |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | DCT procedure, but possibly also other procedures, are usefull not only in China. Based on the approach in this document, for every country or region will be needed an Ammendment with specific text, while in fact only the country/region specific content of the "Table E-5--Operating classes in China" make the difference | Reformulate at least the DCT procedure to become general. Specify that country/region specific parameters are defined in Annex E | Revised. Table E-5 in annex E just defines the operating classes in China and does not mean that the DCT procedure only can be used in China. However, the DCT procedure is defined for CDMG STAs according to the Chinese regulations. It is open that the DCT procedure is used by other STAs defined in 802.11 specification if vendors are willing to use it. Even so there is no need to make changes in Annex E. Propose to add the following paragraph as the last paragraph in 10.49.1(General) to describe such possibility. “Although the DCT procedure is defined for CDMG STAs according to the Chinese regulations, it can be used by other STAs defined in IEEE 802.11 specification to negotiate operating channels between BSSs.”
863 | BUCANEG, DEMETRIO JR | 1 | 5 | 24.3.2 | 167 | 33 | T | No | 167 | 33 | 24.3.2 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | In "Figure 24-1", label the corresponding "0.0 db' line in the diagram. | As noted in the comment column. | Accepted.
864 | BUCANEG, DEMETRIO JR | 1 | 5 | 24.1.2.3 | 163 | 57 | E | No | 163 | 57 | 24.1.2.3 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | Staring in Sub-clause 24.1.2.3, Line 57 regarding this written style of "See 20.1.2.2 (service specifications method)". Suggest deleting this pattern of 'phrase' or adding a brief narrative with reference to that particular 'Section' of the document. Same phrase-pattern occurs in this document. Line 65 of Page 57 also showed similar pattern and all the way to Page 238. | As noted in the comment column. | Revised. The txt in the section used this “phrase-pattern” is exactly as the same as that in the corresponding section defined in clause 20 (Directional multi-gigabit (DMG) PHY specification). So this pattern of “phrase” is used to save space and avoid unnecessary duplicate txt when 802.11aj is merged into the whole 802.11 spec. While in order to improve readability, proposed to insert appropriate description for each instance of this “phrase-pattern” as follows for example: “24.1.2.3 Service specification method The description for service specification method is the same as that contained in 20.1.2.2 (service specification method).” … 24.2 CDMG PHY service interface 24.2.1 Introduction The introduction txt for CDMG PHY service interface is the same as that contained in 20.2.1 (introduction).” Do the similar changes where applicable in the draft.
865 | BUCANEG, DEMETRIO JR | 1 | 5 | 10.32.5 | 103 | 22 | G | No | 103 | 22 | 10.32.5 |  | V | Shiwen He | 11-17/0639r2 | motion 1 in 11-17/0539r3 | Include in the 'Definitions' ther terms "beamformer" and "beamformee" respectively. Terminoligies are used in several lines in this Sub-clause and elsewhere in the document. | As noted in the comment column. | Revised. The beamformer and beamformee refer to the CMMG beamformer and CMMG beamformee, respectively. The definitions of CMMG beamformer and CMMG beamformee are given out in Clause 3, respectively. The details of the corresponding revision please refer to CID 860.
866 | BUCANEG, DEMETRIO JR | 1 | 5 | 6.3.3.3.2 | 7 | 14 | G | No | 7 | 14 | 6.3.3.3.2 |  | J | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | Starting with this 'insert note' that it is stated as 'untitled table' and it is in Pages 7-17. Suggest adding their respective proper 'Table Titles' in the final format of this standard. | As noted in the comment column. | Rejected. This standard will eventually merge into IEEE 802.11spec. Currently, there are hundreds of such tables (may be about 300~400) in clause 6 in IEEE802.11-2016. These tables have the same purpose that contain corresponding descriptions for parameters of each primitive. If we add an index and a name for each table then there will have hundreds of new tables to be included in the list of Tables in IEEE 802.11 spec. So suggest not doing so.
867 | Karocki, Piotr | 1 | 5 | 24.3.2 | 167 | 26 | E | No | 167 | 26 | 24.3.2 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | "KHz" | "kHz" - "kilo" prefix should be small "k". | Accepted.
868 | McCann, Stephen | 1 | 5 | 10.64.2.3 | 144 | 41 | E | No | 144 | 41 | 10.64.2.3 |  | A | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | typo "GH" -> "GHz" | as per comment | Accepted.
869 | McCann, Stephen | 1 | 5 | 25.3.5.2 | 203 | 65 | E | No | 203 | 65 | 25.3.5.2 |  | A | Shiwen He | 11-17/0639r2 | motion 1 in 11-17/0539r3 | The phrase "...and mod is the modulus operation" is repeated several times throughout the document and is not required. The MOD operation is well known and defined within IEEE 802.11-2016. | Remove all occurances of this phrase on P203L65, P204L26, P205L12, P206L12, P215L7 | Accepted.
870 | Yang, Yunsong | 1 | 5 | 6.3.8.5.2 | 12 | 30 | T | No | 12 | 30 | 6.3.8.5.2 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | There is no "VHT Capabilities" parameter in MLME-REASSOCIATE.response primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Propose to change the editing instruction and parameters list as follows: “Insert the following two new parameters after “GLK-GCR Parameter Set,(11ak)” in the primitive parameters list in 6.3.8.5.2 as follows: The primitive parameters are as follows: MLME-REASSOCIATE.response( ... GLK Capabilities, (11ak) GLK-GCR Parameter Set, (11ak), CDMG Capabilities, CMMG Capabilities, VendorSpecificInfo )
871 | Yang, Yunsong | 1 | 5 | 6.3.8.3.2 | 11 | 14 | T | No | 11 | 14 | 6.3.8.3.2 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | There is no "VHT Capabilities" parameter in MLME-REASSOCIATE.confirm primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Propose to change the editing instruction and parameters list as follows: “Insert the following two new parameters after “GLK-GCR Parameter Set,(11ak)” in the primitive parameters list in 6.3.8.3.2 as follows: The primitive parameters are as follows: MLME-REASSOCIATE.confirm( ... GLK Capabilities, (11ak) GLK-GCR Parameter Set, (11ak), CDMG Capabilities, CMMG Capabilities, VendorSpecificInfo )
872 | Yang, Yunsong | 1 | 5 | 6.3.8.2.2 | 10 | 33 | T | No | 10 | 33 | 6.3.8.2.2 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | There is no "VHT Capabilities" parameter in MLME-REASSOCIATE.request primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Propose to change the editing instruction and parameters list as follows: “Insert the following two new parameters after “GLK-GCR Parameter Set,(11ak)” in the primitive parameters list in 6.3.8.2.2 as follows: The primitive parameters are as follows: MLME-REASSOCIATE.request( ... GLK Capabilities, (11ak) GLK-GCR Parameter Set, (11ak), CDMG Capabilities, CMMG Capabilities, VendorSpecificInfo )
873 | Yang, Yunsong | 1 | 5 | 6.3.7.5.2 | 9 | 57 | T | No | 9 | 57 | 6.3.7.5.2 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | There is no "VHT Capabilities" parameter in MLME-ASSOCIATE.response primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Propose to change the editing instruction and parameters list as follows: “Insert the following two new parameters after “GLK-GCR Parameter Set,(11ak)” in the primitive parameters list in 6.3.7.5.2 as follows: The primitive parameters are as follows: MLME-ASSOCIATE.response( ... GLK Capabilities, (11ak) GLK-GCR Parameter Set, (11ak), CDMG Capabilities, CMMG Capabilities, VendorSpecificInfo )
874 | Yang, Yunsong | 1 | 5 | 6.3.7.3.2 | 8 | 39 | T | No | 8 | 39 | 6.3.7.3.2 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | There is no "VHT Capabilities" parameter in MLME-ASSOCIATE.confirm primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Propose to change the editing instruction and parameters list as follows: “Insert the following two new parameters after “GLK-GCR Parameter Set,(11ak)” in the primitive parameters list in 6.3.7.3.2 as follows: The primitive parameters are as follows: MLME-ASSOCIATE.confirm( ... GLK Capabilities, (11ak) GLK-GCR Parameter Set, (11ak), CDMG Capabilities, CMMG Capabilities, VendorSpecificInfo )
875 | Yang, Yunsong | 1 | 5 | 6.3.7.2.2 | 7 | 63 | T | No | 7 | 63 | 6.3.7.2.2 |  | V | Jiamin Chen | 11-17/0789r1 | motion 1 in 11-17/0539r3 | There is no "VHT Capabilities" parameter in MLME-ASSOCIATE.request primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Propose to change the editing instruction and parameters list as follows: “Insert the following two new parameters after “GLK-GCR Parameter Set,(11ak)” in the primitive parameters list in 6.3.7.2.2 as follows: The primitive parameters are as follows: MLME-ASSOCIATE.request( ... GLK Capabilities, (11ak) GLK-GCR Parameter Set, (11ak), CDMG Capabilities, CMMG Capabilities, VendorSpecificInfo )

## Revision History
Revision | Date | Description
R0 | 2017-04-24 | Comments received from TGaj initial sponsor ballot.
R1 | 2017-04-27 | Added assignees for each comment.
R2 | 2017-05-08 | Changed Assignees for CID 870-875.
R3 | 2017-05-10 | Added the resolution and motion information for each CID.

## References
References:
1. This document utilizes the template in the IEEE 802.11 comment spreadsheet.