## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/0613r5
Venue Date: | June 2017
First Author: | Jiamin CHEN, Huawei/HiSilicon
Subject: | Comments from TGaj initial sponsor ballot
Full Date: | 2017-06-08
Author(s): | Name(s) | Jiamin CHEN | Shiwen He
| Affiliation | Huawei/HiSilicon | SEU
Address
Phone:
Fax:
| email: | jiamin.chen@mail01.huawei.com | shiwenhe@seu.edu.cn
Abstract:
This document contains comments received from the initial sponsor ballot on 802.11aj D5.0. This document is periodically updated to reflect the status of those comments.

## Comments
CID | Commenter | SB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
801 | Chen, Jiamin | 1 | 5 | 11.50.4 | 160 | 21 | E | No | 160 | 21 | 11.50.4 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r2 | "A recipient CMMG STA in the BSS STA that has dot11SpectrumManagementRequired ..." Typo, remove the extra "STA". | Change to "A recipient CMMG STA in the BSS that has dot11SpectrumManagementRequired ..." Ditto at P160L49. | Accepted.
802 | Chen, Jiamin | 1 | 5 | 11.50.4 | 159 | 43 | E | No | 159 | 43 | 11.50.4 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r2 | " The value of the New Channel Number field is set to the value that dot11CurrentPrimaryChannel have after the switch." Typo, should be "has" not "have". | Change to "The value of the New Channel Number field is set to the value that dot11CurrentPrimaryChannel has after the switch." | Accepted.
803 | Chen, Jiamin | 1 | 5 | 11.49.2 | 155 | 49 | T | No | 155 | 49 | 11.49.2 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r2 | Two or more 1.08 GHz and/or 2.16 GHz channels may be occupied when a new BSS comes. Illustrate a number of possible use cases for the DCT procedure. | As comment. | Revised. Make changes under CID 803 in 11-17/789r3 (https://mentor.ieee.org/802.11/dcn/17/11-17-0789-03-00aj-proposed-resolution-to-cid-803-806-807-809-810-811-813-814-818-819-826-828-833-836-846-847-861-864-866-868-and-870-875-from-initial-sponsor-ballot.docx). These changes insert a figure providing an example of the use of the DCT procedure, as well as explanatory text.
804 | Chen, Jiamin | 1 | 5 | 11.2.3.21 | 152 | 19 | E | No | 152 | 19 | 11.2.3.21 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r2 | "A CMMG AP may allow non-AP CMMG STAs in TXOP power save mode to enter the Doze state during a TXOP. " Should be "doze state". | "A CMMG AP may allow non-AP CMMG STAs in TXOP power save mode to enter the doze state during a TXOP." Do the same changes throughout the draft where applicable. | Accepted.
805 | Chen, Jiamin | 1 | 5 | 11.2.3.21 | 153 | 35 | T | No | 153 | 35 | 11.2.3.21 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r3 | "... but the COLOR in the RXVECTOR parameter does not match the COLOR indicated by the AP to which the STA is associated." Reword. | Suggest to change to "... but the RXVECTOR parameter COLOR does not match the COLOR indicated by the AP to which the STA is associated." | Accepted.
806 | Chen, Jiamin | 1 | 5 | 10.64.3 | 146 | 49 | G | No | 146 | 49 | 10.64.3 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r4 | "..., to request the AP or PCP to shift its operating channel to one of the 1.08 GHz channels (e.g. Channel 5) within its original 2.16 GHz. ..." Incomplete statement at the end of the sentence. | Change to "..., to request the AP or PCP to shift its operating channel to one of the 1.08 GHz channels (e.g. Channel 5) within its original 2.16 GHz channel...." | Accepted.
807 | Chen, Jiamin | 1 | 5 | 10.64.2.2 | 141 | 54 | G | No | 141 | 54 | 10.64.2.2 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r5 | "During the BTI on the 2.16 GHz channel, the AP or PCP shall transmit a DMG Beacon frame containing the Dynamic Bandwidth Control element that information on the operating status of the BSS through the DBC Control field and Channel Number field...." May be syntax error. | Change to "During the BTI on the 2.16 GHz channel, the AP or PCP shall transmit a DMG Beacon frame containing the Dynamic Bandwidth Control element that includes information on the operating status of the BSS through the DBC Control field and Channel Number field. " | Accepted.
808 | Chen, Jiamin | 1 | 5 | 10.39a.1 | 138 | 27 | E | No | 138 | 27 | 10.39a.1 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r6 | "...can be used to obtain Link Margin information," Should be "link margin information" i.e., lowercase the initial letter because it is not a frame or field name here. | Change to "...can be used to obtain link margin information,". | Accepted.
809 | Chen, Jiamin | 1 | 5 | 10.38.9 | 136 | 5 | G | No | 136 | 5 | 10.38.9 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r7 | "An enhanced beam tracking initiator requesting Transmit enhanced beam tracking shall set the..." Should be "enhanced transmit beam tracking" here. | Change to "An enhanced beam tracking initiator requesting enhanced transmit beam tracking shall set the..." | Accepted.
810 | Chen, Jiamin | 1 | 5 | 10.37a.6 | 133 | 21 | T | No | 133 | 21 | 10.37a.6 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r8 | "If the SPSH in the CDMG AP or PCP Cluster subfield..." Wrong subfield name.Should be "SPSH in a CDMG AP or PCP Cluster subfield" as defined in 9.4.2.222.3. | Further suggestion is to change the subfield name to "SPSH in CDMG Cluster". | Accepted.
811 | Chen, Jiamin | 1 | 5 |  | 130 | 48 | E | No | 130 | 48 |  |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r9 | "If the AP or PCP cannot detects the presence of " Typo here. | Change to "If the AP or PCP cannot detect the presence of ". | Accepted.
812 | Chen, Jiamin | 1 | 5 | 10.37.3.4 | 122 | 55 | E | No | 122 | 55 | 10.37.3.4 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r10 | "If the non-AP and non-PCP STA is the source CMMG STA of an SP and if the non-AP and non-PCP determines that it needs to perform a TXSS before continuing to transmit to the destination CMMG STA of the SP,..." Missing "STA", should be "the non-AP and non-PCP STA". | Change to "If the non-AP and non-PCP STA is the source CMMG STA of an SP and if the non-AP and non-PCP STA determines that it needs to perform a TXSS before continuing to transmit to the destination CMMG STA of the SP,..." | Accepted.
813 | Chen, Jiamin | 1 | 5 | 10.36.11 | 121 | 64 | E | No | 121 | 64 | 10.36.11 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r11 | "If the NoPrimaryChannel field in the BF Control field is equal to 1..." It should be "NoPrimaryChannel subfield". | Change to "If the NoPrimaryChannel subfield in the BF Control field is equal to 1..." | Accepted.
814 | Chen, Jiamin | 1 | 5 | 10.36.11 | 121 | 47 | T | No | 121 | 47 | 10.36.11 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r12 | "..., the CDMG STA shall respond with a DELTS frame to the AP or PCP with the Reason Code field (9.4.1.7 (Reason Code field)) set to 68 to indicate the alternative channel is occupied upon the reception of a DMG CTS-to-self frame from the AP or PCP during the ATI." The specific value, which is defined in 9.4.1.7 (Reason Code field)to indicate the alternative channel is occupied, may be changed during the development of 802.11 spec and the value mentioned here might not be timely updated. It is difficult for editor to check and update the values that might be mentioned throughout the draft. So not to mention the spcific value here. | Remove the specific value and change to "..., the CDMG STA shall respond with a DELTS frame to the AP or PCP with the Reason Code field set to the value defined in 9.4.1.7 (Reason Code field) that indicate the alternative channel is occupied upon the reception of a DMG CTS-to-self frame from the AP or PCP during the ATI." Ditto at P121L50/L53. | Accepted.
815 | Chen, Jiamin | 1 | 5 | 10.36.10 | 118 | 32 | E | No | 118 | 32 | 10.36.10 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r13 | "...the variable NAV_CHANNEL indicated the channel that the Duration field is received," Should use present tense rather than past tense here. | Change to "indicates" | Accepted.
816 | Chen, Jiamin | 1 | 5 | 10.36.10 | 118 | 31 | E | No | 118 | 31 | 10.36.10 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r14 | "...and has associated variables NAV_RTSCANCELABLE, NAV_DTSCANCELABLE and NAV_CHANNEL which is only used by CMMG STAs,..." Use of "which" should generally be preceded by a comma or preposition. | Change "which" to "that". | Accepted.
817 | Chen, Jiamin | 1 | 5 | 10.36.6.6.4 | 116 | 39 | T | No | 116 | 39 | 10.36.6.6.4 |  | V | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r15 | "CMMG STAs shall also include the Interferer Channel Bandwidth subfield in the report, and the Interferer Channel Bandwidth subfield shall be set to the CHBAND of the NAV timer." What is "CHBAND"? | Define or explain what is "CHBAND". | Revised. This is a typo. Change "CHBAND" to "CH_BANDWIDTH", i.e. change the sentence to "CMMG STAs shall also include the Interferer Channel Bandwidth subfield in the report, and the Interferer Channel Bandwidth subfield shall be set to the CH_BANDWIDTH of the NAV timer."
818 | Chen, Jiamin | 1 | 5 | 10.36.6.6.2a | 115 | 8 | E | No | 115 | 8 | 10.36.6.6.2a |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r16 | "...after an SIFS interval." 1. In reference to 802.11-2016, use "a SIFS" rather than "an SIFS". 2. According to the 802.11 style guide, a SIFS indicates a Short Interframe Space and is already a noun phrase. There is no need to follow with "spacing/interval/period". | Change "an SIFS" to "a SIFS" and remove "interval". Similarly change "SIFS period" to "SIFS". Do the same throughout the draft. | Accepted.
819 | Chen, Jiamin | 1 | 5 | 10.36.6.6.2a | 114 | 36 | E | No | 114 | 36 | 10.36.6.6.2a |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r17 | "...otherwise, the CDMG AP or PCP shall set the Protected Period subfield to 0 to indicate the source and destination CDMG STAs do not have to establish a protected period for the SP." Missed "that" after "indicate". Ditto at P114L33/L55/L62, P51L24, P121L47. | "...otherwise, the CDMG AP or PCP shall set the Protected Period subfield to 0 to indicate that the source and destination CDMG STAs do not have to establish a protected period for the SP." Do the same changes at P114L33/L55/L62, P51L24, P121L47. | Accepted.
820 | Chen, Jiamin | 1 | 5 | 10.36.6.6.2 | 113 | 50 | E | No | 113 | 50 | 10.36.6.6.2 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r18 | "...its NAV timers corresponding to this channel are not equal to zero." According to the 802.11 Style Guide, values are shown as digits when representing the value of fields. | Change to "...its NAV timers corresponding to this channel are not equal to 0." | Accepted.
821 | Chen, Jiamin | 1 | 5 | 10.36.6.6.1 | 112 | 54 | T | No | 112 | 54 | 10.36.6.6.1 |  | V | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r19 | "In the CMMG band, the SP can have different bandwidth, 540MH or 1080 MHz, so another intent of CMMG protected period is to use dynamic bandwidth operation to negotiate a bandwidth can be use in this SP." The description is not clear, may have syntax problem. | Reword. | Revised. Change "In the CMMG band, the SP can have different bandwidth, 540MH or 1080 MHz, so another intent of CMMG protected period is to use dynamic bandwidth operation to negotiate a bandwidth can be use in this SP." to "In the CMMG protected period that have 540MHz or 1080 MHz bandwidth, the STA can use dynamic bandwidth operation to negotiate a bandwidth that can be use in this SP."
822 | Chen, Jiamin | 1 | 5 | 10.31.4 | 101 | 39 | T | No | 101 | 39 | 10.31.4 |  | V | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r20 | There is no definition for the +CMMGC frame. | Define it in reference to the definition of the +HTC frame in 9.2.2. | Revised. Change the sentence at P101L39 from "In an MFB response solicited by an MRQ that was not carried in the +CMMGC frame with NDP Announcement subfield set to 1 frame, the MFB is computed based on RXVECTOR parameters CH_BANDWIDTH, NUM_STS, BEAMFORMED, and STBC of the received PPDU that carried the MRQ and might additionally be based on other factors that are not part of the RXVECTOR." to "In an MFB response solicited by an MRQ that was not carried in a NDP Announcement frame, the MFB is computed based on RXVECTOR parameters CH_BANDWIDTH, NUM_STS, BEAMFORMED, and STBC of the received PPDU that carried the MRQ and might additionally be based on other factors that are not part of the RXVECTOR."
823 | Chen, Jiamin | 1 | 5 | 10.22.2.5 | 97 | 32 | T | No | 97 | 32 | 10.22.2.5 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r21 | The rules for the EDCA channel access in a CMMG BSS are defined in 10.22.2.12. No need to have related description in 10.22.2.5. | Remove proposed changes to 10.22.2.5. | Accepted.
824 | Chen, Jiamin | 1 | 5 | 10.2 | 95 | 8 | E | No | 95 | 8 | 10.2 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r22 | "Table 10-9 Settings for the TXVECTOR parameter PARTIAL_AID for CMMG STAs for VHT STAs". Typo and remove "...for CMMG STAs...". | Per comment. | Accepted.
825 | Chen, Jiamin | 1 | 5 | 9.6.31.3 | 84 | 54 | E | No | 84 | 54 | 9.6.31.3 |  | V | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r23 | "The Noncompressed Beamforming frame is ...". Incomplete frame name, should be "The CMMG Noncompressed Beamforming frame is ...". Ditto at P85L27 | Per comment. | Revised. Discussion: There are two methods for CSI feedback in the draft. This will lead to market confusion like that manufacturers didn't know what to implement as it has led in 802.11n. Remove Noncompressed CSI feedback method and leave only compressed CIS feedback method. Remove 9.6.31.3 (CMMG Noncompressed Beamforming frame format), which contains the paragraph "The Noncompressed Beamforming frame is ..." at P84L54, from the draft. Change the sentence at P85L27 from “The Compressed Beamforming frame is an Action or an Action No Ack frame of category CMMG….” to “The CMMG Compressed Beamforming frame is an Action or an Action No Ack frame of category CMMG….”
826 | Chen, Jiamin | 1 | 5 | 9.4.2.132 | 43 | 56 | E | No | 43 | 56 | 9.4.2.132 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r24 | Typo. Change "The Truncation Type subfield is equal to 0w." to " The Truncation Type subfield is equal to 0." | Fix it. | Accepted.
827 | Chen, Jiamin | 1 | 5 | 9.4.1.47 | 32 | 1 | T | No | 32 | 1 | 9.4.1.47 |  | V | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r25 | Usually one subclause contains one definition for one field. Insert a new subclause for the CMMG Parameters field. | Per comment. | Revised. Change the title of 9.4.1.47 from "DMG Parameters field and CMMG Parameters field" to "9.4.1.47 DMG Parameters field" and remove "NOTE—The definition of the CMMG parameters field is the same as the definition of the DMG parameters field" from 9.4.1.47. Insert the following subclauses, 9.4.1.47a after 9.4.1.47 : "9.4.1.47a CMMG Parameters field The definition of the CMMG parameters field is the same as the definition of the DMG parameters field."
828 | Chen, Jiamin | 1 | 5 | 9.3.4.2 | 29 | 29 | E | No | 29 | 29 | 9.3.4.2 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r26 | This is a subfield rather than a field. Change "the SPSH Measurement Enabled field" to "the SPSH Measurement Enabled subfield". | Per comment. | Accepted.
829 | Chen, Jiamin | 1 | 5 | 9.2.4.6a | 26 | 55 | T | No | 26 | 55 | 9.2.4.6a |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r27 | The subfield name in the CMMG Control field is wrong. Change "The AC Constraint subfield of the CMMG Control field" to "The CMMG AC Constraint subfield of the CMMG Control field" | Per comment. | Accepted.
830 | Chen, Jiamin | 1 | 5 | 9.2.4.6a | 24 | 19 | E | No | 24 | 19 | 9.2.4.6a |  | V | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r28 | The CMMG NDP Announcement subfield is 1 bit and the RDG/More PPDU subfield is 2 bits in Length. So the bit labels above them are wrong. | Fix it. | Revised. In Figure 9-15a, change the bit labels of the subfield CMMG NDP Announcement from “B25 B26” to “B25”; change the number of the bits of subfield RDG/More PPDU from “1” to “2” and change the corresponding bit label above from “B27” to “B28”; change the number of the bits of the subfield Reserved from “4” to “3” and change the corresponding bit label from “B28 B31” to “B29 B31”.
831 | Chen, Jiamin | 1 | 5 | 4.3.27 | 6 | 6 | G | No | 6 | 6 | 4.3.27 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r29 | "... allows it to operate in an Infrastructure BSS, in an IBSS, and in a PBSS." Change to "...allows it to operate in an Infrastructure BSS, in an IBSS, or in a PBSS. " | Per comment. | Accepted.
832 | Chen, Jiamin | 1 | 5 | 4.3.27 | 5 | 46 | E | No | 5 | 46 | 4.3.27 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r30 | "Normal Guard Interval" -> "Normal guard interval" | Per comment. | Accepted.
833 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 15 | E | No | 5 | 15 | 4.3.26 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r31 | "...Clause 24 (China directional multi-gigabit (CDMG) PHY specification)..." Wrong font size, use size 10. | Per comment. | Accepted.
834 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 13 | G | No | 5 | 13 | 4.3.26 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r32 | "In addition to DMG features, a CDMG STA supports DMG features as described in 4.3.21 (DMG STA)." Remove "In addition to DMG features,..." | Per comment. | Revised. Discussion: This is a typo. It should be "In addition to CDMG features... ". Change "In addition to DMG features, a CDMG STA supports DMG features as described in 4.3.21 (DMG STA)." to "In addition to CDMG features, a CDMG STA supports DMG features as described in 4.3.21 (DMG STA)."
835 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 12 | G | No | 5 | 12 | 4.3.26 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r33 | Change "...CDMG operation on Chinese 60 GHz frequency band..." to " CDMG operation in Chinese 60 GHz frequency band " | Per comment. | Accepted.
836 | Chen, Jiamin | 1 | 5 | 4.3.26 | 5 | 12 | G | No | 5 | 12 | 4.3.26 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r34 | Change "The IEEE Std 802.11 CDMG STA is a DMG STA that..." to " The IEEE 802.11 CDMG STA is a IEEE 802.11 DMG STA that...". Remove "Std" in reference to 802.11-2016. Ditto in line 33, 62. | Per comment. | Accepted.
837 | Chen, Jiamin | 1 | 5 | 9.2.3 | 23 | 27 | T | No | 23 | 27 | 9.2.3 |  | V | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r35 | No need to define an additional MAC frame format for CMMG STAs for only a minor difference with the existing frame format. | Add the CMMG Control field with a length of "0 or 4" as a new field to the MAC frame format in reference to the "HT Control" field. Add related description in the first paragraph of 9.2.3. | Revised. Insert field name "CMMG Control" in the third sentence of the first paragraph of 9.2.3 as follows: “…The fields Address 2, Address 3, Sequence Control, Address 4, QoS Control, HT Control, CMMG Control, and Frame Body are present only in certain frame types and subtypes….” Insert the “CMMG Control” field after the "HT Control” field with the length of “0 or 4” in Figure 9-1. Change the title of Figure 9-1 in 802.11aj D5.0 from "Figure 9-1-MAC frame format of MPDUs contained in PPDUs that are not CMMG PPDUs" to "Figure 9-1-MAC frame format" (as the same as the title in IEEE 802.11-2016) Remove Figure 9-1a.
838 | Li, Dejian | 1 | 5 | 10.64.2.2 | 141 | 1 | T | No | 141 | 1 | 10.64.2.2 |  | A | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r36 | Channel number 5,6,7,8 have been changed to 35,36,37,38 in annex E. | Change the channel number 5,6,7,8 to 35,36,37,38 throughout the 11aj D5.0, respectively. | Accepted.
839 | Li, Dejian | 1 | 5 | 10.37a.2.2 | 129 | 25 | T | No | 129 | 25 | 10.37a.2.2 |  | V | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r37 | It is not clear for the purpose of the step f | Change to "The AP or PCP shall join the S-AP's cluster at the selected cluster time offset on the channel of the S-AP and transmit DMG Beacon frames with the AP or PCP Clustering Control field." | Revised. Discussion: It is not clear for the purpose of the step f). The suggested remedy can make the step f more clear. Make additional changes to make it more clear as follows: Change the last bullet f) from "f) The AP or PCP shall operate its BSS at the selected cluster time offset on the channel of the S-AP and transmit DMG Beacon frames with the AP or PCP Clustering Control field." to "f) The AP or PCP shall join the cluster of S-AP at the selected cluster time offset on the channel of the S-AP and transmit DMG Beacon frames with the AP or PCP Clustering Control field." Change the second bullet of 9.4.2.132 from "—The Truncation Type subfield is equal to 0." to "— The Truncatable subfield is equal to 1 and the Truncation Type subfield is equal to 0." Change the first sentence of the fourth paragraph of 10.36.8.2 from "A CDMG AP or PCP should determine the Truncation Type fields according to the allocation type requirements of the STAs in its BSS, in order to satisfy the channel access requirements of the STAs using the potential released time of SPs. …" to "A CDMG AP or PCP should determine the Truncatable subfield and the Truncation Type subfield according to the allocation type requirements of the STAs in its BSS, in order to satisfy the channel access requirements of the STAs using the potential released time of SPs. …"
840 | Li, Dejian | 1 | 5 | 10.37a.2.2 | 128 | 61 | T | No | 128 | 61 | 10.37a.2.2 |  | V | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r38 | It is not clear what is "the current cluster" | Change "the current cluster" to "the current S-AP's cluster" | Accepted.
841 | Li, Dejian | 1 | 5 | 9.4.2.147 | 45 | 45 | T | No | 45 | 45 | 9.4.2.147 |  | A | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r39 | In 802.11ad, we use the term "ECPAC", which denotes "Extended Centralized PCP or AP Cluster". However, in 802.11-2016, we use the term ECAPC (Extended Centralized AP or PCP Cluster). We need to align this definition with 802.11-2016 | Change all the "ECPAC" to "ECAPC" throughout the 11aj D5.0. | Accepted.
842 | Li, Dejian | 1 | 5 | 10.64.1 | 140 | 32 | T | No | 140 | 32 | 10.64.1 |  | A | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r40 | It is not clear in "A pair of CDMG BSSs operating on the adjacent 1.08 GHz channels (e.g. Channel 5 and Channel 6) within a 2.16 GHz channel (i.e. Channel 2) should maintain synchronization with each other". | It is not appropriate to say "a pair of BSSs" should maintain synchronization with each other. Change "a pair of BSSs" to "a pair of APs or PCPs". | Accepted.
843 | Li, Dejian | 1 | 5 | Abstract | ii | 3 | E | No | ii | 3 | Abstract |  | A | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r41 | Grammer mistake in "at around 60 GHz" and "at around 45 GHz" | Change to "around 60 GHz" and "around 45 GHz" | Accepted.
844 | Li, Dejian | 1 | 5 | 24.3.6.1 | 170 | 65 | E | No | 170 | 65 | 24.3.6.1 |  | A | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r42 | Typo in letter "F" | Delete the letter "F" | Accepted.
845 | Li, Dejian | 1 | 5 | 9.4.2.132 | 42 | 50 | E | No | 42 | 50 | 9.4.2.132 |  | V | Dejian Li | 11-17/0792r2 | Motion 1 in 11-17/0849r43 | typo in "Figure 9-517--Allocation field format" | Change to "Figure 9-517--Allocation Control field format". So does P43L9. | Revised. Discussion: In addition to both the two changes in the "proposed change" from the commenter, the "Figure 9-517..." should be "Figure 9-518..." at P42L50 and the "Figure 9-517a..." should be "Figure 9-518a..." at P43L9. Make changes as follows: Change "Figure 9-517—Allocation field format (DMG)" to "Figure 9-518—Allocation control field format (DMG) " at P42L50. And change "Figure 9-517a—Allocation field format (CDMG)" to "Figure 9-518a—Allocation Control field format (CDMG)" at P43L9.
846 | Li, Dejian | 1 | 5 | 9.4.2.132 | 43 | 56 | E | No | 43 | 56 | 9.4.2.132 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r44 | typo in "The Truncation Type subfield is equal to 0w." | change to "The Truncation Type subfield is equal to 0." | Accepted.
847 | Goodall, David | 1 | 5 | 10.64.5 | 148 | 63 | T | Yes | 148 | 63 | 10.64.5 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r45 | If the authentication algorithm is other than 'Open' then an authentication frame exchange may also be required as part of the join. | Perhaps just leave that sentence out. | Revised. Discussion: Association is only a part of the procedure to join a BSS. The purpose of the txt here is to indicate that a DMG STA can technically request to join a CDMG BSS. The DMG STA definitely shall follow the rules and procedures to join a BSS, which are defined in 802.11 spec elsewhere. So no need to mention the detailed information about how to join a BSS here. Change the sentence at P148L64 from "…A DMG STA can request to join a CDMG BSS by transmitting an Association Request frame to the CDMG AP or PCP. The CDMG AP or PCP shall schedule SPs and/or CBAPs on the 2.16 GHz channel for those associated DMG STAs in its BSS....” to "...A DMG STA can request to join a CDMG BSS. If the DMG STA successfully joins the CDMG BSS, the CDMG AP or PCP of the BSS shall schedule SPs and/or CBAPs for the DMG STA on the 2.16 GHz channel...."
848 | Goodall, David | 1 | 5 | 10.64.2.2 | 142 | 7 | T | Yes | 142 | 7 | 10.64.2.2 |  | V | Dejian Li | 11-17/0791r2 | Motion 1 in 11-17/0849r46 | Is the guard interval mentioned in this sentence a PHY layer guard interval or an interframe space? | Please clarify. | Revised. Discussion: The guard interval here is an interframe space. We need to add description to clarify it is a frame interspace here. Change the first sentence of paragraph at P142L7 from "A guard interval (GI) may follow a NP/BHI on the 2.16 GHz channel as shown in Figure 10-89a and Figure 10-89b .... " to "A guard interval (GI) that is an interframe space follows a NP/BHI on the 2.16 GHz channel as shown in Figure 10-89a and Figure 10-89b .... ".
849 | Goodall, David | 1 | 5 | 9.6.30.7 | 83 | 8 | E | No | 83 | 8 | 9.6.30.7 |  | v | Dejian Li | 11-17/0791r2 | Motion 1 in 11-17/0849r47 | The title of the section needs to be more specific, i.e. "Allocation Response frame format" doesn't indicate what the response is for. | Specify what the response is for. | Revised. Discussion: The Allocation Response frame is already in the category of CDMG Action frame, which is used only for CDMG STAs (11aj). Make the following changes to avoid potential conflicts and confusion: Change the “Allocation Response frame” to “CDMG Allocation Response frame” throughout the draft .
850 | Goodall, David | 1 | 5 | 9.6.30.6 | 82 | 52 | E | No | 82 | 52 | 9.6.30.6 |  | V | Dejian Li | 11-17/0791r2 | Motion 1 in 11-17/0849r48 | The title of the section needs to be more specific, i.e. "Allocation Request frame format" doesn't indicate what the request is for. | Specify what the request is for. | Revised. Discussion: The Allocation Request frame is already in the category of CDMG Action frame, which is used only for CDMG STAs (11aj). Make the following changes to avoid potential conflicts and confusion: Change all the “Allocation Request frame” to “CDMG Allocation Request frame” throughout the draft.
851 | Lepp, James | 1 | 5 | 4.3.27 | 5 | 62 | E | No | 5 | 62 | 4.3.27 |  | A | Shiwen He | 11-17/0622r4 | Motion 1 in 11-17/0849r49 | "IEEE Std 802.11" only needs to be used once on line 33. Can just call it a CMMG STA the second time around on line 62. | Remove IEEE Std 802.11 on line 62 | Accepted.
852 | Kasher, Assaf | 1 | 5 | 25.2.2. | 192 | 39 | T | Yes | 192 | 39 | 25.2.2. |  | V | Shiwen He | 11-17/0639r3 | Motion 1 in 11-17/0849r50 | MIMO MCS are defined, however, there is no discussion (in clause 10 how beamforming training is done in the case of several MIMO antenna arrays | Explain how beamforming training works in this case. | Revised. Discussion: MIMO MCS is only used for a transmission that uses an omnidirectional antenna pattern or quasiomni antenna pattern. It also means that the beamforming training is not a necessary step for MIMO MCS mechanism. Therefore, The beamforming training that works in the case of several MIMO antenna arrays is not defined in IEEE 802.11aj draft. To make it clear, change the bullet at P190L47 from "— Support MIMO transmission (SC mode and OFDM mode transmit and receive)" to "— Support MIMO transmission with omnidirectional antenna pattern or quasiomni antenna pattern (SC mode and OFDM mode transmit and receive)". Insert a note at the end of subclause 25.1.1: "Note: MIMO transmission only applies in the case where the antenna pattern is the omnidirectional antenna pattern or quasiomni antenna pattern."
853 | Kasher, Assaf | 1 | 5 | 25.3 | 196 | 52 | T | Yes | 196 | 52 | 25.3 |  | J | Shiwen He | 11-17/0639r3 | Motion 1 in 11-17/0849r51 | Channelization, (what channels CMMG operates in is not clearly defined in the PHY clause) | Add definition\clarify | Rejected. Discussion: The channelization is clearly described in 25.10 and 25.11.
854 | Kasher, Assaf | 1 | 5 | 25.3.5.2 | 203 | 62 | T | Yes | 203 | 62 | 25.3.5.2 |  | V | Shiwen He | 11-17/0639r3 | Motion 1 in 11-17/0849r52 | Sequences of length 256 are too long at the sample rate of 540MHz with maximum frequency offset of 20ppm. 40ppm (between two statios) at 45GHz translates to 1.8MHz. A full cycle at 1.8MHz as 0.55usec, just slightly longer than the 0.47usec of the sequence. This means that integration of a full sequence will use inverse phase for half the sequence, lowering the correlator output | shorten the sequence, or justify the length | Revised. According to the comment, shorten the sequence and justify the length as follows: Change the first sentence of the first paragraph of 25.3.5.2 form "The Short Training field is composed of 14 repetitions of the sequence Z(n) of length 256." to "The Short Training field is composed of 50 repetitions of the sequence Z(n) of length 32. " Insert a new subclause 25.3.5.2.1 (STF of control mode) in 25.3.5.2, then move the two paragraphs of 25.3.5.2 to 25.3.5.2.1 (STF of control mode). Insert a new subclause 25.3.5.2.2: "25.3.5.2.2 STF of SC and OFDM mode The Short Training fields of SC and OFDM modes share the same definition. The common Short Training field is composed of 17 repetitions of the sequence Z(n) of length 32. The sequences Z(n) is defined in 25.8 (ZCZ sequence)."
855 | Kasher, Assaf | 1 | 5 | 25.3.5.2 | 203 | 62 | T | No | 203 | 62 | 25.3.5.2 |  | V | Shiwen He | 11-17/0639r3 | Motion 1 in 11-17/0849r53 | The length of the control PHY preamble is equal to that of a the SC and OFDM PHY. This does not makes sense as the operate in signficantly different SNRs. | Lengthen the control PHY preamble and shorten the OFDM and SC | Revised. According to the comment, lengthen the control PHY preamble and shorten the OFDM and SC as follows: Change the first sentence of the first paragraph of 25.3.5.2 form "The Short Training field is composed of 14 repetitions of the sequence Z(n) of length 256." to "The Short Training field is composed of 50 repetitions of the sequence Z(n) of length 32. " Insert a new subclause 25.3.5.2.1 (STF of control mode) in 25.3.5.2, then move the two paragraphs of 25.3.5.2 to 25.3.5.2.1 (STF of control mode). Insert a new subclause 25.3.5.2.2: "25.3.5.2.2 STF of SC and OFDM mode The Short Training fields of SC and OFDM modes share the same definition. The common Short Training field is composed of 17 repetitions of the sequence Z(n) of length 32. The sequences Z(n) is defined in 25.8 (ZCZ sequence)."
856 | Kasher, Assaf | 1 | 5 | 25.2.3 | 193 | 24 | E | No | 193 | 24 | 25.2.3 |  | V | Shiwen He | 11-17/0635r3 | Motion 1 in 11-17/0849r54 | Channel matrices should have only one type. Compression is part of the MAC packet format and of no business of the PHY | Simplify the interface to a single format of channel matrix matrix | Revised. Make changes under CID 856 in 11-17/635r3 (https://mentor.ieee.org/802.11/dcn/17/11-17-0635-03-00aj-proposed-resolution-to-cid-856-858-and-860-on-tgaj-d5-0.doc). These changes satisfy the comment and proposed change by removing noncompressed matrix type and leaving only compressed matrix type.
857 | Kasher, Assaf | 1 | 5 | 25.2.2 | 192 | 41 | E | No | 192 | 41 | 25.2.2 |  | V | Shiwen He | 11-17/0635r3 | Motion 1 in 11-17/0849r55 | It is not clear why the expansion matrices are transmitted in 3 methods from the MAC. The expansion matrix, should be computed by the MAC and sent in a single format to the PHY | Simplify the interface to a single format of expension matrix | Revised. Make changes under CID 857 in 11-17/635r3 (https://mentor.ieee.org/802.11/dcn/17/11-17-0635-03-00aj-proposed-resolution-to-cid-856-858-and-860-on-tgaj-d5-0.doc). These changes satisfy the comment and proposed change by removing noncompressed channel feedback type and leaving only compressed channel feedback type.
858 | Kasher, Assaf | 1 | 5 | 9.4.2.232.2 | 58 | 46 | T | Yes | 58 | 46 | 9.4.2.232.2 |  | V | Shiwen He | 11-17/0635r3 | Motion 1 in 11-17/0849r56 | CMMG antenna is used but not defined | Define what is a CMMG antenna (is related to an omni antenan or to an TX/RX chain) | Revised. Discussion: This is a typo. There is no CMMG antenna defined in the draft. CMMG STA uses the same antenna pattern as defined for DMG antenna. Change the following subfields’ name in Figure 9-589y and Table 9-262b: “CMMG TXOP PS” to “TXOP PS”; “CMMG Delayed Block Ack” to “Delayed Block Ack”; “Number of Rx CMMG Antennas” to “Number of Rx DMG Antennas”.
859 | Kasher, Assaf | 1 | 5 | 10.38.9 | 135 | 32 | T | Yes | 135 | 32 | 10.38.9 |  | V | Dejian Li | 11-17/0791r2 | Motion 1 in 11-17/0849r57 | It is not clear in what frames is the SSW report element carried, and in what place in the mentioned flows (SLS, BRP) is it sent. | Describe when and how is the SSW report element sent in the SLS and BRP phases. | Revised. Discussion: SSW Report element is carried in the BRP frame(s) during the first BRP phase after the SLS. Insert the following new paragraph at the end of 9.6.22.3: "The SSW report element is defined in 9.4.2.225 (SSW Report element)." Change the first two sentences of the third paragraph of 10.38.9 from "The initial alternative link of the peer STA under enhanced beam tracking is configured in the SLS or BRP phase. Specifically, in the SLS or BRP phase, the initiator STA returns the sector and antenna IDs of the alternative link to the responder STA, via transmitting the SSW Report element or the Enhanced Beam Tracking element in the SLS or BRP phase, respectively." to "The initial alternative link of the peer STA under enhanced beam tracking is configured in the BRP phase. Specifically, in the first BRP phase after the SLS, the initiator STA returns the sector and antenna IDs of the alternative link to the responder STA, via transmitting the SSW Report element or the Enhanced Beam Tracking element in the BRP frame(s)."
860 | Kasher, Assaf | 1 | 5 | 9.4.1.63 | 35 | 1 | T | Yes | 35 | 1 | 9.4.1.63 |  | V | Shiwen He | 11-17/0635r3 | Motion 1 in 11-17/0849r58 | There are two methods for CSI feedback. This will lead to interoperabiolity nightmare as it has led in 802.11n. One method should be chosen as it has been in 802.11ac | Chose the compressed beamforming report and remove other methods | Revised. Discussion: The following changes achieve the intent expressed in the comment by retaining the compressed beamforming report and removing other methods. The changes remove noncompressed CSI feedback method related subclauses, subfields and descriptions; leaving compressed CSI feedback method only. Make changes under CID 860 in 11-17/635r3 (https://mentor.ieee.org/802.11/dcn/17/11-17-0635-03-00aj-proposed-resolution-to-cid-856-858-and-860-on-tgaj-d5-0.doc).
861 | Goldhamer, Mariana | 1 | 5 |  |  |  | G | No |  |  |  |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r59 | DCT means "Discrete Cosine Transform" and is very confusing having the same acronym for another function | Change "Transfer" in "Dynamic Channel Transfer" to "Switch" | Revised. Change “Dynamic Channel Transfer (DCT)” to “Dynamic Channel Selection (DCS)” throughout the draft. Using of “Dynamic Channel Selection (DCS)” may avoid possible confusion with too many existing instances of phrase “channel switch” in IEEE 802.11 specification.
862 | Goldhamer, Mariana | 1 | 5 |  |  |  | G | Yes |  |  |  |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r60 | DCT procedure, but possibly also other procedures, are usefull not only in China. Based on the approach in this document, for every country or region will be needed an Ammendment with specific text, while in fact only the country/region specific content of the "Table E-5--Operating classes in China" make the difference | Reformulate at least the DCT procedure to become general. Specify that country/region specific parameters are defined in Annex E | Revised. Table E-5 in annex E just defines the operating classes in China and does not mean that the DCT procedure only can be used in China. However, the DCT procedure is defined for CDMG STAs according to the Chinese regulations. It is open that the DCT procedure is used by other STAs defined in 802.11 specification if vendors are willing to use it. Even so there is no need to make changes in Annex E. Insert the following paragraph as the last paragraph in 10.49.1(General) to describe such possibility: “Although the DCT procedure is defined for CDMG STAs according to the Chinese regulations, it can be used by other STAs defined in IEEE 802.11 specification to negotiate operating channels between BSSs.”
863 | BUCANEG, DEMETRIO JR | 1 | 5 | 24.3.2 | 167 | 33 | T | No | 167 | 33 | 24.3.2 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r61 | In "Figure 24-1", label the corresponding "0.0 db' line in the diagram. | As noted in the comment column. | Accepted.
864 | BUCANEG, DEMETRIO JR | 1 | 5 | 24.1.2.3 | 163 | 57 | E | No | 163 | 57 | 24.1.2.3 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r62 | Staring in Sub-clause 24.1.2.3, Line 57 regarding this written style of "See 20.1.2.2 (service specifications method)". Suggest deleting this pattern of 'phrase' or adding a brief narrative with reference to that particular 'Section' of the document. Same phrase-pattern occurs in this document. Line 65 of Page 57 also showed similar pattern and all the way to Page 238. | As noted in the comment column. | Revised. Discussion: The txt in the section used this “phrase-pattern” is exactly as the same as that in the corresponding section defined in clause 20 (Directional multi-gigabit (DMG) PHY specification). This pattern of “phrase” is used to save space and avoid unnecessary duplicate txt when 802.11aj is merged into the whole 802.11 spec. To improve readability, for each of the following subclauses, replace the first sentence of each subclause with the text shown below.: “24.1.2.3 Service specification method The description for service specification method is the same as that contained in 20.1.2.2 (service specification method).” ... 24.2.1 Introduction The introduction txt for CDMG PHY service interface is the same as that contained in 20.2.1 (introduction). ... 24.3.3.5 Transmit rampup and rampdown The description for transmit rampup and rampdown for CDMG PHY is the same as that contained in 20.3.3.5 (Transit rampup and rampdown). ... 24.3.5.1 General The description for CDMG PHY packet structure and related equations is the same as that contained in 20.3.5.1 (General). ... 24.3.5.2 Windowing function The description for CDMG PHY windowing function is the same as that contained in 20.3.5.2 (Windowing function). ... 24.3.7 HCS calculation for headers of CDMG control mode and CDMG SC mode The description for HCS calculation for headers of CDMG control mode and CDMG SC mode is the same as that contained in 20.3.7 (HCS calculation for headers of DMG control mode, DMG OFDM mode, DMG SC mode). ... 24.3.8 Common LDPC parity matrices The description for common LDPC parity matrices for CDMG PHY is the same as that contained in 20.3.8 (Common LDPC parity matrices). ... 24.3.9 Scrambler The description for CDMG PHY scrambler is the same as that contained in 20.3.9 (Scrambler). ... 24.3.10 Received channel power indicator (RCPI) measurement The description for received channel power indicator (RCPI) measurement for CDMG PHY is the same as that contained in 20.3.10 (Received channel power indicator (RCPI) measurement). ... 24.4.3.3 Data field The description for Data field for CDMG control mode is the same as that contained in 20.4.3.3 (Data field). ... 24.4.4.1.2 Transmit EVM The description for transmit EVM for CDMG control mode is the same as that contained in 20.4.4.1.2 (Transmit EVM). ... 24.5.3.1.4 Header encoding and modulation The description for header encoding and modulation for CDMG SC mode is the same as that contained in 20.6.3.1.4 (Header encoding and modulation). ... 24.5.3.2.2 Scrambler The description for CDMG SC mode scrambler is the same as that contained in 20.6.3.2.2 (Scrambler). ... 24.5.3.2.3 Encoding The description for CDMG SC mode encoding is the same as that contained in 20.6.3.2.3 (Encoding). ... 24.5.3.2.4.2 π/2-BPSK modulation The description for CDMG SC mode π/2-BPSK modulation is the same as that contained in 20.6.3.2.4.2 (π/2-BPSK modulation). ... 24.5.3.2.4.3 π/2-QPSK modulation The description for CDMG SC mode π/2-QPSK modulation is the same as that contained in 20.6.3.2.4.3 (π/2-QPSK modulation). ... 24.5.3.2.4.4 π/2-16-QAM modulation The description for CDMG SC mode π/2-16-QAM modulation is the same as that contained in 20.6.3.2.4.4 (π/2-16-QAM modulation). ... 24.5.3.2.5 Symbol blocking and guard insertion The description for CDMG SC mode symbol blocking and guard insertion is the same as that contained in 20.6.3.2.5 (Symbol blocking and guard insertion). ... 24.6.2.2.2 Header encoding and modulation The description for header encoding and modulation for CDMG low-power SC mode is the same as that contained in 20.7.2.2.2 (Header encoding and modulation). ... 24.6.2.3 Data field The description for CDMG SC mode Data field is the same as that contained in 20.7.2.3 (Data field). ... 24.9.1 Beamforming concept The beamforming concept is the same as that contained in 20.10.1 (Beamforming concept). ... 24.9.2.2.3 BRP packet header fields The description for BRP packet header fields is the same as that contained in 20.10.2.2.3 (BRP packet header fields). ... 24.9.2.2.6 TRN field The description for TRN field is the same as that contained in 20.10.2.2.6 (TRN field) ... 24.9.2.2.7 Channel measurement The description for channel measurement is the same as that contained in 20.10.2.2.7 (Channel measurement).”.
865 | BUCANEG, DEMETRIO JR | 1 | 5 | 10.32.5 | 103 | 22 | G | No | 103 | 22 | 10.32.5 |  | V | Shiwen He | 11-17/0639r3 | Motion 1 in 11-17/0849r63 | Include in the 'Definitions' ther terms "beamformer" and "beamformee" respectively. Terminoligies are used in several lines in this Sub-clause and elsewhere in the document. | As noted in the comment column. | Revised. Discussion: The "beamformer" and "beamformee" here refer to the "CMMG beamformer" and "CMMG beamformee", respectively. The "CMMG beamformer" and "CMMG beamformee" are defined in Clause 3, respectively. Change “beamformer” and “beamformee” to “CMMG beamformer” and “CMMG beamformee” respecitively throughout the draft.
866 | BUCANEG, DEMETRIO JR | 1 | 5 | 6.3.3.3.2 | 7 | 14 | G | No | 7 | 14 | 6.3.3.3.2 |  | J | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r64 | Starting with this 'insert note' that it is stated as 'untitled table' and it is in Pages 7-17. Suggest adding their respective proper 'Table Titles' in the final format of this standard. | As noted in the comment column. | Rejected. This standard will eventually merge into IEEE 802.11spec. Currently, there are hundreds of such tables (may be about 300~400) in clause 6 in IEEE802.11-2016. These tables have the same purpose that contain corresponding descriptions for parameters of each primitive. If we add an index and a name for each table then there will have hundreds of new tables to be included in the list of Tables in IEEE 802.11 spec.
867 | Karocki, Piotr | 1 | 5 | 24.3.2 | 167 | 26 | E | No | 167 | 26 | 24.3.2 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r65 | "KHz" | "kHz" - "kilo" prefix should be small "k". | Accepted.
868 | McCann, Stephen | 1 | 5 | 10.64.2.3 | 144 | 41 | E | No | 144 | 41 | 10.64.2.3 |  | A | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r66 | typo "GH" -> "GHz" | as per comment | Accepted.
869 | McCann, Stephen | 1 | 5 | 25.3.5.2 | 203 | 65 | E | No | 203 | 65 | 25.3.5.2 |  | A | Shiwen He | 11-17/0639r3 | Motion 1 in 11-17/0849r67 | The phrase "...and mod is the modulus operation" is repeated several times throughout the document and is not required. The MOD operation is well known and defined within IEEE 802.11-2016. | Remove all occurances of this phrase on P203L65, P204L26, P205L12, P206L12, P215L7 | Accepted.
870 | Yang, Yunsong | 1 | 5 | 6.3.8.5.2 | 12 | 30 | T | No | 12 | 30 | 6.3.8.5.2 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r68 | There is no "VHT Capabilities" parameter in MLME-REASSOCIATE.response primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Discussion: The commenter is correct. The mention of VHT Capabilities is both wrong and superfluous. At 12.30 delete the line 'VHT Capabilities,'"
871 | Yang, Yunsong | 1 | 5 | 6.3.8.3.2 | 11 | 14 | T | No | 11 | 14 | 6.3.8.3.2 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r69 | There is no "VHT Capabilities" parameter in MLME-REASSOCIATE.confirm primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Discussion: The commenter is correct. The mention of VHT Capabilities is both wrong and superfluous. At 11.14 delete the line 'VHT Capabilities,'"
872 | Yang, Yunsong | 1 | 5 | 6.3.8.2.2 | 10 | 33 | T | No | 10 | 33 | 6.3.8.2.2 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r70 | There is no "VHT Capabilities" parameter in MLME-REASSOCIATE.request primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Discussion: The commenter is correct. The mention of VHT Capabilities is both wrong and superfluous. At 10.33 delete the line 'VHT Capabilities,'"
873 | Yang, Yunsong | 1 | 5 | 6.3.7.5.2 | 9 | 57 | T | No | 9 | 57 | 6.3.7.5.2 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r71 | There is no "VHT Capabilities" parameter in MLME-ASSOCIATE.response primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Discussion: The commenter is correct. The mention of VHT Capabilities is both wrong and superfluous. At 9.57 delete the line 'VHT Capabilities,'"
874 | Yang, Yunsong | 1 | 5 | 6.3.7.3.2 | 8 | 39 | T | No | 8 | 39 | 6.3.7.3.2 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r72 | There is no "VHT Capabilities" parameter in MLME-ASSOCIATE.confirm primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Discussion: The commenter is correct. The mention of VHT Capabilities is both wrong and superfluous. At 8.39 delete the line 'VHT Capabilities,'"
875 | Yang, Yunsong | 1 | 5 | 6.3.7.2.2 | 7 | 63 | T | No | 7 | 63 | 6.3.7.2.2 |  | V | Jiamin Chen | 11-17/0789r3 | Motion 1 in 11-17/0849r73 | There is no "VHT Capabilities" parameter in MLME-ASSOCIATE.request primitive. Use a parameter existing in the baseline document to show where the two new parameters are inserted. | Change as commented. | Revised. Discussion: The commenter is correct. The mention of VHT Capabilities is both wrong and superfluous. At 7.63 delete the line 'VHT Capabilities,'"

## Revision History
Revision | Date | Description
R0 | 2017-04-24 | Comments received from TGaj initial sponsor ballot.
R1 | 2017-04-27 | Added assignees for each comment.
R2 | 2017-05-08 | Changed Assignees for CID 870-875.
R3 | 2017-05-10 | Added the resolution and motion information for each CID.
R4 | 2017-05-10 | Change subssion number from "11-17/0622r2" to "11-17/06222r3"
R5 | 2017-06-08 | Updated resolutions for a number of CIDs.

## References
References:
1. This document utilizes the template in the IEEE 802.11 comment spreadsheet.