## Slide 1: IEEE 802.11aj May Closing Report
Date: 2017-05-12
Author:

## Slide 2: Abstract
This document is the TGaj closing report for the May 2017 session.

## Slide 3: Work Completed (1/2)
  Approved March 2017 meeting minutes (11-17/0518r0) and April 27th conference call meeting minutes (11-17/0636r0)
The following comment resolution proposals have been presented and approved
  CID 803, 806-807, 809-810, 811, 813-814, 818-819, 826, 828, 833-836, 846-847, 861-864, 866-868 and 870-875 (from 11-17/0789r2)
  CID 801, 802, 804, 805, 808, 812, 815-817, 820-825, 827, 829-832, 837, and 851 (from 11-17/0622r3)
  CID 856-858 and 860 (from 11-17/0635r2)
  CID 854-855, 865 and 869 (from 11-17/0639r2)
  CID 848-850, 859 (from 11-17/0791r1)
  CID 838-845 (from 11-17/0792r1)
Completed comment resolution for the initial SB on D5.0

## Slide 4: Work Completed (2/2)
Instruct the editor to prepare Draft 6.0 incorporating those approved resolutions
Approved a 10-day Sponsor Recirculation Ballot asking the question “Should P802.11aj D6.0 be forwarded to RevCom?”
Updated TG timeline

## Slide 5: Plan for July meeting
Complete comment resolution for TGaj Recirculation Sponsor Ballot
Conditional IEEE 802 EC approval
Prepare draft press release for WG approval
Timeline update if needed

## Slide 6: Conference Call Time
  8th Jun, 2017, 10 pm ET for 2 hours
  (9th Jun, 2017, 10 am Beijing Time)
  15th Jun, 2017, 10 pm ET for 2 hours
  (16th Jun, 2017, 10 am Beijing Time)
  22nd Jun, 2017, 10 pm ET for 2 hours
  (23rd Jun, 2017, 10 am Beijing Time)
  29th Jun, 2017, 11 pm ET for 2 hours
  (30th Jun, 2017, 11 am Beijing Time)
  6th July, 2017, 10 pm ET for 2 hours
  (7th July, 2017, 10 am Beijing Time)

## Slide 7
Thank you！