## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/0927r27
Venue Date: | November 2018
First Author: | Mark Hamilton, Ruckus/ARRIS
Subject: | REVmd Working Group Comments for MAC ad-hoc
Full Date: | 2018-11-2
Author(s): | Name(s) | Mark Hamilton
| Company | Ruckus/ARRIS
Address
Phone:
Fax:
| email: | mark.hamilton@arris.com
Abstract:
This document contains comments in the "MAC ad hoc" group, submitted on REVmd Comment Collections and WG Ballots on the published IEEE Std 802.11-2016 and subsequent amendments.

## Revision History
Revision | Date | Description
0 | 2017-06-23 | Initial revision after WG Comment Collection.
1 | 2017-06-23 | Moved Comment Groups {DMG, MAC-PHY, Power saving, and Security} to PHY Ad-hoc
2 | 2017-06-29 | Adds Assignee for all CIDs (not all have agreed,yet, though :) ), adds submission for some CIDs
3 | 2017-07-12 | CIDs ready for motion on "Motion MAC-A": 88, 105, 343, 344, 345, 349, 352, 353, 354. BRC discussion on 'Obsolete' CIDs: 57, 58, 59, 60, 61, 62, 63, 64, 65, 66, 67, 69. Took 'Obsolete' CIDs from other ad-hocs: 67, 69, 70, 72, 137, 198.
4 | 2017-07-12 | Fixed resolution for CID 88 to capture the Ad-hoc notes and agreement of the BRC (database error correction)
5 | 2017-08-18 | CIDs ready for motion on "Motion MAC-B" (from Thursday afternoon of Berlin F2F): 255, 227, 220, 200, 365, 364, 336. CIDs ready for motion on "Motion MAC-C" (collecting resolutions from teleconferences, so far): 53, 52, 35, 34, 33.
6 | 2017-09-04 | CIDs ready for motion, added to "Motion MAC-C" tab: 186,187.
7 | 2017-09-14 | CIDs ready for motion on "Motion MAC-D" (from Waikoloa F2F, through Wednesday evening): 219, 178, 162, 161, 155, 149, 83, 110, 109, and CIDs ready for motion on "Motion MAC-ESP" from document 11-17/1192r4: 259, 215, 56, 55, 54, 31.
8 | 2017-09-14 | CIDs ready for motion on "Motion MAC-E" tab (from Waikoloa F2F, Thurs PM1): 330, 281, 230, 185, 181, 160, 142, 132, 363, 23, 42, 41, 39.
9 | 2017-09-14 | Updates from Waikoloa F2F, Thus PM2; CIDs ready for motion on "Motion MAC-F" tab: 87, 113, 46, 43, 37, 36. Prior motioned CIDs moved to EDITOR (and out of this sheet).
10 | 2017-11-02 | Updates from teleconferences. CIDs ready for motion on "Motion MAC-G": 326, 266, 357, 66, 60, 51, 50, 15.
11 | 2017-11-09 | CIDs ready for motion on "Motion MAC-H" tab (from Orlando F2F, Mon/Tues/Wed: 294, 189, 163, 112.
12 | 2017-12-08 | CIDs ready for motion on "Motion MAC-I" tab (Friday, at Orlando F2F): 264, 198, 197, 148. CIDs ready for motion on "Motion MAC-J" tab (from Piscataway ad hoc F2F): 301, 282, 231, 218, 152, 137, 74, 72, 17, 351, 47, 40.
13 | 2018-01-15 | CIDs ready for motion on "Motion MAC-J" and "Motion MAC-K" tabs (from Piscataway ad hoc and January teleconference): 301, 282, 231, 218, 152, 137, 74, 72, 17, 351, 47, 40, 283, 338. CIDs ready for motion on "Motion MAC-L" tab (from Irvine F2F, Mon): 116, 305, 194, 180, 179, 337, 106, 3, 341, 340, 362.
14 | 2018-01-17 | CIDs ready for motion on "Motion MAC-M" tab (from Irvine F2F): 290, 339, 70. Motions ready for motion per 11-17/1192r15: 259, 251, 217, 216, 215, 214, 213, 212, 56, 55, 54, 31, 30.
15 | 2018-04-05 | Updated with comments from LB232 on REVmd D1.0. Categorized all into proposed Comment Group, and with initial Assignee.
16 | 2018-04-16 | CIDs ready for Motion on "Motion MAC-N" tab (from teleconferences, and FLL ad hoc): 1391, 1299, 1308, 1313, 1347, 1356, 1358, 1381, 1147, 1390, 1554, 1392, 1398, 1425, 1504, 1469, 1528, 1477, 1382.
17 | 2018-05-06 | 11-18/0702, has proposed resolutions to CIDs: 1100, 1103, 1105, 1106, and 1107, and 11-18/0704r0 has proposed resolution for CID 1443. CID 1382 has a proposed update for its resolution, since the REVmd teleconference agreement to Reject. CID 1011 is ready for Discussion.
18 | 2018-05-10 | Updates from discussions at Warsaw session. CIDs ready for motion on "Motion MAC-O" tab: 1397, 1394, 1369, 1354, 1189, 1021. CID 1504 resolution document updated to r3. CID 1382 pulled from Motion MAC-N for more discussion.
19 | 2018-07-11 | Updates from last day at Warsaw session and teleconferences: CIDs ready for motion on "Motion MAC-P": 1296, 1030, 1268, 1276, 1289, 1290, 1291, 1292, 1293, 1015, 1295, 1586, 1297, 1318, 1319, 1320, 1382, 1384, 1395, 1533, 1294. Updates from San Diego F2F, through Tuesday: CIDs ready for motion on "Motion MAC-Q": 1486, 1420, 1412, 1374, 1154, 1153, 1152, 1151, 1150, 1149, 1065, 1064, 1063, 1062, 1506.
20 | 2018-07-12 | CIDs ready to motion, from San Diego session through Wednesday, on "Motion MAC-R" tab: 1440, 1404, 1402, 1317, 1274, 1259, 1029, 1025.
21 | 2018-07-16 | CIDs ready for motion from last meeting slot in San Diego, on "Motion MAC-S" tab: 1364, 1258, 1244. (Note, CID 1244 was resolved in April, but got lost from going to motion.) CIDs for all motions from San Diego have been transferred to Editor.
22 | 2018-09-09 | CIDs ready for motion from teleconferences and Portland ad-hoc meeting, on "Motion MAC-T" tab: 1190, 1009, 1010, 1011, 1012, 1018, 1033, 1056, 1103, 1105, 1106, 1008, 1114, 1452, 1268, 1281, 1282, 1305, 1400, 1401, 1403, 1405, 1414, 1443, 1447, 1107.
23 | 2018-09-13 | CIDs ready for motion from Waikoloa F2F on "Motion MAC-U" tab: 1298, 1074, 1075, 1082, 1100, 1102, 1104, 1241, 1243, 1261, 1262, 1007, 1288, 1544, 1300, 1310, 1312, 1314, 1334, 1335, 1336, 1337, 1338, 1343, 1493, 1542, 1543, 1287.
24 | 2018-09-13 | Corrected typo in CID 1298, now references (correctly) document 11-18/1296r2.
25 | 2018-09-13 | CIDs ready for motion from Waikoloa F2F on Thursday, ready for motion, on tab "Motion MAC-V": 1485, 1536, 1349, 1339, 1273.
26 | 2018-10-12 | CIDs ready for motion from teleconferences, on tab "Motion MAC-V": 1503, 1195, 1238, 1256, 1286, 1315, 1375, 1396, 1073, 1431, 1614, 1505, 1526, 1553, 1560, 1569, 1572, 1573, 1593, 1594, 1415.
27 | 2018-11-02

## Chris Hansen
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1161 | Christopher Hansen | 232 | 1 | 10.25 | 1713 | 50 | T | Y | 1713.5 | 50 | 10.25 |  |  | Chris Hansen |  |  | Exchange of ADDBA Request/Response Frames is inefficient. | Contribution on unsolicited block ack will be provided. |  | MAC | New feature | Submission Required |  |  |  |  | 2018-04-04 22:55 | MAC

## Ganesh Venkatesan
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1145 | Yongho Seok | 232 | 1 | 9.4.2.166 | 1265 | 38 | T | Y | 1265.38 | 38 | 9.4.2.166 |  |  | Ganesh Venkatesan | 11-18/885 |  | An S1G STA can use the Fine Timing Measurement procedure. Add S1G PPDU format into Table 9-272 (Format And Bandwidth field). | Add S1G PPDU format into Table 9-272 (Format And Bandwidth field). |  | MAC | FTM | Submission Required | MAC: 2018-06-15 17:39:16Z - Reviewed proposed changes, in detail. Editorial cleanup, no further comments. Still waiting for discussion about market need, and how well this works with 1 MHz bandwidth. Submission is expected with that discusison. Note that position accuracy is less at 1 MHz bandwidth, but use cases exist for lower accuracy with this PHY. MAC: 2018-05-10 13:10:01Z: Reviewed 11-18/885 at Warsaw F2F. Generally supportive. Need to hear rationale for adding this feature, first. |  |  |  | 2018-06-15 17:41 | MAC

## Mark Hamilton
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1620 | Albert Petrick | 232 | 1 | 9.4.2.194 | 1298 | 64 | T | N | 1298.64 | 64 | 9.4.2.194 |  |  | Mark Hamilton |  |  | Note has normative text "can be set to".... Notes can only contain informative text. | Extract the normative information in the paragraph on line 60. |  | MAC | Clarification/correction | Submission Required |  |  |  |  | 2018-04-05 00:57 | MAC
1609 | Peter Ecclesine | 232 | 1 | 2 | 138 | 8 | E | N | 138.08 | 8 | 2 |  |  | Mark Hamilton |  |  | IEEE 802.3 has been updated | Update all clause 2 references for current versions |  | MAC | Minor Correction | Submission Required | MAC: 2018-08-03 16:11:38Z - This is submission required because an evaluation must be done of each occurrence of a reference to confirm that the chnages since the currently referenced version do not invalidate/change any 802.11 text, before the reference can be changed. It is known, from previous discussions/similar evaluations that some references were (at least at some time) dependent on the particular revision of the referenced standard/spec. MAC: 2018-04-30 23:13:00Z - status set to: Submission Required EDITOR: 2018-04-30 21:41:13Z - status set to: Assigned EDITOR: 2018-04-30 21:40:03Z - feedback from TGmd telecon(4/27): Revised. At 271.52: change “IEEE Std 802.3-2012” to “IEEE Std 802.3”. At 138.8, change “IEEE Std 802.3™-2012, IEEE Standard for Ethernet” to “IEEE Std 802.3™-2015, IEEE Standard for Ethernet”. However, this comment is related to CID 1545. Assign it to Mark H and transfer to MAC too. EDITOR: 2018-04-02 22:20:57Z - status set to: Discuss |  |  |  | 2018-08-03 16:15 | MAC
1565 | Mark Hamilton | 232 | 1 | 6.3.31.2.2 | 415 | 45 | T | Y | 415.45 | 45 | 6.3.31.2.2 |  |  | Mark Hamilton |  |  | Saying the LCI Management Request parameter is defined in 9.6.7.32 is pointless and not helpful. 9.6.7.32 actually says that this is a Measurement Request element (defined in 9.4) with most of the fields set to known (constant) values. We should only pass the information that is actually variable to this primitive. | Replace this parameter with two parameters, with column information: "Parallel", "Boolean", "true, false", "As defined in 9.4.2.20.1", and "Optional subelements", "As defined in 9.4.2.20.10", "As listed in Table 9-106", "Zero or more subelements to include in the request". Same for Location Civic Measurement Request. Same in the Neighbor Report indication. Same in the FTM request and indication, and FTM Request request and indication. |  | MAC | Minor Correction | Submission Required | MAC: 2018-08-03 16:15:57Z - status set to: Submission Required, to provide details of referenced/changed text. GEN: 2018-07-31 19:38:22Z - status set to: Discuss - reference does not seem correct. |  |  |  | 2018-08-03 16:17 | MAC
1557 | Mark Hamilton | 232 | 1 | 10.2.1 | 1563 | 28 | T | Y | 1563.28 | 28 | 10.2.1 |  |  | Mark Hamilton |  |  | HCF doesn't really use DCF architecturally. It 'replaces' DCF. | Change Figure 10-1 to show HCF (EDCA and HCCA) as directly using the PHY. Cleanup text in 10.2, 10.3 and 10.22 to not describe HCF as using DCF. |  | MAC | HCF | Submission Required | MAC: 2018-04-05 20:52:47Z - status set to: Submission Required |  |  |  | 2018-04-05 20:53 | MAC
1556 | Mark Hamilton | 232 | 1 | 14.9.2 | 2557 | 57 | T | Y | 2557.5701 | 57 | 14.9.2 |  |  | Mark Hamilton |  |  | What is a "test frame" | Replace "[the] test frame" with "a nominal frame". Same thing in Table 14-4, and in 14.9.3 in Table 14-6. |  | MAC | Testing | Discuss | MAC: 2018-04-24 17:28:49Z - status set to: Discuss |  |  |  | 2018-04-24 17:29 | MAC
1545 | Michael Fischer | 232 | 1 | 2 | 137 | 49 | E | N | 137.49 | 49 | 2 |  |  | Mark Hamilton |  |  | The reference to 802.1Q-2003 is obsolete | Replace with the current version of the standard for virtual bridged LANs |  | MAC | Minor Correction | Submission Required | MAC: 2018-08-03 16:11:38Z - This is submission required because an evaluation must be done of each occurrence of a reference to 802.1Q to confirm that the chnages since 2003 do not invalidate/change any 802.11 text, before the reference can be changed. It is known, from previous discussions/similar evaluations that some references were (at least at some time) dependent on the particular revision of 802.1Q. MAC: 2018-04-30 23:13:15Z - status set to: Submission Required EDITOR: 2018-04-30 21:39:22Z - status set to: Assigned EDITOR: 2018-04-30 21:37:24Z - feedback from TGmd teleconf (4/27): Revised. At 137.53 change “IEEE Std 802.1Q™-2011” to ““IEEE Std 802.1Q™-2014” Note to commenter: IEEE Std 802.1Q™-2003 is specifically used at 1051.30. We still need IEEE Std 802.1Q™-2003. Need more work to clean references in the draft. Assign it to Mark H and transfer to MAC. EDITOR: 2018-04-02 22:19:41Z - status set to: Discuss |  |  |  | 2018-08-03 16:14 | MAC
1532 | Mark RISON | 232 | 1 | 9.4.2.179 | 1277 | 33 | T | Y | 1277.33 | 33 | 9.4.2.179 |  |  | Mark Hamilton |  |  | "0: Reserved, FILS Public Key is undefined." -- this can't be used, nor can any values above 3 | Delete the line at 1277.33 and at the end of the referenced subclause add "Other values are reserved." |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 17:01:53Z - status set to: Discuss |  |  |  | 2018-08-03 17:02 | MAC
1520 | Mark RISON | 232 | 1 | 10.23.2.8 | 1676 | 63 | T | Y | 1676.63 | 63 | 10.23.2.8 |  |  | Mark Hamilton |  |  | "Note that when transmitting multiple frames in a TXOP using acknowledgment mechanisms other than Normal Ack," -- it is not clear what this means; it seems to be inadvertently omitting implicit BA | Change the cited text at the referenced location to "Note that when transmitting multiple frames in a TXOP using acknowledgment mechanisms other than immediate acknowledgement," |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 17:07:10Z - status set to: Discuss |  |  |  | 2018-08-03 17:07 | MAC
1519 | Mark RISON | 232 | 1 | 9.4.2.36 | 1066 | 25 | T | Y | 1066.25 | 25 | 9.4.2.36 |  |  | Mark Hamilton |  |  | "Set to 4 for 80+80 MHz operating channel width" is not consistent with the other sentences | Change the cited text at the referenced location to "Set to 4 for 80+80 MHz BSS bandwidth" |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 21:38:58Z - status set to: Discuss |  |  |  | 2018-08-03 21:39 | MAC
1511 | Mark RISON | 232 | 1 | 10.7 | 1644 | 20 | T | Y | 1644.2 | 20 | 10.7 |  |  | Mark Hamilton |  |  | "For MSDUs or A-MSDUs belonging to the service class of QoSAck when the receiver is a QoS STA, set to Normal Ack or Implicit Block Ack Request, PSMP Ack, or Block Ack." is missing some words (what is set?) | Change the cited text in the referenced location to "For MSDUs or A-MSDUs belonging to the service class of QoSAck when the receiver is a QoS STA, the QoS Data frames that are used to send these MSDUs or A-MSDUs shall have the Ack Policy subfield in the QoS Control field set to Normal Ack or Implicit Block Ack Request, PSMP Ack, or Block Ack." |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 17:06:44Z - status set to: Discuss |  |  |  | 2018-08-03 17:07 | MAC
1498 | Mark RISON | 232 | 1 |  |  |  | E | Y | [5 empty] | Mark Hamilton |  |  | There is no such thing as "DSSS/CCK mode" | Change "DSSS/CCK Mode" (or "mode") to "DSSS/CCK PPDUs" in 9.4.2.55.2 (3x), 11.15.8 (4x), C.3 (1x). Change "dot11RMNeighborReportHTDSSCCKModein40MHz" to "dot11RMNeighborReportHTDSSCCKPPDUsin40MHz" in C.3 (3x) |  | MAC | DSSS-CCK | Discuss | MAC: 2018-08-03 16:10:10Z - status set to: Discuss MAC: 2018-04-05 20:43:03Z - status set to: Submission Required EDITOR: 2018-04-04 21:51:14Z - It seems a technical comment. Transfered it to MAC. |  |  |  | 2018-08-03 16:10 | MAC
1444 | Mark RISON | 232 | 1 | 9.7.3 | 1535 | 1 | E | Y | 1535.01 | 1 | 9.7.3 |  |  | Mark Hamilton |  |  | The A-MPDU context tables randomly mix "MPDU" and "frame" | Change "MPDU" to "frame" throughout Tables 9-491 to 9-496, when not preceded by "A-" (i.e. do not change "A-MPDU" to "A-frame") |  | MAC | Minor Correction | Submission Required | MAC: 2018-05-06 16:54:57Z - status set to: Submission Required EDITOR: 2018-04-13 21:43:46Z - Transder to MAC. EDITOR: 2018-04-03 17:53:03Z - status set to: Discuss |  |  |  | 2018-05-06 16:55 | MAC

## Mark Rison
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1483 | Mark RISON | 232 | 1 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Per the ad-hoc notes for CID 15: Bring back other changes for consistency elsewhere in the Std: - Continue list in 11-17/1412r1 - Search for all "0 or ..." and check that they all have "(optional)" - On "<i> x n" expressions, can 'n' be 0 or more, or always 1 or more? Sometimes it says "0 or (<i> x n)" (9-255). - Keep OI length as "<j>" for ease of maintenance. | Make the changes referred to in the comment, i.e. say "(optional)" for all optional subfields, say "(optional)" and "0 or (4xn)" for fields where zero-length is allowed (implication being just "4xn" would not allow n=0) |  | MAC | Frame formats | Submission Required | MAC: 2018-04-05 20:50:47Z - status set to: Submission Required |  |  |  | 2018-04-05 20:51 | MAC
1476 | Mark RISON | 232 | 1 | 10.6 |  |  | T | Y |  |  | 10.6 |  |  | Mark Rison |  |  | The multirate rules are an impenetrable mess. It's impossible to determine whether they are complete, let alone whether they are correct | Rewrite as a flowchart or table, so that it can be seen that the rules are complete and correct |  | MAC | Multirate | Submission Required | MAC: 2018-04-05 20:55:31Z - status set to: Submission Required |  |  |  | 2018-04-05 20:56 | MAC
1466 | Mark RISON | 232 | 1 | 11 |  |  | T | Y |  |  | 11 |  |  | Mark Rison |  |  | Discussions related to CID 7592 and 7593 in mc have revealed that the description of legacy PS and U-APSD is hopelessly muddled in terms of things like how PS-Polls operate for U-APSD and duplication of statements and consistency of description | Refactor the wording |  | MAC | Power mgmt | Submission Required |  |  |  |  | 2018-04-11 15:34 | MAC

## Menzo Wentink
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1267 | Joseph Levy | 232 | 1 | 11.23.6.5 | 2143 | 20 | G | Y | 2143.2 | 20 | 11.23.6.5 |  |  | Menzo Wentink |  |  | Calling a S1G 2, 4, 8, or 16 MHz off-channel TDLS direct link a "wide bandwidth off-channel direct link" seems a bit confusing. I understand the need to allow for an off-channel direct link for S1G STAs, but shouldn't it be called something else. Also the way the feature is implemented in the section 11.23.6.5 seems very awkward. It would be better to add a new set of clauses for the "S1G off-channel direct link", which duplicate 11.23.6.5 with the S1G changes. This would also eliminate the need to keep switching between VHT and S1G requirements. | Remove the (11ah) additions to 11.23.6.5 which added S1G to the wide bandwidth off-channel direct link and add a new section "11.23.6.6 Setting up a S1G off-channel direct link" with the S1G requirements. |  | MAC | S1G | Submission Required | MAC: 2018-04-10 18:59:54Z - status set to: Submission Required MAC: 2018-04-10 18:58:03Z: Discussed at FLL ad hoc, supportive: 5, not supportive: 1, no opinion: 4. |  |  |  | 2018-09-13 01:07 | MAC
1263 | Xiaofei Wang | 232 | 1 | 10.50.2 | 1921 | 25 | T | Y | 1921.25 | 25 | 10.50.2 |  |  | Menzo Wentink | 11-18/1654 |  | The reachable address update procedure may create an error in the following situation: 1. STA1 who is originally associated with relay AP1, moves to relay AP2, under the same root AP, without perfroming disassociation with relay AP1 2. relay AP2 performs reachable address update to the root AP based on condition 1) in L23 3. Before the max idle period expiry of STA1 in relay AP1, another STA2 associates with relay AP1 4. relay AP1 sends reachable address update frame containing "current list" STA1 and STA2 to root AP based on condition 1) in L23, overwriting the correct forwarding entry for STA1 in root AP 5. Later traffic to STA1 is forwarded to relay AP1, causing relay AP1 disassociation of STA1, which triggers another reachable address update frame sent to root AP, based on condition 2) in L23. This completely removes STA1 from root AP's "current list" of reachbale addresses | A potential solution may be: An S1G relay STA shall send a Reachable Address Update frame that contains the modifications of reachable addresses to the AP to which it is associated when one of the following conditions occurs: 1)A new non-AP STA associates with the S1G relay AP of the relay 2)A non-AP STA is disassociated or deauthenticated from the S1G relay AP of the S1G relay 3)A Reachable Address Update frame is received at the S1G relay AP of the S1G relay For condition 1) and 2), the reachable address update frame only contains the newly associated/disassocated STA addresses For condition 3), the relay AP ignores/removes an address from the reachable address element with add/remove subfield set to 0, from the received reachable address update frame, if the current forwarding relay for the address is not the same as the the STA sending the reachable address update frame to the relay AP |  | MAC | S1G | Submission Required | MAC: 2018-10-15 15:49:29Z - Reviewed 11-18/1756r0. Concerns about Option 2's need for relative timestamps to the TU granularity, which can be hard to do with transmission delays. Will discuss further off-line. Option 3 suggested, to have (strong hints of?) when an update collision occurred, and only require additional recovery(?) when that happens. MAC: 2018-09-12 - 5.7.2.3 The “for the STAs satisfying the following conditions:” then the conditions are not able to both be true. Need to change to “…one of the following…” 5.7.2.4 Discussion on how often the refresh can be done. 5.7.2.5 This change was discussed in 11ah, but the change was not made then and the thought by the commenter that they could bring later during the revision. 5.7.2.7 This is a real problem that will need more thought to resolve. Addition review is requested to continue working with Xiaofei. 5.7.2.9 Note that in document 11-18/1300 it had proposed a reject for this CID. This submission is proposing an alternate suggestion, but it needs more work off-line. MAC: 2018-08-03 17:10:16Z - status set to: Submission Required |  |  |  | 2018-11-01 22:26 | MAC
1143 | Robert Stacey | 232 | 1 | 9.9.1 | 1550 | 35 | T | N | 1550.35 | 35 | 9.9.1 |  |  | Menzo Wentink |  |  | There are 8 NDP CMAC control frames and 2 NDP CMAC management frames. Surely there is a general frame format -- an architecture -- behind this menagerie. | Define a general MAC frame format for CMAC frames. It looks like there might be two basic types: a 24-bit frame and a 36-bit frame (distinguished by the PPDU fomat that carrier them). Define a general MAC frame format for each -- this may just be a Frame Tpe field and Frame Body field. Define the Frame body for each of the individual frames (no need to show the Frame Type field for each since this is common to all) |  | MAC | S1G | Submission Required | MAC: 2018-08-03 21:58:00Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC
1142 | Robert Stacey | 232 | 1 | 9.9 | 1550 | 10 | T | N | 1550.1 | 10 | 9.9 |  |  | Menzo Wentink |  |  | The (spec) architecture around NDP CMAC frames is misguided. NDP CMAC frames are another (MAC) frame format like the PV0 and PV1 formats. PV0 and PV1 frames go into an A-MPDU which becomes the PSDU that is transferred to the PHY using the PHY SAP defined in Clause 8. Similarly, NDP CMAC frames SHOULD become the PSDU that is trnasferred to the PHY using the PHY SAP. | Focus 9.9 on the frame formats. Remove references to figures and PPDU formats in Clause 23. Add a general statement: "NDP CMAC frames are carried in the S1G NDP PPDU". Remove the NDP_CMAC_FRAME_BODY parameter from the TX/RXVECTOR. Add a description to 23.3.18 and 23.3.19 to descibe the mapping of the PSDU to and from the SIG field. |  | MAC | S1G | Submission Required | MAC: 2018-08-03 21:57:45Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC
1128 | Robert Stacey | 232 | 1 | 9.8.1 | 1538 | 4 | T | N | 1538.04 | 4 | 9.8.1 |  |  | Menzo Wentink |  |  | Subclause 9.2.1 describes both PV0 and PV1 frames. 9.8.1 just repeats this for PV1 frames. | Remove 9.8.1 (including its content) |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:04:33Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1126 | Robert Stacey | 232 | 1 | 9.4.1.48.2 | 889 | 54 | T | N | 889.54 | 54 | 9.4.1.48.2 |  |  | Menzo Wentink |  |  | S1G band is not defined. Given the statement at P215L39 and the lack of global harminzation, it should probably be plural. | Define "S1G bands" as "Frequency bands below 1 GHz excluding the TV white space bands" or maybe "Frequency bands for which an S1G operating class is defined in Annex E." Replace "S1G band" with "S1G bands" throughout. |  | MAC | S1G | Discuss | MAC: 2018-08-03 16:50:27Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1124 | Robert Stacey | 232 | 1 | 11.2.3.2 | 1969 | 52 | T | N | 1969.52 | 52 | 11.2.3.2 |  |  | Menzo Wentink |  |  | This seems to redefine "non-TIM STA". See P173L36. | Remove either this statement or the one at P173L36. |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:11:18Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1123 | Robert Stacey | 232 | 1 | 11.2.3.2 | 1969 | 13 | T | N | 1969.13 | 13 | 11.2.3.2 |  |  | Menzo Wentink |  |  | It looks like paragraphs at L13, L19 and L32 describe a negotiation that establishes the type of PS mode used by the S1G non-AP STA. The sentence at L13 is thus inaccurate and the overall description could be better. Clarify if the procedure applies to both association and reassociation (some (Re) are missing). Define behavior for all possible cases: define what happens if the non-AP STA sends 0 and receives 1, and sends 1 and receives 0. | Change the sentence at L13 to read "An S1G non-AP STA determines the type of PS mode it uses (TIM mode or non-TIM mode) through the (Re)Association Request/(Re)Association Response frame exchange with the AP. The S1G non-AP STA may request operation in non-TIM mode by setting the Non-TIM Support field in the S1G Capabilities element in the (Re)Association Request frame to 1. If the AP sets the Non-TIM Support field in the S1G Capabilities element in the (Re)Association Response frame to 1 then the STA shall operate in the non-TIM mode following association. If the S1G non-AP STA sets the Non-TIM Support field in the S1G Capabilities element in the (Re)Association Request frame to 0 or the S1G AP sets the Non-TIM Support field in the S1G Caapbilities element in the (Re)Association Response frame to 0, then the S1G non-AP STA shall operatin in the TIM mode following association. The S1G non-AP STA shall use the negotiated PS mode until either a new mode is negotiated through the PS mode switch (see ), a termporary PS mode switch has occured (see ) or the STA is disassociated. An S1G non-AP STA in non-TIM mode sets dot11NonTImModeActivated to true and sets it to false otherwise." And remove most of the other text. |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:11:06Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1122 | Robert Stacey | 232 | 1 | 11.2.3.2 | 1969 | 7 | T | N | 1969.0699 | 7 | 11.2.3.2 |  |  | Menzo Wentink |  |  | It is not clear what "during the whole operation time" means in this context. | Remove here and at L11 |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:10:54Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1110 | Robert Stacey | 232 | 1 | 10.35.5.1 | 1785 | 48 | T | N | 1785.48 | 48 | 10.35.5.1 |  |  | Menzo Wentink |  |  | There are a number of problems here. Prodiving the reader with editing instructions is inappropriate and uneccessary. Placing this in a subclause titled "VHT sounding protocol" makes it hard for the S1G STA implementor to find it. Referencing a subclause from within the subclause creates an infinite loop causing the reader's brain to explode (a reader that carried out the instruction would replace "with "VHT" is replaced with "S1G"" with "with "S1G" is replaced with "S1G"" is replaced with "with "S1G" is replaced with "S1G""... bang). | Add a new subclause "10.35.6a S1G sounding protocol" with the statements: "The VHT sounding protocol defined in 10.35.5 applies to an S1G STA with the following exceptions: [bullet] The STA transmitting the steering matrix is called the S1G beamformer but otherwise performs the role of the VHT beamformer [bullet] The STA for which reception is optimized is called the S1G beamformee but otherwise performs with role of the VHT beamformee [bullet] The MIB objects dot11S1GSUBeamformerOptionImplemented, dot11S1GMUBeamformerOptionImplemented, ... apply instead of dot11VHTSUBeamformerOptionImplemented, dot11VHTMUBeamformerOptionImplemented, ..., respectively. [bullet] The SU Beamformer Capable, MU Beamformer Capable, ... fields of the S1G Capabilties element apply instead of the SU Beamformer Capable, MU Beamformer Capable, ... fields of the VHT Capabilities element. [bullet] An S1G NDP is used instead of a VHT NDP" Also, move the statements at P1786L25 and L30 into this new subclause. |  | MAC | S1G | Submission Required | MAC: 2018-08-03 17:08:54Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC
1090 | Robert Stacey | 232 | 1 | 9.8.3.1 | 1538 | 43 | T | N | 1538.4301 | 43 | 9.8.3.1 |  |  | Menzo Wentink |  |  | There is a problem with the grammar here, but more significantly, the exception is not well described. | "The general form of the Frame Control field of the PV1 MAC header for all PV1 frames except the PV1 Probe Request frame, PV1 Resrouce Allocation frame, and PV1 Control frames is defined in Figure 9-881. The Frame Control fields for the PV1 Probe Response frame, Reseource Allocation frame and PV1 Control frames are defined in 9.8.5.3, 9.8.5.4, and 9.8.4 respectively." |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:04:54Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1088 | Robert Stacey | 232 | 1 | 9.8.1 | 1538 | 12 | T | N | 1538.12 | 12 | 9.8.1 |  |  | Menzo Wentink |  |  | What is an IEEE 32-bit CRC? Is it different from a 32-bit CRC based on ITU-T V.42 [B54] (P725L31)? We either need a reference for IEEE 32-bit CRC or we need to align the two definitions here. | Either align the definitions or provide a reference for IEEE 32-bit CRC. |  | MAC | S1G | Submission Required | MAC: 2018-08-03 17:04:41Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC

## Robert Stacey
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1307 | Allen Heberling | 232 | 1 | 9.4.2.1 | 915 | 51 | T | Y | 915.51 | 51 | 9.4.2.1 |  |  | Robert Stacey |  |  | Editor's note regarding the Element ID Extension | Please provide the correct Element ID extension for the Vendor Specific Request element in Table9-87 |  | MAC | ANA | Submission Required | MAC: 2018-04-05 00:52:42Z - status set to: Submission Required |  |  |  | 2018-04-05 00:53 | MAC
1081 | Robert Stacey | 232 | 1 | 10.2.3.2 | 1567 | 27 | T | N | 1567.27 | 27 | 10.2.3.2 |  |  | Robert Stacey |  |  | I'm not sure "MIB attributes" is accurate here. MIB attributes might be things like MAX-ACCESS, STATUS, etc. There reference to "MIB attributes that correspond to fields in an EDCA Parameter Set element" is a little vague. Why not reference dot11EDCATable directly? | A QoS STA shall update its dot11EDCATable within... |  | MAC | MIB | Discuss | MAC: 2018-08-03 17:05:45Z - status set to: Discuss |  |  |  | 2018-08-03 17:06 | MAC
1080 | Robert Stacey | 232 | 1 | 10.2.3.2 | 1567 | 27 | T | N | 1567.27 | 27 | 10.2.3.2 |  |  | Robert Stacey |  |  | Not necessarily consistent with P3788L55 ("Changes take effect as soon as practical in the implementation"). Also, was the intent to ensure that the MIB is up to date or that the EDCA parameters take effect within a certain time? This statement certainly does not achieve the latter. | Update the MIB object descriptions and/or the statement here. E.g., "A QoS STA, on receiving an updated EDCA Parameter Set element, should update the dot11EDCATable as soon as pratical in the implementain but shall update the dot11EDCATable within an interval of time equal to one beacon interval." |  | MAC | MIB | Submission Required |  |  |  |  | 2018-04-05 20:54 | MAC

## Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1073 | Robert Stacey | 232 | 1 | 10.47 | 1901 | 37 | T | N | 1901.37 | 37 | 10.47 |  | V | Menzo Wentink |  |  | The statement "an S1G STA shall set dot11PageSlicingImplemented to true if it supports page slicing" is not a testable requirement since it is not clear what "supports page slicing" entails. Also "S1G STA with dot11PageSlicingImplemented equal to true" (as used in this subclause) is a cumbersome STA descriptor. | Define something called a "page slicing S1G STA" as an S1G STA that declares a certain capability. It is more direct to define the STA type as one that sets its capability element a certain way rather than as one that sets a MIB object a certain way since the MIB is not required and rarely implemented. A statement such as "a page slicing S1G STA is an S1G STA that sets the Page Slicing Support field to 1 in the S1G Capabilities elements it transmits." would do the trick. The MIB object setting can be one of the requirements on such a beast: "A page slicing S1G STA shall set dot11PageSlicingImplemented to true." And, now that we know how to identify the beast (take a wireless sniffer and look for S1G Capability elements with the Page Slicing Support field set to 1) we can apply testable requirements to the breast, e.g., "A page slicing S1G STA shall process all received TIM elements..." (P1902L30). | REVISED (MAC: 2018-10-01 15:58:37Z): Replace the 1st paragraph in subclause 10.47 with the following: If an S1G STA supports the page slicing mechanism as defined in this subclause, then it shall set dot11PageSlicingImplemented to true. Otherwise, an S1G STA that does not support the page slicing mechanism or a non-S1G STA shall set dot11PageSlicingImplemented to false. Move 5th paragraph in subclause 10.47 to the beginning of the subclause. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-01 16:00:54Z - status set to: Ready for Motion MAC: 2018-09-13 00:31:18Z - Work off-line to make this similar to existing style. (Existing style is not consistent, itself. However, look at dot11RadioMeasurementActivated in 11.10 for at least one example.) MAC: 2018-08-03 17:09:47Z - status set to: Submission Required |  |  |  | 2018-10-01 16:04 | MAC
1080 | Robert Stacey | 232 | 1 | 10.2.3.2 | 1567 | 27 | T | N | 1567.27 | 27 | 10.2.3.2 |  |  | Robert Stacey |  |  | Not necessarily consistent with P3788L55 ("Changes take effect as soon as practical in the implementation"). Also, was the intent to ensure that the MIB is up to date or that the EDCA parameters take effect within a certain time? This statement certainly does not achieve the latter. | Update the MIB object descriptions and/or the statement here. E.g., "A QoS STA, on receiving an updated EDCA Parameter Set element, should update the dot11EDCATable as soon as pratical in the implementain but shall update the dot11EDCATable within an interval of time equal to one beacon interval." |  | MAC | MIB | Submission Required |  |  |  |  | 2018-04-05 20:54 | MAC
1081 | Robert Stacey | 232 | 1 | 10.2.3.2 | 1567 | 27 | T | N | 1567.27 | 27 | 10.2.3.2 |  |  | Robert Stacey |  |  | I'm not sure "MIB attributes" is accurate here. MIB attributes might be things like MAX-ACCESS, STATUS, etc. There reference to "MIB attributes that correspond to fields in an EDCA Parameter Set element" is a little vague. Why not reference dot11EDCATable directly? | A QoS STA shall update its dot11EDCATable within... |  | MAC | MIB | Discuss | MAC: 2018-08-03 17:05:45Z - status set to: Discuss |  |  |  | 2018-08-03 17:06 | MAC
1088 | Robert Stacey | 232 | 1 | 9.8.1 | 1538 | 12 | T | N | 1538.12 | 12 | 9.8.1 |  |  | Menzo Wentink |  |  | What is an IEEE 32-bit CRC? Is it different from a 32-bit CRC based on ITU-T V.42 [B54] (P725L31)? We either need a reference for IEEE 32-bit CRC or we need to align the two definitions here. | Either align the definitions or provide a reference for IEEE 32-bit CRC. |  | MAC | S1G | Submission Required | MAC: 2018-08-03 17:04:41Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC
1090 | Robert Stacey | 232 | 1 | 9.8.3.1 | 1538 | 43 | T | N | 1538.4301 | 43 | 9.8.3.1 |  |  | Menzo Wentink |  |  | There is a problem with the grammar here, but more significantly, the exception is not well described. | "The general form of the Frame Control field of the PV1 MAC header for all PV1 frames except the PV1 Probe Request frame, PV1 Resrouce Allocation frame, and PV1 Control frames is defined in Figure 9-881. The Frame Control fields for the PV1 Probe Response frame, Reseource Allocation frame and PV1 Control frames are defined in 9.8.5.3, 9.8.5.4, and 9.8.4 respectively." |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:04:54Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1110 | Robert Stacey | 232 | 1 | 10.35.5.1 | 1785 | 48 | T | N | 1785.48 | 48 | 10.35.5.1 |  |  | Menzo Wentink |  |  | There are a number of problems here. Prodiving the reader with editing instructions is inappropriate and uneccessary. Placing this in a subclause titled "VHT sounding protocol" makes it hard for the S1G STA implementor to find it. Referencing a subclause from within the subclause creates an infinite loop causing the reader's brain to explode (a reader that carried out the instruction would replace "with "VHT" is replaced with "S1G"" with "with "S1G" is replaced with "S1G"" is replaced with "with "S1G" is replaced with "S1G""... bang). | Add a new subclause "10.35.6a S1G sounding protocol" with the statements: "The VHT sounding protocol defined in 10.35.5 applies to an S1G STA with the following exceptions: [bullet] The STA transmitting the steering matrix is called the S1G beamformer but otherwise performs the role of the VHT beamformer [bullet] The STA for which reception is optimized is called the S1G beamformee but otherwise performs with role of the VHT beamformee [bullet] The MIB objects dot11S1GSUBeamformerOptionImplemented, dot11S1GMUBeamformerOptionImplemented, ... apply instead of dot11VHTSUBeamformerOptionImplemented, dot11VHTMUBeamformerOptionImplemented, ..., respectively. [bullet] The SU Beamformer Capable, MU Beamformer Capable, ... fields of the S1G Capabilties element apply instead of the SU Beamformer Capable, MU Beamformer Capable, ... fields of the VHT Capabilities element. [bullet] An S1G NDP is used instead of a VHT NDP" Also, move the statements at P1786L25 and L30 into this new subclause. |  | MAC | S1G | Submission Required | MAC: 2018-08-03 17:08:54Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC
1122 | Robert Stacey | 232 | 1 | 11.2.3.2 | 1969 | 7 | T | N | 1969.0699 | 7 | 11.2.3.2 |  |  | Menzo Wentink |  |  | It is not clear what "during the whole operation time" means in this context. | Remove here and at L11 |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:10:54Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1123 | Robert Stacey | 232 | 1 | 11.2.3.2 | 1969 | 13 | T | N | 1969.13 | 13 | 11.2.3.2 |  |  | Menzo Wentink |  |  | It looks like paragraphs at L13, L19 and L32 describe a negotiation that establishes the type of PS mode used by the S1G non-AP STA. The sentence at L13 is thus inaccurate and the overall description could be better. Clarify if the procedure applies to both association and reassociation (some (Re) are missing). Define behavior for all possible cases: define what happens if the non-AP STA sends 0 and receives 1, and sends 1 and receives 0. | Change the sentence at L13 to read "An S1G non-AP STA determines the type of PS mode it uses (TIM mode or non-TIM mode) through the (Re)Association Request/(Re)Association Response frame exchange with the AP. The S1G non-AP STA may request operation in non-TIM mode by setting the Non-TIM Support field in the S1G Capabilities element in the (Re)Association Request frame to 1. If the AP sets the Non-TIM Support field in the S1G Capabilities element in the (Re)Association Response frame to 1 then the STA shall operate in the non-TIM mode following association. If the S1G non-AP STA sets the Non-TIM Support field in the S1G Capabilities element in the (Re)Association Request frame to 0 or the S1G AP sets the Non-TIM Support field in the S1G Caapbilities element in the (Re)Association Response frame to 0, then the S1G non-AP STA shall operatin in the TIM mode following association. The S1G non-AP STA shall use the negotiated PS mode until either a new mode is negotiated through the PS mode switch (see ), a termporary PS mode switch has occured (see ) or the STA is disassociated. An S1G non-AP STA in non-TIM mode sets dot11NonTImModeActivated to true and sets it to false otherwise." And remove most of the other text. |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:11:06Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1124 | Robert Stacey | 232 | 1 | 11.2.3.2 | 1969 | 52 | T | N | 1969.52 | 52 | 11.2.3.2 |  |  | Menzo Wentink |  |  | This seems to redefine "non-TIM STA". See P173L36. | Remove either this statement or the one at P173L36. |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:11:18Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1126 | Robert Stacey | 232 | 1 | 9.4.1.48.2 | 889 | 54 | T | N | 889.54 | 54 | 9.4.1.48.2 |  |  | Menzo Wentink |  |  | S1G band is not defined. Given the statement at P215L39 and the lack of global harminzation, it should probably be plural. | Define "S1G bands" as "Frequency bands below 1 GHz excluding the TV white space bands" or maybe "Frequency bands for which an S1G operating class is defined in Annex E." Replace "S1G band" with "S1G bands" throughout. |  | MAC | S1G | Discuss | MAC: 2018-08-03 16:50:27Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1128 | Robert Stacey | 232 | 1 | 9.8.1 | 1538 | 4 | T | N | 1538.04 | 4 | 9.8.1 |  |  | Menzo Wentink |  |  | Subclause 9.2.1 describes both PV0 and PV1 frames. 9.8.1 just repeats this for PV1 frames. | Remove 9.8.1 (including its content) |  | MAC | S1G | Discuss | MAC: 2018-08-03 17:04:33Z - status set to: Discuss |  |  |  | 2018-09-13 01:07 | MAC
1142 | Robert Stacey | 232 | 1 | 9.9 | 1550 | 10 | T | N | 1550.1 | 10 | 9.9 |  |  | Menzo Wentink |  |  | The (spec) architecture around NDP CMAC frames is misguided. NDP CMAC frames are another (MAC) frame format like the PV0 and PV1 formats. PV0 and PV1 frames go into an A-MPDU which becomes the PSDU that is transferred to the PHY using the PHY SAP defined in Clause 8. Similarly, NDP CMAC frames SHOULD become the PSDU that is trnasferred to the PHY using the PHY SAP. | Focus 9.9 on the frame formats. Remove references to figures and PPDU formats in Clause 23. Add a general statement: "NDP CMAC frames are carried in the S1G NDP PPDU". Remove the NDP_CMAC_FRAME_BODY parameter from the TX/RXVECTOR. Add a description to 23.3.18 and 23.3.19 to descibe the mapping of the PSDU to and from the SIG field. |  | MAC | S1G | Submission Required | MAC: 2018-08-03 21:57:45Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC
1143 | Robert Stacey | 232 | 1 | 9.9.1 | 1550 | 35 | T | N | 1550.35 | 35 | 9.9.1 |  |  | Menzo Wentink |  |  | There are 8 NDP CMAC control frames and 2 NDP CMAC management frames. Surely there is a general frame format -- an architecture -- behind this menagerie. | Define a general MAC frame format for CMAC frames. It looks like there might be two basic types: a 24-bit frame and a 36-bit frame (distinguished by the PPDU fomat that carrier them). Define a general MAC frame format for each -- this may just be a Frame Tpe field and Frame Body field. Define the Frame body for each of the individual frames (no need to show the Frame Type field for each since this is common to all) |  | MAC | S1G | Submission Required | MAC: 2018-08-03 21:58:00Z - status set to: Submission Required |  |  |  | 2018-09-13 01:07 | MAC
1145 | Yongho Seok | 232 | 1 | 9.4.2.166 | 1265 | 38 | T | Y | 1265.38 | 38 | 9.4.2.166 |  |  | Ganesh Venkatesan | 11-18/885 |  | An S1G STA can use the Fine Timing Measurement procedure. Add S1G PPDU format into Table 9-272 (Format And Bandwidth field). | Add S1G PPDU format into Table 9-272 (Format And Bandwidth field). |  | MAC | FTM | Submission Required | MAC: 2018-06-15 17:39:16Z - Reviewed proposed changes, in detail. Editorial cleanup, no further comments. Still waiting for discussion about market need, and how well this works with 1 MHz bandwidth. Submission is expected with that discusison. Note that position accuracy is less at 1 MHz bandwidth, but use cases exist for lower accuracy with this PHY. MAC: 2018-05-10 13:10:01Z: Reviewed 11-18/885 at Warsaw F2F. Generally supportive. Need to hear rationale for adding this feature, first. |  |  |  | 2018-06-15 17:41 | MAC
1146 | Yongho Seok | 232 | 1 | 10.19 | 1657 | 30 | T | Y | 1657.3 | 30 | 10.19 |  | V | Mark Hamilton |  |  | Please clarify how the PARTIAL_AID is calculated when the Multiple BSSID is used. For example, do BSSID[39:47], BSSID[44:47], and BSSID[40:43] are derived from a transmitted BSSID or a non-transmitted BSSID? 802.11ah had the same discussion, the following sentence has been added into the spec. NOTE--When a STA for which dot11MultiBSSIDActivated is true is associated with ith BSSID of an AP, the BSSID means the value of BSSID(i). If VHT PPDU follows the same rule, please add the same NOTE into the spec. | As in comment. | REVISED (MAC: 2018-11-02 17:15:36Z): At P1661.52, delete the note, “NOTE—When a STA for which dot11MultiBSSIDActivated is true is associated with ith BSSID of an AP, the BSSID means the value of BSSID(i).” Response to commenter: References used within AP (or STA within an AP) behaviour, when the AP happens to be operating within a Multiple BSSID Set, are not altered from the simple behaviour (when not within a Multiple BSSID Set). Therefore, it is assumed that references to AP attributes (such as BSSID, etc.) are references to this AP’s attributes. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:16:31Z - status set to: Ready for Motion |  |  |  | 2018-11-02 17:18 | MAC
1161 | Christopher Hansen | 232 | 1 | 10.25 | 1713 | 50 | T | Y | 1713.5 | 50 | 10.25 |  |  | Chris Hansen |  |  | Exchange of ADDBA Request/Response Frames is inefficient. | Contribution on unsolicited block ack will be provided. |  | MAC | New feature | Submission Required |  |  |  |  | 2018-04-04 22:55 | MAC
1192 | James Lepp | 232 | 1 | 9.4.1.31 | 867 | 8 | T | N | 867.08 | 8 | 9.4.1.31 |  | V | Michael Montemurro |  |  | Mention that IEEE RA recommends CID if you want a 24-bit number, but many legacy OUIs are MA-Ls. The IEEE RA doesn't have a product called "OUI" any more. | Update the first three sentances in 9.4.1.31 to: The Organization Identifier field contains a public unique identifier assigned by the IEEE Registration Authority. The order of the Organization Identifier field is described in 9.2.2 (Conventions). The IEEE has assigned organizationally unique identifiers both of 24-bit length (MA-L and CID) and longer length. | REVISED (MAC: 2018-11-02 17:09:46Z): incorporate the changes in 11-18/1819r1 <https://mentor.ieee.org/802.11/dcn/18/11-18-1819-01-000m-lb232-cid-1192.docx> which corrects the wording along the lines requested. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:10:29Z - status set to: Ready for Motion MAC: 2018-10-12 15:15:43Z - Needs further discussion to confirm alignment of the text with the RAC terminology. MAC: 2018-04-05 21:00:42Z - status set to: Discuss MAC: 2018-04-05 21:00:34Z - status set to: Submission Required |  |  |  | 2018-11-02 17:11 | MAC
1195 | Guido Hiertz | 232 | 1 | 10.23.2.8 | 1675 | 44 | T | Y | 1675.4399 | 44 | 10.23.2.8 |  | V | Guido Hiertz | 18/810, 18/1260, 18/1368 |  | Except for DL-MU-MIMO the current EDCA rules prevent frames of different ACs being transmitted together. This rule intends providing prioritization between different ACs making the access functions to idepdently compete for the wireless medium. However, the more we strive for higher data rates, throughput, and efficiency, the more each backoff diminishes efficiency. It seems counter intuitive to not fill a TXOP to its max and rather stop transmitting to undergo another backoff just because frames in different queues must not be mixed. For our OFDM PHYs table 9-148 limits the default duration of AC_BE TXOPs to 2.5 ms and AC_VI to 4 ms. According to various aggregation rules, transmission duration up to 5 ms is possible. Thus, high priority transmission may be delayed because they cannot be transmitted with low priority transmission. Since the priority marking is anyway broken in 802.11, I deem it more important to improve 802.11's efficiency. Thus, I propose to remove the restriction of a TXOP holding frames of a single AC only. | There are two options: a) Remove all restrictions: lower or higher priority traffic may be transmitted within a TXOP as long as the primary AC is exhausted and no more packets are pending the primary AC. b) Permit higher priority traffic in lower priority TXOPs: Once a primary AC has no more packets pending it permitted to transmit packets of higher priority ACs. | REVISED (MAC: 2018-10-05 15:20:17Z): Incorporate the changes shows in https://mentor.ieee.org/802.11/dcn/18/11-18-1260-05-000m-resolution-to-cid-1195.docx. This accomplishes the feature requested by the commenter. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-05 15:20:14Z - status set to: Ready for Motion MAC: 2018-09-28 14:45:17Z - Reviewed 11-18/1260r3. Agree with direction. Updates to wording. Need to confirm all admission control limits are covered and this doesn't allow a "cheat". MAC: 2018-09-12 00:13:32Z - 11-18/1260r0 reviewed. Updated 11-18/1368r2 reviewed. MAC: 2018-08-29 15:46:33Z - See also 11-18/1368 MAC: 2018-06-15 17:28:50Z - Reviewed 11-18/810r0. Generally supportive. Rules are needed. Need specific changes, next. MAC: 2018-04-05 20:57:15Z - status set to: Submission Required |  |  |  | 2018-10-05 15:22 | MAC
1238 | Menzo Wentink | 232 | 1 | 10.25 | 1713 | 50 | T | N | 1713.5 | 50 | 10.25 |  | V | Graham Smith |  |  | A couple items need to be cleaned up as part of the deletion of the basic block ack protocol. | A submission will be prepared. | REVISED (MAC: 2018-10-05 16:18:17Z): Incorporate changes in https://mentor.ieee.org/802.11/dcn/18/11-18-0672-01-000m-resolutions-for-block-ack-related-comments.docx for CID 1308. These changes clarify immediate block ack policy and delayed block ack policy, generally. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-05 16:19:28Z - status set to: Ready for Motion1413 |  |  |  | 2018-10-05 16:20 | MAC
1249 | Kazuyuki Sakoda | 232 | 1 | 14.8.3 | 2557 | 10 | T | N | 2557.1001 | 10 | 14.8.3 |  | V | Kazuyuki Sakoda | 11-18/1254 |  | Sentence reads "Upon reception of a Mesh Link Metric Report frame, the mesh STA may update its local link metric information using the link metric information received. The procedure to update the local link metric information with the link metric information received from a neighbor peer mesh STA is outside the scope of the standard." This sounds like the standard does not specify anything. At least, an example practice of this link metric information should be described in annex. | Add a subclause in annex S (Mesh BSS operation) showing one example of how the link metric report is used. Commenter is willing to provide resolution text. | REVISED (MAC: 2018-10-05 16:35:00Z): Incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1249-02-0ngv-ngv-mac-discussion.pptx, which add a new subclause describing a link metric reporting example, as requested. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:37:26Z - status set to: Ready for Motion MAC: 2018-07-12 21:09:03Z - Reviewed 11-18/1254r0. Editorial corrections suggested. Some minor rewording suggested, will work off-line with Jouni. MAC: 2018-04-05 20:53:30Z - status set to: Submission Required |  |  |  | 2018-11-02 17:37 | MAC
1256 | Kazuyuki Sakoda | 232 | 1 | 10.3.4 | 1606 | 48 | T | Y | 1606.48 | 48 | 10.3.4 |  | J | Assaf Kasher |  |  | DMG STA's CCA requirement is very vague. I could not find clear requirement for receiver for the CS, particularly AWV related operation. In clause 10.3.1, there is a paragraph stating "... , a DMG STA can configure its receive antenna to a quasi-omni pattern ... ", which does not specify requirement for the receiver or AWV. (This is not a normative behavior specified by "shall" language) In clause 10.3.4.2, there is a paragraph stating "A DMG STA ... may configure its receiving antenna array to a quasi-omni antenna pattern ... " , which does not specify requirement. In the same subclause, there is a note stating "NOTE--The steady state of the antenna configuration might depend on the actual applications in which a DMG STA is involved. For example, a DMG STA that expects transactions with several STAs during a CBAP configures the receiving antenna to a quasi-omni pattern to be ready to receive transmission from any of the STAs. A DMG STA that expects transactions with a single STA (e.g., AP or PCP) might keep its receiving antenna directed to the peer STA.", which gives some idea but again does not specify requirements. In the same subclause, there is a paragraph stating "A DMG STA ... should configure its receiving antenna array to be directed ...", which does not specify requirement again. In clause 10.3.4.3, there are paragraphs showing example DMG STA CCA operations among STAs using Figure 10-18 and Figure 10-19. However, this subclause does not specify requirement how DMG STA controls AWV. In clause 10.37.5, there is a paragraph stating "Within a CBAP a STA with multiple DMG antennas should use only one DMG antenna in its frame transmission, CCA and frame reception...", which does not specify requirement. | Please specify DMG STA's CCA requirement with "shall" language. Lack of clear requirement for CS could result in selfish STA deployment, wich could be harmful. | REJECTED (MAC: 2018-10-12 14:51:02Z): The second paragraph in 10.3.4.2 applies to DMG STA – a DMG STA may transmit if the medium is idle and the backoff counter expired. The AWV setting of the receive antenna while sensing the medium is intentionally kept in a non-binding (no “shall”) language. This is because even the term quasi-omni is fairly vauge and defining the relation between RX pattern and TX pattern in any directional mode is very problematic. Considering this, it will be very hard to test whether a device complies with AWV specific sensing requirements. This is the reason the “should” language is used. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 14:52:04Z - status set to: Ready for Motion MAC: 2018-04-24 17:23:05Z - status set to: Submission Required |  |  |  | 2018-10-12 14:52 | MAC
1263 | Xiaofei Wang | 232 | 1 | 10.50.2 | 1921 | 25 | T | Y | 1921.25 | 25 | 10.50.2 |  |  | Menzo Wentink | 11-18/1654 |  | The reachable address update procedure may create an error in the following situation: 1. STA1 who is originally associated with relay AP1, moves to relay AP2, under the same root AP, without perfroming disassociation with relay AP1 2. relay AP2 performs reachable address update to the root AP based on condition 1) in L23 3. Before the max idle period expiry of STA1 in relay AP1, another STA2 associates with relay AP1 4. relay AP1 sends reachable address update frame containing "current list" STA1 and STA2 to root AP based on condition 1) in L23, overwriting the correct forwarding entry for STA1 in root AP 5. Later traffic to STA1 is forwarded to relay AP1, causing relay AP1 disassociation of STA1, which triggers another reachable address update frame sent to root AP, based on condition 2) in L23. This completely removes STA1 from root AP's "current list" of reachbale addresses | A potential solution may be: An S1G relay STA shall send a Reachable Address Update frame that contains the modifications of reachable addresses to the AP to which it is associated when one of the following conditions occurs: 1)A new non-AP STA associates with the S1G relay AP of the relay 2)A non-AP STA is disassociated or deauthenticated from the S1G relay AP of the S1G relay 3)A Reachable Address Update frame is received at the S1G relay AP of the S1G relay For condition 1) and 2), the reachable address update frame only contains the newly associated/disassocated STA addresses For condition 3), the relay AP ignores/removes an address from the reachable address element with add/remove subfield set to 0, from the received reachable address update frame, if the current forwarding relay for the address is not the same as the the STA sending the reachable address update frame to the relay AP |  | MAC | S1G | Submission Required | MAC: 2018-10-15 15:49:29Z - Reviewed 11-18/1756r0. Concerns about Option 2's need for relative timestamps to the TU granularity, which can be hard to do with transmission delays. Will discuss further off-line. Option 3 suggested, to have (strong hints of?) when an update collision occurred, and only require additional recovery(?) when that happens. MAC: 2018-09-12 - 5.7.2.3 The “for the STAs satisfying the following conditions:” then the conditions are not able to both be true. Need to change to “…one of the following…” 5.7.2.4 Discussion on how often the refresh can be done. 5.7.2.5 This change was discussed in 11ah, but the change was not made then and the thought by the commenter that they could bring later during the revision. 5.7.2.7 This is a real problem that will need more thought to resolve. Addition review is requested to continue working with Xiaofei. 5.7.2.9 Note that in document 11-18/1300 it had proposed a reject for this CID. This submission is proposing an alternate suggestion, but it needs more work off-line. MAC: 2018-08-03 17:10:16Z - status set to: Submission Required |  |  |  | 2018-11-01 22:26 | MAC
1267 | Joseph Levy | 232 | 1 | 11.23.6.5 | 2143 | 20 | G | Y | 2143.2 | 20 | 11.23.6.5 |  |  | Menzo Wentink |  |  | Calling a S1G 2, 4, 8, or 16 MHz off-channel TDLS direct link a "wide bandwidth off-channel direct link" seems a bit confusing. I understand the need to allow for an off-channel direct link for S1G STAs, but shouldn't it be called something else. Also the way the feature is implemented in the section 11.23.6.5 seems very awkward. It would be better to add a new set of clauses for the "S1G off-channel direct link", which duplicate 11.23.6.5 with the S1G changes. This would also eliminate the need to keep switching between VHT and S1G requirements. | Remove the (11ah) additions to 11.23.6.5 which added S1G to the wide bandwidth off-channel direct link and add a new section "11.23.6.6 Setting up a S1G off-channel direct link" with the S1G requirements. |  | MAC | S1G | Submission Required | MAC: 2018-04-10 18:59:54Z - status set to: Submission Required MAC: 2018-04-10 18:58:03Z: Discussed at FLL ad hoc, supportive: 5, not supportive: 1, no opinion: 4. |  |  |  | 2018-09-13 01:07 | MAC
1273 | Jouni Malinen | 232 | 1 | 9.4.2.24.1 | 1019 | 57 | T | Y | 1019.57 | 57 | 9.4.2.24.1 |  | A | Mark Hamilton |  |  | "AES-128-CMAC" is a name of the integrity protection algorithm used by the cipher that is called "BIP-CMAC-128". However, couple of places that are clearly referring to a cipher are incorrectly using the name of the algorithm rather than the cipher. | Replace "AES-128-CMAC" with "BIP-CMAC-128" at page 1019 line 57 and page 1020 line 27. | ACCEPTED (MAC: 2018-09-14 03:29:28Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-09-14 03:29:34Z - status set to: Ready for Motion MAC: 2018-08-03 16:54:13Z - status set to: Discuss |  |  |  | 2018-09-14 03:30 | MAC
1286 | Jouni Malinen | 232 | 1 | 9.4.1.8 | 842 | 18 | T | Y | 842.18 | 18 | 9.4.1.8 |  | A | Mark Hamilton |  |  | IEEE Std 802.11-2016 modified the definition of AID field to say "A non-DMG STA assigns the value of the AID in the range of 1 to 2007; the 5 MSBs of the AID field are reserved" while the 802.11-2012 definition said "The value assigned as the AID is in the range 1-2007 and is placed in the 14 LSBs of the AID field, with the two MSBs of the AID field set to 1". This changes behavior in a backwards incompatible manner due to the general convention (see 9.2.2): "Reserved fields and subfields are set to 0 upon transmission and are ignored upon reception.". In other words, this change would imply that the two MSBs are set to 0 instead 1. This results in interoperability issues with deployed devices in particular with (Re)Association Response frames where a non-AP STA may either reject the frame if the two MSBs of the AID are not 1 or there might be undefined behavior when matching the received value against the value used in PS-Poll frames. This type of "cleanup" change is not acceptable and needs to be reverted to avoid interoperability issues with deployed devices. This comment is proposing a change for the 802.11-2012 case. A similar change could be considered for DMG and S1G cases as well, if those are expected to have interoperability issues. Alternatively, the AID field definition could be left as-is and the specific uses of AID field in the relevant frames (at least (Re)Association Response frames) could be specified to set the two MSBs to 1. | Replace "A non-DMG and non-S1G STA assigns the value of the AID in the range of 1 to 2007; the 5 MSBs of the AID field are reserved." with "A non-DMG and non-S1G STA assigns the value of the AID in the range of 1 to 2007. This value is placed in the 14 LSBs of the AID field, with the two MSBs of the AID field set to 1." | ACCEPTED (MAC: 2018-10-12 20:59:09Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 20:59:11Z - status set to: Ready for Motion MAC: 2018-09-10 15:33:35Z - Reviewed 11-18/669r5. Menzo to look at the issue, and Mark HAMILTON will check with Michael Fischer. MAC: 2018-05-10 12:46:11Z - Discuss between Mark H, Jouni, and Emily. MAC: 2018-04-05 00:51:19Z - status set to: Discuss |  |  |  | 2018-10-12 20:59 | MAC
1307 | Allen Heberling | 232 | 1 | 9.4.2.1 | 915 | 51 | T | Y | 915.51 | 51 | 9.4.2.1 |  |  | Robert Stacey |  |  | Editor's note regarding the Element ID Extension | Please provide the correct Element ID extension for the Vendor Specific Request element in Table9-87 |  | MAC | ANA | Submission Required | MAC: 2018-04-05 00:52:42Z - status set to: Submission Required |  |  |  | 2018-04-05 00:53 | MAC
1315 | Li-Hsiang Sun | 232 | 1 | 9.5.4 | 1371 | 60 | T | Y | 1371.6 | 60 | 9.5.4 |  | V | Assaf Kasher |  |  | The L-RX subfield description can be reworded to use the trem TRN unit instead of TRN-R subfileds x4 | change to :"If the MID-REQ subfield is set to 0, the L-RX subfield indicates the number of TRN-R units requested by the transmitting STA as part of beam refinement. Possible values range from 0 to 16. Other values are reserved. If the subfield is set to 0, the transmitting STA does not need receive training as part of beam refinement..If the MID-REQ subfield is set to 1, the L-RX subfield indicates the number of TRN-R units that the STA uses during the MID phase for each tx sector/awv" | REVISED (MAC: 2018-10-12 14:45:10Z): Incorporate the changes as shown in 11-18/1114r1 (https://mentor.ieee.org/802.11/dcn/18/11-18-1114-01-000m-dmg-mac-cid-resolution-i.docx), for CID 1315. These changes reword the paragraph to add the usage of TRN unit. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 20:57:52Z - status set to: Ready for Motion MAC: 2018-04-05 19:54:11Z - status set to: Discuss |  |  |  | 2018-10-12 20:58 | MAC
1339 | Mark RISON | 232 | 1 | 10.35.5.2 | 1787 | 1 | T | Y | 1787.01 | 1 | 10.35.5.2 |  | V | Youhan Kim | 11-18/0879 |  | "A VHT beamformer may use the following worst-case parameters to estimate the duration of the expected frame(s) that contain(s) the feedback response(s): lowest rate in basic VHT-MCS set, no grouping." -- also need to specify the codebook size | Change the cited text at the referenced location to "A VHT beamformer may use the following worst-case parameters to estimate the duration of the expected frame(s) that contain(s) the feedback response(s): lowest rate in basic VHT-MCS set, no grouping, highest-precision codebook." | REVISED (MAC: 2018-09-14 00:30:27Z): Implement the proposed text update for CID 1339 in https://mentor.ieee.org/802.11/dcn/18/11-18-0879-01-000m-d1-0-vht-related-cids.docx. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-09-14 00:30:53Z - status set to: Ready for Motion MAC: 2018-09-10 18:42:44Z - From May session minutes, "Instruction to Editor: Implement the proposed text update for CID 1339 in https://mentor.ieee.org/802.11/dcn/18/11-18-0879-01-000m-d1-0-vht-related-cids.docx." This text, "includes the codebook side to the list as suggested by the commenter, but also clarifies that there are other parameters involved." Confirm with the group this is ready for motion. MAC: 2018-08-03 17:09:05Z - status set to: Discuss |  |  |  | 2018-09-14 00:31 | MAC
1349 | Mark RISON | 232 | 1 | 11.42.3 | 2287 | 18 | T | Y | 2287.1799 | 18 | 11.42.3 |  | V | Mark Hamilton |  |  | "A GDD dependent STA shall cease all transmission when (#172)dot11GDDEnablementValidityTimer has expired" -- a MIB variable cannot expire | Change the cited text in the referenced location to "A GDD dependent STA shall cease all transmission when the GDD enablement validity timer has expired". In the para above delete "by decrementing dot11GDDEnablementValidityTimer". In Figure 11-51 change "dot11GDDEnablementValidityTimer has expired" to "GDD enablement validity timer has expired". In 11.42.4.1 change "it reinitializes the dot11GDDEnablementValidityTimer to" to "it reinitializes the GDD enablement validity timer". In C.3 delete dot11GDDEnablementValidityTimer. In Tables E-8 and E-11 delete the dot11GDDEnablementValidityTimer row | REVISED (MAC: 2018-09-14 03:25:14Z): Incorporate the changes shown in https://mentor.ieee.org/802.11/dcn/18/11-18-0669-07-000m-revmd-mac-comments-assigned-to-hamilton.docx for CID 1349. These make changes in the direction proposed by the commenter. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-09-14 03:26:28Z - status set to: Ready for Motion MAC: 2018-08-03 17:13:34Z - status set to: Discuss |  |  |  | 2018-09-14 03:27 | MAC
1370 | Mark RISON | 232 | 1 | 11.1.7 | 1964 | 60 | T | Y | 1964.6 | 60 | 11.1.7 |  | V | Mark Hamilton |  |  | 11.1.4.6 Operation of Supported Rates and BSS Membership Selectors element and Extended Supported Rates and BSS Membership Selectors element and 11.1.7 Supported rates and extended supported rates advertisement cover the same material | Merge 11.1.7 into 11.1.4.6 then delete 11.1.7 | REVISED (MAC: 2018-11-02 17:16:44Z): Replace the text of 11.1.4.6 with the revised text shown in 11-18/0669r10 under CID 1370. (Editor: Please renumber “NOTE”s appropriately.) Delete subclause 11.1.7. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:16:50Z - status set to: Ready for Motion |  |  |  | 2018-11-02 17:19 | MAC
1375 | Mark RISON | 232 | 1 | 11.22.16.2 | 2182 | 9 | T | Y | 2182.0901 | 9 | 11.22.16.2 |  | V | Mark Rison |  |  | It should be possible to cancel multiple DMS streams | Allow a list of DMSIDs in DMS cancellation, i.e. the length is not necessarily set to 1. The STA should be able to send the cancellation with multiple DMSIDs | REVISED (MAC: 2018-10-12 21:12:32Z): Make the changes shown under "Proposed changes" for CID 1375 in 11-18/1306r5, which specify the mechanism whereby multiple DMS streams may be terminated simultaneously. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:13:13Z - status set to: Ready for Motion REVISED (MAC: 2018-07-12 22:06:14Z): Make the changes shown under "Proposed changes" for CID 1375 in 11-18/1306, which specify the mechanism whereby multiple DMS streams may be terminated simultaneously. Except fix "the DMS provider" to be "a DMS provider" first, after checking with some experts. MAC: 2018-04-05 20:56:39Z - status set to: Submission Required |  |  |  | 2018-10-12 21:13 | MAC
1378 | Mark RISON | 232 | 1 | 10.30 | 1750 | 35 | T | Y | 1750.35 | 35 | 10.3 |  | V | Graham Smith |  |  | PSMP is obsolete and should be deleted | At the start of the referenced subclause add "PSMP is obsolete. Support for this mechanism might be removed in a later revision of the standard." | REVISED (MAC: 2018-11-02 16:22:04Z): With reference to D1.5 At P1874L11 Insert “PSMP is obsolete. Support for this mechanism might be removed in a later revision of the standard." At 9.4.1.24 P908L46 insert “PSMP is obsolete. Support for this mechanism might be removed in a later revision of the standard." At 9.4.1.25 P909L17 insert “PSMP is obsolete. Support for this mechanism might be removed in a later revision of the standard." At 9.6.11.4 P1546L35 insert “PSMP is obsolete. Support for this mechanism might be removed in a later revision of the standard." At B.4.4.1 P3551L21 Add in second column “PSMP is obsolete. Support for this mechanism might be removed in a later revision of the standard." | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 16:31:55Z - status set to: Ready for Motion MAC: 2018-08-03 17:08:20Z - status set to: Discuss MAC: 2018-04-10 14:19:20Z: Dorothy will email the reflector with a request for comments about making PSMP obsolete. |  |  |  | 2018-11-02 16:32 | MAC
1396 | Mark RISON | 232 | 1 | 10.2.6 | 1571 | 15 | T | Y | 1571.15 | 15 | 10.2.6 |  | V | Mark Hamilton |  |  | "A QoS Data frame with a TID matching an existing block ack agreement may be transmitted outside an A-MPDU with its Ack Policy subfield set to Normal Ack" -- also in an S-MPDU | Append ", or in an S-MPDU" to the cited text at the referenced location | REVISED (MAC: 2018-10-12 20:59:40Z): Change, "outside an A-MPDU" to "in a non-A-MPDU" in the cited paragraph. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:00:14Z - status set to: Ready for Motion MAC: 2018-08-03 17:06:09Z - status set to: Discuss |  |  |  | 2018-10-12 21:00 | MAC
1415 | Mark RISON | 232 | 1 | 9.2.4.5.4 | 743 | 3 | T | Y | 743.03 | 3 | 9.2.4.5.4 |  | V | Mark Rison | 11-18/1306 |  | The way the ack policy is referred to is confusing/inconsistent. Do you refer to the options indicated by the bit pattern (e.g. "Normal Ack or Implicit Block Ack Request") or do you refer to only the type of ack being requested in the context being requested (e.g. just "Implicit Block Ack Request" in the case of an A-MPDU)? | Change "The Ack Policy subfield is 2 bits in length and identifies the acknowledgment policy that is followed upon the delivery of the MPDU." to "The Ack Policy subfield is 2 bits in length and identifies, together with other information such as whether it is in the context of an S-MPDU and the value of bit 6 of the Frame Control field, the acknowledgment policy that is followed upon the delivery of the MPDU." at the referenced location | REVISED (MAC: 2018-10-12 14:40:54Z): Incorporate the changes in 11-18/1306r6 <https://mentor.ieee.org/802.11/dcn/18/11-18-1306-06-000m-resolutions-for-some-comments-on-11md-d1-0-lb232.docx> which makes the changes in the direction the commenter requested. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 14:42:28Z - status set to: Ready for Motion See also CID 1526 |  |  |  | 2018-10-12 14:45 | MAC
1431 | Mark RISON | 232 | 1 | 11.31.1 | 2249 | 15 | T | Y | 2249.1499 | 15 | 11.31.1 |  | A | Mark Hamilton |  |  | "the Capabilities element, the Operation element" -- there are no such elements. Discussions with 11ad experts suggests the intent is that you use all the elements relevant to the target band/PHY | In the referenced subclause change "A multi-band capable device shall include, in any transmitted FST Setup Request frame and in any transmitted FST Setup Response frame, the Capabilities element, the Operation element, the EDCA Parameter Set element, Supported Rates and BSS Membership Selectors element, Extended Supported Rates and BSS Membership Selectors element, and Supported Channels element that are applicable to the band and channel number indicated within its most recently transmitted Multi-band element that was transmitted on the same band and channel number on which it is transmitting the FST Setup Request or FST Setup Response frames." to "A multi-band capable device shall include, in any transmitted FST Setup Request frame and in any transmitted FST Setup Response frame, all the elements that are applicable to the band, PHY and channel number indicated within its most recently transmitted Multi-band element that was transmitted on the same band and channel number on which it is transmitting the FST Setup Request or FST Setup Response frames." | ACCEPTED (MAC: 2018-10-12 21:00:34Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:00:36Z - status set to: Ready for Motion MAC: 2018-08-03 17:13:22Z - status set to: Discuss MAC: 2018-04-05 20:51:23Z - status set to: Submission Required |  |  |  | 2018-10-12 21:01 | MAC
1442 | Mark RISON | 232 | 1 | 9.2.4.5.4 | 743 | 45 | T | Y | 743.45 | 45 | 9.2.4.5.4 |  | V | Mark Hamilton |  |  | The terms "require acknowledgment" or "requires acknowledgment" are not clear, because some ack policies other than 00 do require ack, just not immediate (e.g. Block Ack, PSMP Ack, No Explicit Acknowledgment) | Add "immediate" before "acknowledgement" in "require acknowledgement"/"requires acknowledgement" in 9.3.1.3 (2x), 10.3.2.10 at 1592.24 and 1594.47/51, 10.3.4.4, 10.3.4.5, 11.2.3.6 (4x), 14.14.9.2, G.3 (2x) | REVISED (MAC: 2018-10-31 11:28:25Z): Add "immediate" before "acknowledgement" in "require acknowledgement"/"requires acknowledgement" in 9.3.1.3 (2x), 10.3.2.10 at 1592.24 and 1594.47/51, 10.3.4.4, 10.3.4.5, 11.2.3.6 (4x), 14.14.9.2, G.3 (2x). Note to Editor: Not all occurrences of “acknowledgement” in the above cited clauses have the replacement, only those with “require” or “requires” before “acknowledgement”. Similarly, add “immediate” before “acknowledgement” at P1593.12, P1599.42, P1608.32, P1669.45, P1674.39, P1984.8, P3992.49, and P3991.24 | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-31 11:28:38Z - status set to: Ready for Motion MAC: 2018-08-03 16:29:47Z - May need to wait for CIDs 1415 and 1526 to settle, per 11-18/1306, to confirm consistent (and complete) wording changes. MAC: 2018-08-03 16:21:16Z - status set to: Discuss |  |  |  | 2018-10-31 11:29 | MAC
1444 | Mark RISON | 232 | 1 | 9.7.3 | 1535 | 1 | E | Y | 1535.01 | 1 | 9.7.3 |  |  | Mark Hamilton |  |  | The A-MPDU context tables randomly mix "MPDU" and "frame" | Change "MPDU" to "frame" throughout Tables 9-491 to 9-496, when not preceded by "A-" (i.e. do not change "A-MPDU" to "A-frame") |  | MAC | Minor Correction | Submission Required | MAC: 2018-05-06 16:54:57Z - status set to: Submission Required EDITOR: 2018-04-13 21:43:46Z - Transder to MAC. EDITOR: 2018-04-03 17:53:03Z - status set to: Discuss |  |  |  | 2018-05-06 16:55 | MAC
1448 | Mark RISON | 232 | 1 | 9.4.3 | 1535 | 51 | T | Y | 1535.51 | 51 | 9.4.3 |  | J | Mark Hamilton |  |  | "The preceding PPDU" is behaviour not format | Move from Clause 9 to Clause 10 | REJECTED (MAC: 2018-10-31 11:34:01Z): Table 9-492 describes the valid contents of the A-MPDU subframes in a PPDU, and thus are part of the format description for A-MPDUs. It is necessary to reference preceding PPDUs to determine these valid contents, but such reference does not make this a behavioural requirement. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-31 11:34:08Z - status set to: Ready for Motion |  |  |  | 2018-10-31 11:35 | MAC
1449 | Mark RISON | 232 | 1 | 11.10.9.6 | 2095 | 24 | T | Y | 2095.24 | 24 | 11.10.9.6 |  | V | Mark Hamilton |  |  | "Originator Requesting MAC address field" -- no such field (and bad case) | Change all instances of "Originator Requesting MAC address" to "Originator Requesting STA MAC Address field" throughout the document | REVISED (MAC: 2018-10-31 11:35:56Z): Change all instances of "Originator Requesting MAC address" to "Originator Requesting STA MAC Address" throughout the document | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-31 11:36:02Z - status set to: Ready for Motion MAC: 2018-08-03 17:12:07Z - status set to: Discuss |  |  |  | 2018-11-01 16:01 | MAC
1450 | Mark RISON | 232 | 1 | 9.4.1.4 | 835 | 50 | T | Y | 835.5 | 50 | 9.4.1.4 |  | A | Mark Hamilton |  |  | "An AP sets the ESS subfield to 1 and the IBSS subfield to 0 within transmitted Beacon or Probe Response frames. Otherwise, the ESS and IBSS subfields are reserved. An IBSS STA sets the ESS subfield to 0 and the IBSS subfield to 1 in transmitted Beacon or Probe Response frames. A mesh STA sets the ESS and IBSS subfields to 0 in transmitted Beacon or Probe Response frames." is either unclear as to the setting for non-AP non-mesh non-IBSS STAs, or self-contradictory for IBSS and mesh STAs | Change the cited text to "An AP sets the ESS subfield to 1 and the IBSS subfield to 0 within transmitted Beacon or Probe Response frames. An IBSS STA sets the ESS subfield to 0 and the IBSS subfield to 1 in transmitted Beacon or Probe Response frames. A mesh STA sets the ESS and IBSS subfields to 0 in transmitted Beacon or Probe Response frames. Otherwise, the ESS and IBSS subfields are reserved." | ACCEPTED (MAC: 2018-10-15 11:36:30Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:36:10Z - status set to: Ready for Motion MAC: 2018-08-03 16:33:31Z - status set to: Discuss |  |  |  | 2018-11-02 17:37 | MAC
1454 | Mark RISON | 232 | 1 | 11.3.5 | 2019 | 52 | T | Y | 2019.52 | 52 | 11.3.5 |  | V | Mark Hamilton |  |  | It is not clear what is reset in the case of (re)association to a different AP | At the end of the last step of 11.3.5.2 add "All states, agreements and allocations shall be deleted or reset to initial values." At the end of the last step of 11.3.5.3 add "All states, agreements and allocations pertaining to the STA that has associated shall be deleted or reset to initial values." At the end of the last step of 11.3.5.5, add "In the case of reassociation to a different AP, all states, agreements and allocations pertaining to the STA that has reassociated shall be deleted or reset to initial values." | REVISED (MAC: 2018-11-02 15:59:58Z): incorporate the changes for CID 1454 in doc 11-18/669r12 <https://mentor.ieee.org/802.11/dcn/18/11-18-0669-12-000m-revmd-mac-comments-assigned-to-hamilton.docx>. These changes are, in effect, per the commenter's request. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:20:00Z - status set to: Ready for Motion MAC: 2018-08-03 17:11:37Z - status set to: Discuss MAC: 2018-04-05 21:33:03Z - status set to: Submission Required |  |  |  | 2018-11-02 17:20 | MAC
1462 | Mark RISON | 232 | 1 | 9 |  |  | T | Y |  |  | 9 |  | V | Mark Hamilton |  |  | It is not necessary in Clause 9 to say things are done according to the conventions in 9.2.2. It is confusing to do so, because it implies something unusual is happening | Delete the sentences like "The order of the Organization Identifier field is described in 9.2.2 (Conventions)." or "All fields use the bit convention from 9.2.2 (Conventions)." or " It is encoded following the conventions in 9.2.2 (Conventions)." at [mc/D6.0 references] 685.46, 827.4, 828.41, 881.22, 881.26, 881.62, 882.43, 883.44, 999.59, 999.64, 1007.33, 1083.20, 1101.58, 1101.62, 1130.33, 1144.47. Delete the NOTE at 706.48. Change 880.20 to say "The MDID field contains an arbitrary value." At 951.39 delete ", encoded according to 9.2.2 (Conventions)". At 1085.14 delete " and is encoded following the conventions given in 9.2.2 (Conventions)" | REVISED (MAC: 2018-11-02 17:13:21Z): The occurrences of “the sentences like” specifically mentioned in the comment are all associated with text that is describing a type of object which is encoded using special rules in 9.2.2. Alerting the reader to such special rules, at the point where they are invoked, is an aid to understanding the Standard correctly. However, other locations are to be changed. Editor, make the following changes: - Delete the NOTE at the end of 9.4.1.48.1 - In 9.4.2.46, replace “The MDID field is a 2-octet value that follows the ordering conventions defined in 9.2.2 (Conventions).” with “The MDID field is a 2-octet value that is an identifier that names a mobility domain.” - In 9.4.2.47, delete both occurrences of “It is encoded following the conventions in 9.2.2 (Conventions).” - In 9.4.2.48, delete “It is encoded following the conventions in 9.2.2 (Conventions).” - In 9.4.2.77, delete “encoded according to 9.2.2 (Conventions).” - In 9.4.5.1, delete “The 2-octet Info ID field is encoded following the conventions given in 9.2.2 (Conventions).” - In 9.4.5.1, delete “and is encoded following the conventions given in 9.2.2 (Conventions).” - In 9.4.6.1, delete “The 2-octet Info ID field is encoded following the conventions given in 9.2.2 (Conventions).” - In 9.4.6.1, delete “and is encoded following the conventions given in 9.2.2 (Conventions).” | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:15:05Z - status set to: Ready for Motion |  |  |  | 2018-11-02 17:16 | MAC
1466 | Mark RISON | 232 | 1 | 11 |  |  | T | Y |  |  | 11 |  |  | Mark Rison |  |  | Discussions related to CID 7592 and 7593 in mc have revealed that the description of legacy PS and U-APSD is hopelessly muddled in terms of things like how PS-Polls operate for U-APSD and duplication of statements and consistency of description | Refactor the wording |  | MAC | Power mgmt | Submission Required |  |  |  |  | 2018-04-11 15:34 | MAC
1476 | Mark RISON | 232 | 1 | 10.6 |  |  | T | Y |  |  | 10.6 |  |  | Mark Rison |  |  | The multirate rules are an impenetrable mess. It's impossible to determine whether they are complete, let alone whether they are correct | Rewrite as a flowchart or table, so that it can be seen that the rules are complete and correct |  | MAC | Multirate | Submission Required | MAC: 2018-04-05 20:55:31Z - status set to: Submission Required |  |  |  | 2018-04-05 20:56 | MAC
1483 | Mark RISON | 232 | 1 |  |  |  | E | Y | [5 empty] | Mark Rison |  |  | Per the ad-hoc notes for CID 15: Bring back other changes for consistency elsewhere in the Std: - Continue list in 11-17/1412r1 - Search for all "0 or ..." and check that they all have "(optional)" - On "<i> x n" expressions, can 'n' be 0 or more, or always 1 or more? Sometimes it says "0 or (<i> x n)" (9-255). - Keep OI length as "<j>" for ease of maintenance. | Make the changes referred to in the comment, i.e. say "(optional)" for all optional subfields, say "(optional)" and "0 or (4xn)" for fields where zero-length is allowed (implication being just "4xn" would not allow n=0) |  | MAC | Frame formats | Submission Required | MAC: 2018-04-05 20:50:47Z - status set to: Submission Required |  |  |  | 2018-04-05 20:51 | MAC
1485 | Mark RISON | 232 | 1 | 11.10.6 | 2084 | 47 | T | Y | 2084.47 | 47 | 11.10.6 |  | V | Mark Hamilton |  |  | " A STA refusing a measurement request within an individually addressed Radio Measurement Request frame shall respond with a measurement report indicating that it is refusing the measurement request. A STA shall not respond to measurement requests received in Radio Measurement Request frames in this manner." is self-contradictory | Add "group addressed" after "shall not respond to" in the cited text at the referenced location | REVISED (MAC: 2018-09-14 03:31:32Z): Insert “group addressed” after “received in”, in the cited sentence. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-09-14 03:31:42Z - status set to: Ready for Motion MAC: 2018-08-03 17:11:59Z - status set to: Discuss |  |  |  | 2018-09-14 03:32 | MAC
1498 | Mark RISON | 232 | 1 |  |  |  | E | Y | [5 empty] | Mark Hamilton |  |  | There is no such thing as "DSSS/CCK mode" | Change "DSSS/CCK Mode" (or "mode") to "DSSS/CCK PPDUs" in 9.4.2.55.2 (3x), 11.15.8 (4x), C.3 (1x). Change "dot11RMNeighborReportHTDSSCCKModein40MHz" to "dot11RMNeighborReportHTDSSCCKPPDUsin40MHz" in C.3 (3x) |  | MAC | DSSS-CCK | Discuss | MAC: 2018-08-03 16:10:10Z - status set to: Discuss MAC: 2018-04-05 20:43:03Z - status set to: Submission Required EDITOR: 2018-04-04 21:51:14Z - It seems a technical comment. Transfered it to MAC. |  |  |  | 2018-08-03 16:10 | MAC
1500 | Mark RISON | 232 | 1 | 9.3.3.2 | 794 | 18 | T | Y | 794.18 | 18 | 9.3.3.2 |  | V | Mark Hamilton |  |  | "All fields and elements are mandatory unless stated otherwise and appear in the specified, relative order, with gaps allowed." -- it is not clear what "with gaps allowed" means. It seems to suggest you can just put random filler between fields/elements | Delete ", with gaps allowed" in the cited text at the referenced location | REVISED (MAC: 2018-10-31 23:44:58Z): Replace the cited sentence with: “All fields and elements are mandatory unless stated otherwise. Fields and elements appear in the specified, relative order, skipping fields or elements that are not present." | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-31 23:45:28Z - status set to: Ready for Motion MAC: 2018-08-03 16:32:06Z - status set to: Discuss |  |  |  | 2018-10-31 23:46 | MAC
1503 | Mark RISON | 232 | 1 | 10.23.2.4 | 1670 | 10 | T | Y | 1670.1 | 10 | 10.23.2.4 |  | J | Mark Hamilton |  |  | The precedence of the actions on page 1670 is not clear | At 1670.14 and 1670.22 change "At each" to "Otherwise, at each" | REJECTED (MAC: 2018-10-12 21:08:22Z): There is a preceding 'shall' statement that one and only one of the actions shall occur, and the actions are each subject to conditions, which are mutually exclusive. Thus, there is no precendance relationship. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:08:46Z - status set to: Ready for Motion MAC: 2018-08-03 17:06:57Z - status set to: Discuss |  |  |  | 2018-10-12 21:11 | MAC
1505 | Mark RISON | 232 | 1 | 10.3.3 |  |  | T | Y |  |  | 10.3.3 |  | V | Menzo Wentink | 11-18/1426 |  | There are several issues with the [QS]SRC/LRC stuff: sometimes it's per-MPDU (p.1290 in mc/D6.0), sometimes it's per-MSDU/MMPDU (p.1295); sometimes it's Data frames only (p.1290), sometimes Management too (p.1295) | Frankly, I can't work it out. Tell me whether SRC/LRC is per-MPDU or per-MSDU/MMPDU, and whether it includes Managament frames/MMPDUs, and I'll come up with the changes | REVISED (MAC: 2018-10-05 15:05:18Z): Incorporate the changes shown in 1https://mentor.ieee.org/802.11/dcn/18/11-18-1426-05-000m-cid-1505.docx. . These changes simplify and clarify the "short/long retry counter"s and the Q[SL]RC counters. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-05 15:05:13Z - status set to: Ready for Motion MAC: 2018-10-05 15:03:16Z - Reviewed 11-18/1426r4. More cleanup done. Generally okay with the result (11-18/1426r5), after off-line review. Consider ready for motion unless a concern is raised. MAC: 2018-09-28 14:32:21Z - Reviewed 11-18/1426r2. Generally agree, after rejecting the change to delete "f)" from the list at P1775.44. Need to also mark associated MIB attributes as no longer used. MAC: 2018-04-05 01:00:21Z - status set to: Submission Required |  |  |  | 2018-10-05 15:23 | MAC
1509 | Mark RISON | 232 | 1 | 11.5.4 | 2058 | 1 | T | Y | 2058.01 | 1 | 11.5.4 |  | A | Mark Hamilton |  |  | It is not clear what "corresponding to the TID for which the block ack policy is set" means | Change each of the three instances in the referenced subclause to "with the TID for the block ack agreement" | ACCEPTED (MAC: 2018-11-02 17:17:48Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-11-02 17:17:51Z - status set to: Ready for Motion MAC: 2018-08-03 17:11:50Z - status set to: Discuss |  |  |  | 2018-11-02 17:18 | MAC
1511 | Mark RISON | 232 | 1 | 10.7 | 1644 | 20 | T | Y | 1644.2 | 20 | 10.7 |  |  | Mark Hamilton |  |  | "For MSDUs or A-MSDUs belonging to the service class of QoSAck when the receiver is a QoS STA, set to Normal Ack or Implicit Block Ack Request, PSMP Ack, or Block Ack." is missing some words (what is set?) | Change the cited text in the referenced location to "For MSDUs or A-MSDUs belonging to the service class of QoSAck when the receiver is a QoS STA, the QoS Data frames that are used to send these MSDUs or A-MSDUs shall have the Ack Policy subfield in the QoS Control field set to Normal Ack or Implicit Block Ack Request, PSMP Ack, or Block Ack." |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 17:06:44Z - status set to: Discuss |  |  |  | 2018-08-03 17:07 | MAC
1519 | Mark RISON | 232 | 1 | 9.4.2.36 | 1066 | 25 | T | Y | 1066.25 | 25 | 9.4.2.36 |  |  | Mark Hamilton |  |  | "Set to 4 for 80+80 MHz operating channel width" is not consistent with the other sentences | Change the cited text at the referenced location to "Set to 4 for 80+80 MHz BSS bandwidth" |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 21:38:58Z - status set to: Discuss |  |  |  | 2018-08-03 21:39 | MAC
1520 | Mark RISON | 232 | 1 | 10.23.2.8 | 1676 | 63 | T | Y | 1676.63 | 63 | 10.23.2.8 |  |  | Mark Hamilton |  |  | "Note that when transmitting multiple frames in a TXOP using acknowledgment mechanisms other than Normal Ack," -- it is not clear what this means; it seems to be inadvertently omitting implicit BA | Change the cited text at the referenced location to "Note that when transmitting multiple frames in a TXOP using acknowledgment mechanisms other than immediate acknowledgement," |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 17:07:10Z - status set to: Discuss |  |  |  | 2018-08-03 17:07 | MAC
1526 | Mark RISON | 232 | 1 | 9.2.4.5.4 | 743 | 3 | T | Y | 743.03 | 3 | 9.2.4.5.4 |  | V | Mark Rison | 11-18/1306 |  | The way the ack policy is referred to is confusing/inconsistent. Do you refer to the options indicated by the bit pattern (e.g. "Normal Ack or Implicit Block Ack Request") or do you refer to only the type of ack being requested in the context being requested (e.g. just "Implicit Block Ack Request" in the case of an A-MPDU)? | See 17/1243r6 | REVISED (MAC: 2018-10-12 14:40:54Z): Incorporate the changes in 11-18/1306r6 <https://mentor.ieee.org/802.11/dcn/18/11-18-1306-06-000m-resolutions-for-some-comments-on-11md-d1-0-lb232.docx> which makes the changes in the direction the commenter requested. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 14:42:11Z - status set to: Ready for Motion MAC: 2018-10-12 14:38:12Z - Reviewed 11-18/1306r5 (edited to be r6). Only one open item left, about how 11ah handles a RTS and other situations. We'll go with the r6, best guess, for how this is handled, and approve the changes. MAC: 2018-10-05 16:48:52Z - Reviewed 11-18/1306r4 for CIDs 1415 and 1526. Still open items to confirm with 11ah experts. Also resolve the appearance of phrases like "no ack ack policy". Straw poll chose to live with "No Ack ack policy". Mark will update to 1306r5, and bring back. See also CID 1415 |  |  |  | 2018-10-12 14:44 | MAC
1532 | Mark RISON | 232 | 1 | 9.4.2.179 | 1277 | 33 | T | Y | 1277.33 | 33 | 9.4.2.179 |  |  | Mark Hamilton |  |  | "0: Reserved, FILS Public Key is undefined." -- this can't be used, nor can any values above 3 | Delete the line at 1277.33 and at the end of the referenced subclause add "Other values are reserved." |  | MAC | Clarification/correction | Discuss | MAC: 2018-08-03 17:01:53Z - status set to: Discuss |  |  |  | 2018-08-03 17:02 | MAC
1536 | Mark RISON | 232 | 1 | 9.4.2.169.2 | 1267 | 56 | T | Y | 1267.5601 | 56 | 9.4.2.169.2 |  | A | Mark Hamilton |  |  | " Values of Operating Class are shown in Table E-4 (Global operating classes), of which operating classes that, together with the channel number, indicate the primary channel is valid (see 11.42.8 (Reduced neighbor report))." -- this sentence doesn't make sense | Delete the referenced sentence in the referenced location | ACCEPTED (MAC: 2018-09-14 03:30:35Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-09-14 03:30:37Z - status set to: Ready for Motion MAC: 2018-08-03 17:01:25Z - status set to: Discuss |  |  |  | 2018-09-14 03:31 | MAC
1545 | Michael Fischer | 232 | 1 | 2 | 137 | 49 | E | N | 137.49 | 49 | 2 |  |  | Mark Hamilton |  |  | The reference to 802.1Q-2003 is obsolete | Replace with the current version of the standard for virtual bridged LANs |  | MAC | Minor Correction | Submission Required | MAC: 2018-08-03 16:11:38Z - This is submission required because an evaluation must be done of each occurrence of a reference to 802.1Q to confirm that the chnages since 2003 do not invalidate/change any 802.11 text, before the reference can be changed. It is known, from previous discussions/similar evaluations that some references were (at least at some time) dependent on the particular revision of 802.1Q. MAC: 2018-04-30 23:13:15Z - status set to: Submission Required EDITOR: 2018-04-30 21:39:22Z - status set to: Assigned EDITOR: 2018-04-30 21:37:24Z - feedback from TGmd teleconf (4/27): Revised. At 137.53 change “IEEE Std 802.1Q™-2011” to ““IEEE Std 802.1Q™-2014” Note to commenter: IEEE Std 802.1Q™-2003 is specifically used at 1051.30. We still need IEEE Std 802.1Q™-2003. Need more work to clean references in the draft. Assign it to Mark H and transfer to MAC. EDITOR: 2018-04-02 22:19:41Z - status set to: Discuss |  |  |  | 2018-08-03 16:14 | MAC
1553 | Jouni Malinen | 232 | 1 | 11.1.4.3.4 | 1953 | 52 | T | N | 1953.52 | 52 | 11.1.4.3.4 |  | A | Mark Hamilton |  |  | A Probe Request frame may contain the DSS Parameter Set element regardless of whether the receiving STA has radio measurements activated. As such, the local value of dot11RadioMeasurementActivated should not be used as a condition for using this information when deciding whether to reply to a Probe Request frame. | Replace "The STA has dot11RadioMeasurementActivated equal to true and the Probe Request frame contains a DSSS Parameter Set element" with "The Probe Request frame contains a DSSS Parameter Set element". | ACCEPTED (MAC: 2018-10-12 21:02:07Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:02:10Z - status set to: Ready for Motion MAC: 2018-08-03 17:10:31Z - status set to: Discuss |  |  |  | 2018-10-12 21:02 | MAC
1556 | Mark Hamilton | 232 | 1 | 14.9.2 | 2557 | 57 | T | Y | 2557.5701 | 57 | 14.9.2 |  |  | Mark Hamilton |  |  | What is a "test frame" | Replace "[the] test frame" with "a nominal frame". Same thing in Table 14-4, and in 14.9.3 in Table 14-6. |  | MAC | Testing | Discuss | MAC: 2018-04-24 17:28:49Z - status set to: Discuss |  |  |  | 2018-04-24 17:29 | MAC
1557 | Mark Hamilton | 232 | 1 | 10.2.1 | 1563 | 28 | T | Y | 1563.28 | 28 | 10.2.1 |  |  | Mark Hamilton |  |  | HCF doesn't really use DCF architecturally. It 'replaces' DCF. | Change Figure 10-1 to show HCF (EDCA and HCCA) as directly using the PHY. Cleanup text in 10.2, 10.3 and 10.22 to not describe HCF as using DCF. |  | MAC | HCF | Submission Required | MAC: 2018-04-05 20:52:47Z - status set to: Submission Required |  |  |  | 2018-04-05 20:53 | MAC
1560 | Mark Hamilton | 232 | 1 | 10.25.5.3 | 1719 | 60 | T | Y | 1719.6 | 60 | 10.25.5.3 |  | V | Mark Hamilton |  |  | Data MPDU is rarely used. "Data frame" is overwhelmingly preferred. | Change the remaining 5 "data MPDU"s to "data frame"s | REVISED (MAC: 2018-10-12 21:03:02Z): Revised. Change 6 occurences (relative to draft 1.6) of "data MPDU" to "Data frame". Note to Editor, locations are: P252.47, P1844.24, P1844.26, P1844.50 (note, maintain the plural), P1845.43, P1845.45, P1850.43. | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:03:20Z - status set to: Ready for Motion MAC: 2018-08-03 17:07:28Z - status set to: Discuss |  |  |  | 2018-10-12 21:03 | MAC
1565 | Mark Hamilton | 232 | 1 | 6.3.31.2.2 | 415 | 45 | T | Y | 415.45 | 45 | 6.3.31.2.2 |  |  | Mark Hamilton |  |  | Saying the LCI Management Request parameter is defined in 9.6.7.32 is pointless and not helpful. 9.6.7.32 actually says that this is a Measurement Request element (defined in 9.4) with most of the fields set to known (constant) values. We should only pass the information that is actually variable to this primitive. | Replace this parameter with two parameters, with column information: "Parallel", "Boolean", "true, false", "As defined in 9.4.2.20.1", and "Optional subelements", "As defined in 9.4.2.20.10", "As listed in Table 9-106", "Zero or more subelements to include in the request". Same for Location Civic Measurement Request. Same in the Neighbor Report indication. Same in the FTM request and indication, and FTM Request request and indication. |  | MAC | Minor Correction | Submission Required | MAC: 2018-08-03 16:15:57Z - status set to: Submission Required, to provide details of referenced/changed text. GEN: 2018-07-31 19:38:22Z - status set to: Discuss - reference does not seem correct. |  |  |  | 2018-08-03 16:17 | MAC
1569 | Mark Hamilton | 232 | 1 | 9.4.2.146 | 1236 | 30 | T | Y | 1236.3 | 30 | 9.4.2.146 |  | V | Mark Hamilton |  |  | What is "A/C power"? Is PoE sufficient? Battery backup? | Change "A/C Power" in the Figure to "Mains power", and in the descriptive text to "Mains or grid power". | REVISED (MAC: 2018-10-12 21:01:15Z): Change to "The A/C Power subfield indicates whether the STA is power constrained or not. It is set to 1 if the STA is not power constrained, i.e., supplied by external power, including PoE, wall plug, etc.; otherwise, it is set to 0." | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:01:49Z - status set to: Ready for Motion MAC: 2018-09-13 - 7.7.4.3 Question on the POE as a possible issue. Need definition of the power that is being described. Maybe we should include an example of what the power usage is being needed here. 7.7.4.4 There may be a bigger issue of capability vs is currently having power currently supplied. 7.7.4.5 This is a bit in a capability field, so is the value set to one if capable, or is it that the device is using the power. The bit is only useful if it is telling if the device is on AC power or not. If it is a capability, then it is not very useful. 7.7.4.6 Discussion on if this is a capability or not. 7.7.4.7 Original text: “The A/C Power subfield indicates whether the STA is capable of obtaining A/C Power. It is set to 1 if the STA is capable of being supplied by AC Power, otherwise it is set to 0.” 7.7.4.8 Proposed Alternative Change 1): “The A/C Power subfield indicates whether the STA is using AC Power. It is set to 1 if the STA is supplied by AC Power, including PoE, wall plug, etc.; otherwise it is set to 0.” 7.7.4.9 Proposed Alternative Change 2): “The A/C Power subfield indicates whether the STA is capable of using AC Power. It is set to 1 if the STA is capable of being supplied by AC Power, including PoE, wall plug, etc.; otherwise it is set to 0.” 7.7.4.10 Straw Poll: 7.7.4.10.1 Choice option 1 or Option 2) 7.7.4.10.2 Results: 4 – 4 7.7.4.11 Need to check with DMG experts to determine what the intent of this bit when defined. 7.7.4.12 ACTION ITEM #5: Mark HAMILTON to check with DMG experts on the intent of the A/C Power subfield definition. MAC: 2018-08-03 17:01:04Z - status set to: Discuss |  |  |  | 2018-10-12 21:02 | MAC
1572 | Mark Hamilton | 232 | 1 | 9.4.5.21 | 1360 | 26 | T | Y | 1360.26 | 26 | 9.4.5.21 |  | V | Mark Hamilton |  |  | Can the NAI Realm field have zero NAI Realm Tuple subfields? If so, what does the AoC element mean? Does the Plan Information have to have valid information including the XML description? | Clarify if the NAI Realm field can be zero length or not, and if it can be, clarify (in 11.23.3.3.12) how the "information is provided on a per NAI realm basis" works. | REVISED (MAC: 2018-10-12 21:04:12Z): At the cited location, replace: "The NAI Realm Encoding, NAI Realm Length and NAI Realm fields are defined in 9.4.5.10 (NAI Realm ANQP-element)." with "The NAI Realm Encoding and NAI Realm Length are defined in 9.4.5.10 (NAI Realm ANQP-element). The NAI Realm subfield is one or more NAI Realms formatted as defined in 9.4.5.10 (NAI Realm ANQP-element)." | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:04:46Z - status set to: Ready for Motion MAC: 2018-04-05 00:53:11Z - status set to: Submission Required |  |  |  | 2018-10-12 21:05 | MAC
1573 | Mark Hamilton | 232 | 1 | 11.23.3.3.12 | 2211 | 6 | T | Y | 2211.0601 | 6 | 11.23.3.3.12 |  | A | Mark Hamilton |  |  | Consider having a default charge that applies if none of the NAI Realms in the Advice of Charge Duples matches. | Add "Plan information for the special NAI realm "*" is indicated, if none of the explicit NAI realms are currently applicable." | ACCEPTED (MAC: 2018-10-12 21:05:13Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:05:15Z - status set to: Ready for Motion MAC: 2018-08-03 17:13:07Z - status set to: Discuss MAC: 2018-04-05 20:56:24Z - status set to: Submission Required |  |  |  | 2018-10-12 21:05 | MAC
1593 | Mark Hamilton | 232 | 1 | 9.3.3.9 | 809 | 28 | T | Y | 809.28 | 28 | 9.3.3.9 |  | A | Mark Hamilton |  |  | In Table 9-36 (the "Reassociation Response frame body"), Order 31 appears twice. Association Response (up about 5 pages) has the same problem, with Order 27. | Renumber the tables with sequential Order | ACCEPTED (MAC: 2018-10-12 21:05:30Z) | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:05:32Z - status set to: Ready for Motion MAC: 2018-08-03 16:32:18Z - status set to: Discuss |  |  |  | 2018-10-12 21:06 | MAC
1594 | Mark Hamilton | 232 | 1 | 9.2.2 | 726 | 6 | T | Y | 726.06 | 6 | 9.2.2 |  | V | Mark Hamilton |  |  | Things are wrong with this sentence, "An ASCII or UTF-8 string a sequence of ASCII-encoded octets without a terminating null." First, there's no verb. Probably supposed to be "... string _is_ a sequence of ..." Secondly, how can an UTF-8 string be ASCII-encoded? The point of UTF-8 is to encode stuff ASCII can't do. (Yes, extended ASCII could arguably contain the octets of the UTF-8, but that is just confusing things.) | Replace with, "An ASCII or UTF-8 string is a sequence of ASCII or UTF-8 encoded octets without a terminating null." | REVISED (MAC: 2018-10-12 21:06:02Z): Replace the cited sentence with, "An ASCII or UTF-8 string is a sequence of ASCII or UTF-8 encoded code points, respectively, without a terminating null." | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:06:14Z - status set to: Ready for Motion MAC: 2018-08-03 16:18:10Z: May also need to disambiguate the "or"s. For example, two sentences: ""An ASCII string is a sequence of ASCII encoded octets without a terminating null. A UTF-8 string is a sequence of UTF-8 encoded octets without a terminating null." |  |  |  | 2018-10-12 21:06 | MAC
1609 | Peter Ecclesine | 232 | 1 | 2 | 138 | 8 | E | N | 138.08 | 8 | 2 |  |  | Mark Hamilton |  |  | IEEE 802.3 has been updated | Update all clause 2 references for current versions |  | MAC | Minor Correction | Submission Required | MAC: 2018-08-03 16:11:38Z - This is submission required because an evaluation must be done of each occurrence of a reference to confirm that the chnages since the currently referenced version do not invalidate/change any 802.11 text, before the reference can be changed. It is known, from previous discussions/similar evaluations that some references were (at least at some time) dependent on the particular revision of the referenced standard/spec. MAC: 2018-04-30 23:13:00Z - status set to: Submission Required EDITOR: 2018-04-30 21:41:13Z - status set to: Assigned EDITOR: 2018-04-30 21:40:03Z - feedback from TGmd telecon(4/27): Revised. At 271.52: change “IEEE Std 802.3-2012” to “IEEE Std 802.3”. At 138.8, change “IEEE Std 802.3™-2012, IEEE Standard for Ethernet” to “IEEE Std 802.3™-2015, IEEE Standard for Ethernet”. However, this comment is related to CID 1545. Assign it to Mark H and transfer to MAC too. EDITOR: 2018-04-02 22:20:57Z - status set to: Discuss |  |  |  | 2018-08-03 16:15 | MAC
1614 | Albert Petrick | 232 | 1 | 9.4.2.187 | 1286 | 60 | T | N | 1286.6 | 60 | 9.4.2.187 |  | V | Mark Hamilton |  |  | Payload of each element is limited to a maximum of 254 or 255 octets. The should be limited to one single value. If it can be either or then clarify the condition for each. | Fix as commented | REVISED (MAC: 2018-10-12 21:07:52Z): Replace the cited paragraph with two paragraphs: Elements are defined to have a common general format, per 9.4.2.1. The Length field of an Element is one octet, and thus limited to indicate 255 octets of payload in the Information field. However, since the Element ID Extension field is optional and included in the single-octet Length count, the actual Information payload of an Element is limited to 254 octets if the Element ID Extension is present. If the Information to be represented in an element is too large for this 255 or 254 octet limit, it is necessary to fragment the information as described in 10.28.11 (Element fragmentation(11ai)) and 10.28.12 (Element defragmentation(11ai)). The format of the Fragment element is shown(#243) in Figure 9-646 (Fragment element format(11ai)). | MAC | Motion MAC-V | Ready for Motion | MAC: 2018-10-12 21:07:58Z - status set to: Ready for Motion |  |  |  | 2018-10-12 21:08 | MAC
1620 | Albert Petrick | 232 | 1 | 9.4.2.194 | 1298 | 64 | T | N | 1298.64 | 64 | 9.4.2.194 |  |  | Mark Hamilton |  |  | Note has normative text "can be set to".... Notes can only contain informative text. | Extract the normative information in the paragraph on line 60. |  | MAC | Clarification/correction | Submission Required |  |  |  |  | 2018-04-05 00:57 | MAC