## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/0931r1
Venue Date: | June 2017
First Author: | Yunsong Yang (Huawei Technologies)
Subject: | Comments from 2nd Recirculation Sponsor Ballot (SB2) on P802.11aq D9.0
Full Date: | 2017-07-03
Author(s): | Name(s) | Yunsong Yang
| Company | Huawei Technologies
Address
Phone:
Fax:
| email: | yangyunsong@huawei.com
Abstract:
This document records the 75 comments (numbered as CIDs 8001 - 8075) received from the 2nd Recirculation Sponsor Ballot (SB2) on P802.11aq D9.0 and any resolutions approved by 802.11 TGaq (CRC). The comments are organized as follows: A tab for all SB2 comments; and
A tab per comment group for SB2 comments:
Tabs named with clause # or techical subject are for coments not ready-for-motion.
Tabs named with a date are for comments that are ready-for-motion or approved.
Mappig of CID numbers of all previous and current WG LBs and SBs are as follows:
Draft 1.0, LB208 (Initial WG Ballot, failed) CIDs 1001 to 1801
Draft 3.0, LB216 (Initial WG Ballot, passed) CIDs 2000 to 2399
Draft 4.0, LB219 (First Recirc) CIDs 3001 to 3071
Draft 5.0, LB221 (Second Recirc) CIDs 4001 to 4065
Draft 6.0, LB222 (Third Recirc) CIDs 5001 to 5043 Draft 7.0, LB1000 (Initial Sponsor Ballot) CIDs 6001 to 6235
Draft 8.0, LB2000 (First Recirc Sponsor Ballot) CIDs 7001 to 7175
Draft 9.0, LB3000 (2nd Recirc Sponsor Ballot) CIDs 8001 to 8075

## Revision History
Revision | Date | Description
0 | 2017-06-26 | Initial export from DB.
1 | 2017-07-03 | With initial sorting and assignment.

## All SB2 Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8001 | Alessi, Julie | 3000 | 9 |  |  |  | E | No | [5 empty] | Lee Armstrong |  |  | Draft meets all editorial requirements. |  |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8002 | McCann, Stephen | 3000 | 9 | 4.5.9.1 | 21 | 62 | T | No | 21 | 62 | 4.5.9.1 | [5 empty] | ANQP also performs network discovery in addition to network selection. | Change the start of the bullet point to read "Disocvery and selection of a suitable IEEE Std 802.11...." |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8003 | McCann, Stephen | 3000 | 9 | 6.3.73.2.2 | 28 | 24 | T | No | 28 | 24 | 6.3.73.2.2 | [5 empty] | IEEE 802.21-2008 has now been superceeded by IEEE 802.21-2017 | Replace "802.21-2008" with "802.21-2017". Alternatively just replace with ANQP as an example. Same change at P29L65, P31L45 and P33L33. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8004 | McCann, Stephen | 3000 | 9 | 9.4.1.9 | 38 | 33 | E | No | 38 | 33 | 9.4.1.9 |  |  | Lee Armstrong |  |  | The ANA values needs to be reserved | Update this ANA value |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8005 | McCann, Stephen | 3000 | 9 | 9.4.2.217 | 41 | 25 | T | No | 41 | 25 | 9.4.2.217 | [5 empty] | This sentence mentions a Bloom filter, but it's not clear what a Bloom filter is. | Change "Bloom filter" to "Bloom Filter Bit Array". The same change should also be made to P42L38 |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8006 | McCann, Stephen | 3000 | 9 | 9.4.2.217 | 42 | 44 | E | No | 42 | 44 | 9.4.2.217 |  |  | Lee Armstrong |  |  | On this line, shold bloom filter have a capital "B" or not? | Edit the line to use a capital "B" on bloom filter or not. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8007 | McCann, Stephen | 3000 | 9 | 9.4.5.29 | 47 | 26 | E | No | 47 | 26 | 9.4.5.29 |  |  | Lee Armstrong |  |  | typo "Lenght" | Change to "Length" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8008 | McCann, Stephen | 3000 | 9 | 9.4.5.28 | 46 | 42 | T | No | 46 | 42 | 9.4.5.28 |  |  | Stephen McCann |  |  | There is a worked example of how the request and response attribute fields could look in document https://mentor.ieee.org/802.11/dcn/17/11-17-0632-00-00aq-aligning-11aq-with-higher-layer-service-discovery-protocol.ppt | It would be useful to create an 11aq annex with some of these worked examples |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8009 | McCann, Stephen | 3000 | 9 | 11.25.3.2.1 | 57 | 3 | E | No | 57 | 3 | 11.25.3.2.1 |  |  | Stephen McCann |  |  | Figure 11-40d has a different style from other figures in 802.11 | Re-draw Figure 11-40d to match the 802.11 style |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8010 | McCann, Stephen | 3000 | 9 | 11.25.3.3.1 | 64 | 17 | E | No | 64 | 17 | 11.25.3.3.1 |  |  | Lee Armstrong |  |  | typo extra "7" | remove "7" from the "ANQP-element name" column in table 11-15 |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8011 | McCann, Stephen | 3000 | 9 | 11.25.3.3.1 | 63 | 60 | T | No | 63 | 60 | 11.25.3.3.1 | [5 empty] | When the acronym is expanded, the text "ANQP query request" becomes "Access Network Query Protocol query request" which overworks the query. | Change all occurances of "ANQP query request" to "ANQP request". Similarly change all occurances of "ANQP query response" ro "ANQP response" |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8012 | McCann, Stephen | 3000 | 9 | 11.25a.1 | 65 | 35 | E | No | 65 | 35 | 11.25a.1 |  |  | Lee Armstrong |  |  | typo "1s" | change "1s" to "1" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8013 | McCann, Stephen | 3000 | 9 | 11.25a.2 | 66 | 22 | T | No | 66 | 22 | 11.25a.2 |  |  | Stephen McCann |  |  | The last paragraph does not explain why the authentication and association procedure would be used. | Change the last paragraph to: "The non-AP and non-PCP STA may use the received information regarding which services are reachable to determine the next step of network selection. If a service is matched, the non-AP and non-PCP STA might select the BSS and then proceed with the authentication and association procedure (see 11.3) based on the indicated false positive probability and the requirements of the service or the SIC. If a serivce is not matched, requires verification or requires more information, the non-AP and non-PCP STA might proceed with the solicited PAD procedure (see 11.25a.3). Otherwise the non-AP and non-PCP STA might terminate the network selection process. For futher examples see W.1." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8014 | McCann, Stephen | 3000 | 9 | 11.25a.3.1 | 66 | 40 | E | No | 66 | 40 | 11.25a.3.1 |  |  | Lee Armstrong |  |  | typo "7" | remove the "7" from this line |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8015 | McCann, Stephen | 3000 | 9 | 11.25a.3.1 | 66 | 43 | E | No | 66 | 43 | 11.25a.3.1 |  |  | Lee Armstrong |  |  | I'm not sure what "The Interworking field ..." is referring to. | Change "The Interworking..." to "An Interworking..." |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8016 | McCann, Stephen | 3000 | 9 | 11.25a.3.2 | 66 | 45 | E | No | 66 | 45 | 11.25a.3.2 |  |  | Lee Armstrong |  |  | There's a spurious "7" in the title | Remove the "7" from the title |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8017 | McCann, Stephen | 3000 | 9 | 11.25a.3.2 | 67 | 2 | T | No | 67 | 2 | 11.25a.3.2 |  |  | Stephen McCann |  |  | The design of GAS and ANQP requires null (or zero length) responses to be returned when there is no information (e.g. a matched service) available. It's probably worthwhile making this clear. | Add the following text to the end of the paragraph on P67L2: "This notifies the non-AP and non-PCP STA that the required service is not available." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8018 | McCann, Stephen | 3000 | 9 | 11.25a.3.2 | 67 | 6 | T | No | 67 | 6 | 11.25a.3.2 |  |  | Stephen McCann |  |  | The last paragraph does not explain why the authentication and association procedure would be used. | Change the last paragraph to: "The SIC receives service information from the contents of the Service Information Response ANQP-element. If the service information is suitable, the non-AP and non-PCP STA might select the BSS and then proceed with the authentication and association procedure (see 11.3). If the service information is not suitable, requires verification or requires more information, the non-AP and non-PCP STA might proceed with the another solicited PAD procedure (see 11.25a.3). Otherwise the non-AP and non-PCP STA might terminate the network selection process. For futher examples see W.1." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8019 | McCann, Stephen | 3000 | 9 | C.3 | 76 | 61 | T | No | 76 | 61 | C.3 |  |  | Dan Harkins |  |  | The MIB variable "dot11MACPrivacyActivated" does not appear to have been defined | Provide a definition of "dot11MACPrivacyActivated" in clause C.3 within the OBJECT-TYPE definitions |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8020 | McCann, Stephen | 3000 | 9 | C.3 | 77 | 43 | T | No | 77 | 43 | C.3 |  |  | Stephen McCann |  |  | The MIB variable "dot11GASExtensionImplemented" needs to be added to the SEQUENCE list starting on P74 | Add "dot11GASExtensionImplemented" to the SEQUENCE list starting on P74 |  | GEN | Annex BnC | [5 empty] | 2017-07-03 17:56 | GEN
8021 | McCann, Stephen | 3000 | 9 | C.3 | 78 | 4 | T | No | 78 | 4 | C.3 |  |  | Stephen McCann |  |  | The MIB vairables "dot11GASExtensionImplemented" and "dot11MACPrivacyActivated" need to be added to the PADComplianceGroup | Add the two MIB variables per the comment |  | GEN | Annex BnC | [5 empty] | 2017-07-03 17:56 | GEN
8022 | McCann, Stephen | 3000 | 9 | W.1 | 79 | 16 | T | No | 79 | 16 | W.1 |  |  | Stephen McCann |  |  | Remove the reference to clause 11.25.3.2.16 as it no longer exists | Remove the reference to 11.25.3.2.16 from this line. |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8023 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 24 | T | No | 79 | 24 | W.1.1 |  |  | Stephen McCann |  |  | The applications are running on a STA and that should be mentioned. | Change the start of the paragraph to "STA applications that run...". The same change can also be made to the start of W1.2. |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8024 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 27 | T | No | 79 | 27 | W.1.1 |  |  | Stephen McCann |  |  | It's not a "solicited PAD search" | Change "solicited PAD search" to solicted PAD procedure" |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8025 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 52 | T | No | 79 | 52 | W.1.1 |  |  | Stephen McCann |  |  | What does the "Service Information Response Attribute subfield" do? | Add the following text to the end of the paragraph: "This subfield contains information about the service(s) that was requested." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8026 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 40 | T | No | 79 | 40 | W.1.1 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the sentence to read "Upon receiving a Beacon or DMG Beacon frame, the SIC in a non-AP and non-PCP STA processes the Service Hash and Service Hint elements..." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8027 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 44 | T | No | 79 | 44 | W.1.1 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the paragraph to read " If the probability of false positives as indicated in the False Positive Probability Range field of the Service Hint element is considered relatively high by the SIC in the non-AP and non-PCP STA (see Figure W-1), the SIC can send a Service Information Request ANQP-element through the non-AP and non-PCP STA, containing Service Information Request Attribute subfield to confirm if a service is reachable through the AP or PCP. |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8028 | McCann, Stephen | 3000 | 9 | W.1.1 | 80 | 1 | T | No | 80 | 1 | W.1.1 |  |  | Stephen McCann |  |  | This sentence should be moved down to the paragraph after Figure W-1 | As per comment |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8029 | McCann, Stephen | 3000 | 9 | W.1.1 | 80 | 29 | T | No | 80 | 29 | W.1.1 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the paragraph to read " If the probability of false positive as indicated in False Positive Probability Range field of the Service Hint element is considered relatively low by the SIC in the non-AP and non-PCP STA, the SIC may choose the AP or PCP as a candidate BSS. The SIC may choose to send a Service Information Request ANQP-element to confirm if a service is reachable through the AP or PCP as shown in Figure W-1. Based on the results of these steps the SIC in the non-AP and non-PCP STA may choose to associate with the BSS." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8030 | McCann, Stephen | 3000 | 9 | W.1.1 | 80 | 40 | T | No | 80 | 40 | W.1.1 |  |  | Stephen McCann |  |  | typo "containing Service" | change text to "containing a Service" |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8031 | McCann, Stephen | 3000 | 9 | W.1.1 | 81 | 1 | T | No | 81 | 1 | W.1.1 |  |  | Stephen McCann |  |  | This sentence should be moved down to the paragraph after Figure W-1 | As per comment |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8032 | McCann, Stephen | 3000 | 9 | W.1.2 | 81 | 32 | T | No | 81 | 32 | W.1.2 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the text "whereby the non-AP..." to "whereby the SIC in the non-AP..." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8033 | McCann, Stephen | 3000 | 9 | W.1.2 | 81 | 38 | T | No | 81 | 38 | W.1.2 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the sentence to read: "Following these service message exchanges the SIC in the non-AP and non-AP STA can make an informed decision about choosing to associate to the AP or PCP." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8034 | Levy, Joseph | 3000 | 9 | 6.3.73.2.2 | 27 | 51 | E | No | 27 | 51 | 6.3.73.2.2 | [5 empty] | VendorSpecificInfo should not have been deleted from the MLME-GAS request. This removal will impact legacy GAS behavior. Note VendorSpecificInfo is only removed from the listing, it is still in the table. | Reinsert "VendorSpecificInfo" as the last primitive parameter. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8035 | Levy, Joseph | 3000 | 9 | 10.3.2.11.2 | 53 | 4 | E | No | 53 | 4 | 10.3.2.11.2 |  |  | Lee Armstrong |  |  | Editor instructions call out the wrong clause number 11.3.2.11.1 instead of 10.3.2.11.2. | Correct the clause number, as in comment. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8036 | Levy, Joseph | 3000 | 9 | 11.25.3.2.1 | 55 | 27 | E | No | 55 | 27 | 11.25.3.2.1 |  |  | Lee Armstrong |  |  | There seems to be a misuse capitalization: GAS Query Response, is not the name of a frame, hence I think it should be GAS query response. I believe this may need to be corrected in several other locations. | Change the case of: "GAS Query Response" to be "GAS query response" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8037 | Levy, Joseph | 3000 | 9 | 11.25.3.2.1 | 56 | 2 | E | No | 56 | 2 | 11.25.3.2.1 |  |  | Lee Armstrong |  |  | "Frame" is upper case, but it should be lower case "frame". | Change: "Frame" to be "frame" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8038 | Levy, Joseph | 3000 | 9 | 11.25.3.2.3 | 59 | 34 | E | No | 59 | 34 | 11.25.3.2.3 |  |  | Lee Armstrong |  |  | The term "GAS Extension information" is not a direct reference to the frame or element, hence "Extension" should not be upper case. | Change the case of "Extension" to "extension". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8039 | Levy, Joseph | 3000 | 9 | 11.25.3.2.4 | 62 | 19 | E | No | 62 | 19 | 11.25.3.2.4 |  |  | Lee Armstrong |  |  | "GAS Extension" is not referring to a frame or an element, therefore "Extension" should be lower case. | Change case of "Extension" to be "extension" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8040 | Montemurro, Michael | 3000 | 9 | 4.5.9.2.3 | 23 | 54 | T | No | 23 | 54 | 4.5.9.2.3 |  |  | Stephen McCann |  |  | The text in this sub-clause and two subsequent subc-clauses do not accurately describe the behavior of the SIC and SIR. | at P23L54, Change "The SIC and SIR are used to exchange service information between higher layer entities above both the STAs." to "The SIC and SIR are used to exchange PAD service information between STAs." In 4.5.9.2.4, change: "The SIR contains information ..." to "The SIR is configured with information ..." "How the SIR obtains the information about services is outside the scope of this standard." to "The configuration of service information in the SIR is outside the scope of this standard." In 4.5.9.2.5, change: "The SIC initiates service discovery." To "The SIC initiates service discovery to obtain service information in behalf of higher layer entities above the STA. The configuration of service discovery information in the SIC is outside the scope of this standard." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8041 | Montemurro, Michael | 3000 | 9 | 11.25a.2 | 66 | 23 | T | No | 66 | 23 | 11.25a.2 |  |  | Stephen McCann |  |  | "How to proceed" is not descriptive enough in this context. | Change "to determine how to proceed" to "as input to network discovery and selection procedures." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8042 | Montemurro, Michael | 3000 | 9 | 11.25a.3.2 | 66 | 48 | E | No | 66 | 48 | 11.25a.3.2 |  |  | Lee Armstrong |  |  | Minor editorial | change "request detailed" to "request detailed" (remove the additional space) |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8043 | Montemurro, Michael | 3000 | 9 | 11.25a.3.2 | 67 | 1 | T | No | 67 | 1 | 11.25a.3.2 |  |  | Stephen McCann |  |  | "can" should be a "may" | change "can" to "may" |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8044 | Hartman, Chris | 3000 | 9 | 9.6.8.36 | 50 | 26 | E | No | 50 | 26 | 9.6.8.36 |  |  | Lee Armstrong |  |  | "The GAS Extension element indicates parameters that the AP or PCP may use to in transmiting a response back to the requesting STA." - "to in" is superfluous. | Change to either: "... may use to transmit...", or "... may use in transmitting". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8045 | Hartman, Chris | 3000 | 9 | 11.25.3.2.3f | 59 | 45 | T | No | 59 | 45 | 11.25.3.2.3f |  |  | Mike Montemurro |  |  | The response specified in this clause is not time-bounded. The requesting STA may indicate it's Maximum Channel Time in the GAS Extension Element, but there is no requirement for the Responding STA to attempt to honor the requesting STA's time restrictions. | Add a sentence to subclause 11.25.3.2.3 f) along the following lines: "If a GAS Request frame contains a GAS Extension Element, the the responding STA shall attempt to transmit an individually addressed GAS Initial Response frame to the requesting STA within the indicated Maximum Channel Time." |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN
8046 | Hamilton, Mark | 3000 | 9 | 3.1 | 18 | 47 | E | No | 18 | 47 | 3.1 |  |  | Lee Armstrong |  |  | Typo - meant "Insert the following new definition in Clause 3.1 ..." | Change "references" to "new defintion" and "2" to "3.1" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8047 | Hamilton, Mark | 3000 | 9 | 4.5.4.10 | 21 | 31 | T | Yes | 21 | 31 | 4.5.4.10 |  |  | Dan Harkins |  |  | "a non-AP STA uses" implies all non-AP STAs will always do this. But, these privacy enhancements are not universally used. | Change "uses" to "may use" |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8048 | Hamilton, Mark | 3000 | 9 | 4.5.9.2.2 | 23 | 39 | E | No | 23 | 39 | 4.5.9.2.2 |  |  | Lee Armstrong |  |  | Figure numbering got messed up. | Change Figure 5 to Figure 4-15b. Also, fix the reference in text at P22.64. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8049 | Hamilton, Mark | 3000 | 9 | 9.4.1.9 | 38 | 34 | E | Yes | 38 | 34 | 9.4.1.9 |  |  | Lee Armstrong |  |  | <ANA> needs to be replaced with a value by this point in Sponsor Ballot. | Replace "<ANA>" with the appropriate value. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8050 | Hamilton, Mark | 3000 | 9 | 9.4.2.177 | 40 | 30 | T | Yes | 40 | 30 | 9.4.2.177 |  |  | Yunsong Yang |  |  | The entries in the new Table 9-258b do not match (in values or meaning) the entries in Table 9-214. Table 9-214 was used in 802.11-2016 as the definition of the CAG Tuple field. The backward compatibility mechanism to handle this change in semantics is not clear. | Clarify how this field is to interpreted to provide backward compatibility. |  | GEN | CAG | [5 empty] | 2017-07-03 17:53 | GEN
8051 | Hamilton, Mark | 3000 | 9 | 9.4.2.217 | 41 | 24 | T | Yes | 41 | 24 | 9.4.2.217 | [5 empty] | This field represents parameters of "the Bloom filter". What Bloom filter? There is no antecedent for "the". | Replace "the Bloom filter" with "a Bloom filter that conveys the probabilistic data." |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8052 | Hamilton, Mark | 3000 | 9 | 9.6.8.13 | 48 | 55 | T | Yes | 48 | 55 | 9.6.8.13 |  |  | Mike Montemurro |  |  | The new field (GAS Extension) in this Action format needs some text explanation. | Add a (probably short) paragraph to the end of 9.6.8.13 that describes the use of the GAS Extention field in this frame. |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN
8053 | Hamilton, Mark | 3000 | 9 | 11.25a.1 | 65 | 31 | T | Yes | 65 | 31 | 11.25a.1 |  |  | Dan Harkins |  |  | Is this supposed to be a normative requirement? | Change "invokes" to "shall invoke" |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8054 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 27 | E | No | 68 | 27 | 12.2.10 |  |  | Lee Armstrong |  |  | "membership" in what is ambiguous. | Insert "BSS" before "membership" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8055 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 30 | E | No | 68 | 30 | 12.2.10 |  |  | Dan Harkins |  |  | This sentence sounds like the complete list of times when the STA shall defer changing its MAC address, but it is not complete. | Add "during association to a BSS or ESS, or" before "during a transactional exchange" |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8056 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 38 | T | Yes | 68 | 38 | 12.2.10 |  |  | Dan Harkins |  |  | The requirement to change a STA's MAC address "prior" to establishing a connection is: 1) contradictory with 2 paragraphs down that says it is static during association to an ESS; 2) breaks any pre-association negotiations (pre-auth, FT over-the-DS, etc.; and 3) is ambiguous in terms of how much prior to establishing the connection, and what point is determined to "establishing a connection" (for example, should it be after the Authentication, but before Association? clearly, not.) | Change "shall" to "should", and add explanation that the change can only occur if there are no persistent agreements in place with the new BSS's AP. |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8057 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 53 | T | No | 68 | 53 | 12.2.10 |  |  | Dan Harkins |  |  | No need to generate 48 bits of random value, and then bash 2 of them to fixed values. Just generate 46 bits. | Change to "To set a random MAC address, a STA shall set the sixth bit ... and the seventh bit ... and shall assign a random 46-bit value to the remaining bits." |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8058 | Hamilton, Mark | 3000 | 9 | C.3 | 77 | 49 | E | Yes | 77 | 49 | C.3 |  |  | Lee Armstrong |  |  | Stray sentence. | Delete "GAS Extension Support Activated." |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8059 | Yang, Yunsong | 3000 | 9 | 4.5.4.10 | 21 | 33 | T | No | 21 | 33 | 4.5.4.10 |  |  | Dan Harkins |  |  | Regarding "Post-association, a non-AP STA uses a unique random MAC address ... for an established network connnection.", today, most STAs use their globally unique MAC addresses for post-association connection. Is the cited sentence meant to be a requirement (or at least a recommended practice) as a part of the MAC privacy enhancements in order not to reveal the globally unique MAC address of the STA? If it is intended to be a requirement or a recommended practice, should make it clear. | Please clarify. |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8060 | Yang, Yunsong | 3000 | 9 | 4.5.9.2.5 | 24 | 15 | T | No | 24 | 15 | 4.5.9.2.5 | [5 empty] | Probe request is no longer used for PAD. | Delete "probe requests and" from the cited sentence. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8061 | Yang, Yunsong | 3000 | 9 | 6.3.73.4.2 | 31 | 64 | E | No | 31 | 64 | 6.3.73.4.2 |  |  | Lee Armstrong |  |  | "GAS extension element" should be "GAS Extension element". | Change "extension" to "Extension" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8062 | Yang, Yunsong | 3000 | 9 | 9.4.1.9 | 38 | 36 | T | No | 38 | 36 | 9.4.1.9 |  |  | Mike Montemurro |  |  | GAS Extension element is introduced in GAS Comeback Request frame to request for re-transmission of missing GAS fragment. However, it is not clear how the requesting STA knows that the responding STA is capable of re-transmitting missing GAS fragment. Possible solutions: 1) A non-capable responding STA uses a new Status Code value in the GAS Comeback Response frame to indicate that it isn't capable of re-transmitting any missing GAS fragment when responding to a request to re-transmit missing GAS fragment, which means that the requesting STA doesn't know the responding STA's lack of such capability before-handed; 2) the responding STA indicates whether it is capable of re-transmitting missing GAS fragment before the requesting STA requests so. Such an indication can be a new Extended Capabilities bit or a new flag bit in the GAS Extension element in the first GAS Comeback Response frame whenever Query Response fragmentation is needed. | Consider one of the following remedies as described in the comment: a new Status code value (such as RETRANSMITTING GAS FRAGMENT NOT SUPPORTED), a new Extended Capabilities bit, a new flag bit in the GAS Extension element in (at least) the first GAS Comeback Response frame whenever Query Response fragmentation is required. |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN
8063 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 43 | 17 | T | No | 43 | 17 | 9.4.2.219 |  |  | Mike Montemurro |  |  | There are two problems in this sentence. First, there is no such thing called "group-addressed GAS Initial Response frame". Secondly, there are two possible ways to interpret this sentence. One is that the presence of the element in the GAS Initial Request frame indicates that the STA is capable of receiving Group-addressed GAS Response frame (so the capability is affirmed by the presence of the element). The alternative interpretation is that the GAS Extension element indicates whether the STA is capable of receiving Group-addressed GAS Response frame (so the capability, either yes or no, is indicated by the element, presumably by the Group-addressed GAS subfield in the GAS Flags field). The commenter believes that the alternative interpretation is in line with the definition of the Group-addressed GAS subfield on L55. However, also need to double-check with the added text on P54L34. | Change the cited sentence to read: "When present in the GAS Initial Request frame, the GAS Extension element indicates whether the STA is capable of receiving a Group Addressed GAS Response frame." And change the sentence on L55 to read: "Group-addressed GAS sub-field is set to 1 to indicate that the STA is capable of receiving Group Addressed GAS frames and is set to 0 otherwise." |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN
8064 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 43 | 64 | E | No | 43 | 64 | 9.4.2.219 |  |  | Lee Armstrong |  |  | The sentence "The Response Map Flag sub-field is ..." should start a new paragraph. | Use the cited sentence to start a new paragraph below. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8065 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 44 | 7 | E | No | 44 | 7 | 9.4.2.219 |  |  | Lee Armstrong |  |  | "The Fragment ID field in the GAS Comeback Request indicates ..." is not the right expression. | Change "The Fragment ID field in the GAS Comeback Request indicates" to "The Fragment ID field, when present in the GAS Comeback Request, indicates". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8066 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 44 | 21 | E | No | 44 | 21 | 9.4.2.219 |  |  | Lee Armstrong |  |  | The last sentence of this paragraph should be in the previous paragraph, since it talks about the value of the Number of Response Map Duples field. | Delete the cited sentence. And add the following to the end of previous paragrah on L14: "When present, the Number of Response Map Duples field is set to a nonzero value and the value of zero is reserved." |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8067 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 44 | 40 | E | No | 44 | 40 | 9.4.2.219 |  |  | Lee Armstrong |  |  | Missing period (".") at the end. | Add a period at the end of the sentence. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8068 | Yang, Yunsong | 3000 | 9 | 9.4.5.29 | 47 | 14 | E | No | 47 | 14 | 9.4.5.29 |  |  | Lee Armstrong |  |  | "length" in the figure should be "Length" since it is a part of the field name. | Change "length" to "Length". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8069 | Yang, Yunsong | 3000 | 9 | 11.25.3.2.2 | 58 | 12 | T | No | 58 | 12 | 11.25.3.2.2 |  |  | Yunsong Yang |  |  | "a cached version" may be confused with the "CAG Version" later. Similar issue also exists on P56L57. The commenter believes that "a cached version" here refers to "a cached version" of the information that the requesting STA requests, while a "CAG Version" refers to a number. Therefore, from English PoV, adding "of" after "a cached version" would make it sufficiently clear. | Add "of" after "a cached version". And add "of" after "a cached version" on P56L57 as well. |  | GEN | CAG | [5 empty] | 2017-07-03 17:53 | GEN
8070 | Yang, Yunsong | 3000 | 9 | 9.6.8.37 | 50 | 59 | T | No | 50 | 59 | 9.6.8.37 | [5 empty] | CID 7151 questioned the need of GAS Comeback Delay field in the Group Addressed GAS Response frame (because the field will always be set to 0) and the proposed change included the removal of the field and related text. The resolution to CID 7151 was "Accepted". However, the GAS Comeback Delay field remains in D9.0. | Delete the row of GAS Comeback Delay from Table 9-325b. Delete the entire paragraph (describing GAS Comeback Delay field) on P51L23-L26. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8071 | Yang, Yunsong | 3000 | 9 | 11.25.3.2.1 | 56 | 61 | T | No | 56 | 61 | 11.25.3.2.1 |  |  | Yunsong Yang |  |  | It is ambiguous which Advertisement Server is "relevant". | Change "a relevant Advertisement Server," to "a relevant Advertisement Server as indicated by the Advertisement Protocol and Server ID, which is provided by the requesting STA in the same CAG Tuple field that contains the cached CAG Version," |  | GEN | CAG | [5 empty] | 2017-07-03 17:53 | GEN
8072 | Yang, Yunsong | 3000 | 9 | 11.25.3.2.4 | 62 | 21 | T | No | 62 | 21 | 11.25.3.2.4 | [5 empty] | There are some redundancy and self-contradiction in "the Fragment ID sub field of the GAS Flags field set to one, and the Fragment ID field set to the fragment ID of the Query Response to be retransmitted". | Delete "one, and the Fragment ID field set to". |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8073 | Yang, Yunsong | 3000 | 9 | 11.25a.3.1 | 66 | 40 | E | No | 66 | 40 | 11.25a.3.1 |  |  | Lee Armstrong |  |  | An extra "7" | Delete "7" on L40 and L45. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8074 | Yang, Yunsong | 3000 | 9 | B.4.20 | 73 | 10 | T | No | 73 | 10 | B.4.20 |  |  | Stephen McCann |  |  | TGaq should consider a separate PICS entry for support of re-transmission of missing Query Response fragment, because it isn't the same as support of Group-addressed GAS Response. | Add a new entry for "Re-transmission of missing Query Response fragment" |  | GEN | Annex BnC | [5 empty] | 2017-07-03 17:56 | GEN
8075 | Yang, Yunsong | 3000 | 9 | W.1 | 80 | 34 | E | No | 80 | 34 | W.1 |  |  | Lee Armstrong |  |  | An extra "can" at the end. | Delete "can" at the end of the sentence. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN

## Procedures
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8009 | McCann, Stephen | 3000 | 9 | 11.25.3.2.1 | 57 | 3 | E | No | 57 | 3 | 11.25.3.2.1 |  |  | Stephen McCann |  |  | Figure 11-40d has a different style from other figures in 802.11 | Re-draw Figure 11-40d to match the 802.11 style |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8013 | McCann, Stephen | 3000 | 9 | 11.25a.2 | 66 | 22 | T | No | 66 | 22 | 11.25a.2 |  |  | Stephen McCann |  |  | The last paragraph does not explain why the authentication and association procedure would be used. | Change the last paragraph to: "The non-AP and non-PCP STA may use the received information regarding which services are reachable to determine the next step of network selection. If a service is matched, the non-AP and non-PCP STA might select the BSS and then proceed with the authentication and association procedure (see 11.3) based on the indicated false positive probability and the requirements of the service or the SIC. If a serivce is not matched, requires verification or requires more information, the non-AP and non-PCP STA might proceed with the solicited PAD procedure (see 11.25a.3). Otherwise the non-AP and non-PCP STA might terminate the network selection process. For futher examples see W.1." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8017 | McCann, Stephen | 3000 | 9 | 11.25a.3.2 | 67 | 2 | T | No | 67 | 2 | 11.25a.3.2 |  |  | Stephen McCann |  |  | The design of GAS and ANQP requires null (or zero length) responses to be returned when there is no information (e.g. a matched service) available. It's probably worthwhile making this clear. | Add the following text to the end of the paragraph on P67L2: "This notifies the non-AP and non-PCP STA that the required service is not available." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8018 | McCann, Stephen | 3000 | 9 | 11.25a.3.2 | 67 | 6 | T | No | 67 | 6 | 11.25a.3.2 |  |  | Stephen McCann |  |  | The last paragraph does not explain why the authentication and association procedure would be used. | Change the last paragraph to: "The SIC receives service information from the contents of the Service Information Response ANQP-element. If the service information is suitable, the non-AP and non-PCP STA might select the BSS and then proceed with the authentication and association procedure (see 11.3). If the service information is not suitable, requires verification or requires more information, the non-AP and non-PCP STA might proceed with the another solicited PAD procedure (see 11.25a.3). Otherwise the non-AP and non-PCP STA might terminate the network selection process. For futher examples see W.1." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8040 | Montemurro, Michael | 3000 | 9 | 4.5.9.2.3 | 23 | 54 | T | No | 23 | 54 | 4.5.9.2.3 |  |  | Stephen McCann |  |  | The text in this sub-clause and two subsequent subc-clauses do not accurately describe the behavior of the SIC and SIR. | at P23L54, Change "The SIC and SIR are used to exchange service information between higher layer entities above both the STAs." to "The SIC and SIR are used to exchange PAD service information between STAs." In 4.5.9.2.4, change: "The SIR contains information ..." to "The SIR is configured with information ..." "How the SIR obtains the information about services is outside the scope of this standard." to "The configuration of service information in the SIR is outside the scope of this standard." In 4.5.9.2.5, change: "The SIC initiates service discovery." To "The SIC initiates service discovery to obtain service information in behalf of higher layer entities above the STA. The configuration of service discovery information in the SIC is outside the scope of this standard." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8041 | Montemurro, Michael | 3000 | 9 | 11.25a.2 | 66 | 23 | T | No | 66 | 23 | 11.25a.2 |  |  | Stephen McCann |  |  | "How to proceed" is not descriptive enough in this context. | Change "to determine how to proceed" to "as input to network discovery and selection procedures." |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN
8043 | Montemurro, Michael | 3000 | 9 | 11.25a.3.2 | 67 | 1 | T | No | 67 | 1 | 11.25a.3.2 |  |  | Stephen McCann |  |  | "can" should be a "may" | change "can" to "may" |  | GEN | Procedures | [5 empty] | 2017-07-03 17:59 | GEN

## Miscellaneous
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8002 | McCann, Stephen | 3000 | 9 | 4.5.9.1 | 21 | 62 | T | No | 21 | 62 | 4.5.9.1 | [5 empty] | ANQP also performs network discovery in addition to network selection. | Change the start of the bullet point to read "Disocvery and selection of a suitable IEEE Std 802.11...." |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8003 | McCann, Stephen | 3000 | 9 | 6.3.73.2.2 | 28 | 24 | T | No | 28 | 24 | 6.3.73.2.2 | [5 empty] | IEEE 802.21-2008 has now been superceeded by IEEE 802.21-2017 | Replace "802.21-2008" with "802.21-2017". Alternatively just replace with ANQP as an example. Same change at P29L65, P31L45 and P33L33. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8005 | McCann, Stephen | 3000 | 9 | 9.4.2.217 | 41 | 25 | T | No | 41 | 25 | 9.4.2.217 | [5 empty] | This sentence mentions a Bloom filter, but it's not clear what a Bloom filter is. | Change "Bloom filter" to "Bloom Filter Bit Array". The same change should also be made to P42L38 |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8011 | McCann, Stephen | 3000 | 9 | 11.25.3.3.1 | 63 | 60 | T | No | 63 | 60 | 11.25.3.3.1 | [5 empty] | When the acronym is expanded, the text "ANQP query request" becomes "Access Network Query Protocol query request" which overworks the query. | Change all occurances of "ANQP query request" to "ANQP request". Similarly change all occurances of "ANQP query response" ro "ANQP response" |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8034 | Levy, Joseph | 3000 | 9 | 6.3.73.2.2 | 27 | 51 | E | No | 27 | 51 | 6.3.73.2.2 | [5 empty] | VendorSpecificInfo should not have been deleted from the MLME-GAS request. This removal will impact legacy GAS behavior. Note VendorSpecificInfo is only removed from the listing, it is still in the table. | Reinsert "VendorSpecificInfo" as the last primitive parameter. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8051 | Hamilton, Mark | 3000 | 9 | 9.4.2.217 | 41 | 24 | T | Yes | 41 | 24 | 9.4.2.217 | [5 empty] | This field represents parameters of "the Bloom filter". What Bloom filter? There is no antecedent for "the". | Replace "the Bloom filter" with "a Bloom filter that conveys the probabilistic data." |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8060 | Yang, Yunsong | 3000 | 9 | 4.5.9.2.5 | 24 | 15 | T | No | 24 | 15 | 4.5.9.2.5 | [5 empty] | Probe request is no longer used for PAD. | Delete "probe requests and" from the cited sentence. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8070 | Yang, Yunsong | 3000 | 9 | 9.6.8.37 | 50 | 59 | T | No | 50 | 59 | 9.6.8.37 | [5 empty] | CID 7151 questioned the need of GAS Comeback Delay field in the Group Addressed GAS Response frame (because the field will always be set to 0) and the proposed change included the removal of the field and related text. The resolution to CID 7151 was "Accepted". However, the GAS Comeback Delay field remains in D9.0. | Delete the row of GAS Comeback Delay from Table 9-325b. Delete the entire paragraph (describing GAS Comeback Delay field) on P51L23-L26. |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN
8072 | Yang, Yunsong | 3000 | 9 | 11.25.3.2.4 | 62 | 21 | T | No | 62 | 21 | 11.25.3.2.4 | [5 empty] | There are some redundancy and self-contradiction in "the Fragment ID sub field of the GAS Flags field set to one, and the Fragment ID field set to the fragment ID of the Query Response to be retransmitted". | Delete "one, and the Fragment ID field set to". |  | GEN | Miscellaneous | [5 empty] | 2017-07-03 17:59 | GEN

## MAC Privacy
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8019 | McCann, Stephen | 3000 | 9 | C.3 | 76 | 61 | T | No | 76 | 61 | C.3 |  |  | Dan Harkins |  |  | The MIB variable "dot11MACPrivacyActivated" does not appear to have been defined | Provide a definition of "dot11MACPrivacyActivated" in clause C.3 within the OBJECT-TYPE definitions |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8047 | Hamilton, Mark | 3000 | 9 | 4.5.4.10 | 21 | 31 | T | Yes | 21 | 31 | 4.5.4.10 |  |  | Dan Harkins |  |  | "a non-AP STA uses" implies all non-AP STAs will always do this. But, these privacy enhancements are not universally used. | Change "uses" to "may use" |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8053 | Hamilton, Mark | 3000 | 9 | 11.25a.1 | 65 | 31 | T | Yes | 65 | 31 | 11.25a.1 |  |  | Dan Harkins |  |  | Is this supposed to be a normative requirement? | Change "invokes" to "shall invoke" |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8055 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 30 | E | No | 68 | 30 | 12.2.10 |  |  | Dan Harkins |  |  | This sentence sounds like the complete list of times when the STA shall defer changing its MAC address, but it is not complete. | Add "during association to a BSS or ESS, or" before "during a transactional exchange" |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8056 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 38 | T | Yes | 68 | 38 | 12.2.10 |  |  | Dan Harkins |  |  | The requirement to change a STA's MAC address "prior" to establishing a connection is: 1) contradictory with 2 paragraphs down that says it is static during association to an ESS; 2) breaks any pre-association negotiations (pre-auth, FT over-the-DS, etc.; and 3) is ambiguous in terms of how much prior to establishing the connection, and what point is determined to "establishing a connection" (for example, should it be after the Authentication, but before Association? clearly, not.) | Change "shall" to "should", and add explanation that the change can only occur if there are no persistent agreements in place with the new BSS's AP. |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8057 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 53 | T | No | 68 | 53 | 12.2.10 |  |  | Dan Harkins |  |  | No need to generate 48 bits of random value, and then bash 2 of them to fixed values. Just generate 46 bits. | Change to "To set a random MAC address, a STA shall set the sixth bit ... and the seventh bit ... and shall assign a random 46-bit value to the remaining bits." |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN
8059 | Yang, Yunsong | 3000 | 9 | 4.5.4.10 | 21 | 33 | T | No | 21 | 33 | 4.5.4.10 |  |  | Dan Harkins |  |  | Regarding "Post-association, a non-AP STA uses a unique random MAC address ... for an established network connnection.", today, most STAs use their globally unique MAC addresses for post-association connection. Is the cited sentence meant to be a requirement (or at least a recommended practice) as a part of the MAC privacy enhancements in order not to reveal the globally unique MAC address of the STA? If it is intended to be a requirement or a recommended practice, should make it clear. | Please clarify. |  | GEN | MAC Privacy | [5 empty] | 2017-07-03 17:54 | GEN

## GAS Extension
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8045 | Hartman, Chris | 3000 | 9 | 11.25.3.2.3f | 59 | 45 | T | No | 59 | 45 | 11.25.3.2.3f |  |  | Mike Montemurro |  |  | The response specified in this clause is not time-bounded. The requesting STA may indicate it's Maximum Channel Time in the GAS Extension Element, but there is no requirement for the Responding STA to attempt to honor the requesting STA's time restrictions. | Add a sentence to subclause 11.25.3.2.3 f) along the following lines: "If a GAS Request frame contains a GAS Extension Element, the the responding STA shall attempt to transmit an individually addressed GAS Initial Response frame to the requesting STA within the indicated Maximum Channel Time." |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN
8052 | Hamilton, Mark | 3000 | 9 | 9.6.8.13 | 48 | 55 | T | Yes | 48 | 55 | 9.6.8.13 |  |  | Mike Montemurro |  |  | The new field (GAS Extension) in this Action format needs some text explanation. | Add a (probably short) paragraph to the end of 9.6.8.13 that describes the use of the GAS Extention field in this frame. |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN
8062 | Yang, Yunsong | 3000 | 9 | 9.4.1.9 | 38 | 36 | T | No | 38 | 36 | 9.4.1.9 |  |  | Mike Montemurro |  |  | GAS Extension element is introduced in GAS Comeback Request frame to request for re-transmission of missing GAS fragment. However, it is not clear how the requesting STA knows that the responding STA is capable of re-transmitting missing GAS fragment. Possible solutions: 1) A non-capable responding STA uses a new Status Code value in the GAS Comeback Response frame to indicate that it isn't capable of re-transmitting any missing GAS fragment when responding to a request to re-transmit missing GAS fragment, which means that the requesting STA doesn't know the responding STA's lack of such capability before-handed; 2) the responding STA indicates whether it is capable of re-transmitting missing GAS fragment before the requesting STA requests so. Such an indication can be a new Extended Capabilities bit or a new flag bit in the GAS Extension element in the first GAS Comeback Response frame whenever Query Response fragmentation is needed. | Consider one of the following remedies as described in the comment: a new Status code value (such as RETRANSMITTING GAS FRAGMENT NOT SUPPORTED), a new Extended Capabilities bit, a new flag bit in the GAS Extension element in (at least) the first GAS Comeback Response frame whenever Query Response fragmentation is required. |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN
8063 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 43 | 17 | T | No | 43 | 17 | 9.4.2.219 |  |  | Mike Montemurro |  |  | There are two problems in this sentence. First, there is no such thing called "group-addressed GAS Initial Response frame". Secondly, there are two possible ways to interpret this sentence. One is that the presence of the element in the GAS Initial Request frame indicates that the STA is capable of receiving Group-addressed GAS Response frame (so the capability is affirmed by the presence of the element). The alternative interpretation is that the GAS Extension element indicates whether the STA is capable of receiving Group-addressed GAS Response frame (so the capability, either yes or no, is indicated by the element, presumably by the Group-addressed GAS subfield in the GAS Flags field). The commenter believes that the alternative interpretation is in line with the definition of the Group-addressed GAS subfield on L55. However, also need to double-check with the added text on P54L34. | Change the cited sentence to read: "When present in the GAS Initial Request frame, the GAS Extension element indicates whether the STA is capable of receiving a Group Addressed GAS Response frame." And change the sentence on L55 to read: "Group-addressed GAS sub-field is set to 1 to indicate that the STA is capable of receiving Group Addressed GAS frames and is set to 0 otherwise." |  | GEN | GAS Extension | [5 empty] | 2017-07-03 17:58 | GEN

## Editorial
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8001 | Alessi, Julie | 3000 | 9 |  |  |  | E | No | [5 empty] | Lee Armstrong |  |  | Draft meets all editorial requirements. |  |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8004 | McCann, Stephen | 3000 | 9 | 9.4.1.9 | 38 | 33 | E | No | 38 | 33 | 9.4.1.9 |  |  | Lee Armstrong |  |  | The ANA values needs to be reserved | Update this ANA value |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8006 | McCann, Stephen | 3000 | 9 | 9.4.2.217 | 42 | 44 | E | No | 42 | 44 | 9.4.2.217 |  |  | Lee Armstrong |  |  | On this line, shold bloom filter have a capital "B" or not? | Edit the line to use a capital "B" on bloom filter or not. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8007 | McCann, Stephen | 3000 | 9 | 9.4.5.29 | 47 | 26 | E | No | 47 | 26 | 9.4.5.29 |  |  | Lee Armstrong |  |  | typo "Lenght" | Change to "Length" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8010 | McCann, Stephen | 3000 | 9 | 11.25.3.3.1 | 64 | 17 | E | No | 64 | 17 | 11.25.3.3.1 |  |  | Lee Armstrong |  |  | typo extra "7" | remove "7" from the "ANQP-element name" column in table 11-15 |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8012 | McCann, Stephen | 3000 | 9 | 11.25a.1 | 65 | 35 | E | No | 65 | 35 | 11.25a.1 |  |  | Lee Armstrong |  |  | typo "1s" | change "1s" to "1" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8014 | McCann, Stephen | 3000 | 9 | 11.25a.3.1 | 66 | 40 | E | No | 66 | 40 | 11.25a.3.1 |  |  | Lee Armstrong |  |  | typo "7" | remove the "7" from this line |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8015 | McCann, Stephen | 3000 | 9 | 11.25a.3.1 | 66 | 43 | E | No | 66 | 43 | 11.25a.3.1 |  |  | Lee Armstrong |  |  | I'm not sure what "The Interworking field ..." is referring to. | Change "The Interworking..." to "An Interworking..." |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8016 | McCann, Stephen | 3000 | 9 | 11.25a.3.2 | 66 | 45 | E | No | 66 | 45 | 11.25a.3.2 |  |  | Lee Armstrong |  |  | There's a spurious "7" in the title | Remove the "7" from the title |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8035 | Levy, Joseph | 3000 | 9 | 10.3.2.11.2 | 53 | 4 | E | No | 53 | 4 | 10.3.2.11.2 |  |  | Lee Armstrong |  |  | Editor instructions call out the wrong clause number 11.3.2.11.1 instead of 10.3.2.11.2. | Correct the clause number, as in comment. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8036 | Levy, Joseph | 3000 | 9 | 11.25.3.2.1 | 55 | 27 | E | No | 55 | 27 | 11.25.3.2.1 |  |  | Lee Armstrong |  |  | There seems to be a misuse capitalization: GAS Query Response, is not the name of a frame, hence I think it should be GAS query response. I believe this may need to be corrected in several other locations. | Change the case of: "GAS Query Response" to be "GAS query response" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8037 | Levy, Joseph | 3000 | 9 | 11.25.3.2.1 | 56 | 2 | E | No | 56 | 2 | 11.25.3.2.1 |  |  | Lee Armstrong |  |  | "Frame" is upper case, but it should be lower case "frame". | Change: "Frame" to be "frame" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8038 | Levy, Joseph | 3000 | 9 | 11.25.3.2.3 | 59 | 34 | E | No | 59 | 34 | 11.25.3.2.3 |  |  | Lee Armstrong |  |  | The term "GAS Extension information" is not a direct reference to the frame or element, hence "Extension" should not be upper case. | Change the case of "Extension" to "extension". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8039 | Levy, Joseph | 3000 | 9 | 11.25.3.2.4 | 62 | 19 | E | No | 62 | 19 | 11.25.3.2.4 |  |  | Lee Armstrong |  |  | "GAS Extension" is not referring to a frame or an element, therefore "Extension" should be lower case. | Change case of "Extension" to be "extension" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8042 | Montemurro, Michael | 3000 | 9 | 11.25a.3.2 | 66 | 48 | E | No | 66 | 48 | 11.25a.3.2 |  |  | Lee Armstrong |  |  | Minor editorial | change "request detailed" to "request detailed" (remove the additional space) |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8044 | Hartman, Chris | 3000 | 9 | 9.6.8.36 | 50 | 26 | E | No | 50 | 26 | 9.6.8.36 |  |  | Lee Armstrong |  |  | "The GAS Extension element indicates parameters that the AP or PCP may use to in transmiting a response back to the requesting STA." - "to in" is superfluous. | Change to either: "... may use to transmit...", or "... may use in transmitting". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8046 | Hamilton, Mark | 3000 | 9 | 3.1 | 18 | 47 | E | No | 18 | 47 | 3.1 |  |  | Lee Armstrong |  |  | Typo - meant "Insert the following new definition in Clause 3.1 ..." | Change "references" to "new defintion" and "2" to "3.1" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8048 | Hamilton, Mark | 3000 | 9 | 4.5.9.2.2 | 23 | 39 | E | No | 23 | 39 | 4.5.9.2.2 |  |  | Lee Armstrong |  |  | Figure numbering got messed up. | Change Figure 5 to Figure 4-15b. Also, fix the reference in text at P22.64. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8049 | Hamilton, Mark | 3000 | 9 | 9.4.1.9 | 38 | 34 | E | Yes | 38 | 34 | 9.4.1.9 |  |  | Lee Armstrong |  |  | <ANA> needs to be replaced with a value by this point in Sponsor Ballot. | Replace "<ANA>" with the appropriate value. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8054 | Hamilton, Mark | 3000 | 9 | 12.2.10 | 68 | 27 | E | No | 68 | 27 | 12.2.10 |  |  | Lee Armstrong |  |  | "membership" in what is ambiguous. | Insert "BSS" before "membership" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8058 | Hamilton, Mark | 3000 | 9 | C.3 | 77 | 49 | E | Yes | 77 | 49 | C.3 |  |  | Lee Armstrong |  |  | Stray sentence. | Delete "GAS Extension Support Activated." |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8061 | Yang, Yunsong | 3000 | 9 | 6.3.73.4.2 | 31 | 64 | E | No | 31 | 64 | 6.3.73.4.2 |  |  | Lee Armstrong |  |  | "GAS extension element" should be "GAS Extension element". | Change "extension" to "Extension" |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8064 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 43 | 64 | E | No | 43 | 64 | 9.4.2.219 |  |  | Lee Armstrong |  |  | The sentence "The Response Map Flag sub-field is ..." should start a new paragraph. | Use the cited sentence to start a new paragraph below. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8065 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 44 | 7 | E | No | 44 | 7 | 9.4.2.219 |  |  | Lee Armstrong |  |  | "The Fragment ID field in the GAS Comeback Request indicates ..." is not the right expression. | Change "The Fragment ID field in the GAS Comeback Request indicates" to "The Fragment ID field, when present in the GAS Comeback Request, indicates". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8066 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 44 | 21 | E | No | 44 | 21 | 9.4.2.219 |  |  | Lee Armstrong |  |  | The last sentence of this paragraph should be in the previous paragraph, since it talks about the value of the Number of Response Map Duples field. | Delete the cited sentence. And add the following to the end of previous paragrah on L14: "When present, the Number of Response Map Duples field is set to a nonzero value and the value of zero is reserved." |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8067 | Yang, Yunsong | 3000 | 9 | 9.4.2.219 | 44 | 40 | E | No | 44 | 40 | 9.4.2.219 |  |  | Lee Armstrong |  |  | Missing period (".") at the end. | Add a period at the end of the sentence. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8068 | Yang, Yunsong | 3000 | 9 | 9.4.5.29 | 47 | 14 | E | No | 47 | 14 | 9.4.5.29 |  |  | Lee Armstrong |  |  | "length" in the figure should be "Length" since it is a part of the field name. | Change "length" to "Length". |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8073 | Yang, Yunsong | 3000 | 9 | 11.25a.3.1 | 66 | 40 | E | No | 66 | 40 | 11.25a.3.1 |  |  | Lee Armstrong |  |  | An extra "7" | Delete "7" on L40 and L45. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN
8075 | Yang, Yunsong | 3000 | 9 | W.1 | 80 | 34 | E | No | 80 | 34 | W.1 |  |  | Lee Armstrong |  |  | An extra "can" at the end. | Delete "can" at the end of the sentence. |  | EDITOR | Editorial | [5 empty] | 2017-07-03 17:53 | GEN

## CAG
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8050 | Hamilton, Mark | 3000 | 9 | 9.4.2.177 | 40 | 30 | T | Yes | 40 | 30 | 9.4.2.177 |  |  | Yunsong Yang |  |  | The entries in the new Table 9-258b do not match (in values or meaning) the entries in Table 9-214. Table 9-214 was used in 802.11-2016 as the definition of the CAG Tuple field. The backward compatibility mechanism to handle this change in semantics is not clear. | Clarify how this field is to interpreted to provide backward compatibility. |  | GEN | CAG | [5 empty] | 2017-07-03 17:53 | GEN
8069 | Yang, Yunsong | 3000 | 9 | 11.25.3.2.2 | 58 | 12 | T | No | 58 | 12 | 11.25.3.2.2 |  |  | Yunsong Yang |  |  | "a cached version" may be confused with the "CAG Version" later. Similar issue also exists on P56L57. The commenter believes that "a cached version" here refers to "a cached version" of the information that the requesting STA requests, while a "CAG Version" refers to a number. Therefore, from English PoV, adding "of" after "a cached version" would make it sufficiently clear. | Add "of" after "a cached version". And add "of" after "a cached version" on P56L57 as well. |  | GEN | CAG | [5 empty] | 2017-07-03 17:53 | GEN
8071 | Yang, Yunsong | 3000 | 9 | 11.25.3.2.1 | 56 | 61 | T | No | 56 | 61 | 11.25.3.2.1 |  |  | Yunsong Yang |  |  | It is ambiguous which Advertisement Server is "relevant". | Change "a relevant Advertisement Server," to "a relevant Advertisement Server as indicated by the Advertisement Protocol and Server ID, which is provided by the requesting STA in the same CAG Tuple field that contains the cached CAG Version," |  | GEN | CAG | [5 empty] | 2017-07-03 17:53 | GEN

## Annex W
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8008 | McCann, Stephen | 3000 | 9 | 9.4.5.28 | 46 | 42 | T | No | 46 | 42 | 9.4.5.28 |  |  | Stephen McCann |  |  | There is a worked example of how the request and response attribute fields could look in document https://mentor.ieee.org/802.11/dcn/17/11-17-0632-00-00aq-aligning-11aq-with-higher-layer-service-discovery-protocol.ppt | It would be useful to create an 11aq annex with some of these worked examples |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8022 | McCann, Stephen | 3000 | 9 | W.1 | 79 | 16 | T | No | 79 | 16 | W.1 |  |  | Stephen McCann |  |  | Remove the reference to clause 11.25.3.2.16 as it no longer exists | Remove the reference to 11.25.3.2.16 from this line. |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8023 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 24 | T | No | 79 | 24 | W.1.1 |  |  | Stephen McCann |  |  | The applications are running on a STA and that should be mentioned. | Change the start of the paragraph to "STA applications that run...". The same change can also be made to the start of W1.2. |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8024 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 27 | T | No | 79 | 27 | W.1.1 |  |  | Stephen McCann |  |  | It's not a "solicited PAD search" | Change "solicited PAD search" to solicted PAD procedure" |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8025 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 52 | T | No | 79 | 52 | W.1.1 |  |  | Stephen McCann |  |  | What does the "Service Information Response Attribute subfield" do? | Add the following text to the end of the paragraph: "This subfield contains information about the service(s) that was requested." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8026 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 40 | T | No | 79 | 40 | W.1.1 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the sentence to read "Upon receiving a Beacon or DMG Beacon frame, the SIC in a non-AP and non-PCP STA processes the Service Hash and Service Hint elements..." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8027 | McCann, Stephen | 3000 | 9 | W.1.1 | 79 | 44 | T | No | 79 | 44 | W.1.1 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the paragraph to read " If the probability of false positives as indicated in the False Positive Probability Range field of the Service Hint element is considered relatively high by the SIC in the non-AP and non-PCP STA (see Figure W-1), the SIC can send a Service Information Request ANQP-element through the non-AP and non-PCP STA, containing Service Information Request Attribute subfield to confirm if a service is reachable through the AP or PCP. |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8028 | McCann, Stephen | 3000 | 9 | W.1.1 | 80 | 1 | T | No | 80 | 1 | W.1.1 |  |  | Stephen McCann |  |  | This sentence should be moved down to the paragraph after Figure W-1 | As per comment |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8029 | McCann, Stephen | 3000 | 9 | W.1.1 | 80 | 29 | T | No | 80 | 29 | W.1.1 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the paragraph to read " If the probability of false positive as indicated in False Positive Probability Range field of the Service Hint element is considered relatively low by the SIC in the non-AP and non-PCP STA, the SIC may choose the AP or PCP as a candidate BSS. The SIC may choose to send a Service Information Request ANQP-element to confirm if a service is reachable through the AP or PCP as shown in Figure W-1. Based on the results of these steps the SIC in the non-AP and non-PCP STA may choose to associate with the BSS." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8030 | McCann, Stephen | 3000 | 9 | W.1.1 | 80 | 40 | T | No | 80 | 40 | W.1.1 |  |  | Stephen McCann |  |  | typo "containing Service" | change text to "containing a Service" |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8031 | McCann, Stephen | 3000 | 9 | W.1.1 | 81 | 1 | T | No | 81 | 1 | W.1.1 |  |  | Stephen McCann |  |  | This sentence should be moved down to the paragraph after Figure W-1 | As per comment |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8032 | McCann, Stephen | 3000 | 9 | W.1.2 | 81 | 32 | T | No | 81 | 32 | W.1.2 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the text "whereby the non-AP..." to "whereby the SIC in the non-AP..." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN
8033 | McCann, Stephen | 3000 | 9 | W.1.2 | 81 | 38 | T | No | 81 | 38 | W.1.2 |  |  | Stephen McCann |  |  | It's the SIC that should determine service discovery behaviour on the STA. | Change the sentence to read: "Following these service message exchanges the SIC in the non-AP and non-AP STA can make an informed decision about choosing to associate to the AP or PCP." |  | GEN | Annex W | [5 empty] | 2017-07-03 17:56 | GEN

## Annex BnC
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8020 | McCann, Stephen | 3000 | 9 | C.3 | 77 | 43 | T | No | 77 | 43 | C.3 |  |  | Stephen McCann |  |  | The MIB variable "dot11GASExtensionImplemented" needs to be added to the SEQUENCE list starting on P74 | Add "dot11GASExtensionImplemented" to the SEQUENCE list starting on P74 |  | GEN | Annex BnC | [5 empty] | 2017-07-03 17:56 | GEN
8021 | McCann, Stephen | 3000 | 9 | C.3 | 78 | 4 | T | No | 78 | 4 | C.3 |  |  | Stephen McCann |  |  | The MIB vairables "dot11GASExtensionImplemented" and "dot11MACPrivacyActivated" need to be added to the PADComplianceGroup | Add the two MIB variables per the comment |  | GEN | Annex BnC | [5 empty] | 2017-07-03 17:56 | GEN
8074 | Yang, Yunsong | 3000 | 9 | B.4.20 | 73 | 10 | T | No | 73 | 10 | B.4.20 |  |  | Stephen McCann |  |  | TGaq should consider a separate PICS entry for support of re-transmission of missing Query Response fragment, because it isn't the same as support of Group-addressed GAS Response. | Add a new entry for "Re-transmission of missing Query Response fragment" |  | GEN | Annex BnC | [5 empty] | 2017-07-03 17:56 | GEN