## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/0956r6
Venue Date: | September 2017
First Author: | Emily Qi (Intel Corporation)
Subject: | REVmd Working Group Comments for EDITOR ad-hoc
Full Date: | 2017-09-14
Author(s): | Name(s) | Emily Qi
| Company | Intel Corporation
Address
Phone:
Fax:
| email: | emily.h.qi@intel.com
Abstract:
|  |  | Tab Name | Number of comments
|  |  | Editor comments | 75
This document contains comments in the "EDITOR ad hoc" group, submitted on REVmd Comment Collections and WG Ballots on the published IEEE Std 802.11-2016 and subsequent amendments.

## Motion-C
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
28 | Graham Smith | 25 | 0.1 | 4.2.5 | 187 | 20 | E | N | 187 | 20 | 4.2.5 |  | J |  |  |  | "handle" replace with "handles" or delete the "the" in front of "IEEE Std" | As per comment | REJECTED (EDITOR: 2017-09-14 03:49:00Z). Reject Reason: IEEE publication editor has approved this text multiple times. No change is needed. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 03:49:48Z - status set to: Ready for Motion EDITOR: 2017-07-13 11:39:39Z - status set to: Discuss |  |  |  | 2017-09-14 03:50 | EDITOR
100 | Jouni Malinen | 25 | 0.1 | 9.2.4.1.3 | 675 | 22 | E | N | 675 | 22 | 9.2.4.1.3 |  | J |  |  |  | Table 9-1 uses binary numbers to identify Type and Subtype values. IMHO, it would be clearer to refer to these fields as base-10 integers instead (i.e., 00 --> 0, 01 --> 1, 10 --> 2, 11 --> 3; and similarly for the 4-bit Subtype values). | Consider replacing binary values for multi-bit-integers in Table 9-1 and all similar tables throughout the draft with base-10 integers. | REJECTED (EDITOR: 2017-09-14 03:49:56Z). Reject Reason: Do not see any benefit to change to base-10 integers in Table 9-1. Table 9-1 with this format has been there since IEEE 802.11-1999 (at least), these is no need to change to a different format. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 03:50:32Z - status set to: Ready for Motion EDITOR: 2017-07-12 11:40:24Z - status set to: Discuss EDITOR: 2017-07-10 13:29:18Z - status set to: Review EDITOR: 2017-07-10 13:28:06Z - status set to: Discuss REJECTED (EDITOR: 2017-07-10 13:12:04Z)- Do not see any benefit to change base-10 integers in Table 9-1. The Table 9-1 with this format has been there since IEEE 802.11-2007 (at least), these is no need to change a different format. |  |  |  | 2017-09-14 03:51 | EDITOR
119 | Mark Hamilton | 25 | 0.1 | 3.1 | 139 | 4 | E | Y | 139 | 4 | 3.1 |  | J |  |  |  | "unspecified ", "not specified", "implementation dependent", "outside the scope", and "beyond the scope" - all are okay, but do we need all these different ways to say it? | Choose one (or maybe two?) and change the others to match | REJECTED (EDITOR: 2017-09-14 19:36:52Z) - REJECTED (EDITOR: 2017-07-10 12:41:39Z) Reject Reason: The proposed resolution does not provide changes to the draft that can be immediately adapted to satisfy the comment. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 03:54:45Z - status set to: Ready for Motion EDITOR: 2017-09-14 03:54:43Z - status set to: Discuss EDITOR: 2017-07-10 13:36:41Z - status set to: Discuss EDITOR: 2017-07-10 13:29:41Z - status set to: Review Suggestion: Reject, "Not Specified", "implementation dependent" and "outside of the scope" are different. Using these different ways to say it is appropriate . |  |  |  | 2017-09-14 19:37 | EDITOR
147 | Mark RISON | 25 | 0.1 | 9.4.2.21.10 | 877 | 37 | E | N | 877 | 37 | 9.4.2.21.10 |  | J |  |  |  | There should not be two Maximum Age Subelement definitions | Define a new "Fields that are not elements" for this, and then make 877.28 and 890.26 refer back to this | REJECTED (EDITOR: 2017-09-14 03:50:44Z). Reject Reason: A subelement is a “local” parameter (subelement). The subelement usage is in the scope of a particular field or element. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 03:51:39Z - status set to: Ready for Motion EDITOR: 2017-06-24 23:23:40Z - status set to: Discuss |  |  |  | 2017-09-14 03:52 | EDITOR
210 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | There are 3 instances of " transmission of an A-MPDU or frame in", but though this is technically defensible when followed by "a PSDU" it is confusing (the usual layering confusion: an A-MPDU contains frames (a.k.a. MPDUs); it is not at the same level) and the middle instance is not even followed by "a PSDU" anyway | Change "QSRC[AC] shall be incremented every time transmission of an A-MPDU or frame in a PSDU of length less than or equal to dot11RTSThreshold fails, regardless of the presence or value of the DEI field. When dot11RobustAVStreamingImplemented is true, QSDRC[AC] shall be incremented every time transmission of an A-MPDU or frame in which the HT variant HT Control field is present," to "QSRC[AC] shall be incremented every time transmission of a PSDU of length less than or equal to dot11RTSThreshold fails, regardless of the presence or value of the DEI field. When dot11RobustAVStreamingImplemented is true, QSDRC[AC] shall be incremented every time a transmission in which the HT variant HT Control field is present," Change "QLRC[AC] shall be incremented every time transmission of an A-MPDU or frame in a PSDU" to "QLRC[AC] shall be incremented every time transmission of a PSDU" | REVISED (EDITOR: 2017-09-14 02:36:51Z). See comment resolution under CID 210 in https://mentor.ieee.org/802.11/dcn/17/11-17-1191-05-000m-cc25-proposed-resolutions-for-editorial-comments.doc. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 02:37:38Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:36:45Z - status set to: Discuss |  |  |  | 2017-09-14 02:38 | EDITOR
257 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | It is not necessary in Clause 9 to say things are done according to the conventions in 9.2.2. It is confusing to do so, because it implies something unusual is happening | Delete the sentences like "The order of the Organization Identifier field is described in 9.2.2 (Conventions)." or "All fields use the bit convention from 9.2.2 (Conventions)." or " It is encoded following the conventions in 9.2.2 (Conventions)." at [mc/D6.0 references] 685.46, 827.4, 828.41, 881.22, 881.26, 881.62, 882.43, 883.44, 999.59, 999.64, 1007.33, 1083.20, 1101.58, 1101.62, 1130.33, 1144.47. Delete the NOTE at 706.48. Change 880.20 to say "The MDID field contains an arbitrary value." At 951.39 delete ", encoded according to 9.2.2 (Conventions)". At 1085.14 delete " and is encoded following the conventions given in 9.2.2 (Conventions)" | REJECTED (EDITOR: 2017-09-14 02:36:13Z) Reject Reason: There is no confusion. It helps the ready who hasn’t read 9.2.2. The text is correct as written. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 02:37:47Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:26:26Z - status set to: Discuss |  |  |  | 2017-09-14 02:38 | EDITOR
260 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | Like "RSNE", other abbreviations for elements should either never or always be used | Globally replace all instances of the expansion of MME, FFE, FTE, MDE, PWE, RDE and TIE with their abbreviation, except in Clause 3 | REJECTED (EDITOR: 2017-09-14 02:35:51Z). Reject reason: The proposed resolution does not provide changes to the draft that can be immediately adapted to satisfy the comment. Applying the proposed will cause the loss of the clause titles. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 02:37:53Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:35:54Z - status set to: Discuss |  |  |  | 2017-09-14 02:38 | EDITOR
270 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | " The Measurement Report Element field is included in the Location Track Notification frame if the Location Parameters Element field contains a Location Indication Options subelement" -- move this condition to be in the table with all the other conditions (Table 9-318---Location Parameters Element field for Location Track Notification frame) | As it says in the comment | REJECTED (EDITOR: 2017-09-14 02:35:14Z). Reject reason: Table 9-328 is for allowed subelements for the Location Parameters Element field. The cited text is for the Measurement Report Element field, which is different context. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 02:38:10Z - status set to: Ready for Motion EDITOR: 2017-07-12 11:39:11Z - status set to: Discuss EDITOR: 2017-06-24 22:43:54Z - status set to: Review REJECTED (EDITOR: 2017-06-19 22:56:46Z): Table 9-328 is for Allowed subelements, not for Element. |  |  |  | 2017-09-14 02:38 | EDITOR
277 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | Some of the ResultCodes in the SAP have underscores (e.g. JOIN_FAILURE_TIMEOUT, NOT_SUPPORTED) some not (e.g. AUTH FAILURE TIMEOUT, ANTI-CLOGGING TOKEN REQUIRED) | Remove the underscores from all the ResultCodes in the SAP | REJECTED (EDITOR: 2017-09-14 02:34:19Z). Reject Reason: There is no rule on whether ResultCode should include underscores or not. Uderscores are used for ResultCode everywhere. No need to remove them. The current usage create no confusion. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 02:38:16Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:43:36Z - status set to: Discuss |  |  |  | 2017-09-14 02:38 | EDITOR
278 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | There are about 20 instances of "zero or one", but some are followed by the singular and some are followed by the plural | Either always follow with plural or always with singular | REVISED (EDITOR: 2017-09-14 02:32:33Z). Change to use “plural”. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 02:33:00Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:42:35Z - status set to: Discuss |  |  |  | 2017-09-14 02:33 | EDITOR
327 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | There seem to be at least three flavours of awake window: mesh, TDLS and DMG. The first seems to be so denoted, but the others not | Add "TDLS" or "DMG" before "awake window" where "mesh" is not present there | REJECTED (EDITOR: 2017-09-14 03:52:40Z). Reject Reason: Proposed changes are not specific and do not handle the IBSS awake window case. | EDITOR |  | Ready for Motion | EDITOR: 2017-09-14 03:53:03Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:41:14Z - status set to: Discuss |  |  |  | 2017-09-14 03:53 | EDITOR

## Ready for Motion (20170913)
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
123 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | It is not necessary to specify the size of an integer when the size is given in the Figure descibing the field | Delete the "x-bit" or "xxx bit" before "unsigned integer" | REVISED (EDITOR: 2017-08-04 22:45:36Z) In Clause 6, delete the "x-bit unsigned" or "xxx bit unsigned " before "integer", and change "integer" to “Integer". In Clause 9, if the size of an integer is given in the figure and the cited text is in the same subclause of the figure, delete the "x-bit" or "xxx bit" before "unsigned integer". Otherwise, no change. | EDITOR |  | Ready for Motion | EDITOR: 2017-08-04 22:45:46Z - status set to: Ready for Motion EDITOR: 2017-07-13 15:41:24Z - status set to: Discuss EDITOR: 2017-07-12 11:22:36Z - status set to: Review EDITOR: 2017-06-17 21:27:26Z - status set to: Submission Required REVISED (EDITOR: 2017-07-12 11:20:14Z) - If the size of an integer is given in the figure and the cited text is in the same subclause of the figure, delete the "x-bit" or "xxx bit" before "unsigned integer". Otherwise, no change. |  |  |  | 2017-08-04 22:46 | EDITOR
164 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | It is confusing to have both a "Beamforming Report Poll frame" and "BRP frame" | Change "BRP frame" to "Beam Refinement Protocol frame" throughout the draft | REJECTED (EDITOR: 2017-08-04 22:46:09Z)- Reject reason: In clause 3.4 Abbreviations and acronyms, BRP is defined as “beam refinement protocol”. It should be clear that BRP frame is for “beam refinement protocol” frame. There is no need to rename it. | EDITOR |  | Ready for Motion | EDITOR: 2017-08-04 22:46:26Z - status set to: Ready for Motion EDITOR: 2017-07-13 11:40:04Z - status set to: Discuss EDITOR: 2017-06-24 22:33:26Z - status set to: Review |  |  |  | 2017-08-04 22:46 | EDITOR
169 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | There is no point in the distinction between Measurement Request frames and Radio Measurement Request frames | Delete "Radio" in "Radio Measurement Request" and "Radio Measurement Report" throughout the draft | REJECTED (EDITOR: 2017-08-04 22:46:36Z)- Reject reason: There are differences between the Measurement Request/Report frame and Radio Measurement Request/Report frame. The Measurement Request/Response frames are Spectrum management Action frames, see 9.6.2. The Radio Measurement Request/Report frames are Radio Measurement action frames, see 9.6.7. | EDITOR |  | Ready for Motion | EDITOR: 2017-08-04 22:46:44Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:38:29Z - status set to: Discuss |  |  |  | 2017-08-04 22:47 | EDITOR
203 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There is a definition for "DMG STA", namely "A STA whose radio transmitter is capable of transmitting and receiving DMG physical layer (PHY) protocol data units (PPDUs)." However, there is no definition for "$PHY STA", where $PHY is "DSSS", "HR/DSSS", "OFDM", "ERP", "HT", "VHT" or "TVHT" as "A STA whose radio transmitter is capable of transmitting and receiving DMG physical layer (PHY) protocol data units (PPDUs)." There is absolutely no reason to have the "DMG STA" definition | Delete the "DMG STA" definition | ACCEPTED (EDITOR: 2017-08-04 22:46:51Z) | EDITOR |  | Ready for Motion | EDITOR: 2017-08-04 22:46:53Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:37:09Z - status set to: Discuss |  |  |  | 2017-08-04 22:47 | EDITOR
204 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | There is a definition for "DMG AP", "DMG BSS". We don't do this for other PHYs. There is absolutely no reason to have these definitions | Delete the "DMG AP" and "DMG BSS" definitions | REJECTED (EDITOR: 2017-08-04 22:46:56Z)- Reason: In the usage of <adjective> AP and <adjective> BSS, the situation is not always clear, without a definition. In the case of DMG BSS, confusion can also arise from whether a PBSS is a type of DMG BSS or not. | EDITOR |  | Ready for Motion | EDITOR: 2017-08-04 22:47:11Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:37:01Z - status set to: Discuss |  |  |  | 2017-08-04 22:47 | EDITOR
208 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | In two locations, "elements" is referring to a parameter, not an element | Make the changes shown in 16/0839r3 under CID 8145 | REVISED (EDITOR: 2017-08-04 22:47:26Z)- At 348.40, 349.40: change “elements” to “parameters”. At 352.35: change “protection elements” to “ProtectDescriptors”. At 352.38: change “Protectlist” to “ProtectDescriptor”. | EDITOR |  | Ready for Motion | EDITOR: 2017-08-04 22:47:38Z - status set to: Ready for Motion EDITOR: 2017-07-12 11:26:37Z - status set to: Discuss EDITOR: 2017-06-24 23:42:02Z - status set to: Submission Required. I cannot find locations and reference in 16/0839r3. |  |  |  | 2017-08-04 22:48 | EDITOR
229 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | There are 14 instances of "may cause". However, this should only be used when this is a choice open to the implementation rather than the possible result of something. The referenced location is only an exemplar | Change "may cause" to "might cause" unless it's really an implementation choice | REVISED (EDITOR: 2017-08-18 16:06:22Z) - Accept proposed changes, except following locations: 1551.47, 2136.27 (D0.2). ACCEPTED (EDITOR: 2017-06-17 21:49:13Z) | EDITOR |  | Ready for Motion | EDITOR: 2017-08-18 16:08:32Z - status set to: Ready for Motion |  | EDITOR: 2017-08-18 16:07:41Z - Editor need to remove changes in those two locations (in D0.2). EDITOR2: 2017-07-29 09:19:13Z - Reviewed EDITOR: 2017-07-24 22:17:55Z |  | 2017-08-18 16:10 | EDITOR
243 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V | Mark Rison |  |  | "is shown in" (Figure, Table, etc.) or similar wooly statements ("is illustrated in") should be "is defined in" (at least in Clause 9 and the cases where the figure/table is the thing that normatively defines the structure/valid values) | As it says in the comment | REVISED (EDITOR: 2017-08-18 15:54:22Z) - See comment resolution in 11-17-1243-02-000m-resolutions-for-some-comments-on-11md-d0-1-cc25.docx | EDITOR |  | Ready for Motion | EDITOR: 2017-08-18 15:56:35Z - status set to: Ready for Motion EDITOR: 2017-07-11 06:14:22Z - status set to: Discuss EDITOR: 2017-06-24 22:35:32Z - status set to: Review |  |  |  | 2017-08-18 16:14 | EDITOR
248 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | Should common words in field names (e.g. "of", "in", "per") be upper- or lower-case? E.g. "FTMs per Burst" v. "Format And Bandwidth" at 1076.3 (this is just an example, not a complete set) | Be consistent | REJECTED (EDITOR: 2017-08-18 16:15:23Z). Reject Reason: There is no style guidance for function words (of, in etc… ) in the field name. The proposed resolution does not provide changes to the draft that can be immediately adapted to satisfy the comment. | EDITOR |  | Ready for Motion | EDITOR: 2017-08-18 16:15:44Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:41:55Z - status set to: Discuss |  |  |  | 2017-08-18 16:16 | EDITOR
249 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are about 70 instances of "when a valid" -- what defines validity? | Delete "valid" in all instances | ACCEPTED (EDITOR: 2017-08-04 22:45:04Z) | EDITOR |  | Ready for Motion | EDITOR: 2017-08-04 22:45:06Z - status set to: Ready for Motion EDITOR: 2017-07-12 11:39:51Z - status set to: Discuss EDITOR: 2017-06-24 22:34:37Z - status set to: Review REJECTED (EDITOR: 2017-06-24 22:34:25Z)- Validity depends on the context. |  |  |  | 2017-08-04 22:45 | EDITOR
254 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | Is the subfield called "FMS Counters" or "FMS Counter"? I think the latter | Use "FMS Counter" and say "field". [In 802.11mc/D6.0: Delete the "s" in "FMS Counters" at 946.1 (rightmost). Add "field" after "FMS Counter" at 946.1 (rightmost) and 946.16. At 946.6, 1594.23 (2x) lowercase "Counter". At 1594.19, 1594.23, 1595.5 (2x), 1595.7, 1595.11, 1595.56, 1596.17 lowercase "Stream"] | REVISED (EDITOR: 2017-08-18 16:16:15Z). See comment resolution provided in 11-17-1191-01-000m-CC25-ProposedResolutions-for-EditorialComments.doc. | EDITOR |  | Ready for Motion | EDITOR: 2017-08-18 16:17:02Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:26:50Z - status set to: Discuss |  |  |  | 2017-08-18 16:17 | EDITOR
261 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | J |  |  |  | "intended for" is a bit vague | Change to "addressed to" throughout | REJECTED (EDITOR: 2017-08-18 15:59:02Z) - Reject Reason:The proposed change introduces errors into the draft. For example, 1981.1 and 1480.19 show the problem the change caused in d0.2. ACCEPTED (EDITOR: 2017-06-17 21:54:08Z) | EDITOR |  | Ready for Motion | EDITOR: 2017-08-18 16:01:18Z - status set to: Ready for Motion EDITOR: 2017-06-24 22:42:25Z - status set to: Review |  | EDITOR: 2017-08-18 15:59:17Z - Editor need to redo this comment. remove all changes made in D0.2. EDITOR2: 2017-07-29 09:12:45Z - Reviewed EDITOR: 2017-07-24 22:46:47Z- No change to "If the TSPEC element is intended for EDCA Admission Control, the Maximum Service Interval field is used to indicate a latency limit,…" and "At the end of the ATIM window duration resume the backoff for any pending frames intended for transmission outside the ATIM window." . |  | 2017-08-18 16:06 | EDITOR
269 | Mark RISON | 25 | 0.1 | 11.33.1 | 2001 | 25 | E | N | 2001 | 25 | 11.33.1 |  | J |  |  |  | " the Capabilities element, the Operation element," -- there are no such elements | Prepend "DMG" to both | REJECTED (EDITOR: 2017-08-18 16:02:58Z) - Reject Reason: the capabilities and operation element being referred to may or may not be the DMG elements. ACCEPTED (EDITOR2: 2017-06-24 21:22:31Z) | EDITOR |  | Ready for Motion | EDITOR: 2017-08-18 16:04:28Z - status set to: Ready for Motion |  | EDITOR: 2017-08-18 16:03:55Z - Editor need to remove all changes that were made in D0.2. EDITOR: 2017-07-26 17:43:42Z -Reviewed EDITOR2: 2017-07-17 21:40:56Z - |  | 2017-08-18 16:05 | EDITOR

## Comments for approving(201707)
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
13 | Emily Qi | 25 | 0.1 | 9.6.24.2 | 1389 | 8 | E | Y | 1389 | 8 | 9.6.24.2 |  | A |  |  |  | In the field "FILS IP Address Assignment elements", "elements" should be "Element". Also, the reference doesn't need to be included in the table. | At 1389.8, Change "FILS IP Address Assignment elements (defined in 9.4.2.185 (FILS IP Address Assignment element(11ai)))" to "FILS IP Address Assignment Element" . At 1389.22, change " The FILS IP Address Assignment element carries the FILS parameters for IP address assignment and DNS server information." to "The FILS IP Address Assignment Element field contains one or more FILS IP Address Assignment elements as defined in 9.4.2.185 (FILS IP Address Assignment element)." | ACCEPTED (EDITOR: 2017-06-24 23:36:30Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:36:41Z - status set to: Review |  |  |  | 2017-06-24 23:37 | EDITOR
18 | Graham Smith | 25 | 0.1 | 6.3.3.3.2. | 277 | 12 | E | N | 277 | 12 | 6.3.3.3.2. |  | A |  |  |  | 6.3.3.3.2. P277L12 L17 L21 L26 L32 L38 L43 L49 "probe response" should be "Probe Response" P279L29 L34 "probe request" should be "Probe Request" | "probe request" should be "Probe Request" | ACCEPTED (EDITOR: 2017-06-24 23:06:16Z) | EDITOR | [6 empty] | 2017-06-24 23:06 | EDITOR
19 | Graham Smith | 25 | 0.1 | 4.5.3.3 | 225 | 18 | E | N | 225 | 18 | 4.5.3.3 |  | A |  |  |  | "... authenticate and associate with the AP with reduced number of frame transmissions." Add "a" between "with" and "reduced" to read "with a reduced number ..." | At cited text, add "a" between "with" and "reduced" to read "with a reduced" | ACCEPTED (EDITOR: 2017-06-24 23:05:11Z) | EDITOR | [6 empty] | 2017-06-24 23:05 | EDITOR
21 | Graham Smith | 25 | 0.1 | 4.5.4.8 | 229 | 22 | E | N | 229 | 22 | 4.5.4.8 |  | A |  |  |  | "When FILS authentication is used during a handover across mobility domains, the overhead incurred during the FT initial mobility domain association in an RSN is further reduced." Seems backward. | Replace cited with "During a handover across mobility domains, the overhead incurred during the FT initial mobility domain association in an RSN can be reduced using FILS authentication." | ACCEPTED (EDITOR: 2017-06-24 23:06:05Z) | EDITOR | [6 empty] | 2017-06-24 23:06 | EDITOR
27 | Graham Smith | 25 | 0.1 | 4.2.4 | 187 | 6 | E | N | 187 | 6 | 4.2.4 |  | V |  |  |  | Delete "actually" or replace with "might" (prefer deletion) | As per comment | REVISED (EDITOR: 2017-06-24 23:03:07Z): at 187.6, delete "actually". | EDITOR | [6 empty] | 2017-06-24 23:05 | EDITOR
28 | Graham Smith | 25 | 0.1 | 4.2.5 | 187 | 20 | E | N | 187 | 20 | 4.2.5 |  | A |  |  |  | "handle" replace with "handles" or delete the "the" in front of "IEEE Std" | As per comment | ACCEPTED (EDITOR: 2017-06-19 23:09:39Z) | EDITOR | [6 empty] | 2017-06-19 23:10 | EDITOR
86 | Jouni Malinen | 25 | 0.1 | 9.6.11 | 1308 | 59 | E | N | 1308 | 59 | 9.6.11 |  | A |  |  |  | Table 9-349 (Public Action field values defined for Protected Dual of Public Action frames) claims values 16 and 17 be reserved even though they are assigned for QAB Request/Response. | Replace "14-17" with "14-15" for the Reserved row in Table 9-349. | ACCEPTED (EDITOR: 2017-06-24 23:35:59Z) | EDITOR | [6 empty] | 2017-06-24 23:36 | EDITOR
89 | Jouni Malinen | 25 | 0.1 | 9.4.2.158.2 | 1167 | 54 | E | N | 1167 | 54 | 9.4.2.158.2 |  | A |  |  |  | Incorrect MIB variable name used in NOTE 11 of Table 9-250. | Replace "dot11VHTExtendedNSSCapable" with "dot11VHTExtendedNSSBWCapable" in NOTE 11 in Table 9-250. | ACCEPTED (EDITOR: 2017-06-24 23:27:32Z) | EDITOR | [6 empty] | 2017-06-24 23:28 | EDITOR
90 | Jouni Malinen | 25 | 0.1 | 9.4.2.158.3 | 1168 | 46 | E | N | 1168 | 46 | 9.4.2.158.3 |  | A |  |  |  | Typo in MIB variable name in Table 9-251. | In Table 9-251, replace "dot11VHTEtxtendedNSSBWCapable" with "dot11VHTExtendedNSSBWCapable". | ACCEPTED (EDITOR: 2017-06-24 23:27:39Z) | EDITOR | [6 empty] | 2017-06-24 23:28 | EDITOR
123 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | It is not necessary to specify the size of an integer when the size is given in the Figure descibing the field | Delete the "x-bit" or "xxx bit" before "unsigned integer" | REVISED (EDITOR: 2017-07-12 11:20:14Z) - If the cited text is given in the figure and is in the same subclause of the figure, delete the "x-bit" or "xxx bit" before "unsigned integer". Otherwise, no change. | EDITOR |  | Review | EDITOR: 2017-07-12 11:22:36Z - status set to: Review EDITOR: 2017-06-17 21:27:26Z - status set to: Submission Required Locations should be identified. Suggest assigning this comment to the commenter for a submission. |  |  |  | 2017-07-12 11:24 | EDITOR
124 | Mark RISON | 25 | 0.1 | 9.4.2.15 | 854 | 37 | E | N | 854 | 37 | 9.4.2.15 |  | A |  |  |  | "coded as a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:23:02Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:23:00Z - status set to: Review |  |  |  | 2017-06-24 23:23 | EDITOR
125 | Mark RISON | 25 | 0.1 | 9.4.2.15 | 854 | 43 | E | N | 854 | 43 | 9.4.2.15 |  | A |  |  |  | "coded as a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:23:15Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:23:15Z - status set to: Review |  |  |  | 2017-06-24 23:23 | EDITOR
126 | Mark RISON | 25 | 0.1 | 9.4.2.37 | 982 | 57 | E | N | 982 | 57 | 9.4.2.37 |  | A |  |  |  | "a 2-octet signed integer" does not fully specify the encoding | Change the cited text to "a 2s complement signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:24:41Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:24:46Z - status set to: Review |  |  |  | 2017-06-24 23:25 | EDITOR
127 | Mark RISON | 25 | 0.1 | 9.4.2.71.5 | 1055 | 2 | E | N | 1055 | 2 | 9.4.2.71.5 |  | A |  |  |  | "is a signed integer, 1 octet in length," does not fully specify the encoding | Change the cited text to "a 2s complement signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:26:49Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:26:52Z - status set to: Review |  |  |  | 2017-06-24 23:27 | EDITOR
128 | Mark RISON | 25 | 0.1 | 9.4.2.71.5 | 1055 | 14 | E | N | 1055 | 14 | 9.4.2.71.5 |  | A |  |  |  | "is a signed integer, 1 octet in length," does not fully specify the encoding | Change the cited text to "a 2s complement signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:26:40Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:26:43Z - status set to: Review |  |  |  | 2017-06-24 23:27 | EDITOR
129 | Mark RISON | 25 | 0.1 | 9.4.2.84 | 1072 | 63 | E | N | 1072 | 63 | 9.4.2.84 |  | A |  |  |  | "a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:26:59Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:27:02Z - status set to: Review |  |  |  | 2017-06-24 23:27 | EDITOR
130 | Mark RISON | 25 | 0.1 | 9.4.6.4 | 1236 | 37 | E | N | 1236 | 37 | 9.4.6.4 |  | A |  |  |  | "a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:35:06Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:35:09Z - status set to: Review |  |  |  | 2017-06-24 23:35 | EDITOR
131 | Mark RISON | 25 | 0.1 | 9.4.8.30 | 1291 | 40 | E | N | 1291 | 40 | 9.4.8.30 |  | A |  |  |  | "a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:35:22Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:35:27Z - status set to: Review |  |  |  | 2017-06-24 23:35 | EDITOR
141 | Mark RISON | 25 | 0.1 | 9.6.8.12 | 1276 | 49 | E | N | 1276 | 49 | 9.6.8.12 |  | A |  |  |  | "Query Response length" has the wrong case | Change the cited text to "Query Response Length" | ACCEPTED (EDITOR: 2017-06-24 23:35:18Z) | EDITOR | [6 empty] | 2017-06-24 23:35 | EDITOR
150 | Mark RISON | 25 | 0.1 | 9.4.2.21.19 | 889 | 33 | E | N | 889 | 33 | 9.4.2.21.19 |  | A |  |  |  | "Neighbor Report Subelements field" -- there is no such field | Change each of the 2 instances of the cited text to "Neighbor Report subelement" | ACCEPTED (EDITOR: 2017-06-24 23:24:36Z) | EDITOR | [6 empty] | 2017-06-24 23:25 | EDITOR
154 | Mark RISON | 25 | 0.1 | 9.4.2.5 | 845 | 50 | E | N | 845 | 50 | 9.4.2.5 |  | V |  |  |  | The CF Parameter Set element format figure has spaces after the "CFP"s and there is one instance of "CFP duration", two of "CFP DurRemaining" outside the figure, two of "aCFPMaxDuration" (spurious "a") | Fix the issues identified in the comment | REVISED (EDITOR: 2017-06-24 23:17:10Z) - Throughout the draft, change "CFP Count" to "CFPCount"; change "CFP duration", "aCFPMaxDuration" and "CFP MaxDuration" to "CFPMaxDuration"; change "CFP Period" to "CFPPeriod"; change "CFP DurRemaining" to "CFPDurRemaining". | EDITOR | [6 empty] | 2017-06-24 23:40 | EDITOR
164 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | It is confusing to have both a "Beamforming Report Poll frame" and "BRP frame" | Change "BRP frame" to "Beam Refinement Protocol frame" throughout the draft | REVISED (EDITOR: 2017-06-24 22:32:55Z) - Change" Beamforming Report Poll frame" to "BRP frame". | EDITOR |  | Review | EDITOR: 2017-06-24 22:33:26Z - status set to: Review |  |  |  | 2017-07-11 06:17 | EDITOR
165 | Mark RISON | 25 | 0.1 | 9.4.2.1 | 833 | 26 | E | N | 833 | 26 | 9.4.2.1 |  | A |  |  |  | Cross-references are missing for the FTM Synchronization Information, Extended Request and Future Channel Guidance elements | Add "(see 9.xxx)" after each | ACCEPTED (EDITOR: 2017-06-24 23:11:05Z) | EDITOR | [6 empty] | 2017-06-24 23:11 | EDITOR
172 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "when the dot11<blah> <is blah>" has a spurious article | Delete "the" in "when the dot11" throughout the draft | ACCEPTED (EDITOR: 2017-06-17 21:26:06Z) | EDITOR | [6 empty] | 2017-06-17 21:26 | EDITOR
175 | Mark RISON | 25 | 0.1 | 8.3.5.2.2 | 658 | 50 | E | N | 658 | 50 | 8.3.5.2.2 |  | A |  |  |  | Missing comma | Add a comma after "DATA" | ACCEPTED (EDITOR: 2017-06-24 23:07:10Z) | EDITOR | [6 empty] | 2017-06-24 23:07 | EDITOR
183 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are instances of "variable-length" and "variable length" | Since the IEEE doesn't like hyphens, change hyphens to spaces in "variable-length" throughout the draft | ACCEPTED (EDITOR: 2017-06-17 21:25:45Z) | EDITOR | [6 empty] | 2017-06-17 21:26 | EDITOR
221 | Mark RISON | 25 | 0.1 | 9.4.2.56.2 | 1006 | 21 | E | N | 1006 | 21 | 9.4.2.56.2 |  | A |  |  |  | All the information about the fields is in the table, except for this sentence. This is inconsistent | Delete the sentence at the referenced location. At the end of the rightmost cells for the Tx STBC and Rx STBC rows in the table above append "This field is reserved for a mesh STA." | ACCEPTED (EDITOR: 2017-06-24 23:26:34Z) | EDITOR | [6 empty] | 2017-06-24 23:27 | EDITOR
228 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | "Antenna ID" should not be uppercase unless followed by "field" or start of sentence, heading, etc. | Change "Antenna ID" to "antenna ID" except if followed by "field" or "subfield" or at the start of a sentence/heading/etc. | REVISED (EDITOR: 2017-06-24 22:14:09Z) - at 393.46,393.50,986.6, 986.13, 1650.19,1652.14, 1841.47, 3196.38. 3203.36, and 3208.28, change "Antenna ID" to "antenna ID" | EDITOR | [6 empty] | 2017-06-24 22:25 | EDITOR
229 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are 14 instances of "may cause". However, this should only be used when this is a choice open to the implementation rather than the possible result of something. The referenced location is only an exemplar | Change "may cause" to "might cause" unless it's really an implementation choice | ACCEPTED (EDITOR: 2017-06-17 21:49:13Z) | EDITOR | [6 empty] | 2017-06-17 21:49 | EDITOR
240 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "x through y" is to describe ranges is utterly horrible and on top of that inefficient | Change "through" to "to" wherever it is used to describe a range. To find instances, search for an immediately following digit, parenthesis or "Table/Figure/Clause/Subclause/Equation" | ACCEPTED (EDITOR: 2017-06-24 22:40:00Z) | EDITOR |  | Review | EDITOR: 2017-06-24 22:40:03Z - status set to: Review |  |  |  | 2017-06-24 22:40 | EDITOR
241 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "Originator" and "Responder" should not be uppercase unless part of a field name or start of sentence etc. | Lowercase these terms where appropriate | ACCEPTED (EDITOR: 2017-07-12 11:30:11Z) | EDITOR | [6 empty] | 2017-07-12 11:31 | EDITOR
253 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "Requested TCLAS Not Supported" and "TCLAS Resources Exhausted" in the rightmost column of Table 9-46---Status codes have bogus capitalisation (other rows do too). | Fix the capitalisation here and elsewhere in this table according to the usual rules (so e.g. the first one would become "Requested TCLAS not supported") | ACCEPTED (EDITOR: 2017-06-17 21:18:24Z) | EDITOR | [6 empty] | 2017-06-17 21:19 | EDITOR
261 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "intended for" is a bit vague | Change to "addressed to" throughout | ACCEPTED (EDITOR: 2017-06-17 21:54:08Z) | EDITOR |  | Review | EDITOR: 2017-06-24 22:42:25Z - status set to: Review |  |  |  | 2017-06-24 22:42 | EDITOR
272 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | "Measurement Pilot Interval", when not followed by "field", should not be uppercase | As it says in the comment | REVISED (EDITOR: 2017-06-19 22:59:10Z): at 980.50, 986.63, 1857.48, 3252.49. change "Measurement Pilot Interval" to "measurement pilot interval" | EDITOR |  | Review | EDITOR: 2017-06-24 22:44:19Z - status set to: Review |  |  |  | 2017-06-24 22:44 | EDITOR
274 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "The TDLS responder STA shall discard the message, the TDLS responder STA shall abandon the TPK handshake" is garbled | Change the cited text to ""The TDLS responder STA shall discard the message, abandon the TPK handshake" | ACCEPTED (EDITOR: 2017-06-24 22:49:42Z) | EDITOR | [6 empty] | 2017-06-24 22:50 | EDITOR
285 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are 3 instances of wording like "It is important that designers recognize the need for statistical independence among the random number streams among STAs." (1290.48, 1566.12, 1687.13) but only the last is a NOTE and the wording is not consistent | Make the first two NOTEs too, and change the wording to always be "It is important that designers recognize the need for statistical independence of the random number streams between STAs." | ACCEPTED (EDITOR: 2017-06-17 21:50:35Z) | EDITOR | [6 empty] | 2017-06-17 21:51 | EDITOR
307 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are a few "hash function"s and many more "hash algorithms" | Change the "hash function"s to "hash algorithm"s throughout the draft | ACCEPTED (EDITOR: 2017-06-17 21:55:59Z) | EDITOR | [6 empty] | 2017-06-17 21:56 | EDITOR
342 | Roger Marks | 25 | 0.1 | 9.4.2.171.2 | 1185 | 30 | E | N | 1185 | 30 | 9.4.2.171.2 |  | A |  |  |  | Description of TBTT Information Length subfield can be clarified by referring to the TBTT Information set that includes the TBTT Information fields. | Change the sentence at Page 1185 Lines 30-31 as follows: The TBTT Information Length subfield is 1 octet in length and contains the length in octets of each TBTT Information field that is included in the <insert>TBTT Information set of the</insert> Neighbor AP Information field. | ACCEPTED (EDITOR: 2017-07-10 13:08:56Z) | EDITOR |  | Review | EDITOR: 2017-07-10 13:09:04Z - status set to: Review EDITOR: 2017-06-24 23:29:24Z - status set to: Discuss |  |  |  | 2017-07-10 13:31 | EDITOR
346 | Stephen McCann | 25 | 0.1 | 9.4.5.25 | 1231 | 3 | E | N | 1231 | 3 | 9.4.5.25 |  | J |  |  |  | typo "info ID" | Change "info ID" to "Info ID" | REJECTED (EDITOR: 2017-06-24 23:33:02Z): "info ID" here is not a field or subfield, so that it shall be lower case. | EDITOR | [6 empty] | 2017-06-24 23:38 | EDITOR
350 | Stephen McCann | 25 | 0.1 | 9.4.5.24 | 1231 | 21 | E | N | 1231 | 21 | 9.4.5.24 |  | A |  |  |  | The reference in the sentence "Each ANQP Query ID field value is drawn from Table 9-271 (DNS Info Control subfield settings(11ai))." is incorrect. | Change the sentence to "Each ANQP Query ID field value is drawn from Table 9-281--ANQP-element definitions." | ACCEPTED (EDITOR: 2017-06-24 23:32:37Z) | EDITOR | [6 empty] | 2017-06-24 23:33 | EDITOR
355 | Stephen McCann | 25 | 0.1 | 9.4.5.24 | 1230 | 47 | E | N | 1230 | 47 | 9.4.5.24 |  | A |  |  |  | Replace "ANQP query response" with "ANQP response" per the key in Table 11-15 | Change "ANQP query response" to "ANQP response". Also on P1231L27 and P1964L17 | ACCEPTED (EDITOR: 2017-06-24 23:30:06Z) | EDITOR | [6 empty] | 2017-06-24 23:30 | EDITOR

## Editorial Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
8 | Emily Qi | 25 | 0.1 | 9.4.5.24 | 1230 | 59 | E | Y | 1230 | 59 | 9.4.5.24 |  |  | Emily Qi |  |  | The way of handling variable length lists in REVmc changed to the pattern shown at 1230.5-19. 1230.59 follows the old pattern with repeating fields shown in the frame format. | Change the format of the fields "ANQP Query ID #1", ... "ANQP Query ID #N" to the format that is similar to 1230.5 to 1230.19. |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:30:12Z - status set to: Submission Required |  |  |  | 2017-06-24 23:30 | EDITOR
9 | Emily Qi | 25 | 0.1 | 9.4.5.24 | 1231 | 9 | E | Y | 1231 | 9 | 9.4.5.24 |  |  | Emily Qi |  |  | The way of handling variable length lists in REVmc changed to the pattern shown at 1230.5-19. 1231.9 follows the old pattern with repeating fields shown in the frame format. | Change the format of list of the fields "BSSID" to the format that is similar to 1230.5 to 1230.19. |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:31:01Z - status set to: Submission Required |  |  |  | 2017-06-24 23:31 | EDITOR
10 | Emily Qi | 25 | 0.1 | 9.4.5.25 | 1231 | 33 | E | Y | 1231 | 33 | 9.4.5.25 |  |  | Emily Qi |  |  | The way of handling variable length lists in REVmc changed to the pattern shown at 1230.5-19. 1231.32 follows the old pattern with repeating fields shown in the frame format. | Change the format of list of the fields "AP 1 Identifier", "AP 1 Response Length" , "AP 1 Query Response" to the format that is similar to 1230.5 to 1230.19. |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:34:41Z - status set to: Submission Required |  |  |  | 2017-06-24 23:35 | EDITOR
11 | Emily Qi | 25 | 0.1 | 9.4.5.26 | 1232 | 1 | E | Y | 1232 | 1 | 9.4.5.26 |  |  | Emily Qi |  |  | The way of handling variable length lists in REVmc changed to the pattern shown at 1230.5-19. 1232.1 follows the old pattern with repeating fields shown in the frame format. | Change the format of list of the fields "Realm Identifier" to the format that is similar to 1230.5 to 1230.19. |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:34:48Z - status set to: Submission Required |  |  |  | 2017-06-24 23:35 | EDITOR
12 | Emily Qi | 25 | 0.1 | 9.4.5.27 | 1232 | 18 | E | Y | 1232 | 18 | 9.4.5.27 |  |  | Emily Qi |  |  | The way of handling variable length lists in REVmc changed to the pattern shown at 1230.5-19. 1232.18 follows the old pattern with repeating fields shown in the frame format. | Change the format of list of the fields "Info ID" to the format that is similar to 1230.5 to 1230.19. |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:34:56Z - status set to: Submission Required |  |  |  | 2017-06-24 23:35 | EDITOR
13 | Emily Qi | 25 | 0.1 | 9.6.24.2 | 1389 | 8 | E | Y | 1389 | 8 | 9.6.24.2 |  | A |  |  |  | In the field "FILS IP Address Assignment elements", "elements" should be "Element". Also, the reference doesn't need to be included in the table. | At 1389.8, Change "FILS IP Address Assignment elements (defined in 9.4.2.185 (FILS IP Address Assignment element(11ai)))" to "FILS IP Address Assignment Element" . At 1389.22, change " The FILS IP Address Assignment element carries the FILS parameters for IP address assignment and DNS server information." to "The FILS IP Address Assignment Element field contains one or more FILS IP Address Assignment elements as defined in 9.4.2.185 (FILS IP Address Assignment element)." | ACCEPTED (EDITOR: 2017-06-24 23:36:30Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:36:41Z - status set to: Review |  |  |  | 2017-06-24 23:37 | EDITOR
16 | Emily Qi | 25 | 0.1 | 9.4.2.177 | 1191 | 27 | E | N | 1191 | 27 | 9.4.2.177 |  |  | Emily Qi |  |  | The way of handling variable length lists in REVmc changed to the pattern shown at 1230.5-19. 1191.27 follows the old pattern with repeating fields shown in the frame format. | Change the format of list of the fields "CAG Tuple" to the format that is similar to 1230.5 to 1230.19. |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:29:44Z - status set to: Submission Required |  |  |  | 2017-06-24 23:30 | EDITOR
18 | Graham Smith | 25 | 0.1 | 6.3.3.3.2. | 277 | 12 | E | N | 277 | 12 | 6.3.3.3.2. |  | A |  |  |  | 6.3.3.3.2. P277L12 L17 L21 L26 L32 L38 L43 L49 "probe response" should be "Probe Response" P279L29 L34 "probe request" should be "Probe Request" | "probe request" should be "Probe Request" | ACCEPTED (EDITOR: 2017-06-24 23:06:16Z) | EDITOR | [6 empty] | 2017-06-24 23:06 | EDITOR
19 | Graham Smith | 25 | 0.1 | 4.5.3.3 | 225 | 18 | E | N | 225 | 18 | 4.5.3.3 |  | A |  |  |  | "... authenticate and associate with the AP with reduced number of frame transmissions." Add "a" between "with" and "reduced" to read "with a reduced number ..." | At cited text, add "a" between "with" and "reduced" to read "with a reduced" | ACCEPTED (EDITOR: 2017-06-24 23:05:11Z) | EDITOR | [6 empty] | 2017-06-24 23:05 | EDITOR
21 | Graham Smith | 25 | 0.1 | 4.5.4.8 | 229 | 22 | E | N | 229 | 22 | 4.5.4.8 |  | A |  |  |  | "When FILS authentication is used during a handover across mobility domains, the overhead incurred during the FT initial mobility domain association in an RSN is further reduced." Seems backward. | Replace cited with "During a handover across mobility domains, the overhead incurred during the FT initial mobility domain association in an RSN can be reduced using FILS authentication." | ACCEPTED (EDITOR: 2017-06-24 23:06:05Z) | EDITOR | [6 empty] | 2017-06-24 23:06 | EDITOR
27 | Graham Smith | 25 | 0.1 | 4.2.4 | 187 | 6 | E | N | 187 | 6 | 4.2.4 |  | V |  |  |  | Delete "actually" or replace with "might" (prefer deletion) | As per comment | REVISED (EDITOR: 2017-06-24 23:03:07Z): at 187.6, delete "actually". | EDITOR | [6 empty] | 2017-06-24 23:05 | EDITOR
28 | Graham Smith | 25 | 0.1 | 4.2.5 | 187 | 20 | E | N | 187 | 20 | 4.2.5 |  | A |  |  |  | "handle" replace with "handles" or delete the "the" in front of "IEEE Std" | As per comment | ACCEPTED (EDITOR: 2017-06-19 23:09:39Z) | EDITOR | [6 empty] | 2017-06-19 23:10 | EDITOR
86 | Jouni Malinen | 25 | 0.1 | 9.6.11 | 1308 | 59 | E | N | 1308 | 59 | 9.6.11 |  | A |  |  |  | Table 9-349 (Public Action field values defined for Protected Dual of Public Action frames) claims values 16 and 17 be reserved even though they are assigned for QAB Request/Response. | Replace "14-17" with "14-15" for the Reserved row in Table 9-349. | ACCEPTED (EDITOR: 2017-06-24 23:35:59Z) | EDITOR | [6 empty] | 2017-06-24 23:36 | EDITOR
89 | Jouni Malinen | 25 | 0.1 | 9.4.2.158.2 | 1167 | 54 | E | N | 1167 | 54 | 9.4.2.158.2 |  | A |  |  |  | Incorrect MIB variable name used in NOTE 11 of Table 9-250. | Replace "dot11VHTExtendedNSSCapable" with "dot11VHTExtendedNSSBWCapable" in NOTE 11 in Table 9-250. | ACCEPTED (EDITOR: 2017-06-24 23:27:32Z) | EDITOR | [6 empty] | 2017-06-24 23:28 | EDITOR
90 | Jouni Malinen | 25 | 0.1 | 9.4.2.158.3 | 1168 | 46 | E | N | 1168 | 46 | 9.4.2.158.3 |  | A |  |  |  | Typo in MIB variable name in Table 9-251. | In Table 9-251, replace "dot11VHTEtxtendedNSSBWCapable" with "dot11VHTExtendedNSSBWCapable". | ACCEPTED (EDITOR: 2017-06-24 23:27:39Z) | EDITOR | [6 empty] | 2017-06-24 23:28 | EDITOR
100 | Jouni Malinen | 25 | 0.1 | 9.2.4.1.3 | 675 | 22 | E | N | 675 | 22 | 9.2.4.1.3 | [5 empty] | Table 9-1 uses binary numbers to identify Type and Subtype values. IMHO, it would be clearer to refer to these fields as base-10 integers instead (i.e., 00 --> 0, 01 --> 1, 10 --> 2, 11 --> 3; and similarly for the 4-bit Subtype values). | Consider replacing binary values for multi-bit-integers in Table 9-1 and all similar tables throughout the draft with base-10 integers. |  | EDITOR |  | Discuss | EDITOR: 2017-07-12 11:40:24Z - status set to: Discuss EDITOR: 2017-07-10 13:29:18Z - status set to: Review EDITOR: 2017-07-10 13:28:06Z - status set to: Discuss REJECTED (EDITOR: 2017-07-10 13:12:04Z)- Do not see any benefit to change base-10 integers in Table 9-1. The Table 9-1 with this format has been there since IEEE 802.11-2007 (at least), these is no need to change a different format. |  |  |  | 2017-07-12 11:41 | EDITOR
119 | Mark Hamilton | 25 | 0.1 | 3.1 | 139 | 4 | E | Y | 139 | 4 | 3.1 | [5 empty] | "unspecified ", "not specified", "implementation dependent", "outside the scope", and "beyond the scope" - all are okay, but do we need all these different ways to say it? | Choose one (or maybe two?) and change the others to match | REJECTED (EDITOR: 2017-07-10 12:41:39Z) - "Not Specified", "implementation dependent" and "outside of the scope" are different. Using these different ways to say it is appropriate . | EDITOR |  | Discuss | EDITOR: 2017-07-10 13:36:41Z - status set to: Discuss EDITOR: 2017-07-10 13:29:41Z - status set to: Review Suggestion: Reject, "Not Specified", "implementation dependent" and "outside of the scope" are different. Using these different ways to say it is appropriate . |  |  |  | 2017-07-11 06:11 | EDITOR
123 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | It is not necessary to specify the size of an integer when the size is given in the Figure descibing the field | Delete the "x-bit" or "xxx bit" before "unsigned integer" | REVISED (EDITOR: 2017-07-12 11:20:14Z) - If the cited text is given in the figure and is in the same subclause of the figure, delete the "x-bit" or "xxx bit" before "unsigned integer". Otherwise, no change. | EDITOR |  | Review | EDITOR: 2017-07-12 11:22:36Z - status set to: Review EDITOR: 2017-06-17 21:27:26Z - status set to: Submission Required Locations should be identified. Suggest assigning this comment to the commenter for a submission. |  |  |  | 2017-07-12 11:24 | EDITOR
124 | Mark RISON | 25 | 0.1 | 9.4.2.15 | 854 | 37 | E | N | 854 | 37 | 9.4.2.15 |  | A |  |  |  | "coded as a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:23:02Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:23:00Z - status set to: Review |  |  |  | 2017-06-24 23:23 | EDITOR
125 | Mark RISON | 25 | 0.1 | 9.4.2.15 | 854 | 43 | E | N | 854 | 43 | 9.4.2.15 |  | A |  |  |  | "coded as a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:23:15Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:23:15Z - status set to: Review |  |  |  | 2017-06-24 23:23 | EDITOR
126 | Mark RISON | 25 | 0.1 | 9.4.2.37 | 982 | 57 | E | N | 982 | 57 | 9.4.2.37 |  | A |  |  |  | "a 2-octet signed integer" does not fully specify the encoding | Change the cited text to "a 2s complement signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:24:41Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:24:46Z - status set to: Review |  |  |  | 2017-06-24 23:25 | EDITOR
127 | Mark RISON | 25 | 0.1 | 9.4.2.71.5 | 1055 | 2 | E | N | 1055 | 2 | 9.4.2.71.5 |  | A |  |  |  | "is a signed integer, 1 octet in length," does not fully specify the encoding | Change the cited text to "a 2s complement signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:26:49Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:26:52Z - status set to: Review |  |  |  | 2017-06-24 23:27 | EDITOR
128 | Mark RISON | 25 | 0.1 | 9.4.2.71.5 | 1055 | 14 | E | N | 1055 | 14 | 9.4.2.71.5 |  | A |  |  |  | "is a signed integer, 1 octet in length," does not fully specify the encoding | Change the cited text to "a 2s complement signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:26:40Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:26:43Z - status set to: Review |  |  |  | 2017-06-24 23:27 | EDITOR
129 | Mark RISON | 25 | 0.1 | 9.4.2.84 | 1072 | 63 | E | N | 1072 | 63 | 9.4.2.84 |  | A |  |  |  | "a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:26:59Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:27:02Z - status set to: Review |  |  |  | 2017-06-24 23:27 | EDITOR
130 | Mark RISON | 25 | 0.1 | 9.4.6.4 | 1236 | 37 | E | N | 1236 | 37 | 9.4.6.4 |  | A |  |  |  | "a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:35:06Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:35:09Z - status set to: Review |  |  |  | 2017-06-24 23:35 | EDITOR
131 | Mark RISON | 25 | 0.1 | 9.4.8.30 | 1291 | 40 | E | N | 1291 | 40 | 9.4.8.30 |  | A |  |  |  | "a signed integer" does not fully specify the encoding | Add "2s complement " before "signed integer" | ACCEPTED (EDITOR: 2017-06-24 23:35:22Z) | EDITOR |  | Review | EDITOR: 2017-06-24 23:35:27Z - status set to: Review |  |  |  | 2017-06-24 23:35 | EDITOR
141 | Mark RISON | 25 | 0.1 | 9.6.8.12 | 1276 | 49 | E | N | 1276 | 49 | 9.6.8.12 |  | A |  |  |  | "Query Response length" has the wrong case | Change the cited text to "Query Response Length" | ACCEPTED (EDITOR: 2017-06-24 23:35:18Z) | EDITOR | [6 empty] | 2017-06-24 23:35 | EDITOR
146 | Mark RISON | 25 | 0.1 | 9.2.4.5.4 | 687 | 1 | E | N | 687 | 1 | 9.2.4.5.4 |  |  | Mark RISON |  |  | The way the ack policy is referred to is confusing/inconsistent. Do you refer to the options indicated by the bit pattern (e.g. "Normal Ack or Implicit Block Ack Request") or do you refer to only the type of ack being requested in the context being requested (e.g. just "Implicit Block Ack Request" in the case of an A-MPDU)? | Throughout the draft, in the cases where the bit pattern is being referenced, use the full field name and full type description, e.g. "the Ack Policy subfield in the QoS Control field set to Normal Ack or Implicit Block Ack Request"; in the cases where the specific context is intended do not refer to the full field name, e.g. not "One or more QoS Data frames with the Ack Policy field equal to Implicit Block Ack Request" but "One or more QoS Data frames with the ack policy indicating Implicit Block Ack Request" |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:38:40Z - status set to: Submission Required |  |  |  | 2017-06-24 23:39 | EDITOR
147 | Mark RISON | 25 | 0.1 | 9.4.2.21.10 | 877 | 37 | E | N | 877 | 37 | 9.4.2.21.10 | [5 empty] | There should not be two Maximum Age Subelement definitions | Define a new "Fields that are not elements" for this, and then make 877.28 and 890.26 refer back to this |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 23:23:40Z - status set to: Discuss |  |  |  | 2017-06-24 23:24 | EDITOR
150 | Mark RISON | 25 | 0.1 | 9.4.2.21.19 | 889 | 33 | E | N | 889 | 33 | 9.4.2.21.19 |  | A |  |  |  | "Neighbor Report Subelements field" -- there is no such field | Change each of the 2 instances of the cited text to "Neighbor Report subelement" | ACCEPTED (EDITOR: 2017-06-24 23:24:36Z) | EDITOR | [6 empty] | 2017-06-24 23:25 | EDITOR
154 | Mark RISON | 25 | 0.1 | 9.4.2.5 | 845 | 50 | E | N | 845 | 50 | 9.4.2.5 |  | V |  |  |  | The CF Parameter Set element format figure has spaces after the "CFP"s and there is one instance of "CFP duration", two of "CFP DurRemaining" outside the figure, two of "aCFPMaxDuration" (spurious "a") | Fix the issues identified in the comment | REVISED (EDITOR: 2017-06-24 23:17:10Z) - Throughout the draft, change "CFP Count" to "CFPCount"; change "CFP duration", "aCFPMaxDuration" and "CFP MaxDuration" to "CFPMaxDuration"; change "CFP Period" to "CFPPeriod"; change "CFP DurRemaining" to "CFPDurRemaining". | EDITOR | [6 empty] | 2017-06-24 23:40 | EDITOR
164 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | It is confusing to have both a "Beamforming Report Poll frame" and "BRP frame" | Change "BRP frame" to "Beam Refinement Protocol frame" throughout the draft | REVISED (EDITOR: 2017-06-24 22:32:55Z) - Change" Beamforming Report Poll frame" to "BRP frame". | EDITOR |  | Review | EDITOR: 2017-06-24 22:33:26Z - status set to: Review |  |  |  | 2017-07-11 06:17 | EDITOR
165 | Mark RISON | 25 | 0.1 | 9.4.2.1 | 833 | 26 | E | N | 833 | 26 | 9.4.2.1 |  | A |  |  |  | Cross-references are missing for the FTM Synchronization Information, Extended Request and Future Channel Guidance elements | Add "(see 9.xxx)" after each | ACCEPTED (EDITOR: 2017-06-24 23:11:05Z) | EDITOR | [6 empty] | 2017-06-24 23:11 | EDITOR
169 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | There is no point in the distinction between Measurement Request frames and Radio Measurement Request frames | Delete "Radio" in "Radio Measurement Request" and "Radio Measurement Report" throughout the draft |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:38:29Z - status set to: Discuss |  |  |  | 2017-06-24 22:39 | EDITOR
172 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "when the dot11<blah> <is blah>" has a spurious article | Delete "the" in "when the dot11" throughout the draft | ACCEPTED (EDITOR: 2017-06-17 21:26:06Z) | EDITOR | [6 empty] | 2017-06-17 21:26 | EDITOR
175 | Mark RISON | 25 | 0.1 | 8.3.5.2.2 | 658 | 50 | E | N | 658 | 50 | 8.3.5.2.2 |  | A |  |  |  | Missing comma | Add a comma after "DATA" | ACCEPTED (EDITOR: 2017-06-24 23:07:10Z) | EDITOR | [6 empty] | 2017-06-24 23:07 | EDITOR
183 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are instances of "variable-length" and "variable length" | Since the IEEE doesn't like hyphens, change hyphens to spaces in "variable-length" throughout the draft | ACCEPTED (EDITOR: 2017-06-17 21:25:45Z) | EDITOR | [6 empty] | 2017-06-17 21:26 | EDITOR
201 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [5 empty] | Mark RISON |  |  | There are about 60 instances of "expected to". However, per the reflector emails with subject RE: REVmc comment 7770 sent on 2016-05-10, such a construct is non-grata | Reword all "expected to"s in a less anthropomorphic form |  | EDITOR |  | Submission Required | EDITOR: 2017-06-17 21:25:20Z - status set to: Submission Required |  |  |  | 2017-06-24 23:43 | EDITOR
203 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | There is a definition for "DMG STA", namely "A STA whose radio transmitter is capable of transmitting and receiving DMG physical layer (PHY) protocol data units (PPDUs)." However, there is no definition for "$PHY STA", where $PHY is "DSSS", "HR/DSSS", "OFDM", "ERP", "HT", "VHT" or "TVHT" as "A STA whose radio transmitter is capable of transmitting and receiving DMG physical layer (PHY) protocol data units (PPDUs)." There is absolutely no reason to have the "DMG STA" definition | Delete the "DMG STA" definition |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:37:09Z - status set to: Discuss |  |  |  | 2017-06-24 22:37 | EDITOR
204 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | There is a definition for "DMG AP", "DMG BSS". We don't do this for other PHYs. There is absolutely no reason to have these definitions | Delete the "DMG AP" and "DMG BSS" definitions |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:37:01Z - status set to: Discuss |  |  |  | 2017-06-24 22:37 | EDITOR
208 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | In two locations, "elements" is referring to a parameter, not an element | Make the changes shown in 16/0839r3 under CID 8145 |  | EDITOR |  | Discuss | EDITOR: 2017-07-12 11:26:37Z - status set to: Discuss EDITOR: 2017-06-24 23:42:02Z - status set to: Submission Required. I cannot find locations and reference in 16/0839r3. |  |  |  | 2017-07-12 11:29 | EDITOR
210 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | There are 3 instances of " transmission of an A-MPDU or frame in", but though this is technically defensible when followed by "a PSDU" it is confusing (the usual layering confusion: an A-MPDU contains frames (a.k.a. MPDUs); it is not at the same level) and the middle instance is not even followed by "a PSDU" anyway | Change "QSRC[AC] shall be incremented every time transmission of an A-MPDU or frame in a PSDU of length less than or equal to dot11RTSThreshold fails, regardless of the presence or value of the DEI field. When dot11RobustAVStreamingImplemented is true, QSDRC[AC] shall be incremented every time transmission of an A-MPDU or frame in which the HT variant HT Control field is present," to "QSRC[AC] shall be incremented every time transmission of a PSDU of length less than or equal to dot11RTSThreshold fails, regardless of the presence or value of the DEI field. When dot11RobustAVStreamingImplemented is true, QSDRC[AC] shall be incremented every time a transmission in which the HT variant HT Control field is present," Change "QLRC[AC] shall be incremented every time transmission of an A-MPDU or frame in a PSDU" to "QLRC[AC] shall be incremented every time transmission of a PSDU" |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:36:45Z - status set to: Discuss |  |  |  | 2017-06-24 22:39 | EDITOR
221 | Mark RISON | 25 | 0.1 | 9.4.2.56.2 | 1006 | 21 | E | N | 1006 | 21 | 9.4.2.56.2 |  | A |  |  |  | All the information about the fields is in the table, except for this sentence. This is inconsistent | Delete the sentence at the referenced location. At the end of the rightmost cells for the Tx STBC and Rx STBC rows in the table above append "This field is reserved for a mesh STA." | ACCEPTED (EDITOR: 2017-06-24 23:26:34Z) | EDITOR | [6 empty] | 2017-06-24 23:27 | EDITOR
228 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | "Antenna ID" should not be uppercase unless followed by "field" or start of sentence, heading, etc. | Change "Antenna ID" to "antenna ID" except if followed by "field" or "subfield" or at the start of a sentence/heading/etc. | REVISED (EDITOR: 2017-06-24 22:14:09Z) - at 393.46,393.50,986.6, 986.13, 1650.19,1652.14, 1841.47, 3196.38. 3203.36, and 3208.28, change "Antenna ID" to "antenna ID" | EDITOR | [6 empty] | 2017-06-24 22:25 | EDITOR
229 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are 14 instances of "may cause". However, this should only be used when this is a choice open to the implementation rather than the possible result of something. The referenced location is only an exemplar | Change "may cause" to "might cause" unless it's really an implementation choice | ACCEPTED (EDITOR: 2017-06-17 21:49:13Z) | EDITOR | [6 empty] | 2017-06-17 21:49 | EDITOR
240 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "x through y" is to describe ranges is utterly horrible and on top of that inefficient | Change "through" to "to" wherever it is used to describe a range. To find instances, search for an immediately following digit, parenthesis or "Table/Figure/Clause/Subclause/Equation" | ACCEPTED (EDITOR: 2017-06-24 22:40:00Z) | EDITOR |  | Review | EDITOR: 2017-06-24 22:40:03Z - status set to: Review |  |  |  | 2017-06-24 22:40 | EDITOR
241 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "Originator" and "Responder" should not be uppercase unless part of a field name or start of sentence etc. | Lowercase these terms where appropriate | ACCEPTED (EDITOR: 2017-07-12 11:30:11Z) | EDITOR | [6 empty] | 2017-07-12 11:31 | EDITOR
243 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | "is shown in" (Figure, Table, etc.) or similar wooly statements ("is illustrated in") should be "is defined in" (at least in Clause 9 and the cases where the figure/table is the thing that normatively defines the structure/valid values) | As it says in the comment | ACCEPTED (EDITOR: 2017-06-24 22:35:27Z) | EDITOR |  | Discuss | EDITOR: 2017-07-11 06:14:22Z - status set to: Discuss EDITOR: 2017-06-24 22:35:32Z - status set to: Review |  |  |  | 2017-07-11 06:15 | EDITOR
248 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | Should common words in field names (e.g. "of", "in", "per") be upper- or lower-case? E.g. "FTMs per Burst" v. "Format And Bandwidth" at 1076.3 (this is just an example, not a complete set) | Be consistent |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:41:55Z - status set to: Discuss |  |  |  | 2017-06-24 22:42 | EDITOR
249 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | There are about 70 instances of "when a valid" -- what defines validity? | Delete "valid" in all instances |  | EDITOR |  | Discuss | EDITOR: 2017-07-12 11:39:51Z - status set to: Discuss EDITOR: 2017-06-24 22:34:37Z - status set to: Review REJECTED (EDITOR: 2017-06-24 22:34:25Z)- Validity depends on the context. |  |  |  | 2017-07-12 11:40 | EDITOR
253 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "Requested TCLAS Not Supported" and "TCLAS Resources Exhausted" in the rightmost column of Table 9-46---Status codes have bogus capitalisation (other rows do too). | Fix the capitalisation here and elsewhere in this table according to the usual rules (so e.g. the first one would become "Requested TCLAS not supported") | ACCEPTED (EDITOR: 2017-06-17 21:18:24Z) | EDITOR | [6 empty] | 2017-06-17 21:19 | EDITOR
254 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | Is the subfield called "FMS Counters" or "FMS Counter"? I think the latter | Use "FMS Counter" and say "field". [In 802.11mc/D6.0: Delete the "s" in "FMS Counters" at 946.1 (rightmost). Add "field" after "FMS Counter" at 946.1 (rightmost) and 946.16. At 946.6, 1594.23 (2x) lowercase "Counter". At 1594.19, 1594.23, 1595.5 (2x), 1595.7, 1595.11, 1595.56, 1596.17 lowercase "Stream"] |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:26:50Z - status set to: Discuss |  |  |  | 2017-06-24 22:39 | EDITOR
257 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | It is not necessary in Clause 9 to say things are done according to the conventions in 9.2.2. It is confusing to do so, because it implies something unusual is happening | Delete the sentences like "The order of the Organization Identifier field is described in 9.2.2 (Conventions)." or "All fields use the bit convention from 9.2.2 (Conventions)." or " It is encoded following the conventions in 9.2.2 (Conventions)." at [mc/D6.0 references] 685.46, 827.4, 828.41, 881.22, 881.26, 881.62, 882.43, 883.44, 999.59, 999.64, 1007.33, 1083.20, 1101.58, 1101.62, 1130.33, 1144.47. Delete the NOTE at 706.48. Change 880.20 to say "The MDID field contains an arbitrary value." At 951.39 delete ", encoded according to 9.2.2 (Conventions)". At 1085.14 delete " and is encoded following the conventions given in 9.2.2 (Conventions)" |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:26:26Z - status set to: Discuss |  |  |  | 2017-06-24 22:40 | EDITOR
260 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | Like "RSNE", other abbreviations for elements should either never or always be used | Globally replace all instances of the expansion of MME, FFE, FTE, MDE, PWE, RDE and TIE with their abbreviation, except in Clause 3 |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:35:54Z - status set to: Discuss |  |  |  | 2017-06-24 22:39 | EDITOR
261 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "intended for" is a bit vague | Change to "addressed to" throughout | ACCEPTED (EDITOR: 2017-06-17 21:54:08Z) | EDITOR |  | Review | EDITOR: 2017-06-24 22:42:25Z - status set to: Review |  |  |  | 2017-06-24 22:42 | EDITOR
265 | Mark RISON | 25 | 0.1 | 9.3.1.20 |  |  | E | N |  |  | 9.3.1.20 |  |  | Mark Rison |  |  | In the context of the discussion of CID 7770 (reflector email subject RE: REVmc comment 7770 on 2016-05-10) a suggestion to change "that can provide feedback" to "that is expected to provide feedback" was rejected. However, the result is inconsistency with e.g. 615.27 [in 11mc/D6.0] | Change "that can provide feedback" to "that is expected to provide feedback" at the referenced location |  | EDITOR | [6 empty] | 2017-07-12 11:25 | EDITOR
267 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [5 empty] | Mark RISON |  |  | The table for extended NSS without OMN (Table 9-250) should be folded into the table for extended NSS with OMN (Table 9-75), to get rid of all the duplication. | As it says in the comment |  | EDITOR | [6 empty] | 2017-07-12 10:34 | EDITOR
270 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | " The Measurement Report Element field is included in the Location Track Notification frame if the Location Parameters Element field contains a Location Indication Options subelement" -- move this condition to be in the table with all the other conditions (Table 9-318---Location Parameters Element field for Location Track Notification frame) | As it says in the comment |  | EDITOR |  | Discuss | EDITOR: 2017-07-12 11:39:11Z - status set to: Discuss EDITOR: 2017-06-24 22:43:54Z - status set to: Review REJECTED (EDITOR: 2017-06-19 22:56:46Z): Table 9-328 is for Allowed subelements, not for Element. |  |  |  | 2017-07-12 11:40 | EDITOR
272 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | V |  |  |  | "Measurement Pilot Interval", when not followed by "field", should not be uppercase | As it says in the comment | REVISED (EDITOR: 2017-06-19 22:59:10Z): at 980.50, 986.63, 1857.48, 3252.49. change "Measurement Pilot Interval" to "measurement pilot interval" | EDITOR |  | Review | EDITOR: 2017-06-24 22:44:19Z - status set to: Review |  |  |  | 2017-06-24 22:44 | EDITOR
274 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | "The TDLS responder STA shall discard the message, the TDLS responder STA shall abandon the TPK handshake" is garbled | Change the cited text to ""The TDLS responder STA shall discard the message, abandon the TPK handshake" | ACCEPTED (EDITOR: 2017-06-24 22:49:42Z) | EDITOR | [6 empty] | 2017-06-24 22:50 | EDITOR
275 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | ", and delete existing TPK handshake key state for this sequence" -- the term "TPK handshake key state" is not defined | Delete the cited text | . | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:50:11Z - status set to: Discuss This is a technical comment. |  |  |  | 2017-07-11 06:09 | EDITOR
277 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | Some of the ResultCodes in the SAP have underscores (e.g. JOIN_FAILURE_TIMEOUT, NOT_SUPPORTED) some not (e.g. AUTH FAILURE TIMEOUT, ANTI-CLOGGING TOKEN REQUIRED) | Remove the underscores from all the ResultCodes in the SAP |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:43:36Z - status set to: Discuss |  |  |  | 2017-06-24 22:44 | EDITOR
278 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | There are about 20 instances of "zero or one", but some are followed by the singular and some are followed by the plural | Either always follow with plural or always with singular |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:42:35Z - status set to: Discuss |  |  |  | 2017-06-24 22:43 | EDITOR
285 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are 3 instances of wording like "It is important that designers recognize the need for statistical independence among the random number streams among STAs." (1290.48, 1566.12, 1687.13) but only the last is a NOTE and the wording is not consistent | Make the first two NOTEs too, and change the wording to always be "It is important that designers recognize the need for statistical independence of the random number streams between STAs." | ACCEPTED (EDITOR: 2017-06-17 21:50:35Z) | EDITOR | [6 empty] | 2017-06-17 21:51 | EDITOR
301 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | "FST" is an action (fast session transfer), so what's an "FST session"? It doesn't make sense to say that an FST session is the state resulting from the operation of the FST session setup protocol -- a session is clearly not a state | Change all instances of "FST session" to "FST-capable association" |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:42:03Z - status set to: Discuss |  |  |  | 2017-06-24 22:42 | EDITOR
307 | Mark RISON | 25 | 0.1 |  |  |  | E | N |  |  |  |  | A |  |  |  | There are a few "hash function"s and many more "hash algorithms" | Change the "hash function"s to "hash algorithm"s throughout the draft | ACCEPTED (EDITOR: 2017-06-17 21:55:59Z) | EDITOR | [6 empty] | 2017-06-17 21:56 | EDITOR
326 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | An RTT is the time between a signal going out and coming back. It includes any processing time at the other side. The spec uses "RTT" to mean the total time of flight, not the RTT | Delete the RTT definition from 3.4 and instead add "TOF time of flight" At 83.58 change "round trip time (RTT)" to "distance" At 1771.20 change "an RTT" to "a two-way TOF" At 1772.28 change "The round trip time (RTT)" to "The two-way TOF" and change "RTT" to "TOF" in the equation At 3598.21 change "RTT" to "two-way TOF" (all references are to mc/D5.0) |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:41:42Z - status set to: Discuss This is a technical comment. |  |  |  | 2017-07-11 06:09 | EDITOR
327 | Mark RISON | 25 | 0.1 |  |  |  | E | N | [8 empty] | There seem to be at least three flavours of awake window: mesh, TDLS and DMG. The first seems to be so denoted, but the others not | Add "TDLS" or "DMG" before "awake window" where "mesh" is not present there |  | EDITOR |  | Discuss | EDITOR: 2017-06-24 22:41:14Z - status set to: Discuss |  |  |  | 2017-06-24 22:41 | EDITOR
328 | Mark RISON | 25 | 0.1 | 8.3.4.4 |  |  | E | N |  |  | 8.3.4.4 |  |  | Mark RISON |  |  | The description of the vectors in Clause 8 makes no sense. The various PHYs have very different vectors, so trying to have a generic description just doesn't work ("The name of the field used to specify the Tx data rate and report the Rx data rate may vary for different PHYs"). FWIW, my notes on D4.0 say that the parameters were disposed of as follows: active_rxchain_set: 10.2.5 operating_channel: 22.2.4.2, 22.2.4.3 channel_offset 22.2.4.2, 22.2.4.3 ant-config: T21.1 only group_id_management: 10.41, 22.3.11.4, 22.3.20 partial_aid_list_gid00: 9.20, 22.3.20 partial_aid_list_gid63: 9.20, 22.3.20 listen_to_gid00: 10.41, 22.3.20 listen_to_gid63: 10.41, 22.3.20 | Delete this subclause (or make it just say that each PHY defines its vectors), and move all the information to the PHY clauses. The PHYCONFIG_VECTORs should be described in tabular form, as the TX/RXVECTORs are |  | EDITOR | [6 empty] | 2017-07-12 10:37 | EDITOR
342 | Roger Marks | 25 | 0.1 | 9.4.2.171.2 | 1185 | 30 | E | N | 1185 | 30 | 9.4.2.171.2 |  | A |  |  |  | Description of TBTT Information Length subfield can be clarified by referring to the TBTT Information set that includes the TBTT Information fields. | Change the sentence at Page 1185 Lines 30-31 as follows: The TBTT Information Length subfield is 1 octet in length and contains the length in octets of each TBTT Information field that is included in the <insert>TBTT Information set of the</insert> Neighbor AP Information field. | ACCEPTED (EDITOR: 2017-07-10 13:08:56Z) | EDITOR |  | Review | EDITOR: 2017-07-10 13:09:04Z - status set to: Review EDITOR: 2017-06-24 23:29:24Z - status set to: Discuss |  |  |  | 2017-07-10 13:31 | EDITOR
346 | Stephen McCann | 25 | 0.1 | 9.4.5.25 | 1231 | 3 | E | N | 1231 | 3 | 9.4.5.25 |  | J |  |  |  | typo "info ID" | Change "info ID" to "Info ID" | REJECTED (EDITOR: 2017-06-24 23:33:02Z): "info ID" here is not a field or subfield, so that it shall be lower case. | EDITOR | [6 empty] | 2017-06-24 23:38 | EDITOR
347 | Stephen McCann | 25 | 0.1 | 9.4.5.24 | 1231 | 7 | E | N | 1231 | 7 | 9.4.5.24 |  |  | Emily Qi |  |  | Figure 9-658 is not very clear with repeating BSSID fields | Figure 9-658 needs to be modified to show that there are multiple differing BSSID fields #1 - #N, according to the latest IEEE 802.11 figure style guide. Commenter can provide a submission if required. |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:30:51Z - status set to: Submission Required |  |  |  | 2017-06-24 23:31 | EDITOR
348 | Stephen McCann | 25 | 0.1 | 9.4.5.24 | 1230 | 57 | E | N | 1230 | 57 | 9.4.5.24 |  |  | Emily Qi |  |  | The figures in clauses 9.4.5.24 to 9.4.5.27 have inconsistent styles of showing lists of mutliple sub-fields. Most of them are inconsistent when compared to the earlier ANQP-elements originating from IEEE 802.11-2016 | The figures in clauses 9.4.5.24 to 9.4.5.27 need to be modified so that the sub-fields are shown in a consistent manner, according to the latest IEEE 802.11 figure style guide. Commenter can provide a submission if required |  | EDITOR |  | Submission Required | EDITOR: 2017-06-24 23:30:37Z - status set to: Submission Required |  |  |  | 2017-06-24 23:31 | EDITOR
350 | Stephen McCann | 25 | 0.1 | 9.4.5.24 | 1231 | 21 | E | N | 1231 | 21 | 9.4.5.24 |  | A |  |  |  | The reference in the sentence "Each ANQP Query ID field value is drawn from Table 9-271 (DNS Info Control subfield settings(11ai))." is incorrect. | Change the sentence to "Each ANQP Query ID field value is drawn from Table 9-281--ANQP-element definitions." | ACCEPTED (EDITOR: 2017-06-24 23:32:37Z) | EDITOR | [6 empty] | 2017-06-24 23:33 | EDITOR
355 | Stephen McCann | 25 | 0.1 | 9.4.5.24 | 1230 | 47 | E | N | 1230 | 47 | 9.4.5.24 |  | A |  |  |  | Replace "ANQP query response" with "ANQP response" per the key in Table 11-15 | Change "ANQP query response" to "ANQP response". Also on P1231L27 and P1964L17 | ACCEPTED (EDITOR: 2017-06-24 23:30:06Z) | EDITOR | [6 empty] | 2017-06-24 23:30 | EDITOR