## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/1228r1
Venue Date: | August 2017
First Author: | Jiamin CHEN, Huawei/HiSilicon
Subject: | Comments from TGaj second recirculation sponsor ballot on D7.0
Full Date: | 2017-08-10
Author(s): | Name(s) | Jiamin CHEN | Shiwen He
| Affiliation | Huawei/HiSilicon | SEU
Address
Phone:
Fax:
| email: | jiamin.chen@mail01.huawei.com | shiwenhe@seu.edu.cn
Abstract:
This document contains comments received from the second recirculation sponsor ballot on 802.11aj D7.0. This document is periodically updated to reflect the status of those comments.

## Comments
CID | Commenter | SB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1001 | Chen, Jiamin | 3 | 7 | 9.4.2.232.5 | 219 | 42 | T | N | 219 | 42 | 9.4.2.232.5 |  | A | Jiamin Chen | 11-17/1235r0 | Motion 1 in 11-17/1232r1 | The value of Mse should be "4" rather than "7" when the Nss is 4. | Change the value of Mse from "4" to "7" when the Nss is 4. | Accepted
1002 | Chen, Jiamin | 3 | 7 | 25.6.8.14.2 | 242 | 17 | T | N | 242 | 17 | 25.6.8.14.2 |  | A | Jiamin Chen | 11-17/1235r0 | Motion 1 in 11-17/1232r1 | "Figure 25-27-NDP format" The title of Figure 25-27 needs to be more specific. | Change the title of Figure 25-27 from "NDP format" to "CMMG NDP format". | Accepted
1003 | Li, Dejian | 3 | 7 | 10.37a.6 | 128 | 40 | E | N | 128 | 40 | 10.37a.6 |  | A | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | Typo in " The SP allocation information obtained by receiving ..." | Change to "The SP allocation information is obtained by receiving ..." | Accepted
1004 | Li, Dejian | 3 | 7 | 10.37a.6 | 128 | 38 | T | N | 128 | 38 | 10.37a.6 |  | A | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | As for "for link(s) of other BSSs in the same AP or PCP cluster and according to the interference information from link(s) of other BSS to its BSS and the interference information from link(s) of its BSS to link(s) of other BSS(s) obtained in SPSH measurement phase.", use BSS(s) instead of BSS, make it consistent with the following "BSS(s)". | Change to "for link(s) of other BSSs in the same AP or PCP cluster and according to the interference information from link(s) of other BSS(s) to its BSS and the interference information from link(s) of its BSS to link(s) of other BSS(s) obtained in SPSH measurement phase." | Accepted
1005 | Li, Dejian | 3 | 7 | 10.37a.6 | 128 | 39 | T | N | 128 | 39 | 10.37a.6 |  | A | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | It is not clear what rules are applied for the link(s) of this AP's BSS and the link(s) of other BSS(s). | Add a rule at the end of this paragraph: The scheduled link(s) of the AP's or PCP's BSS and link(s) of other BSS(s) should not interfere with each other during the same SP. | Accepted
1006 | Li, Dejian | 3 | 7 | 24.9.2.2.1 | 182 | 31 | T | N | 182 | 31 | 24.9.2.2.1 |  | A | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | It is not correct for "does not feed back the measurement results". For the BRP-TX case, it is also needed to feedback the measurement results. | Change to "feed back the measurement result" | Revised Discussion: For the BRP-TX packets that have e-TRN-T/TRN-T training sequences appended to them, The receiving STA that performs measurements on these sequences should feedback the measurement results of both TRN-T and “STF+CE” in the e-TRN-T sequence. Change the last sentence of the second bullet in the last paragraph in 24.9.2.2.1 from "The receiving STA performs measurements on these sequences and sends feedback to the STA that transmits the BRP-TX packet, and does not feed back the measurement results of alternative link." to "The receiving STA performs measurements on these sequences and sends feedback to the STA that transmits the BRP-TX packet, including the measurement results of alternative link."
1007 | Li, Dejian | 3 | 7 | 10.37a.2.2 | 122 | 49 | T | N | 122 | 49 | 10.37a.2.2 |  | A | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | Channel Numbers for channel 5,6,7,8 are not correct according to Annex E. | Change Channel 5,6,7,8 to Channel 35,36,37,38, respectively, throughout the 802.11aj SPEC, including Figures and Tables. | Accepted
1008 | Li, Dejian | 3 | 7 | 9.4.2.227 | 50 | 41 | T | N | 50 | 41 | 9.4.2.227 |  | A | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | It is not clear how "The Available Cluster Time Offset Bitmap field is set to the Available Cluster Time Offset Bitmap field of the ECAPC Policy element." what is the ECAPC Policy element? | Change to "The Available Cluster Time Offset Bitmap field is set to the Available Cluster Time Offset Bitmap field of the reported S-AP's ECAPC Policy element." | Accepted
1009 | Li, Dejian | 3 | 7 | 10.37a.2.2 | 123 | 2 | T | N | 123 | 2 | 10.37a.2.2 |  | V | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | It is not clear how to "find an empty Beacon SP". | Add a rule to specify how to "find an empty Beacon SP" based on the received cluster information of the S-AP. | Revised Discussion: A rule that specifies how to find an empty Beacon SP based on the received cluster information of the S-AP is required here. Change the last sentence of the second bullet in the last paragraph in 24.9.2.2.1 from “…, and does not feed back the measurement results of alternative link.” To “…, including the measurement results of alternative link”
1010 | Li, Dejian | 3 | 7 | 10.37a | 117 | 46 | G | N | 117 | 46 | 10.37a |  | V | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | This subclause defines the CDMG clustering, text may needs to be improved. The relationship with the DMG clustering should be specified. | Clarify the relationship with the DMG AP/PCP clustering mechnism and improve the description of this subclause. | Revised Discussion: The relationship with the DMG AP/PCP clustering mechanism is clearly described in 10.37a.1 (General). So, improve some text as follows. Insert the following sentence as the first sentence in the bullet b) in P120L35: "Determine whether the ratio of BI 2 divided by CDMG SBBI of the S-AP or S-PCP is an integer. " Change the last sentence of the bullet b) in P120L35 from "... at the end of BI 2 or BI 3 and the AP or PCP 2 should also adjust its SBBI 2, ..." to "...at the end of BI 2 or BI 3, where the QP comprises the NP and a guard interval (GI) used for channel switching, and the AP or PCP 2 should also adjust its SBBI 2, ..." Insert the following sentence at the end of bullet b) in P120L50: "...For step a) and step b), changing BI on the 2.16 GHz channel or changing SBBI on the 1.08 GHz channel is completed by AP or PCP 1 by negotiation with AP or PCP 2 in a notification period (NP) that comprises NP1 and NP2. AP or PCP 1 transmits the DMG Beacon frame to AP or PCP 2 in NP1 and AP or PCP 2 transmits the DMG Beacon frame to AP or PCP 1 in NP2."
1011 | Li, Dejian | 3 | 7 | 10.36.11 | 116 | 8 | T | N | 116 | 8 | 10.36.11 |  | V | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | It is not clear how many channels on which AP can allocate SPs. | Define a rule to clarify the allocation mechnism when alternative channel is used. | Revised Insert the following sentence as the first sentence of paragraph in 10.36.11: “A CDMG AP or PCP may allocate a pair of STAs to perform SLS on an alternative channel.” Change “CDMG STA” to “CDMG initiator STA” in the second paragraph in 10.36.11. Change the third paragraph from “…in the AllocationType field and BF Control field for the pair of BF initiator and responder.” to “…in the AllocationType field and BF Control field for the initiator and responder that form a BF pair.”
1012 | Li, Dejian | 3 | 7 | 10.37a.6 | 128 | 40 | E | N | 128 | 40 | 10.37a.6 |  | A | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | Grammer mistake in this " The SP allocation information obtained by receiving the Extended Schedule element" | Change to " The SP allocation information is obtained according to the received Extended Schedule element" | Accepted
1013 | Li, Dejian | 3 | 7 | 24.9.2.2.2 | 182 | 46 | T | N | 182 | 46 | 24.9.2.2.2 |  | V | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | It is not clear what is "adjacent links " | Add more description to define the "adjacent links". | Revised Insert the following sentence after the third sentence of the second paragraph in 24.9.2.2.2: "The alternative link is a beam link with different propagation characteristic that cannot be measured accurately by the AGC field and the training field (TRN-R/T) that is used for measuring the adjacent beam links. "
1014 | Li, Dejian | 3 | 7 | 10.38.9 | 129 | 31 | G | N | 129 | 31 | 10.38.9 |  | V | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | Text may need to be improved. For example, the Annex Y should be referred in this subclause. | Annex Y should be referred in this subclause | Revised Insert the following paragraph at the end of 10.38.9: "Example of beam tracking and switching for enhanced beam tracking is shown in Annex Y.3."
1015 | Li, Dejian | 3 | 7 | 10.36.6.6.2a | 109 | 32 | T | N | 109 | 32 | 10.36.6.6.2a |  | V | Dejian Li | 11-17/1237r1 | Motion 1 in 11-17/1232r1 | It is not clear what happened if the first RTS/DMG CTS is failed. | Define a rule for the case of the first RTS/DMG CTS is failed | Revised Insert the following paragraph after Figure 10-56a: "If RTS/DMG CTS on the 1.08GHz channel failed, the CDMG STA shall not perform the subsequent RTS/DMG CTS on the 2.16GHz channel." Change the last sentence of the last paragraph in 10.36.6.6.2a from "...after the listening mode for subsequent SPSH after the beginning of the next BI." to "...after the listening mode for subsequent SPSH with time overlapping SPs for the two pair of STAs after the beginning of the next BI."

## Revision History
Revision | Date | Description
R0 | 2017-08-07 | Comments received from TGaj second recirculation sponsor ballot on D7.0.
R1 | 2017-08-10 | Resolution to each CID is included.

## References
References:
1. This document utilizes the template in the IEEE 802.11 comment spreadsheet.