## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/1574r0
Venue Date: | October 2017
First Author: | Michael Montemurro (BlackBerry Ltd)
Subject: | Privacy comment resolutions from 5th recirculation sb on tgaq d12.0
Full Date: | 2017-10-12
Author(s): | Name(s) | Michael Montemurro
| Company | BlackBerry Ltd.
Address
Phone:
Fax:
| email: | mmontemurro@blackberry.com
Abstract:
Comment resolutions for privacy comments.

## Revision History
Revision | Date | Description
0 | 2017-10-12 | Initial comment resolutions

## MAC
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
11001 | McCann, Stephen | 6000 | 12 | 12.2.10 | 66 | 60 | E | No | 66 | 60 | 12.2.10 |  | A |  |  |  | typo "Ifsuch...." | change to "If such..." at the beginning of the cited sentence | ACCEPTED (GEN: 2017-10-06 16:18:11Z). | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:04 | GEN
11002 | McCann, Stephen | 6000 | 12 | C.3 | 73 | 46 | T | No | 73 | 46 | C.3 |  | V |  |  |  | What is "SLAP" | A definition or reference should be inserted in the text at the cited sentence. | REVISED (GEN: 2017-10-06 16:34:22Z). Insert the following reference in Clause 2, maintaining alphabetic order: "IEEE Std 802c-2017, IEEE Standards for Local and Metropolitan Area Networks: Overview and Architecture Amendment 2: Local Medium Access Control (MAC) Address Usage."; insert the following new abbreviation in Clause 3.4, maintaining alphabetic order: "SLAP Structured Local Address Plan"; and expand the abbreviation in Clause C.3 from "SLAP" to "Structured Local Address Plan (SLAP) as defined in IEEE Std 802c-2017" in the first occurrence. | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:31 | GEN
11003 | McCann, Stephen | 6000 | 12 | C.3 | 74 | 29 | T | No | 74 | 29 | C.3 |  | V |  |  |  | I don't think that "dot11LocallyAdministeredMACConfig" should be part of the "dot11PADComplianceGroup", as this MIB variable has no impact on PAD behaviour | Consider deleting the "dot11LocallyAdministeredMACConfig" from the "dot11PADComplianceGroup". It then needs to be decided whether this MIB variable should reside within another MIB compliance group or not. | REVISED (GEN: 2017-10-06 16:38:26Z). Remove the "dot11LocallyAdministeredMACConfig" MIB variable from the "dot11PADComplianceGroup". | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:32 | GEN
11004 | Yang, Yunsong | 6000 | 12 | C.3 | 73 | 46 | T | No | 73 | 46 | C.3 |  | V |  |  |  | The term SLAP was introduced but not defined in the draft. | Insert the following reference in Clause 2, maintaining alphabetic order: "IEEE Std 802c-2017, IEEE Standards for Local and Metropolitan Area Networks: Overview and Architecture Amendment 2: Local Medium Access Control (MAC) Address Usage."; insert the following new definition in Clause 3.1, maintaining alphabetic order: "Structured Local Address Plan (SLAP): An optional standardized specification for the use of local medium access control (MAC) address space entailing the use of Extended Local Identifier (ELI), Standard Assigned Identifier (SAI), and Administratively Assigned Identifier (AAI) addresses in specific disjoint ranges."; and insert the following new abbreviation in Clause 3.4, maintaining alphabetic order: "SLAP Structured Local Address Plan" | REVISED (GEN: 2017-10-06 16:29:44Z). Insert the following reference in Clause 2, maintaining alphabetic order: "IEEE Std 802c-2017, IEEE Standards for Local and Metropolitan Area Networks: Overview and Architecture Amendment 2: Local Medium Access Control (MAC) Address Usage."; insert the following new abbreviation in Clause 3.4, maintaining alphabetic order: "SLAP Structured Local Address Plan"; and expand the abbreviation in Clause C.3 from "SLAP" to "Structured Local Address Plan (SLAP) as defined in IEEE Std 802c-2017" in the first occurrence. | GEN | 2017-10-06-telco | ready for motion | same resolution as CID 11002. |  |  |  | 2017-10-06 18:32 | GEN
11005 | Thomas, Angela | 6000 | 12 |  |  |  | T | Yes |  |  |  |  | J |  |  |  | RAC comment 1: The RAC is not satisfied with the response to Comment r04-9. We remain concerned that interested parties may have missed the opportunity to participate in the ballot, unaware that the draft would include specifications that present potential interoperability problems with other standards using IEEE-specified addressing. We appreciate the clarity added in the most recent revision by the distinction between addresses adopted for use in pre-association discovery and those adopted for use in subsequent data frames (and other frames) transmitted following such discovery. However, considering the scope of the project, per the PAR ["This amendment defines modifications to the IEEE 802.11 standard, above the physical layer (PHY), to enable delivery of pre-association Service Discovery information discovery by IEEE 802.11 stations (STAs)."], it seems apparent that specifying a new method to assign LAN data frame addresses is out of scope. We disagree with the statement, in response to comment r-04-9, that "These changes include removal of any specification for behavior after discovery and selection." The draft is specifying the assignment of addresses for data frames sent after discovery, which is an important aspect of the behavior after discovery of services. |  | REJECTED 1) The RAC comment is welcomed and appreciated; however, as there is no proposed change, the CRC have rejected this comment. 2) The comment makes a general claim that that there are interoperability issues with other standards that make use of IEEE addressing but does not describe a single interoperability issue or suggest a text change that would address the interoperability . 3) Pre-association Service Discovery mechanisms specified in this amendment have the potential to leak privacy information. The privacy mechanisms incorporated into this amendment address privacy concerns with pre-association service discovery. Therefore it is the view of the CRC that privacy is within scope of the PAR. 4) Although the draft specifies MAC address selection in the pre-associated state, the draft clarifies the selection of the MAC address used when a BSS is selected is associated with the MAC address. | GEN | MAC | [5 empty] | 2017-10-06 18:05 | GEN
11006 | Thomas, Angela | 6000 | 12 |  |  |  | T | Yes |  |  |  |  | J |  |  |  | RAC comment 2: The RAC is not satisfied with the response to Comment r04-8. We appreciate the clarity added in the most recent revision by distinguishing between addresses adopted for use during pre-association discovery and those adopted for use in subsequent data frames (and other frames) transmitted following such discovery, and we accept the view that the two circumstances differ. During the discovery process, the draft still specifies that station adopts a 46-bit random address. The response presumes is that the RAC concerns will be satisfied pre-association, because "frame exchanges between an unassociated STA and an AP take the form of a request/response transaction and are not forwarded to any other devices on the network." The concern remains, because this protocol takes over the entirety of the local address space with the wireless LAN, leaving no local address there safe from possible duplication. We are concerned that some wireless LAN uses may demand a collision-free local address. Unless the WG can demonstrate that conflict in the discovery address cannot negatively impact any network element operating on a fixed local address within the wireless LAN, then the size of the random address space should be reduced to be smaller than the entire space, preferably limited to the AAI space or even a smaller space, such as a CID allocation. We do not see justification for the claim in the response that "The full 46 bits of randomization for the MAC is required to address privacy issues associated with network discovery when the STA is in the unassociated state." We are confident that privacy is attainable in a far smaller space. Also, we suspect that the impact of a smaller space during pre-association is minimal, because (1) the probability of address collision is quite low in discovery since addresses are used only very briefly, and (2) the impact of collision during pre-association discovery [as contrasted to the impact of collisions with data frames] appears to be negligible. |  | REJECTED 1) The RAC comment is welcomed and appreciated; however, as there is no proposed change, the CRC have rejected this comment. 2) In the discovery state, STAs are not operating on a LAN. The only communications is between STAs. Frames transmitted between a STA and an AP terminate at the AP and never reach the LAN. Security and duplication detection mechanisms prevent frames from a non-assocated STA with a conflicting MAC address from affecting any traffic in the BSS. See https://mentor.ieee.org/802.11/dcn/17/11-17-1565-00-00aq-pre-association-summary.ppt for a clarification on pre-associated STA behavior. 3) The privacy concerns with 802.11 devices are documented in European proceeding, for instance in case z2014-00944 at the Dutch Data Protection Authority, and case 2729-2014 at the Swedish Data Protection Authority. Privacy concerns with MAC Randomization has also been studied in technical literature, and found to be a necessary but not sufficient condition for effective privacy protection. See the Dutch Data Protection case z2014-00944 https://autoriteitpersoonsgegevens.nl/sites/default/files/atoms/files/rapport_db_bluetrace.pdf and the Swedish Data Protection Authority case 2729-2014 http://www.datainspektionen.se/Documents/beslut/2015-06-23-vasteras.pdf. 4) The probability of a collision in a crowded space with a 44 bit randomized MAC is high. Take the example of Times Square on New Years eve. There are estimated 1,000,000 people (http://www.newyearseve.nyc/nyc/index.aspx#.Wd0jmhNSwUF) in the square. If there are 250,000 STAs that are all in "earshot" of each other then we have: n = 250,000, m = 44 at 0.001774, which is about 1 in 563 n = 250,000, m = 46 at 0.0004439, which is about 1 in 2252. | GEN | MAC | [5 empty] | 2017-10-06 18:05 | GEN
11007 | Thomas, Angela | 6000 | 12 |  |  |  | T | Yes |  |  |  |  | J |  |  |  | RAC comment 3: The RAC is not satisfied with the response to Comment r04-12. We appreciate the clarity added in the most recent revision by distinguishing between addresses adopted for use during pre-association discovery and those adopted for use in subsequent data frames (and other frames) transmitted following such discovery, and we appreciate the introduction of a mechanism related to post-association address allocation. However, even if the assignment of post-association addresses were within the project scope, the RAC remains concerned with the new mechanism introduced to manage the address allocation. We would prefer a direct control functionality by which the network could specify a local address plan and policy. The current draft instead proposes a MIB-based solution without specifying any method to establish the relevant parameter or how the MAC address is selected based on the content of the MIB variable. Furthermore, the default value ("DEFVAL") of the parameter is 0, so legacy devices and non-provisioned devices will presume that "local addresses do not comply with the SLAP". It appears that this would suggest that all 2^46 addresses are available for random selection. The second sentence in 12.2.10 says " Such a non-AP STA shall periodically change its MAC address to a random value while not associated to a BSS." Nothing specifies that this address is changed prior to association, so presumably the last random value in place before association is the address used during association. Later, in subclause 12.2.10, a paragraph says "To construct a random MAC address..." and goes on to specify a 46-bit random address. So, in spite of the suggestion that this MIB variable would allow the network to change the addressing behavior for associated stations, we see no explicit control. We do not agree with the statement in the response that "Behavior in the Associated state has been modified to allow a STA to be configured to conform to requirements in a Locally Administered address space." |  | REJECTED 1) The RAC comment is welcomed and appreciated; however, as there is no proposed change, the CRC have rejected this comment. 2) The P802.11aq draft has been modified to provide a means for using a randomized MAC address during pre-association. When the device selects and associates to a network using an IEEE 802 technology, it is implied that the device willl conform with IEEE 802 MAC address, either an assigned globally unique MAC address or a locally administerered MAC address conformant with IEEE 802-2014 and IEEE 802c-2017. 3) A STA needs to be properly configured in order to successfully associate and communicate with a network through a BSS. For Enterprise Networks and Carrier Public Networks, this involves the STA being provisioned with security information and IP configuration (e.g. Certificate, SIM or other user credentials, DHCP enabled/disabled, DNS). For Home networks, the device is at least provisioned with a WPA2-Passphrase. For open public networks, no information is configured on the device. However, there is default behavior that is assumed (e.g. use DHCP) when the device connects to the network. Currently there are no protocols defined in IEEE 802 to assign MAC addresses in a locally administerd network, so a device has to be configured to successully connect and operate in that network. This would include the assignment of a locally administered MAC address. The MIB varable defined in the draft allows a STA to assign its MAC address to an administratively configured address. If an IEEE 802 project or an IEEE 802.11 project were to create an automatic way to assign a locally administered MAC address, this MIB variable could be configured to do so. The MIB variable enables direct control functionality by which the network could specify a local address plan and policy. 4) The vast majority of networks that a STA associates with, do not make use of a locally administered addressing plan. Therefore the default value of dot11LocallyAdministeredMAC Config is set to 0 (false) by default. | GEN | MAC | [5 empty] | 2017-10-06 18:05 | GEN
11008 | McCann, Stephen | 6000 | 12 | 11.25a.2 | 64 | 47 | T | No | 64 | 47 | 11.25a.2 |  | V |  |  |  | It's not very clear what "information", the first line of this paragraph is referring to. | change "...the information..." to "...the resulting information from the received Service Hint element or Service Hash element..." | REVISED (GEN: 2017-10-06 16:44:17Z). Change the cited text from: "The non-AP and non-PCP STA may use the information regarding which services are reachable as input to network discovery and selection procedures" to "The non-AP and non-PCP STA may use the resulting information as to which services are reachable as input to network discovery and selection procedures" | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:33 | GEN
11009 | McCann, Stephen | 6000 | 12 | 11.25a.3.2 | 65 | 30 | T | No | 65 | 30 | 11.25a.3.2 |  | A |  |  |  | It may be possible for the STA to use the service information in network selection at this point, in a similar manner to the "unsolicited PAD procedure". | After the first sentence in the paragrpah, add the following sentence "The non-AP and non-PCP STA may use the service information regarding which services are reachable as input to network discovery and selection procedures." | ACCEPTED (GEN: 2017-10-06 16:51:58Z). | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:04 | GEN
11010 | McCann, Stephen | 6000 | 12 | 11.25a.3 | 64 | 56 | T | No | 64 | 56 | 11.25a.3 |  | A |  |  |  | There doesn't appear to be any reason why clauses 11.25a.3.1 and 11.25a.3.2 should exist. It seems reasonable to remove these two sub-clause headings and merge the text into a single clause. | Rename clause 11.25a.3 to "Solicited PAD procedure". Remove the titles of sub-clauses 11.25a.3.1 and 11.25a.3.2 and merge the text into one single new clause (i.e. 11.25a.3) | ACCEPTED (GEN: 2017-10-06 16:54:21Z). | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:04 | GEN
11011 | McCann, Stephen | 6000 | 12 | 11.25a.2 | 64 | 30 | T | No | 64 | 30 | 11.25a.2 |  | V |  |  |  | Step 1 needs to be clarified for the Service Hint element | Change step 1 to "From the received Beacon, DMG Beacon, Announce, or Probe Response frames process the Service Hash elements to generate a list of services reachable via the BSS or process the Service Hint elements to determine the parameters of the bloom filter." | REVISED (GEN: 2017-10-06 16:57:43Z). Change the cited text from: ""From the received Beacon, DMG Beacon, Announce, or Probe Response frames process the Service Hash elements to generate a list of services reachable via the BSS or process the Service Hint elements to determine the parameters of the bloom filter." to "From the received Beacon, DMG Beacon, Announce, or Probe Response frames process the Service Hash elements to generate a list of services reachable via the BSS and process the Service Hint elements to determine the parameters of the bloom filter." | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:36 | GEN
11012 | Hamilton, Mark | 6000 | 12 | 11.25.3.2.3 | 57 | 16 | T | Yes | 57 | 16 | 11.25.3.2.3 |  | V |  |  |  | It is at best very confusing, and more likely technically incorrect, to initialize the PostReplyTimer to one of two variables, which have different units (without converting). I can see that PostReplyTimer is theoretically unitless, and just an abstract time. Howevr, this text is going to lead to implementation errors by those who don't research each reference to this timer in the spec and figure that out. | Change "value of Maximum Channel Time" to "value of Maximum Channel Time times 10" | REVISED (GEN: 2017-10-06 17:03:20Z). Change "value of Maximum Channel Time" to "value of Maximum Channel Time field times 10". | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:04 | GEN
11013 | Marks, Roger | 6000 | 12 | 12.2.10 | 66 | 51 | T | Yes | 66 | 51 | 12.2.10 |  | J |  |  |  | Comment r04-9 suggests that the scope of the draft exceeds that of the PAR ("... to enable delivery of pre-association Service Discovery information discovery..."). The response to that comment says that changes "include removal of any specification for behavior after discovery and selection." However, the draft does not actually delete such out-of-scope specification, because it specifies the randomization of the MAC address but does not specify how the MAC address is restored to a non-randomized condition for use in the associated state. | In the end of the second sentence of 12.2.10, change "periodically" to "temporarily" and add, to the end of the sentence, "and shall restore its MAC address to a non-randomized value prior to initiating association." | REJECTED (GEN: 2017-10-06 17:16:51Z). The change of the term "periodically" alters the behavior described in the cited paragraph, as the change can occur over time, while the STA is in the pre-associated state. The nature of randomisation being temporary is obvious due to behahiour within the second paragraph. The suggested text for the end of the sentence is already covered within the first sentence of the secod paragraph. | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:39 | GEN
11014 | Marks, Roger | 6000 | 12 | 11.1.4.3.1 | 51 | 37 | T | Yes | 51 | 37 | 11.1.4.3.1 |  | V |  |  |  | Comment r04-15 reiterates proposals to ensure that dot11MACPrivacyActivated is optional. Its proposal to change the sentence "A non-AP STA sets dot11MACPrivacyActivated to true to resolve this concern" was not addressed. This sentence should be changed. Firstly, the text should make clear that setting the parameter is optional. Secondly, the suggestion that the "STA" is the actor is inconsistent with the specification of the dot11MACPrivacyActivated object. | Change "A non-AP STA sets dot11MACPrivacyActivated to true to address this concern" to "The SME or an external management entity may set dot11MACPrivacyActivated to true to address this concern" | REVISED (GEN: 2017-10-06 17:38:44Z). Remove clause 11.1 from the 11aq draft. | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:39 | GEN
11015 | Marks, Roger | 6000 | 12 | 12.2.10 | 66 | 49 | T | Yes | 66 | 49 | 12.2.10 |  | V |  |  |  | The sentence has been changed to make the condition be that dot11MACPrivacyActivated is set true "by a non-AP STA". However, the specification of the dot11MACPrivacyActivated object indicates that the variable "is written by an external management entity or the SME." In fact, there is no need for the setter of the variable to limit the condition; the condition should be the truth of the condition, not what set that condition to true. | Delete "by a non-AP STA". | REVISED (GEN: 2017-10-06 17:42:51Z). Delete "by a non-AP STA" at the cited reference. Change the start of the next sentence from "Such a non-AP STA shall..." to "A non-AP STA shall" | GEN | 2017-10-06-telco | ready for motion |  |  |  |  | 2017-10-06 18:40 | GEN
11016 | Marks, Roger | 6000 | 12 | 12.2.10 | 67 | 18 | T | Yes | 67 | 18 | 12.2.10 |  | V |  |  |  | As discussed in prior comments (including r04-14 and r04-16), the proposal to randomize over 46 bits means that the entire local space will be given over to randomized addresses, raising issues of conflict with other addressing schemes in the local space, even though many devices do not benefit from local addresses. Therefore, a decision to randomize over the entire space will negatively affect the development of IEEE 802.11, without benefit. No case has been demonstrated for requiring such a huge address space for a relatively small problem, since collisions within the discovery phase are nearly harmless and since collisions are very unlikely, even in large networks, because the lifespan of a selected address is very short. | Revise the paragraph at line 15-18 to specify that the randomization will take place within the 24-bit address space within a CID block allocated for the purpose by the IEEE Registration Authority. | REVISED At P67L15, Change "To construct a random MAC address, the STA shall set bit 1 of the first octet to 1 (indicating a locally administered MAC address) and bit 0 of the first octet to 0 (indicating unicast) and shall assign random values to the other 46 bits." to "To construct a random MAC address the STA shall select a randomized MAC address according to IEEE Std. 802-2014 and IEEE Std 802c-2017." Note to the editor to add IEEE Std 802c-2017 to the references clause. | GEN | MAC | discussed |  |  |  |  | 2017-10-06 18:42 | GEN