## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-17/1620r0
Venue Date: | November 2017
First Author: | Yunsong Yang (Huawei Technologies)
Subject: | Comments from 6th Recirculation Sponsor Ballot (SB6) on P802.11aq D13.0
Full Date: | 2017-10-31
Author(s): | Name(s) | Yunsong Yang
| Company | Huawei Technologies
Address
Phone:
Fax:
| email: | yangyunsong@huawei.com
Abstract:
This document records the 15 comments (numbered as CIDs 12001 - 12015) received from the 6th Recirculation Sponsor Ballot (SB6) on P802.11aq D13.0 and any resolutions approved by 802.11 TGaq (CRC). The comments are organized as follows: A tab for all SB6 comments; and
A tab per comment group for SB6 comments:
Tabs named with clause # or techical subject are for coments not ready-for-motion.
Tabs named with a date are for comments that are ready-for-motion or approved.
Mapping of CID numbers of all previous and current WG LBs and SBs are as follows:
Draft 1.0, LB208 (Initial WG Ballot, failed) CIDs 1001 to 1801
Draft 3.0, LB216 (Initial WG Ballot, passed) CIDs 2000 to 2399
Draft 4.0, LB219 (First Recirc) CIDs 3001 to 3071
Draft 5.0, LB221 (Second Recirc) CIDs 4001 to 4065
Draft 6.0, LB222 (Third Recirc) CIDs 5001 to 5043 Draft 7.0, LB1000 (Initial Sponsor Ballot) CIDs 6001 to 6235
Draft 8.0, LB2000 (First Recirc Sponsor Ballot) CIDs 7001 to 7175
Draft 9.0, LB3000 (2nd Recirc Sponsor Ballot) CIDs 8001 to 8075
Draft 10.0, LB4000 (3rd Recirc Sponsor Ballot) CIDs 9001 to 9047
Draft 11.0, LB5000 (4th Recirc Sponsor Ballot) CIDs 10001 to 10016
Draft 12.0, LB6000 (5th Recirc Sponsor Ballot) CIDs 11001 to 11016
Draft 13.0, LB7000 (6th Recirc Sponsor Ballot) CIDs 12001 to 12015

## Revision History
Revision | Date | Description
0 | 2017-10-31 | Initial export from DB; all CIDs assigned to the GEN Ad-hoc.

## All SB6 Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
12001 | Yang, Yunsong | 7000 | 13 | 11.0.4.3 | 51 | 22 | T | No | 51 | 22 | 11.0.4.3 | [5 empty] | Comment resolution to CID 11014 is not fully implemented in D13.0. The resolution is not to remove just the title of Clause 11.1, but to remove the entire Clause 11.1, including 11.1.4.3 and 11.1.4.3.1, from 11aq draft, because 11aq will make no change to Clause 11.1 in the baseline document. | Delete the text between L22 and L36. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12002 | Yang, Yunsong | 7000 | 13 | C.3 | 72 | 47 | E | No | 72 | 47 | C.3 | [5 empty] | Typo in "802c-21017". | Change "802c-21017" to "802c-2017". |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12003 | Turner, Michelle | 7000 | 13 | 0 | 0 | 0 | G | No | 0 | 0 | 0 | [5 empty] | This draft meets all editorial requirements. |  |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12004 | Hamilton, Mark | 7000 | 13 | C.3 | 72 | 46 | T | Yes | 72 | 46 | C.3 | [5 empty] | While the dot11LocallyAdministeredMACConfig mode 0 doesn't say 44 bits or 46 bits anymore, it now doesn't say anything. I continue to not understand the rationale for why an 802c conformant address can't be used, in the general case. Surely, 44 bits for unassociated devices is sufficiently random to avoid accidental collision within the radius of the 802.11 signal, which is all thta should be needed. Then, in some specific cases, someone might want to use a more specific allocation/algorithm, but the implication of mode 0 seems to be a free-for-all, rather than a specific purpose-driven method. This is exacerbated by making mode 0 the default. It seems like an 802 standard should make the 802-approved methods the default, with the exception being provided for those cases that need it, but not the default. | Change the usage of dot11LocallyAdminsterdMACConfig to have "local addresses comply with the SLAP" as the default. Suggest doing so by reversing the assignment of "0" and "1". |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12005 | Hamilton, Mark | 7000 | 13 | 12.2.10 | 66 | 57 | T | Yes | 66 | 57 | 12.2.10 | [5 empty] | Since a non-AP STA shall use the MAC address used for/during the creation of any shared state, after association, it would be helpful to be clear that the implication is that the device needs to use an appropriate address (per dot11LocallyAdministeredMACConfig setting) before starting any potential shared state interchange. | Change the second paragraph of 12.2.10 to: If such a non-AP STA starts any transaction that establishes state bound to a MAC address and might elect to establish a connection to a discovered BSS, it shall check the value of dot11LocallyAdministeredMACConfig and shall configure its MAC address according to the rules of the local address space prior to the start of the transaction. The non-AP STA shall continue to use the MAC address used when the state was created throughout the transaction and connection. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12006 | Hamilton, Mark | 7000 | 13 | C.3 | 72 | 47 | E | Yes | 72 | 47 | C.3 | [5 empty] | Typo | Change "21017" to "2017" |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12007 | Malinen, Jouni | 7000 | 13 | C.3 | 72 | 47 | E | Yes | 72 | 47 | C.3 | [5 empty] | Typo in the IEEE 802c reference. | Replace "IEEE Std 802c-21017" with "IEEE Std 802c-2017". |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12008 | Malinen, Jouni | 7000 | 13 | 12.2.10 | 67 | 12 | T | Yes | 67 | 12 | 12.2.10 | [5 empty] | The shall requirement mandating a specific manner of constructing a random MAC address "according to IEEE Std 802-2014 and IEEE Std 802c-2017" is both confusing and also conflicting with P802.11aq descriptions elsewhere. In addition, if the goal of this new language is to severely limit the number of bits used for this, this has also potential for harm on network connectivity due to increased likelihood of collisions when multiple STAs are selecting randomized MAC addresses. IEEE Std 802-2014 does not even have the word "random" or "randomized" in it. IEEE Std 802c-2017 on the other hand is trying to enforce rules that do not match what vendors have used for more than ten years in deployed IEEE 802.11 products. As far as P802.11aq is concerned, the dot11LocallyAdministeredMACConfig variable (as pointed out couple of paragraphs above this modified text) describes how the randomized MAC address is selected. Its default value 0 points to IEEE Std 802c-2017, but the value 2 does not and this new shall statement is clearly in conflict with that case. 46-bit random address space needs to continue to be allowed for data connections to maintain sufficiently small probability of collisions. | Replace "To construct a random MAC address the STA shall select a randomized MAC address according to IEEE Std 802-2014 and IEEE Std 802c-2017." with "To construct a random MAC address the STA shall select a randomized MAC address according to dot11LocallyAdministeredMACConfig." |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12009 | Thomas, Angela | 7000 | 13 |  |  |  | T | Yes | [8 empty] | RAC comment: The RAC remains unsatisfied with the responses to unresolved RAC Mandatory Coordination comments submitted in earlier ballot rounds. | RAC suggested remedy: Implement changes consistent with earlier RAC comments. Because the P802.11aq comment resolution group and responses in those earlier ballot rounds have not addressed the substance at the heart of RAC comments, the RAC believes all remaining Mandatory Coordination issues can best be satisfied by deleting all references and specifications in the draft to use of random MAC addresses. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12010 | Marks, Roger | 7000 | 13 | 12.2.10 | 66 | 47 | T | Yes | 66 | 47 | 12.2.10 | [5 empty] | The draft has reverted to an even more radical stance of precluding backward compatibility with all prior 802.11 products and mandating that no future implementations will comply with IEEE Std 802.11 unless they adopt the proposed new addressing scheme. Despite prior comments (r04-15 and r05-14) on the topic, the ballot resolution group has not specifically acknowledged that its intention is make this behavior mandatory, and yet it has again acted to do so, with requirements such as "A non-AP STA shall periodically change its MAC address to a random value while not associated to a BSS." | Acknowledge definitively in a comment response that the explicit intention of the ballot resolution committee is to ensure that MAC address randomization is mandatory on all 802.11 implementations. Alternatively, state definitively in a comment response that the explicit intention of the ballot resolution committee is to ensure that MAC address randomization is optional, and modify the draft accordingly, in particularly by changes including: (1) changing "MAC privacy enhancements are enabled when dot11MACPrivacyActivated is set to true. A non-AP STA shall periodically change its MAC address to a random value while not associated to a BSS." to "When dot11MACPrivacyActivated is set to true, MAC privacy enhancements are enabled and non-AP STA shall periodically change its MAC address to a random value while not associated to a BSS."; (2) changing at page 51 line 34 as follows "A non-AP STA <insert>optionally</insert> sets dot11MACPrivacyActivated to true to address this concern (see 12.2.10)." |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12011 | Marks, Roger | 7000 | 13 | 11.0.4.3.1 | 51 | 22 | E | Yes | 51 | 22 | 11.0.4.3.1 | [5 empty] | Clause numbering is incorrect (11.0.4.3 and 11.0.4.3.1). | Change to 11.1.4.3 and 11.1.4.3.1, respectively. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12012 | Marks, Roger | 7000 | 13 | 12.2.10 | 66 | 47 | T | Yes | 66 | 47 | 12.2.10 | [5 empty] | The disposition detail of the rejected comment r05-13 fails to acknowledge the comment and its argument that the draft exceeds the scope of the PAR. The comment proposed that PAR randomization be limited to pre-association, in accordance with the PAR scope. The disposition says that the proposed text is "already covered within the first sentence of the second paragraph." This, however, is false; that sentence does not include the proposal or anything remotely like it. | Acknowledge definitively in a comment response that the explicit intention of the ballot resolution committee is to specify MAC address assignment for post-association use and explain how that is consistent with the PAR scope. Alternatively, state definitively in a comment response that the explicit intention of the ballot resolution committee is to not specify MAC address reassignment for post-association use, and reconsider the proposal in r05-13 as a starting point in revising the draft in accordance with that limitation. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12013 | Marks, Roger | 7000 | 13 | 12.2.10 | 67 | 12 | T | Yes | 67 | 12 | 12.2.10 | [5 empty] | The new paragraph says that "To construct a random MAC address the STA shall select a randomized MAC address according to IEEE Std 802-2014 and IEEE Std 802c-2017." IEEE Std 802 (and its amendment 802c) specify architecture of "Local and Metropolitan Area Networks." However, the disposition of RAC comment r05-6 argues that "In the discovery state, STAs are not operating on a LAN." If that statement is valid, then IEEE Std 802 has no relevance or applicability to pre-association discovery. | Acknowledge definitively in a comment response that the explicit intention of the ballot resolution committee is to assert that 802.11 non-AP STAs exchanging frames with an AP in an unassociated state are not operating as a LAN, and explain how this perspective is consistent with the PAR and with IEEE Std 802.11. Alternatively, revisit r05-6 comprehensively. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12014 | Marks, Roger | 7000 | 13 | 12.2.10 |  |  | T | Yes |  |  | 12.2.10 | [5 empty] | The disposition of RAC comment r05-6 presents a mathematical analysis of the probability of random address collision. The analysis is faulty because the model does not consider time as a factor. It presumes that each device selects a single random address and considers whether those addresses could collide. However, this analysis ignores the premise of the comment, when indicates that, when used for pre-association, the selected address is used ephemerally and very briefly, such that subsequent collisions are harmless and irrelevant. In this case, the analytical model presumes that not only that 250,000 STAs are in range of each other but that each conducts pre-association discovery at the identical instance. When the likelihood of simultaneous discovery is considered, the numerical results will be very different. Furthermore, the disposition fails to address the element of comment r05-6 suggesting that "the impact of collision during pre-association discovery [as contrasted to the impact of collisions with data frames] appears to be negligible." | Revisit r05-6 and provide a comprehensive disposition. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN
12015 | Marks, Roger | 7000 | 13 | 12.2.10 |  |  | T | Yes |  |  | 12.2.10 | [5 empty] | The disposition of RAC comment r05-5 includes four elements, but only one of these seems responsive to the comment, which concerns addresses assigned for use in the associated state. Unfortunately, that element of the response is incomprehensible; it says: "4) Although the draft specifies MAC address selection in the pre-associated state, the draft clarifies the selection of the MAC address used when a BSS is selected is associated with the MAC address." | Revisit r05-5 and provide a comprehensive and comprehensible disposition. |  | GEN | [6 empty] | 2017-10-31 17:27 | GEN