## Slide 1: TGax November 2017 Closing Report
Date: 2017-11-09
Authors:

## Slide 2: Abstract
This document is the closing report for the TGax for the November 2017 session.

## Slide 3: Work Completed
The TG almost completed the assignment of comments received on Draft D2.0.
  A lead is identified for various clauses of the draft. The lead is responsible for coordinating resolutions of relevant CIDs.
The TG approved resolutions to 36 CIDs
The TG updated its timeline to reflect the outcome of WG LB.
A TG motion passed to hold an ad hoc meeting in San Diego during the period January 10-12, 2018.
The agenda is available at: https://mentor.ieee.org/802.11/dcn/17/11-17-1546-04-00ax-tgax-november-2017-meeting-agenda.pptx

## Slide 4: Timeline
Old Timeline
May 2014: start of the TG
Nov. 2014: First draft of the TG SFD was approved
Jan. 2016: proposed TG draft
March 2016: Draft D0.1 was approved and CC started
November 2016: Draft 1.0 and WG letter ballot
  LB-225: opened Dec. 1st 2016 and closed January 8th 2017
September 2017: Draft 2.0 and WG letter Ballot
  LB-230: opened at Oct. 5th 2017 and closed Nov. 4th 2017
May 2018: MDR (Mandatory Document Review)
May 2018: Formation of SB pool  Need to change the date
November 2018: Sponsor Ballot
July 2019: RevCom
New Timeline
May 2014: start of the TG
Nov. 2014: First draft of the TG SFD was approved
Jan. 2016: proposed TG draft
March 2016: Draft D0.1 was approved and CC started
November 2016: Draft 1.0 and WG letter ballot – Failed (57.77%)
  LB-225: opened Dec. 1st 2016 and closed January 8th 2017
September 2017: Draft 2.0 and WG letter ballot – Failed (62.84%)
  LB-230: opened Oct 5th and closed Nov 4th, 2017
May 2018: Draft 3.0 and WG letter Ballot
July 2018: MDR (Mandatory Document Review)
February 2019: Formation of SB pool
May 2019: Sponsor Ballot
December 2019: RevCom

## Slide 5: January 2018 Goals
Continue with comment resolution on draft D2.0.

## Slide 6: Conference Call Times
Nov. 30, Dec. 14, Jan 4 10:00 -1200 ET
Dec. 7, 21, Jan 25 20:00 – 22:00 ET