## Slide 1: TGax timeline
Date: 2018-05-10
Authors:

## Slide 2: Abstract
Milestones for the current TGax timeline

## Slide 3: TGax timeline
Pass WG letter ballot with D3.0 release
  The higher the approval rate the better
Turn around D4.0 in 3 meeting cycles (vs 4 for D3.0 and 5 for D2.0)
Turn around D5.0 in 2 meeting cycles
Go to sponsor ballot in May 2019
  Need a high approval rate (95%+) on D5.0
Publish Dec 2019
D1.0
D1.0
D1.0
D2.0
D2.0
D2.0
D3.0
D3.0
D4.0
D5.0
D3.0
D4.0
D5.0
D6.0
D7.0
D5.0
Publish
74%
89%
91%
94%
95%
58%
63%
47%
83%
84%
88%
90%
Nov 2017
Sep 2017
May 2018
11n
11ac
11ax
Publish
Sept 2009
Mar 2019
D4.0
Nov 2018
Mar 2008
Mar 2006
May 2011
Mar 2013
Sponsor Ballot
Sponsor Ballot
802.11 sessions
Dec 2013
Sponsor Ballot
Publish
Dec 2019
Sept 2008
Jan 2007
Sept 2007

## Slide 4: Timeline details
30 day ballot coming out of May 2018 session
  Leaves little time for comment resolution preparation for July 2018
15 day ballot coming out of Nov 2018 session
  Holiday season will impact comment resolution preparation for January 2019
15 day ballot coming out of March 2019 session
Go to sponsor ballot July 2019 plenary
D3.0
Publish
Dec 2019
D5.0
D4.0
May
July
Sept
Nov
Jan
March
May
Nov
July
Sept
2018
2019
30 day
15 day
15 day
Sponsor ballot