## Slide 1: Predicting timelines: the track record
Date: 2018-07-10

## Slide 2: Abstract
Recent presentations have discussed how to reform IEEE’s process for developing amendments, with a view to making it all more efficient
― See 11-18/1259r0, “A cascading process for major amendments”, R. Stacey et al., July 2018
We have been here before: this presentation reviews the track record from ax
The conclusion is that estimates almost always err on the very optimistic side

## Slide 3: Illustration of potential timelines for 802.11ax
long track
fast track
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
Laurent Cariou (Orange)
From 11-14/0617r1, “Discussion on timeline for 802.11ax:, L. Cariou, T. Derham, May 2014

## Slide 4: Illustration of potential timelines for 802.11ax
long track
fast track
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
Laurent Cariou (Orange)
NOW
Overoptimistic
Way
overoptimistic

## Slide 5: Preliminary Timeline Projection, Scenario A, with ‘normalized’* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
2019
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
.11ax Draft 2.0
(Nov 2016)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0
(January 2016)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Sept 14 - July 2015)
11ax SFD
TG Kick Off
(May 2014)
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014 (D2.0: Nov 2016)

## Slide 6: Preliminary Timeline Projection, Scenario B, with ‘normalized* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
2019
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
.11ax Draft 2.0 (Mar 2017)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0 (July 2016)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Nov 14 - Jan 2016)
11ax SFD
TG Kick Off
(May 2014)
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014 (D2.0: Mar 2017)

## Slide 7: Preliminary Timeline Projection, Scenario C, with ‘normalized* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
.11ax Draft 2.0 (Nov 2017)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0 (Jan 2017)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Jan 15 - July 2016)
2019
11ax SFD
TG Kick Off
(May 2014)
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014 (D1.0 Jan 2017; D2.0: Nov 2017)
(!—good estimate!)

## Slide 8: Strawpoll
What scenario should be reflected in the 802.11ax timeline estimate:
A: Scenario A (D1.0 in Jan 2016): 48
B: Scenario B (D1.0 in July 2016): 54
C: Scenario C (D1.0 in Jan 2017): 12
D: Other timeline: 6
E: Don’t know / Abstain: 7
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014
The good news is that we had the exact schedule. The bad news is that we refused to believe it.

## Slide 9: Conclusion
It is not enough to sketch a possible parallel process: without rigorous enforcement mechanisms it just won’t happen that way
Even the most optimistic, least realistic estimates at the beginning of ax did not achieve PAR  D2.0 in 24 months
  Eventually took 44 months
The best timeline estimates are those derived from actual past experience in IEEE 802.11
  Start with 24 month target (PAR  D2.0), and work backwards to see what steps can be fitted in—discard the other steps
  We can’t spend 18 months on an SFD and then get to D2.0 in 24 months