## Slide 1: Predicting timelines: the track record
Date: 2018-07-10

## Slide 2: Abstract
Recent presentations have discussed how to reform IEEE’s process for developing amendments, with a view to making it all more efficient
― 11-18/1259r1, “A cascading process for major amendments”, R. Stacey et al., July 2018;
― 11-18/1284r0, “A proposed way forward”, O. Abould-Magd et al., July 2018
We have been here before: this presentation reviews the track record from ax and ba
One conclusion is that estimates almost always err on the very optimistic side. The proposed ways forward do not really address the reasons for this. This presentation suggests different ways of proceeding.

## Slide 3: Illustration of potential timelines for 802.11ax
long track
fast track
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
Laurent Cariou (Orange)
From 11-14/0617r1, “Discussion on timeline for 802.11ax:, L. Cariou, T. Derham, May 2014

## Slide 4: Illustration of potential timelines for 802.11ax
long track
fast track
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
IEEE802.11
WFA
11ax
11ax/HEW Wave 1
2014
11ax/HEW Wave 2
2015
2016
2017
2018
2019
Laurent Cariou (Orange)
NOW
Overoptimistic
Way
overoptimistic

## Slide 5: Preliminary Timeline Projection, Scenario A, with ‘normalized’* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
2019
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
.11ax Draft 2.0
(Nov 2016)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0
(January 2016)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Sept 14 - July 2015)
11ax SFD
TG Kick Off
(May 2014)
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014 (D2.0: Nov 2016)

## Slide 6: Preliminary Timeline Projection, Scenario B, with ‘normalized* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
2019
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
.11ax Draft 2.0 (Mar 2017)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0 (July 2016)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Nov 14 - Jan 2016)
11ax SFD
TG Kick Off
(May 2014)
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014 (D2.0: Mar 2017)

## Slide 7: Preliminary Timeline Projection, Scenario C, with ‘normalized* .11ac timeline for reference
2018
2017
2015
2014
2013
2016
.11ax Draft 2.0 (Nov 2017)
.11ax Final
PAR Approved
(Mar 2014)
.11ax Draft 1.0 (Jan 2017)
Study Group
Launch
(March 2013)
Spec Framework
Document
(Jan 15 - July 2016)
2019
11ax SFD
TG Kick Off
(May 2014)
Sept ‘08
11ac PAR Approved
11ac SFD R0 (Mar)
Sept ‘09
11ac SFD
SFD R21, D 0.1 (July )
Jan ‘11
.11ac Draft 1.0
Jan
July ‘11
.11ac Draft 2.0
Sept
Feb ‘12
.11ac Final
July
Dec ‘13
* .11ac timeline shown based on the .11ax PAR approval date
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014 (D1.0 Jan 2017; D2.0: Nov 2017)
(!—good estimate!)

## Slide 8: Strawpoll
What scenario should be reflected in the 802.11ax timeline estimate:
A: Scenario A (D1.0 in Jan 2016): 48
B: Scenario B (D1.0 in July 2016): 54
C: Scenario C (D1.0 in Jan 2017): 12
D: Other timeline: 6
E: Don’t know / Abstain: 7
From 11-14/0649r1, “802.11ax timeline scenarios”, R. de Vegt, May 2014
The good news is that we had the exact schedule. The bad news is that we refused to believe it.

## Slide 9: Development Times of Previous Amendments
It takes a long time to develop an amendment in 802.11WG
There are exceptions such as 802.11z and 802.11ae that had a limited and well-defined scope of work
Amendments | PAR approved (t1) | Draft 2.0 (t2) | Duration (t2-t1)
802.11ah | 2010-10-04 | 2014-07-05 | 3 years, 9 months
802.11af | 2009-12-09 | 2012-08-19 | 2 years, 8 months
802.11ac | 2008-09-26 | 2012-02-18 | 3 years, 5 months
802.11ad | 2008-12-10 | 2011-04-05 | 2 years, 3 months
802.11aa | 2008-03-27 | 2010-12-08 | 2 years, 8 months
802.11ae | 2009-12-09 | 2011-02-18 | 1 year, 2 months
802.11s | 2004-05-13 | 2008-05-03 | 4 years
802.11v | 2004-12-08 | 2008-03-15 | 3 years, 3 months
802.11z | 2007-08-22 | 2008-08-20 | 1 year
802.11n | 2003-09-11 | 2007-03-09 | 3 years, 6 months
Reference: http://www.ieee802.org/11/Reports/802.11_Timelines.htm
From 11-16/0722r1, “Proposal for wake-up receiver study group”, M. Park, May 2016

## Slide 10: Proposed Timeline
2016
  July: create a LP-WUR SG
    Define a PAR limited to LP-WUR
  November: create a LP-WUR TG
2017
  May: complete LP-WUR D0.1
  November: complete LP-WUR D1.0
2018
  May: complete LP-WUR D2.0
Nov. ‘16
- Create a LP-WUR TG
July ’16 Create a LP-WUR SG
May ‘17
- LP-WUR D0.1
Nov. ‘17
- LP-WUR D1.0
2016
2017
2018
May. ‘18
- LP-WUR D2.0
Today
May
4 mo.
6 mo.
6 mo.
6 mo.
From 11-16/0722r1, “Proposal for wake-up receiver study group”, M. Park, May 2016
NOW

## Slide 11: Observations
There is pressure to have at least some “blue sky” work
  It’s hard to have ALL projects limited to 2 years
  Efforts to limit one project to 2 years will be futile if there are no parallel projects that allow exploration of blue sky development
An amendment can be 2 years, or “Major”—not both
  “EHT” = Extremely High Throughput, but most candidate technologies have nothing to do with that goal (whatever their other merits)
  If an amendment is tagged “major”, there is pressure to include everything in it
    Especially if it’s the only ongoing “Major” amendment
The SFD process may be a contributor to delay and bloat
  Adds extra decision steps / more votes, allows inclusion of features with inadequate detail, leads to more LBs, longer CR process
  More technical detail earlier would help the process self-regulate

## Slide 12: Proposals
Drive amendments from technology side, not procedure
Use WNG to prove technical feasibility and project viability
  Get to better state of readiness before a project is a “go”
Aim for blend of focused, narrow, near-term projects and blue-sky, longer term projects
  Timeline driven by what the technology will require, not imposed by fiat
  Timeline projections become easier the more mature the effort is by the time it leaves WNG
  Don’t focus excessively on putting projects into competition with each other—hard choices lead to deadlock, conflict, and delay
  Forget about “major” and “minor” amendments—WFA will make its own choices, and eventually the wider market will deliver a verdict