## Slide 1: 802.11bd Timeline
Date: 2019-01-16
Authors:

## Slide 2: Overview of Timelines for 802.11ac,11ax, 11ba, and 11p
Stage | Duration |  |  | 
 | 11ac [1] | 11ax [1][2] | 11ba [5] | 11p [3][4]
PAR approval -> Approved Standard | 64 months | 68 months | 46 months | 70 months
PAR approval -> D0.1 | 29 months | 20 months | 14 months | 6 months
D0.1 – Draft 1.0 | 6 months | 12 months | 8 months | 14 months
Draft 1.0 – Draft 2.0 | 8 months | 10 months | 4 months | 8 months
Draft 2.0 - Final | 22 months | 26 months | 20 months | 42 months
 | 11ac | 11ax | 11ba | 11p
Page count | 429 | 729 | 106 | 34

## Slide 3: Timeline for 802.11bd
PAR [6] includes the following dates:
Initial Sponsor Ballot Sept 2020
Submission to RevCom Sept 2021
Option 1
An aggressive timeline to meet the dates in PAR
PAR to RevCom: 33 months
Option 2
A more realistic alternative timeline
PAR to RevCom: 45 months

## Slide 4: Proposed Timeline for 802.11bd- Option 1
PAR approved Dec 2018
First TG meeting Jan 2019
D0.1 Sept 2019
D1.0 Letter Ballot Nov 2019
D2.0 LB recirculation Mar 2020
Form Sponsor Ballot Pool May 2020
D3.0 LB recirculation May 2020
D3.0 unchanged recirculation July 2020
Initial Sponsor Ballot (D4.0) Sept 2020
Final 802.11 WG approval July 2021
802 EC approval July 2021
RevCom and SASB approval Sept 2021

## Slide 5
PAR approved Dec 2018
First TG meeting Jan 2019
D0.1 Mar 2020
D1.0 Letter Ballot Sept 2020
D2.0 LB recirculation Jan 2021
D3.0 LB recirculation May 2021
Form Sponsor Ballot Pool Sept 2021
D4.0 LB recirculation Sept 2021
D4.0 unchanged LB recirculation Nov 2021
Initial Sponsor Ballot (D5.0) Jan 2022
Final 802.11 WG approval July 2022
802 EC approval July 2022
RevCom and SASB approval Sept 2022
Proposed Timeline for 802.11bd- Option 2

## Slide 6: Proposed Timeline for 802.11bd (option 2)
Stage | Duration |  |  |  | 
 | 11ac [1] | 11ax [1][2] | 11ba [5] | 11p [3][4] | Option 2 for 11bd
PAR approval -> Approved Standard | 64 months | 68 months | 46 months | 70 months | 45 months
PAR approval -> D0.1 | 29 months | 20 months | 14 months | 6 months (?) | 15 months
D0.1 –> Draft 1.0 | 6 months | 12 months | 8 months | 14 months | 6 months
Draft 1.0 –> Draft 2.0 | 8 months | 10 months | 4 months | 8 months | 4 months
Draft 2.0 -> Final | 22 months | 26 months | 20 months | 42 months | 20 months

## Slide 7: Straw Polls
Which option do you prefer for 802.11bd timeline
  Option 1
  Option 2
Do you agree with the timeline presented as option 2 (on slide 5) as the time estimates for the work in 802.11bd?
Yes:
No:
Abstain:

## Slide 8: References
[1] IEEE802.11-14/0649r1, “802.11ax Timeline Scenarios”
[2] IEEE802.11-18/0968r0, “TGax timeline”
[3] http://www.ieee802.org/11/Reports/802.11_Timelines.htm
[4] IEEE802.11-05/0090r0, “Wave Closing Report”
[5] IEEE802.11-18/2109r1 “January TGba agenda”
[6] IEEE802.11-18/0861r9 “NGV-SG-Proposed-PAR”

## Slide 9: Backup Slides

## Slide 10: 11p timeline
Par approval: 09-2004
[D0.1] Jan 2005 report= A draft amendment was presented and is available on the web site [Commenting started]
WG Letter ballots:
D1.0: 04-2006 (56%)
D2.0: 01-2007 (67%)
D3.0: 09-2007 (74%)
D4.0: 05-2008 (79%)
D5.0: 12-2008 (85%)
D6.0: 03-2009 (89%)
D7.0: 06-2009 (85%)
D8.0: 08-2009 (89%)
D9.0: 10-2009 (93%)
WG Sponsor ballots
D9.0: 11-2009 (93%)
D10.0: 2-2010 (96%)
D11.0: 4-2010 (99%)
Standard board approval: 7-2010