## Slide 1: 802.11be Timeline proposal
Date: 2019-05-13
Authors:

## Slide 2: Introduction
This presentation proposes the development timeline for the 11be amendment
  [Rev1] The proposal foresees a 62 months total duration from PAR approval through finalized standard, with a Working Group letter ballot on draft 1.0 in May 2021
The following key factors have influenced the timeline proposal:
  Historical data from 11ax and 11ac development
  Expected complexity (feature wise) of 11be compared to 11ax and 11ac
  maturity of the targeted feature set and of the foundational documents
  Promote Wi-Fi to remain competitive compared to alternative technologies

## Slide 3: Motivation for the proposed timeline (1/2)
In 11ax, the TG spent a very long time developing TG documents such as:
  Simulation scenarios (6-8 months of TG – until Nov 2015)
  Calibration (12 months of TG – until May 2016)
  Functional requirements (4 months)
  Evaluation methodology (6-8 months)
  High level Features proposals (as those were not discussed during the SG)
After completion, some of these documents were completely “forgotten” during the amendment development
  We should not repeat this in 11be

## Slide 4: Motivation for the proposed timeline (2/2)
At the beginning of 11be, there appears to be consensus on some key factors that drive the timeline:
  SG/TG seem to have converged on most of the foundational documents
    Functional requirement, channel model, selection procedure, …
  TG has converged on the list of main features
  As opposed to 11ax which was a major amendment, we hope that the features of 11be will be less complex to define
Given this level of consensus, we are confident that a timeline that is at least 6 months faster than 11ax is realistically achievable

## Slide 5: 802.11ax process and timeline
Spent a lot of time on EM
Spent more time on draft than 11ac: 3.6 years vs 3 years
  Reflects greater complexity
SFD
EM
D0.1–D1.0
HEW SG
TGax
SB: D5.0–Pub
1 year
5.5 years
~2 years
May 2014
Jan 2016
May 2014
May 2013
Nov 2019
Jan 2015
May 2016
~1 year
2013
2014
2015
2016
2017
2018
2019
Mar 2016
Nov 2016
8 months
May 2018
2.5 years
Nov 2019
6 months
D1.0–D3.0
D4.0–D5.0
May 2019
11ac Pub
Dec 2013
expected

## Slide 6: 802.11be process and timeline
Save precious time by starting SFD very early
SFD
EM
D0.1–D1.0
EHT SG
TGbe
SB: D5.0–Pub
5 years
May 2019
May 2019
July 2018
May 2024
May 2019
Sept 2020
~1 year
2018
2019
2020
2021
2022
2023
2024
Nov 2020
May 2021
8 months
Nov 2022
2.5 years
May 2024
6 months
D1.0–D3.0
D4.0–D5.0
Nov2023
11ac Pub
Dec 2013
expected
Laurent Cariou, Intel

## Slide 7: Proposed Timeline for 802.11be
Stage | Duration |  | 
 | 11ac [1] | 11ax [1][2] | 11be
PAR approval -> Approved Standard | 64 months | 68 months | 62 months
PAR approval -> D0.1 | 29 months | 24 months | 20 months
D0.1 –> Draft 1.0 | 6 months | 8 months | 6 months
Draft 1.0 –> Draft 2.0 | 8 months | 10 months | 10 months
Draft 2.0 -> Final | 22 months | 26 months | 26 months
Laurent Cariou, Intel

## Slide 8: Proposed Timeline for 802.11be
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 Letter Ballot May 2021
D2.0 LB Mar 2022
D3.0 LB Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024
Laurent Cariou, Intel

## Slide 9: Proposed Timeline for 802.11be
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 Letter Ballot May 2021
D2.0 LB Mar 2022
D3.0 LB Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024
Laurent Cariou, Intel

## Slide 10: References
[1] IEEE802.11-14/0649r1, “802.11ax Timeline Scenarios”
[2] IEEE802.11-18/0968r0, “TGax timeline”

## Slide 11: Backup Slides

## Slide 12: 802.11ac process and timeline
VHT SG produced two PARs: 11ac and 11ad
11ac process started before 11n publication, but SFD development started late
SFD
LB: D1.0 – D5.0
FR & EM
D0.1–D1.0
VHT SG
TGac
SB: D5.0–Pub
1.5 years
5 years
~2 years
May 2009
Jan 2011
Nov 2008
May 2007
Nov 2013
Sep 2009
Jan 2011
~1 year
2007
2008
2009
2010
2011
2012
2013
Nov 2010
May 2011
6 months
Mar 2013
2 years
Nov 2013
6 months
11n Pub
Sep 2009
Laurent Cariou, Intel

## Slide 13: 802.11ax process and timeline
Spent a lot of time on EM
Spent more time on draft than 11ac: 3.6 years vs 3 years
  Reflects greater complexity
SFD
EM
D0.1–D1.0
HEW SG
TGax
SB: D5.0–Pub
1 year
5.5 years
~2 years
May 2014
Jan 2016
May 2014
May 2013
Nov 2019
Jan 2015
May 2016
~1 year
2013
2014
2015
2016
2017
2018
2019
Mar 2016
Nov 2016
8 months
May 2018
2.5 years
Nov 2019
6 months
D1.0–D3.0
D4.0–D5.0
May 2019
11ac Pub
Dec 2013
expected

## Slide 14: 802.11be process and timeline
Save precious time by starting SFD very early
SFD
EM
D0.1–D1.0
EHT SG
TGax
SB: D5.0–Pub
5.5 years
May 2019
May 2019
July 2018
Nov 2019
May 2019
July 2020
~1 year
2018
2019
2020
2021
2022
2023
2024
Sept 2020
Mar 2021
8 months
Sept 2022
2.5 years
Mar 2024
6 months
D1.0–D3.0
D4.0–D5.0
Sept 2023
11ac Pub
Dec 2013
expected

## Slide 15: Previous proposed Timeline for 802.11be
Stage | Duration |  | 
 | 11ac [1] | 11ax [1][2] | 11be
PAR approval -> Approved Standard | 64 months | 68 months | 60 months
PAR approval -> D0.1 | 29 months | 24 months | 18 months
D0.1 –> Draft 1.0 | 6 months | 8 months | 6 months
Draft 1.0 –> Draft 2.0 | 8 months | 10 months | 10 months
Draft 2.0 -> Final | 22 months | 26 months | 26 months

## Slide 16: Previous proposed Timeline for 802.11be
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 Letter Ballot Mar 2021
D2.0 LB Jan 2022
D3.0 LB Sept 2022
Initial Sponsor Ballot (D4.0) Mar 2023
Final 802.11 WG approval Jan 2024
802 EC approval Jan 2024
RevCom and SASB approval Mar 2024