## Slide 1: TGbc Closing Report
Date: 2019-05-17
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Enhanced Broadcast Services) for May 2019 YEARN, Atlanta, GA, USA.

## Slide 3: Work Completed this week
Group met in three time slots during this week
5 Presentations discussed; topics covered
Functional requirements
System architecture / control plane
Use Cases
Tangible results
Approved additional use cases
Approved additional functional requirements
Confirmation of Carol Ansley (Commscope) as the TGbc Technical Editor

## Slide 4: Plans for July 2019
Approve additional technical requirements
Consolidate the system architecture / control plane discussions
Discuss early drafts of amendment text

## Slide 5: Future Session Planning
Teleconferences:
Tuesday, June 11, 2019, 10:00h ET
14-17 July 2019 F2F meeting, Austria Center Vienna, Vienna, Austria:
Meeting time requested: 3 sessions

## Slide 6: TGbc schedule – unchanged
January 2019 First meeting as a task group
January 2020 Initial WGLB (D1.0)
July 2020 D2.0 WGLB Recirculation LB
January 2021 Form SB Pool
January 2021 MEC/MDR done
March 2021 Initial SB
July 2021 Recirculation SB
Jan 2022 Final WG/EC approval
Feb 2022 Revcom/SASB approval

## Slide 7: References
Agenda for this week: 11-19/0812
Meeting / Chair’s Slide Deck: 11-19/0814
Meeting minutes: 11-19/0819
Snapshot Slide: 11-19/0813
Closing report: 11-19/0815
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135r0
TGbc Functional Requirements: 11-19/0151