## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-19/1180
Venue Date: | July 2019
First Author: | Carlos Cordeiro
Subject: | Comments on TGay/D4.0
Full Date: | 2019-07-09
Author(s): | Carlos Cordeiro
| Company: | Intel
Address
Phone:
Fax:
| email: | carlos.cordeiro@intel.com
Abstract: | Status of comments on 11ay D4.0 submitted as part of LB242.

## All Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
5000 | Albert Petrick | 242 | 4 | 9.4.2.20.16 | 113 | 11 | E | N | 113 | 11 | 9.4.2.20.16 |  | A |  |  | 626 | Table 9-115 should be Table 9-122 as listed in 802.11REVmd_D2.2 | As commented | ACCEPTED (LB242: 2019-07-19 17:30:22Z) - | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:32:55Z |  | 2019-07-19 17:33 | LB242
5001 | Albert Petrick | 242 | 4 | 9.4.2.21.15 | 116 | 1 | E | N | 116 | 1 | 9.4.2.21.15 |  | A |  |  | 626 | Table 9-126 should be Table 9-144 as listed in 802.11REVmd_D2.2 | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:34:31Z |  | 2019-07-19 17:35 | LB242
5002 | Albert Petrick | 242 | 4 | 9.4.2.20.17 | 114 | 35 | E | N | 114 | 35 | 9.4.2.20.17 |  | A |  |  | 626 | Figure 9-214 should be Figure 9-218 as listed in 802.11REVmd_D2.2 | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:33:29Z |  | 2019-07-19 17:33 | LB242
5003 | Albert Petrick | 242 | 4 | 9.4.2.21.16 | 119 | 2 | E | N | 119 | 2 | 9.4.2.21.16 |  | A |  |  | 626 | Figure 9-274 should be Figure 9-278 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:35:03Z |  | 2019-07-19 17:35 | LB242
5004 | Albert Petrick | 242 | 4 | 9.4.2.119 | 122 | 15 | E | N | 122 | 15 | 9.4.2.119 |  | A |  |  | 626 | Figure 9-551 should be Figure 9-555 as listed in 802.11REVmd_D2.2 | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:36:11Z |  | 2019-07-19 17:36 | LB242
5005 | Albert Petrick | 242 | 4 | 9.4.2.129 | 123 | 26 | E | N | 123 | 26 | 9.4.2.129 |  | V |  |  | 632 | Table 9-234 should be Table 9-257 as listed in 802.11REVmd_D2.2. | As commented | REVISED (LB242: 2019-09-17 03:50:40Z) - Should be Table 9-256 | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:41:34Z |  | 2019-09-17 03:51 | LB242
5006 | Albert Petrick | 242 | 4 | 9.4.2.129 | 124 | 2 | E | N | 124 | 2 | 9.4.2.129 |  | V |  |  | 633 | Table 9-235 should be Table 9-257 as listed in 802.11REVmd_D2.2. or should be a new table. | As commented | REVISED (LB242: 2019-09-17 03:51:17Z) - Should be Table 9-257 | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:42:56Z |  | 2019-09-17 03:51 | LB242
5007 | Albert Petrick | 242 | 4 | 9.4.2.131 | 126 | 19 | E | N | 126 | 19 | 9.4.2.131 |  | A |  |  | 626 | Figure 9-518 should be Table 9-561 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:44:49Z |  | 2019-07-21 19:45 | LB242
5008 | Albert Petrick | 242 | 4 | 9.4.2.133 | 126 | 26 | E | N | 126 | 26 | 9.4.2.133 |  | A |  |  | 626 | Figure 9-521 should be Table 9-565 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:43:59Z |  | 2019-07-21 19:44 | LB242
5009 | Albert Petrick | 242 | 4 | 9.4.2.136 | 128 | 15 | E | N | 128 | 15 | 9.4.2.136 |  | A |  |  | 626 | Table 9-240 should be Table 9-264 as listed in 802.11REVmd_D2.2. or should be a new table. | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:46:49Z |  | 2019-07-21 19:47 | LB242
5010 | Albert Petrick | 242 | 4 | 9.4.2.136 | 128 | 15 | E | N | 128 | 15 | 9.4.2.136 |  | A |  |  | 626 | Missing period after "subset" in multiple locations in the "Meaning" column of Table 9-240 | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:46:13Z |  | 2019-07-21 19:46 | LB242
5011 | Albert Petrick | 242 | 4 | 9.4.2.138 | 129 | 24 | E | N | 129 | 24 | 9.4.2.138 |  | A |  |  | 626 | Figure 9-565 should be Figure 9-574 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:47:40Z |  | 2019-07-21 19:48 | LB242
5012 | Albert Petrick | 242 | 4 | 9.4.2.142 | 130 | 9 | E | N | 130 | 9 | 9.4.2.142 |  | A |  |  | 626 | Figure 9-576 should be Figure 9-580 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 22:31:33Z |  | 2019-07-21 22:32 | LB242
5013 | Albert Petrick | 242 | 4 | 9.4.2.142.1 | 130 | 14 | E | N | 130 | 14 | 9.4.2.142.1 |  | A |  |  | 626 | Change "10-2" to "10-2 " | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 19:49:05Z |  | 2019-07-21 19:49 | LB242
5014 | Albert Petrick | 242 | 4 | 9.4.2.43 | 135 | 14 | E | N | 135 | 14 | 9.4.2.43 |  | A |  |  | 626 | Figure 9-572 should be Figure 9-581 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 22:32:07Z |  | 2019-07-21 22:32 | LB242
5015 | Albert Petrick | 242 | 4 | 10.26.6.2 | 236 | 9 | E | N | 236 | 9 | 10.26.6.2 |  | A |  |  | 626 | Change Figure 10-35 to 10-36 as listed in 802.11REVmd_D.2.2. | As commented |  | LB242 | General |  |  | I | LB242: 2019-07-21 22:49:16Z |  | 2019-07-21 22:49 | LB242
5016 | Albert Petrick | 242 | 4 | 10.26.6.2 | 236 | 19 | E | N | 236 | 19 | 10.26.6.2 |  | A |  |  | 626 | Change Figure 10-35 to Figure 10-36 as listed in 802.11REVmd_D.2.2. | As commented |  | LB242 | General |  |  | I | LB242: 2019-07-21 22:49:12Z |  | 2019-07-21 22:49 | LB242
5017 | Albert Petrick | 242 | 4 | 11.37.1 | 385 | 30 | E | N | 385 | 30 | 11.37.1 |  | A |  |  | 626 | Grammar | Change "if ResultCode" to "if the ResultCode" |  | LB242 | General |  |  | I | LB242: 2019-07-21 22:50:30Z |  | 2019-07-21 22:50 | LB242
5018 | Albert Petrick | 242 | 4 | 10.6.7.2 | 223 | 5 | E | N | 223 | 5 | 10.6.7.2 |  | A |  |  | 626 | Missing period | Change "channel) to "channel)." | ACCEPTED (LB242: 2019-07-15 07:56:45Z) | LB242 | General |  |  | I | LB242: 2019-07-21 22:40:13Z |  | 2019-07-21 22:40 | LB242
5019 | Albert Petrick | 242 | 4 | 10.6.7.2 | 223 | 7 | E | N | 223 | 7 | 10.6.7.2 |  | A |  |  | 626 | Missing period | Change "great than 1" to "greater than 1." | ACCEPTED (LB242: 2019-07-15 07:56:36Z) | LB242 | General |  |  | I | LB242: 2019-07-21 22:40:23Z |  | 2019-07-21 22:40 | LB242
5020 | Albert Petrick | 242 | 4 | 10.6.10 | 226 | 7 | E | N | 226 | 7 | 10.6.10 |  | A |  |  | 626 | Table 10-6 should be Table 10-9 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | General |  |  | I | LB242: 2019-07-21 22:45:03Z |  | 2019-07-21 22:45 | LB242
5021 | Albert Petrick | 242 | 4 | 10.6.10 | 226 | 10 | E | N | 226 | 10 | 10.6.10 |  | A |  |  | 626 | Table 10-6 should be Table 10-9 as listed in 802.11REVmd_D2.2. | As commented |  | LB242 | General |  |  | I | LB242: 2019-07-21 22:44:55Z |  | 2019-07-21 22:45 | LB242
5022 | Hiroyuki Motozuka | 242 | 4 | 9.4.2.251 | 145 | 25 | E | N | 145 | 25 | 9.4.2.251 |  | A |  |  | 626 | "Primary Channel" field or "Primary Channel number" field | Replace "The Primary Channel number field indicates ..." with "The Primary Channel field indicates ..." at P145L25 | ACCEPTED (LB242: 2019-07-15 07:55:14Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 22:33:15Z |  | 2019-07-21 22:33 | LB242
5023 | Hiroyuki Motozuka | 242 | 4 | 9.4.2.255 | 156 | 32 | E | N | 156 | 32 | 9.4.2.255 |  | A |  |  | 626 | typo: "the value in the TXSS-PACKETS fields" | "the value in the TXSS-PACKETS field" | ACCEPTED (LB242: 2019-07-15 07:55:44Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 22:33:40Z |  | 2019-07-21 22:34 | LB242
5024 | Hiroyuki Motozuka | 242 | 4 | 29.9.2.2.5 | 606 | 3 | E | N | 606 | 3 | 29.9.2.2.5 |  | A | Motozuka-san |  | 626 | The expression of "Value indicated by the RX TRN-Units per Each TX TRN-Unit field" in Figure 222 is correct, but inconsistent with the expression of "Value of the EDMG-TRN-Unit M field plus one" | Replace with "Value of the RX TRN-Units per Each TX TRN-Unit field plus one" in the figure | ACCEPTED (LB242: 2019-07-16 09:37:01Z) | LB242 | BF |  |  | I | LB242: 2019-07-22 00:22:36Z |  | 2019-07-22 00:23 | LB242
5025 | Hiroyuki Motozuka | 242 | 4 | 9.4.2.258 | 160 | 1 | T | N | 160 | 1 | 9.4.2.258 |  | A | Motozuka-san |  | 625 | On Table 18, the Note for L-TX-RX: "NOTE-- M is equal to the value of the Requested EDMG TRN-Unit M field." | "NOTE-- M is equal to the value of the Requested EDMG TRN-Unit M field plus one." | ACCEPTED (LB242: 2019-07-16 10:05:11Z) | LB242 | BF |  |  | I | LB242: 2019-07-21 22:34:52Z |  | 2019-07-21 22:35 | LB242
5026 | Hiroyuki Motozuka | 242 | 4 | B.4.34.2 | 758 | 1 | E | N | 758 | 1 | B.4.34.2 |  | V | Motozuka-san |  | 626 | The reference for EDMG-P6.2.1.2/TRN Subfield Sequence seems incorrect. | Replace "29.3.3.2.4" with "29.9.2.2.6" Note: 29.9.2.2.6(TRN subfield definition for EDMG SC PPDUs and EDMG control mode PPDUs) specifies the effect of the value of the TRN Subfield Sequence field. | REVISED (LB242: 2019-07-16 10:01:11Z) 1) Agree to replace section number as noted 2) Editor to check all hyperlinks in the PICS and ensure they all work. | LB242 | BF |  |  | I | LB242: 2019-07-21 23:02:38Z |  | 2019-07-21 23:03 | LB242
5027 | Hiroyuki Motozuka | 242 | 4 | B.4.34.2 | 758 | 1 | T | N | 758 | 1 | B.4.34.2 |  | V | Motozuka-san |  | 630 | About EDMG-P6.2.1/EDMG BRP PPDU (TRN fields), I think EDMG BRP is applicable only for EDMG STAs. | Replace "NOT EDMG-M16-9:M" with "CFEDMG AND NOT EDMG-M16.9:M" | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1379-00-00ay-cid5027-pics.docx | LB242 | BF | [5 empty] | 2019-09-17 03:50 | LB242
5028 | Kazuto Yano | 242 | 4 | 9.4.2.269 | 182 | 22 | E | N | 182 | 22 | 9.4.2.269 |  | A | Carlos |  | 626 | In the 7th raw of Table 27, "Table 9-37" must be "Table 9-73." | Please correct the typo. | ACCEPTED (LB242: 2019-07-15 07:55:56Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 22:38:25Z |  | 2019-07-21 22:38 | LB242
5029 | Kazuto Yano | 242 | 4 | 9.4.2.271 | 191 | 21 | E | N | 191 | 21 | 9.4.2.271 |  | A |  |  | 626 | There is a typo; "the scope of tis standard" must be "the scope of this standard." | Please correct the typo. | ACCEPTED (LB242: 2019-07-15 07:56:17Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 22:38:49Z |  | 2019-07-21 22:39 | LB242
5030 | Mark Hamilton | 242 | 4 | 11.32.6.1 | 380 | 15 | T | N | 380 | 15 | 11.32.6.1 |  | A | Carlos |  | 625 | "A device is multi-band discovery assistance capable if the value of both dot11MultibandImplemented and dot11DiscoveryAssistanceActivated are true." Both cooperating STAs in the device need to be multi-band (implemented) and presumably discovery assistance capable. Perhaps _all_ the STAs in the device need to have these attributes true? | To the end of the sentence, add, ", for all discovery assistence cooperating STAs in the device." | ACCEPTED (LB242: 2019-07-15 07:40:57Z) | LB242 | Multi-band |  |  | I | LB242: 2019-07-19 16:58:39Z |  | 2019-07-19 16:59 | LB242
5031 | Mark Hamilton | 242 | 4 | 11.37.3 | 388 | 17 | E | N | 388 | 17 | 11.37.3 |  | A |  |  | 626 | One "TDD sector acknowledge" snuck past CID 4290's resolution. | Replace "TDD sector acknowledge" with "TDD sector switch acknowledge". | ACCEPTED (LB242: 2019-07-15 07:58:58Z) | LB242 | TDD |  |  | I | LB242: 2019-07-21 22:51:16Z |  | 2019-07-21 22:51 | LB242
5032 | Mark Hamilton | 242 | 4 | 4.9.5 | 26 | 22 | E | N | 26 | 22 | 4.9.5 |  | A |  |  | 626 | "Cochannel" is not a word. The baseline uses "co-channel". | Replace "cochannel" with "co-channel" throughout the draft. ("Co-channel" should be added to the list of exceptions in the 802.11 Editorial Style Guide.) | ACCEPTED (LB242: 2019-07-15 07:25:19Z) | LB242 | General |  |  | I | LB242: 2019-07-19 17:08:09Z |  | 2019-07-19 17:08 | LB242
5033 | Mark Hamilton | 242 | 4 | 5.2.5.2 | 316 | 38 | T | N | 316 | 38 | 5.2.5.2 |  | J | Solomon |  | 623 | How does the user of the MAC SAP know if a SAR agreement has been established? Without knowing this, it can't know the maximum MSDU size that it can .request. | Add two new transmission status parameters, "SAR agreement active" and "SAR agreement inactive". Add to the end of the sentence in 5.2.5.1, ", or to indicate a change of status of SAR agreement with the peer MAC." Add after the sentence in 5.2.5.3, "The MA-UNITDATA-STATUS.indication primitive can also be generated unsolicited to indicate to the LLC sublayer entity or bridge port the initial or changed status of a SAR agreement with the MAC peer that is currently servicing the provided destination address." Add after the sentence in 5.2.5.4, "In the case of an unsolicited indication of SAR agreement status, the LLC sublayer or bridge port can update its maximum MSDU size for the indicated destination address." | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1220-00-00ay-lb242-comment-resolution.docx | LB242 | SAR |  |  | I | LB242: 2019-07-19 17:03:33Z |  | 2019-07-19 17:04 | LB242
5034 | Mark Hamilton | 242 | 4 | B.4.34.1 | 753 | 7 | T | N | 753 | 7 | B.4.34.1 |  | V | Solomon |  | 623 | There is no PICS statement for the segmentation and reassembly feature | Add a PICS statement for support of segmentation and reassembly. Presumably, "CFEDMG: O". | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1220-00-00ay-lb242-comment-resolution.docx | LB242 | SAR |  |  | I | LB242: 2019-07-19 17:03:38Z |  | 2019-07-19 17:04 | LB242
5035 | Mark Hamilton | 242 | 4 | 11.1.7 | 367 | 20 | T | N | 367 | 20 | 11.1.7 |  | V | Carlos |  | 625 | _When_ does the SME issue this MLME-DISASSOCIATE? (Probably in response to some event, condition.) | Add to the sentence a description of when this occurs. | REVISED (LB242: 2019-07-16 09:27:25Z) Replace "The SME of a STA with dot11DMGTDDLocalClockModeActivated set to false" by "If a STA with dot11DMGTDDLocalClockModeActivated set to false receives an Announce frame that has the Sync Mode field in the TDD Synchronization element equal to 1, then the SME of the STA" Delete "frame that has the Sync Mode field in the TDD Synchronization element equal to 1" at the end. | LB242 | TDD |  |  | I | LB242: 2019-07-19 16:56:08Z |  | 2019-07-19 16:56 | LB242
5036 | Mark Hamilton | 242 | 4 | C.3 | 765 | 19 | E | N | 765 | 19 | C.3 |  | A |  |  | 626 | Typo | Change "otherwise it does not use the defined TPC procedure" to "otherwise it does not use any defined TPC procedure" | ACCEPTED (LB242: 2019-07-15 07:59:47Z) | LB242 | MIB |  |  | I | LB242: 2019-07-21 22:54:12Z |  | 2019-07-21 22:54 | LB242
5037 | Robert Stacey | 242 | 4 | 9.2.4.7.1 | 95 | 6 | E | N | 95 | 6 | 9.2.4.7.1 |  | V | Carlos |  | 626 | Position of column in table is not defined. Meaning of row entries is not clear without context. | Add table title for context. Modify instruction to identify column position in table. Add left row to table to show context for each row. | REVISED (LB242: 2019-07-21 23:41:19Z) No need to add title. Agree to do the rest. | LB242 | Frame formats |  |  | I | LB242: 2019-07-21 23:41:34Z |  | 2019-07-21 23:42 | LB242
5038 | Robert Stacey | 242 | 4 | 9.3.1.8.1 | 96 | 5 | E | N | 96 | 5 | 9.3.1.8.1 |  | A |  |  | 626 | Reference correct figure. Add figure title for context and to help identify numbering errors when baseline numbering changes. | Figure 9-42--BA Control field format | ACCEPTED (LB242: 2019-07-15 07:26:48Z) | LB242 | Block Ack |  |  | I | LB242: 2019-07-21 23:35:54Z |  | 2019-07-21 23:36 | LB242
5039 | Robert Stacey | 242 | 4 | 9.3.1.8.1 | 96 | 8 | T | N | 96 | 8 | 9.3.1.8.1 |  | A | Solomon |  | 623 | Identify the new fields (No Memory Kept, Memory Configuration Tag) as applicable to EDMG STAs and reserved for non-EDMG STAs. | Change each paragraph to "The <blah> subfield is used by an EDMG STA ... The <blah> subfield is reserved if transmitted by a non-EDMG STA." | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1220-00-00ay-lb242-comment-resolution.docx | LB242 | Block Ack |  |  | I | LB242: 2019-07-19 17:03:21Z |  | 2019-07-19 17:03 | LB242
5040 | Robert Stacey | 242 | 4 | 9.3.1.8.8 | 98 | 4 | E | N | 98 | 4 | 9.3.1.8.8 |  | A | Carlos |  | 626 | Inconsistent field names: BlockAck Starting Sequence Control in figure, but Block Ack Starting Sequence Control (with space) in text. Ditto for BlockAck Bitmap | Add space to names in figure | ACCEPTED (LB242: 2019-07-15 07:27:01Z) | LB242 | Block Ack |  |  | I | LB242: 2019-07-19 17:18:05Z |  | 2019-07-19 17:18 | LB242
5041 | Robert Stacey | 242 | 4 | 9.3.1.8.8 | 98 | 9 | E | N | 98 | 9 | 9.3.1.8.8 |  | A | Carlos |  | 626 | AckType: By convention we use spaces between words in field names. | Change AckType to Ack Type throughout for consistency with similarly named fields (BA Type above, Ack Type in the Multi-STA BlockAck frame in 11ax) | ACCEPTED (LB242: 2019-07-15 07:48:51Z) | LB242 | Block Ack |  |  | I | LB242: 2019-07-19 17:19:09Z |  | 2019-07-19 17:19 | LB242
5042 | Robert Stacey | 242 | 4 | 9.3.1.23 | 100 | 23 | E | N | 100 | 23 | 9.3.1.23 |  | A | Solomon |  | 623 | Don't create a new mapping for integer to AC; use existing mapping. | Delete Table 4 and change "The encoding of the Preferred AC subfield is shown in Table 4." to "The Preferred AC subfield is encoded as the AC index (ACI) defined in Table 9-154. | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1220-00-00ay-lb242-comment-resolution.docx | LB242 | Block Ack |  |  | I | LB242: 2019-07-19 17:03:27Z |  | 2019-07-19 17:03 | LB242
5043 | Robert Stacey | 242 | 4 | 9.3.1.23 | 100 | 21 | T | N | 100 | 21 | 9.3.1.23 |  | A | Solomon |  | 623 | "lowest AC" has no meaning | Change to "lowest priority AC" | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1220-00-00ay-lb242-comment-resolution.docx | LB242 | Block Ack |  |  | I | LB242: 2019-07-19 17:03:24Z |  | 2019-07-19 17:03 | LB242
5044 | Robert Stacey | 242 | 4 | 9.3.1.23 | 100 | 20 | T | N | 100 | 20 | 9.3.1.23 |  | V | Carlos |  | 625 | "the STA's" has no antecedent. Thus it is unclear if this is the STA transmitting the frame or the STA receiving the frame or some other STA. | Clarify whether this is a restriction based on the transmitting STA's capability or receiving STA's capabilities. Better yet, don't make it dependent on capabilities at all; just assign meaning to the field and then add behavioral statements that restrict its use. | REVISED (LB242: 2019-07-15 07:51:47Z) 1) Replace "STA’s EDMG Capabilities element" by "EDMG Capabilities element of the STA that is transmitting this element". This will clarify which STA the statement is talking about. 2) As for whether this refers to transmission or reception, the following sentence already states it as in: "… A-MPDU sent as part of an RDG." | LB242 | Block Ack |  |  | I | LB242: 2019-07-19 16:43:36Z |  | 2019-07-19 16:44 | LB242
5045 | Robert Stacey | 242 | 4 | 9.3.1.24.2 | 102 | 21 | E | N | 102 | 21 | 9.3.1.24.2 |  | A | Carlos |  | 626 | Missing noun | Change to "TDD SSW frame". Don't bother with the Sector Sweep part: if the name is TDD SSW then that is the name. If SSW has some meaning put that meaning in the descriptive text. Ditto for subsequent titles | ACCEPTED (LB242: 2019-07-15 07:27:51Z) | LB242 | TDD |  |  | I | LB242: 2019-07-19 17:22:29Z |  | 2019-07-19 17:22 | LB242
5046 | Robert Stacey | 242 | 4 | 9.3.3.6 | 107 | 3 | E | N | 107 | 3 | 9.3.3.6 |  | A |  |  | 626 | Table number wrong. Add title for context (and to catch numbering errors). | Table 9-36--Association Request frame body | ACCEPTED (LB242: 2019-07-15 07:28:24Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:29:58Z |  | 2019-07-19 17:30 | LB242
5047 | Robert Stacey | 242 | 4 | 9.3.3.7 | 107 | 6 | E | N | 107 | 6 | 9.3.3.7 |  | A |  |  | 626 | Table number wrong. Add title for context and to catch numbering errors. | Table 9-37--Association Response frame body | ACCEPTED (LB242: 2019-07-15 07:32:31Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:29:55Z |  | 2019-07-19 17:30 | LB242
5048 | Robert Stacey | 242 | 4 | 9.3.3.8 | 107 | 9 | E | N | 107 | 9 | 9.3.3.8 |  | A |  |  | 626 | Table number wrong. Add title for context and to catch numbering errors. | Table 9-38--Reassociation Request frame body | ACCEPTED (LB242: 2019-07-15 07:28:10Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:29:52Z |  | 2019-07-19 17:30 | LB242
5049 | Robert Stacey | 242 | 4 | 9.3.3.9 | 107 | 12 | E | N | 107 | 12 | 9.3.3.9 |  | A |  |  | 626 | Table number wrong. Add title for context and to catch numbering errors. | Table 9-39--Reassociation Response frame body | ACCEPTED (LB242: 2019-07-15 07:28:01Z) | LB242 | Frame formats |  |  | I | LB242: 2019-07-19 17:29:46Z |  | 2019-07-19 17:30 | LB242
5050 | Robert Stacey | 242 | 4 |  |  |  | E | N |  |  |  |  | V |  |  | 626 | Many of the modified baseline tables and figures do not have titles and the numbers are incorrect. Add titles since this gives the reader context and helps catch numbering errors. Also, many of the tables do not have header rows. This makes it difficult for the reader to interpret the content of the columns. | Correct table and figure numbers to match baseline. Add header rows to tables where they are missing | REVISED (LB242: 2019-07-21 23:32:22Z) Agree to add figure/table titles for context, correct numbers as appropriate. Additional proposed changes are unnecessary. | LB242 | General |  |  | I | LB242: 2019-07-22 00:12:22Z |  | 2019-07-22 00:12 | LB242
5051 | Robert Stacey | 242 | 4 | 10.3.2.3.8 | 216 | 31 | E | N | 216 | 31 | 10.3.2.3.8 |  | A | Carlos |  | 626 | "Transmission" is not a well defined term and certainly does not have a format with well defined start and end boundaries. Use the term PPDU. With a list, it is preferable to indicate the relationship of the items up front rather than with punctuation and or/and in the list items themselves. Also, it is not clear what is meant by multiple transmission. Presumably spaced closely in time, but that is not specified here. | Change to "The SBIFS shall separate PPDU transmissions in each of the following cases: - PPDUs from a single transmitter during a receive sector sweep or TDD beamforming - back-to-back PPDU transmissions where each PPDU is transmitted with a different transmit antenna configuration and where no immediate response is expected - back-to-back PPDU transmissions from a single transmitter where each PPDU is transmitted with a different transmit RF chain and no immediate response is expected" | ACCEPTED (LB242: 2019-07-16 09:21:22Z) | LB242 | BF |  |  | I | LB242: 2019-07-21 23:01:13Z |  | 2019-07-21 23:01 | LB242
5052 | Robert Stacey | 242 | 4 | 10.3.2.3.8 | 217 | 10 | T | N | 217 | 10 | 10.3.2.3.8 |  | V | Carlos |  | 625 | "as measured on the medium" is insufficiently precise. Close to the device or 100m away? | "as measured at the antenna port" | REVISED (LB242: 2019-07-16 09:44:04Z) replace by "as measured at the DMG antenna" | LB242 | BF |  |  | I | LB242: 2019-07-19 16:52:43Z |  | 2019-07-19 16:53 | LB242
5053 | Robert Stacey | 242 | 4 | 9.3.2.3.8 | 217 | 11 | T | N | 217 | 11 | 9.3.2.3.8 |  | V | Carlos |  | 625 | Frames are not PPDUs. Frame is a synonym for MPDU. | Change "A STA shall not allow the space between frames" to "A STA shall not allow the space between DMG PPDUs" and delete the last sentence. In the previous sentence change "frame" to "PPDU" (2 times) | REVISED (LB242: 2019-07-19 16:48:23Z) Do not delete the last sentence, because it is needed to clarify that the PPDU could also be an EDMG PPDU. Change it to "Two PPDUs separated by a SBIFS shall both be either DMG PPDUs or EDMG PPDUs." | LB242 | BF |  |  | I | LB242: 2019-07-19 16:51:59Z |  | 2019-07-19 16:52 | LB242
5054 | Takenori Sakamoto | 242 | 4 | 29.12.3.3 | 744 |  | T | Y | 744 |  | 29.12.3.3 |  | V | Motozuka-san |  | 629 | TXTIME calculation for EDMG SC mode A-PPDU is missing | Add TXTIME calculation for EDMG SC mode A-PPDU | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1375-00-00ay-comment-resolution-on-cid5054-and-5055.docx | LB242 | PHY | [5 empty] | 2019-09-17 03:49 | LB242
5055 | Takenori Sakamoto | 242 | 4 | 29.12.3.4 | 746 |  | T | Y | 746 |  | 29.12.3.4 |  | V | Motozuka-san |  | 629 | TXTIME calculation for EDMF OFDM mode A-PPDU is missing | Add TXTIME calculation for EDMG OFDM mode A-PPDU | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1375-00-00ay-comment-resolution-on-cid5054-and-5055.docx | LB242 | PHY | [5 empty] | 2019-09-17 03:49 | LB242
5056 | Yongho Seok | 242 | 4 | C.3 | 763 | 14 | T | Y | 763 | 14 | C.3 |  | V | Carlos |  | 625 | 802.11ay D4.0 is amendment to 802.11REVmd D2.2 as amended by 802.11ax D4.1. dot11PHYType value 14 is used by 802.11ax for the HE PHY. Please change dot11PHYType of the EDMG to an non-duplicated value. | Please change dot11PHYType of the EDMG to an non-duplicated value (e.g., 15). | REVISED (LB242: 2019-07-15 07:41:29Z) Use value 15 | LB242 | MIB |  |  | I | LB242: 2019-07-19 17:00:14Z |  | 2019-07-19 17:00 | LB242
5057 | Yongho Seok | 242 | 4 | C.3 | 766 | 42 | T | Y | 766 | 42 | C.3 |  | V | Carlos |  | 625 | 802.11ay D4.0 is amendment to 802.11REVmd D2.2 as amended by 802.11ax D4.1. dot11AMPDUwithMultipleTIDOptionImplemented is used by 802.11ax. Please change dot11AMPDUwithMultipleTIDOptionImplemented to an non-duplicated name (e.g., dot11EDMGAMPDUwithMultipleTIDOptionImplemented). | Please change dot11AMPDUwithMultipleTIDOptionImplemented to an non-duplicated name (e.g., dot11EDMGAMPDUwithMultipleTIDOptionImplemented). | REVISED (LB242: 2019-07-15 07:41:46Z) Use suggestion proposed by commenter. | LB242 | MIB |  |  | I | LB242: 2019-07-19 17:01:40Z |  | 2019-07-19 17:02 | LB242
5058 | Yunsong Yang | 242 | 4 | 9.4.2.127 | 120 | 16 | T | Y | 120 | 16 | 9.4.2.127 |  | V | Solomon |  | 634 | It is better that the new Protected DMG Dual Support subfield be verified in the security context during 4-way handshake and Re(Association) procedures to prevent downgrade attack. TGm defined a new RSN Extension element, which can be used for such purpose (see REVmd D2.3 or doc. 11-19-114r5). | Add the cited bit to the Extended RSN Capabilities field in the RSN Extension element. | REVISED (LB242: 2019-09-18 01:12:49Z) Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1440-01-00ay-proposed-resolution-to-cid-5058.docx | LB242 | Security | [5 empty] | 2019-09-18 01:13 | LB242
5059 | Yunsong Yang | 242 | 4 | 9.4.2.253 | 151 | 1 | T | Y | 151 | 1 | 9.4.2.253 |  | V | Assaf |  | 631 | The style for describing EDMG Channel Measurement Feedback element format using a table is inconsistent with the style used in describing formats of 241 out of 242 elements in REVmd 2.3 and 20 out of the 26 new elements inserted in this draft, i.e., using figures, such as Figure 9-546--DMG Capabilities element format, and paragraphs. There are certain advantages using the baseline style: 1. it is easier to identify an optional field. 2. Bit indices for the fields are specified. 3. there is an easier way to describing a field that repeats for multiple instances. The same issue also exists in subclauses 9.4.2.258 to 9.4.2.261, and 9.4.2.269. | Use the style as in the baseline standard to describe the element format in 9.4.2.253, 9.4.2.258 to 9.4.2.261, and 9.4.2.269. | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1421-01-00ay-lb242-2-cids.docx | LB242 | BF | [5 empty] | 2019-09-17 03:50 | LB242
5060 | Yunsong Yang | 242 | 4 | 9.4.2.269 | 183 | 1 | T | Y | 183 | 1 | 9.4.2.269 |  | V | Li-Hsiang |  | 624 | The current format can not guarantee that the total length is an interger number of octets, given variable number of instances of the repeatable fields, especially some of the repeatable fields have an odd number of bits. | Add a Reserved field with 0-7 bits to the end to ensure that the total length is an interger number of octets. | REVISED (LB242: 2019-07-18 08:42:57Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1270-00-00ay-proposed-resolution-of-cid-5060.docx | LB242 | BF |  |  | I | LB242: 2019-07-19 17:03:53Z |  | 2019-07-19 17:04 | LB242
5061 | Yunsong Yang | 242 | 4 | 9.6.31 | 211 | 17 | T | Y | 211 | 17 | 9.6.31 |  | J | Solomon |  | 635 | Having reviewed the resolutions to previous comments CIDs 4474-4475, agree that the 4 new MIMO BF action frames can be added under the Unprotetced DMG category so that they can be used as Class 1 frames. However, the creation for the Protected Dual of Unprotetced DMG category is still not warranteed, because there is already a robust DMG category. The 8 new protected frames added under the the Protected Dual of Unprotetced DMG category can be added under the DMG category to achieve the same result. The baseline standard uses S1G vs. Unprotected S1G, and WNM vs. Unprotected WNM. As the use of PMF becomes more and more popular, if 11ay can stick to DMG vs. Unprotected DMG (instead of having 3 categories), implementation can be made consistent across the board and less interoperability issues should be expected as a result. | Delete 9.6.31 and the action category of Protected Dual of Unprotected DMG from the draft. Add the 8 new protected DMG action frames defined in Table 38 to Table 9-456 (DMG Action field values), and add 8 new subclauses under 9.6.19 (DMG Action frame details) to describe each of the 8 new protected DMG action frames. An example text for these subclauses can be as follows: "9.6.19.<x> Protected <XXXX> frame format The Protected <XXXX> frame is an Action frame of category DMG and is defined to allow robust STA-STA communication of the same information that is conveyed in the <XXXX> frame that is not robust (see 9.6.21.1 (Unprotected DMG Action field)). The Action field of the Protected <XXXX> frame has the same format as the Action field of the unprotected <XXXX> frame (see 9.6.21.<y> (XXXX frame format)), except that the Order 2 item is the DMG Action field, which is defined in 9.6.19.1 (DMG Action field), instead of the Unprotected DMG Action field." And on P206L4, in Table 9-484, remove the Reserved rows and insert the 4 new unprotected DMG action frames beginning from value 2, instead of value 4. On P120L16, in Figure 9-547, rename the "Protected DMG Dual Support subfield" to "Protected DMG Operations Support subfield". On P121L3, change the sentence to read: "The Protected DMG Operations Support subfield is set to 1 to indicate that the STA supports the protected DMG action frames as described in 12.6.19.<xx> to 12.6.19.<yy>. Otherwise, it is set to 0." On P395, remove the text inserted under 12.6.20. Insert a new subcluase under clause 11, entitled "Protected DMG Operations" with the following text:" "When performing the DMG operations described in 11.28 (DMG beamformed link and BSS maintenance) to 11.31 (Spatial sharing and interference mitigation for DMG STAs), 11.37 (DMG beamforming), and 11.53 (TDD channel access operation), if management frame protection is negotiated and both STAs set the Protected DMG Operations Support field in the RSNXE that they transmit to 1, the STAs shall -- use Protected Announce, Protected BRP, Protected Link Measurement Request, Protected Link Measurement Report, Protected MIMO BF Setup, Protected MIMO BF Poll, Protected MIMO BF Feedback, and Protected MIMO BF Selection frames, instead of Announce, BRP, Link Measurement Request, Link Measurement Report, MIMO BF Setup, MIMO BF Poll, MIMO BF Feedback, and MIMO BF Selection frames, respectively, -- discard any unprotected Announce, BRP, Link Measurement Request, Link Measurement Report, MIMO BF Setup, MIMO BF Poll, MIMO BF Feedback, or MIMO BF Selection frames received from the peer STA, with which management frame protection is negotiated. STAs that exchange Protected Announce, Protected BRP, Protected Link Measurement Request, Protected Link Measurement Report, Protected MIMO BF Setup, Protected MIMO BF Poll, Protected MIMO BF Feedback, or Protected MIMO BF Selection frame shall follow the rules defined in 12.6.19 (Protection of robust Management frames). When management frame protection is not negotiated or the Protected DMG Operations Support field in the RSNXE transmitted by either STA is set to 0, the STAs shall not use any of the Protected Announce, Protected BRP, Protected Link Measurement Request, Protected Link Measurement Report, Protected MIMO BF Setup, Protected MIMO BF Poll, Protected MIMO BF Feedback, and Protected MIMO BF Selection frames." | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1467-00-00ay-revised-resolution-of-cid5061.docx | LB242 | Security |  |  | I | LB242: 2019-07-19 17:03:29Z |  | 2019-09-18 01:14 | LB242
5062 | Yunsong Yang | 242 | 4 | 10.4 | 254 | 8 | T | N | 254 | 8 | 10.4 |  | J | Carlos |  | 625 | Since subclause 10.40, as amended, also specifies the channel access rules for EDMG STAs, the word "EDMG" should be added to the subclause title, like what has been done for 10.15, and for the same reason, should be added to the subclause titles of 10.43 and 10.44 as well. | Change the subclause title of 10.40 to "DMG, CMMG(11aj), and EDMG channel access". Change the subclause title of 10.43 to "DMG and EDMG beamforming". And change the subclause title of 10.44 to "DMG and EDMG link adaptation" | REJECTED (LB242: 2019-07-10 14:52:45Z) DMG encompasses EDMG, therefore there is no need to add "EDMG" to the subclause name. This is also the reason why 11aj did not add "CDMG" the title, since DMG encompasses CDMG. They only added CMMG which is a different type of STA. | LB242 | General |  |  | I | LB242: 2019-07-19 16:52:49Z |  | 2019-07-19 16:53 | LB242
5063 | Yunsong Yang | 242 | 4 | 11.25.1.2 | 376 | 1 | T | Y | 376 | 1 | 11.25.1.2 |  | V | Solomon |  | 623 | TGay defined a number of new action frames under the existing and new action categories. However, the default QMF policies for these new action frames are not defined in Table 11-17 - Default QMF policy. Then, by default, they will use access category AC_BE as their default QMF policies. For this draft to be complete, TGay need to check whether all new action frames defined in this draft should use access category AC_BE as their default QMF policies. If not, add their default policies in Table 11-17. | Determine whether all new action frames defined in this draft should use access category AC_BE as their default QMF policies. If not, add their default policies in Table 11-17. | Resolve as in https://mentor.ieee.org/802.11/dcn/19/11-19-1220-00-00ay-lb242-comment-resolution.docx | LB242 | QMF |  |  | I | LB242: 2019-07-19 17:03:36Z |  | 2019-07-19 17:04 | LB242