## Slide 1: TGbc Closing Report
Date: 2019-09-19
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for September 2019, Hanoi, VN.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week: Discuss and approve SFD text and Draft Submissions
Group met 3 times this week
Accomplishments
  Approved initial text for the Specification Framework Document
  Agreed on additional functional requirements, which were added to the FR document
  Reviewed the functional requirement document to (a) check which FRs are addressed / covered by existing SFD text proposals and (b) identified volunteers to provide SFD text proposals covering others
  Reviewed / confirmed timeline

## Slide 4: Plans for November 2019
Discuss submissions for SFD
Increase technical level of detail for agreed SFD content

## Slide 5: Future Session Planning
Teleconferences:
10-15 November 2019 F2F meeting, Waikoloa, BigIsland, HI, USA:
Meeting time requested: 3 sessions
Group | Dates | Start Time | Duration
TGbc | Tuesday, October 29th | 10:00h ET | 1.5 hour

## Slide 6: TGbc schedule – unchanged
January 2019 First meeting as a task group
January 2020 Initial WGLB (D1.0)
July 2020 D2.0 WGLB Recirculation LB
January 2021 Form SB Pool
January 2021 MEC/MDR done
March 2021 Initial SB
July 2021 Recirculation SB
Jan 2022 Final WG/EC approval
Feb 2022 Revcom/SASB approval

## Slide 7: References
Agenda for this week: 11-19/1426
Meeting / Chair’s Slide Deck: 11-19/1427
Meeting minutes: 11-19/1370
Snapshot Slide: 11-19/1425
Closing report: 11-19/1428
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135r0
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268