## Purpose of this SS
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-19/1839r2
Venue Date: | May 2020
First Author: | Emily Qi (Intel Corporation)
Subject: | TGmd Motion Tracking
Full Date: | 2020-05-11
Author(s): | Name(s) | Emily Qi; Edward Au
Company
Address
Phone:
Fax:
| email: | emily.h.qi@intel.com
Abstract | The purpose of this spreadsheet is to ensure that changes approved by motion without associated comments are tracked properly.
Example of Format
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
| Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/15/11-15-0410-01-000m-dmg-control-response-frame-rate-selection.docx into the draft | 11-15/410r1 |  | Emily | I |  | Edward | y

## Motions in 2020-04
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
180 | Incorporate the text changes into the TGmd draft in https://mentor.ieee.org/802.11/dcn/20/11-20-0459-01-000m-internationalized-character-support.docx into the TGmd draft | 20/0459r1 | Stephen McCann | Emily | I |  | Edward | Reviewed at 1952 ET on April 28, 2020
182 | https://mentor.ieee.org/802.11/dcn/20/11-20-0435-01-000m-resolutions-for-some-comments-on-11md-d3-0-sb1.docx Page 25, related to but distinct from CID 4809 which is already resolved. Incorporate the text changes into the TGmd draft: In D3.2, change “in response to the reception of”/“in response to the receipt of” to “in response to” at 637.33, 971.18/21/22, 1181.14, 1600.24, 1654.28, 1656.30, 2033.55, 2332.48, 2467.55, 2478.38, 3042.28, 3539.50, 4016.40, 4620.37, 4621.55. At 4611.43 change “in response to the receipt of MLME-” to “in response to an MLME-”. [This is all instances of “in response to the rec” except the one on page 1908.] | 20/0141r6 | Mark Rison | Emily | I |  | Edward | Reviewed at 1956 ET on April 28, 2020

## Motions in 2020-02
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
157 | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/20/11-20-0281-01-000m-proposed-resolutions-for-d3-0-public-review-comment.doc , which resolves the public review comment. | 20/0281r1 | Emily Qi | Emily | I | implemented on 2/26/2020. | Edward | Reviewed at 0659 ET on March 6, 2020
158 | Incorporate the changes in “Proposed changes for Item D3.1-2” in https://mentor.ieee.org/802.11/dcn/20/11-20-0141-06-000m-sa1-proposed-resolutions-for-editor-adhoc.doc. | 20/0141r6 | Emily Qi | Emily | I | implemented on 2/26/2020. | Edward | Reviewed and edited at 0704 ET on March 6, 2020

## Motions in 2019-09
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
135 | •Incorporate the changes shown under CID 2041 in document: https://mentor.ieee.org/802.11/dcn/19/11-19-1286-01-000m-lb236-some-xdmg-phy-cids.docx | 11-19-1286r1 | Assaf Kasher | Emily | I |  | Edward | Reviewed at 2212 ET on October 3, 2019
136 | •Incorporate the changes - Shown under “Proposed technical changes” under “Stand-alone changes re optional subelements” in https://mentor.ieee.org/802.11/dcn/19/11-19-0856-10-000m-resolutions-for-some-comments-on-11md-d2-0-lb236.docx | 11-19-0856r10 | Mark Rison | Emily | I |  | Edward | Reviewed and edited at 1202 ET on October 2, 2019
137 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-1173-18-000m-pwe-in-constant-time.docx into the TGmd draft | 11-19-1173r18 | Dan Harkins | Emily | I |  | Edward | Reviewed and edited at 2237 ET on October 3, 2019
138 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-1444-04-000m-proposed-changes-re-ieee-sa-mec-comment-related-to-draft-2-1-of-ieee-p802-11revmd.docx | 11-19-1444r4 | Edward Au | Edward | I | Implemeneted at 0139am ET on September 30, 2019 | Emily | Reviewed.
149 | Incorporate the text changes in slides 8, 9 and 10 in https://mentor.ieee.org/802.11/dcn/19/11-19-1561-04-000m-vht-lo-leakage-requirement.pptx into the TGmd draft | 11-19-1561r4 | Matthrew Fisher | Emily | I |  | Edward | Reviewed and edited at 2240 ET on October 3, 2019

## Motions in 2019-07
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
120 | Incorporate the text changes indicated in the “Additonal changes” section on page 7 of https://mentor.ieee.org/802.11/dcn/19/11-19-0336-02-000m-cids-2709-2710-2711.docx | 19/0336r2 | Sigurd Schelstraete | Edward | I | Implemented on August 14, 2019. | Emily | Yes
121 | Incorporate the text changes indicated on pages 9 through 13 of https://mentor.ieee.org/802.11/dcn/19/11-19-0396-05-000m-resolution-for-cids-related-to-multiple-bssid.docx | 19/0396r5 | Abhishek Patil | Edward | I | Implemented on August 14, 2019. | Emily | Yes

## Motions in 2019-05
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
110 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-0781-00-000m-issues-in-revmd-d2-2-related-to-ccmp-for-pv1-mpdu.doc | 19/0781r0 | Yunsong Yang | Edward | I | Implemented at 2336 ET, May 25, 2019.
111 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-0733-00-000m-fixing-some-sae-issues.docx | 19/0733r0 | Dan Harkins | Edward | I | Implemented at 2324 ET, May 25, 2019.
112 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-0608-02-000m-pics-cf-items.ppt and https://mentor.ieee.org/802.11/dcn/19/11-19-0609-02-000m-pics-pc-items.ppt into the TGmd draft. | 19/608r2;19/609r2 | Edward | Edward | I | Implemented at 2321 ET, May 25, 2019.
114 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-0893-01-000m-may-or-may-not-that-is-the-question.docx into the TGmd draft. | 19/0893r1 | Dan Harkins | Edward | I | Implemented at 2327 ET, May 25, 2019.
115 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-0907-00-000m-fils-association-response-rsne.docx into the TGmd draft. | 19/0907r0 | Jouni | Edward | I | Implemented at 2334 ET, May 25, 2019.
117 | Incorporate the text changes in https://mentor.ieee.org/802.11/dcn/19/11-19-0919-00-000m-ft-initial-md-association-using-cached-pmksa.docx | 19/919r0 | Thomas | Edward | I | Implemented at 2254 ET, May 26, 2019.

## Motions in 2019-03
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
100 | Incorporate the following text change (described in https://mentor.ieee.org/802.11/dcn/19/11-19-0263-00-000m-missing-item-in-10-24-2-2.pptx )into the TGmd draft: On line 10 on page 1798 of [1] (Clause 10.24.2.2) replace “[…] invoked for reason c), d), e), or f) above […]” with “[…] invoked for reason c), d), or e) above […]” | 19-0263r0 |  | Emily | I |  | Edward | Yes, reviewed at 2222 ET, April 21, 2019
101 | MDR: Incorporate the changes in https://mentor.ieee.org/802.11/dcn/19/11-19-0260-06-0000-revmd-mdr-report.docx which are indicated as “Accepted” or “Revised” by the editor. | 19-260r6 | Emily/Edward | Emily/Edward | I
102 | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/19/11-19-0295-06-000m-ipsec-classifier.docx except for the addition of “[B60b] IETF RFC 8200, Internet Protocol, Version 6 (IPv6) Specification”, and with the addition of the complete replacement of RFC 2460 with IETF RFC 8200, Internet Protocol, Version 6 (IPv6) Specification, S. Deering, R. Hinden, 2017. | 19-295r6 | Matthew Fischer | Emily | IR | 1. at 152.19, removed the reference : IETF RFC 2460, Internet Protocol, Version 6 (IPv6), S. Deering, R. Hinden, Dec. 1998. 2. Added IETF RFC 8200 in Clause 2 instead of Annex A because RFC 2460 was in clause 2. | Edward | Yes, reviewed at 2220 ET, April 21, 2019.
104 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/19/11-19-0387-02-000m-addressing-some-sae-comments.docx under the following headings (pages 5 and 6) “No CID: Discrepency between table and state machine” “No CID: Provide Guidance on Weak Diffie-Hellman groups” | 19-0387r2 | Dan Harkins | Emily | I |  | Edward | Yes, reviewed and edited at 2226 ET, April 21, 2019.

## Motions in 2018-11
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
79 | Incorporate the changes indicated in https://mentor.ieee.org/802.11/dcn/18/11-18-1431-01-000m-proposed-resolutions-for-editor-s-notes-in-revmd-d1-4.doc into the TGmd draft. | 18-1431-r1 | Emily Qi | Emily | I |  | Edward | 20181124, 1556pm ET, reviewed.
80 | Incorporate the following changes into the TGmd draft: Change IEEE Std 802.1Q™-2003, IEEE Standard for Local and Metropolitan Area Networks: Media Access Control (MAC) Bridges and Virtual Bridged Local Area Networks. to IEEE Std 802.1Q™-2003, IEEE Standards for local and metropolitan area networks- Virtual Bridged Local Area Networks. And Change IEEE Std 802.1Q ™ -2011, IEEE Standard for Local and Metropolitan Area Networks: Media Access Control (MAC) Bridges and Virtual Bridged Local Area Networks to IEEE Std 802.1QTM, IEEE Standard for Local and Metropolitan Area Networks- Bridges and Bridged Networks |  |  | Emily | I |  | Edward | 20181124, 1538pm ET, reviewed and edited.
84 | •Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/18/11-18-1870-02-000m-suite-b-pmkid.docx into the TGmd draft | 18/1870r2 | Jouni | Emily | I |  | Edward | 20181124, 1540pm ET, reviewed.
85 | •Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/18/11-18-1924-01-000m-fixing-missing-refs-to-ft-akms.doc into the TGmd draft | 18/1924r1 | Thomas Durham | Emily | I |  | Edward | 20181124, 1551pm ET, reviewed and edited.
86 | •Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/18/11-18-1724-04-000m-response-to-d1p1-tgah-comments-from-1099.docx into the TGmd draft | 18/1724r4 | Matthew Fischer | Emily | I |  | Edward | 20181124, 1603pm ET, reviewed and edited.

## Motions in 2018-09
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
69 | Change the second paragraph in 10.37.6.2 (D1.4) as follows An SP allocation that is not an obsolete allocation is assigned to the source DMG STA identified in the Source AID subfield in an Allocation field within the Extended Schedule element. |  |  | Emily | I |  | Edward | 20180723, 1217pm ET, reviewed
70 | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1324-05-000m-fixes-to-multi-band-operations.docx into the TGmd draft | https://mentor.ieee.org/802.11/dcn/18/11-18-1324-05-000m-fixes-to-multi-band-operations.docx | Carlos Cordeiro | Emily | I |  | Edward | 20180723, 1219pm ET, reviewed
71 | Incorporate the following changes into the TGmd draft: (D1.4) At 1105.50 At the end of the paragraph, insert “Classifier Type 2 is deprecated” (D1.4) At 1667.52 Change from “IEEE Std 802.1Q-2011“ to “IEEE Std 802.1Q “ (D1.4) In the notes beginning at 2196.58, delete “Clause 35 of” (2x), “C.3 of” (1x) and delete “-2011” (3x) |  |  | Emily | I |  | Edward | 20180723, 1226pm ET, reviewed and edited
72 | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1177-02-000m-802-11ah-txop-limits.docx into the TGmd draft | https://mentor.ieee.org/802.11/dcn/18/11-18-1177-02-000m-802-11ah-txop-limits.docx | Menzo Wentink | Emily | I |  | Edward | 20180930, 1754pm ET, reviewed
73 | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1479-02-000m-parsing-a-commit-message.docx into the TGmd draft. | https://mentor.ieee.org/802.11/dcn/18/11-18-1479-02-000m-parsing-a-commit-message.docx | Dan Harkins | Emily | I |  | Edward | 20180930, 1752pm ET, reviewed

## Motions in 2018-07
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
55 | Incorporate the following change into the TGmd draft: relative to D1.0, Table 20-15, P2867L22, row entry for 12.4, change “6390” to “6930”. |  |  | Emily | I |  | Edward | 20180723, 1217pm ET, reviewed
56 | Move to incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1071-00-000m-key-names-with-ft-using-sha-384.docx into the TGmd draft. | https://mentor.ieee.org/802.11/dcn/18/11-18-1071-00-000m-key-names-with-ft-using-sha-384.docx | Jouni Malinen | Emily | I |  | Edward | 20180723, 1219pm ET, reviewed
57 | Move to incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1104-00-000m-updated-sae-test-vectors.docx into the TGmd draft. | 57 | Dan Harkins | Emily | I |  | Edward | 20180723, 1226pm ET, reviewed and edited
58 | Move to incorporate the changes in https://mentor.ieee.org/802.11/dcn/17/11-17-1807-12-000m-defense-against-multi-channel-mitm-attacks-via-operating-channel-validation.docx into the TGmd draft. |  | Nehru Bhandaru | Emily | I | Resolution for CID 1365 changed some of the text that was also changed by 1807/r12. In the the TGmd teleconference on 7/27/2018, TGmd discussed this matter and approved additional editorial changes to fix the issues as shown in 18/1353r2. | Edward | 20180723, 1325pm ET, reviewed and edited
59 | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1247-00-000m-post-ballot-comments.docx into the TGmd draft | https://mentor.ieee.org/802.11/dcn/18/11-18-1247-00-000m-post-ballot-comments.docx | Song An | Emily | I |  | Edward | 20180723, 1239pm ET, reviewed
62 | Incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-0334-02-000m-annex-i-dmg-ofdm-removal.docx into the TGmd draft. |  |  | Emily | IR | Changes to Figure 20-16 and 2016-18 have been implemented in D1.1. | Edward | 20180723, 1234pm ET, reviewed
67 | •Incorporate the text changes in https://mentor.ieee.org/802.11/dcn/18/11-18-1178-00-000m-updates-to-multi-band-operations.docx into the TGmd draft. |  | Carlos Cordeiro | Emily | I |  | Edward | 20180723, 1230pm ET, reviewed and edited

## Motions in 2018-05
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
53 | Move to incorporate the changes in https://mentor.ieee.org/802.11/dcn/18/11-18-0747-01-000m-pcf-deletion-cleanup.docx into the TGmd draft. | 18-0747-01 | Menzo Wentink | Emily | I | EDITOR2 edited and reviewed (22:05 ET, 2018/05/20)

## Motions in 2018-01
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
30 | 30) | 11-17-1738r1 | Huizhao Wang hwang@quantenna.com | Emily Qi | I | D1.0 | Edward Au | Reviewed (20180127 - 2156PT)
31 | DMG PHYCONFIG_VECTOR parameters Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/17/11-17-1810-01-000m-20-2-3-phyconfig-vector-parameters.docx into the TGmd draft. | 17/1810r1 | Claudio da Silva | Emily Qi | I | D1.0 | Edward Au | Reviewed (20180127 - 2159PT)
32 | Golay sequence numbering Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/17/11-17-1811-00-000m-20-11-golay-sequences.docx into the TGmd draft. | 32) | Claudio da Silva | Emily Qi | I | D1.0 | Edward Au | Reviewed (20180127 - 2200PT)
35 | At 3176.35 (D0.5) delete the words “if 1 MHz Duplicate PPDU as described in” Duplication and phase rotation: Duplicate 6 symbols of SIG field over each 1 MHz of the CH_BANDWIDTH if 1 MHz Duplicate PPDU. Apply the appropriate phase rotation for each 1 MHz subchannel as described in if 1 MHz Duplicate PPDU as described in 23.3.9.12 (1 MHz and 2 MHz duplicate transmission) and 23.3.7 (Mathematical description of signals). |  |  | Emily Qi | 1 | D1.0 | Edward Au | Reviewed (20180127 - 2202PT). The Editor's note at the end of the subclause is removed accordingly.
36 | SAE state machine Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/17/11-17-1890-01-000m-comments-on-sae-state-machine.docx into the TGmd draft. | 17/1890r1 | Nehru | Emily Qi | I | D1.0 | Edward Au | Reviewed (20180127 - 2205PT)
40 | CSA with channel switch time announcement Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/18/11-18-0203-02-000m-csa-enhancement.docx into the TGmd draft. | 18/0203r2 | Gabor | Emily Qi | I | D1.0 | Edward Au | Reviewed (20180127 - 2234PT)
41 | SAE Password identifier Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/18/11-18-0202-03-000m-identifying-a-password.docx into the TGmd draft | 18/0202r3 | Dan | Emily Qi | I | D1.0 | Edward Au | Reviewed and edited (20180127 - 2226PT). Added Order 22 in Table 9-39. Modified SAE description in Table 9-40. Added a new status code in Table 9-52. Need an ANA code. Fixed a typo in C.3.

## Motions in 2017-11
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
18 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/17/11-17-1610-01-000m-proposed-resolutions-for-editor-s-notes-in-revmd-d0-4.doc | 11-17-1610r1 | Emily Qi | Emily Qi | I | D0.5 |  | EDITOR2: Reviewed (20171210, 0747ET) Dorothy: reviewed.
19 | Incorporate the text changes indicated in https://mentor.ieee.org/802.11/dcn/17/11-17-1602-03-000m-nonce-reuse-prevention.doc | 11-17-1602r3 | Dan Harkin | Emily Qi | I | D0.5 |  | EDITOR2: Reviewed (20171210, 0750ET) Dorothy: reviewed.

## Motions in 2017-09
Motion Number | Text of motion | Submission | Submission Author | Editor | Edit Status | Edit Notes | Reviewer | Reviewed?
8 | Incorporate the text changes in https://mentor.ieee.org/802.11/dcn/17/11-17-0971-03-000m-enhancement-to-beacon-report.docx | 11-17/0971r3 | Gabor Bajko | Emily Qi | I | EDITOR2: Reviewed (20171002, 12:43ET)
9 | Incorporate the text changes in https://mentor.ieee.org/802.11/dcn/17/11-17-1172-01-000m-missed-tgmc-jtc1-sc6-comment.docx | 11-17/1172r1 | Dorothy Stanley | Emily Qi | I | EDITOR2: Reviewed and edited (20171002, 12:56ET)
11 | Incorporate the text changes in https://mentor.ieee.org/802.11/dcn/17/11-17-0940-03-000m-3gpp-ts-reference-per-liaison-11-17-0854-00.doc | 11-17/0940r3 | Stephen McCann | Emily Qi | I | EDITOR2: Reviewed (20171002, 12:52ET)
12 | Incorporate the text changes in https://mentor.ieee.org/802.11/dcn/17/11-17-1260-05-000m-beacon-report-fragmentation.docx | 11-17/1260r5 | Gabor Bajko | Emily Qi | IR | EDITOR2: Reviewed and edited (20171002, 12:48ET) EQ: Some editorial changes. Please review.
13 | Incorporate the text changes in https://mentor.ieee.org/802.11/dcn/17/11-17-1030-01-000m-sae-retry-timeout-clarification.docx | 11-17/1030r1 | Gabor Bajko | Emily Qi | I | EDITOR2: Reviewed (20171002, 12:50ET)