## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-20/112
Venue Date: | January 2020
First Author: | Carlos Cordeiro
Subject: | Comments on TGay/D5.0
Full Date: | 2020-01-10
Author(s): | Carlos Cordeiro
| Company: | Intel
Address
Phone:
Fax:
| email: | carlos.cordeiro@intel.com
Abstract: | Status of comments on 11ay D5.0 submitted as part of the initial SA ballot (SB000).

## All Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
6101 | Kasher, Assaf | 0 | 5 | 20.3.9 | 395 | 12 | T | No | 395 | 12 | 20.3.9 |  | V | Assaf |  | 648 | Rev MD rejecte the solution based on a MIB variable. We need to allign to RevMD. | Replace "the scrambler seed should be set to the dot11ScramblerResetValue." with be "should be set to a random value not based on the scrambler value at the end of the last transmitted PPDU. | REVISED (SB000: 2020-05-09 20:58:36Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0353-01-00ay-resolution-to-some-tgay-sb000-cids-v1.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6102 | Trainin, Solomon | 0 | 5 | AB | 787 | 5 | T | No | 787 | 5 | AB |  | V | Solomon |  | 658 | Annex AB "The purpose of this annex is to show an example implementation of an extended wireless network formation using devices that implement DMG STA functionality" The term "extended wireless network" is not defined and not used in the spec. The "extended network" is used in conjunction with GLK, that the Annex AB does not mention. The Annex AB is irrelevant to the normative part of the spec, does not provide any information that is useful for the features defined in the spec, contains errors and misleading sentences. I propose to remove the Annex. | Remove the annex | REVISED (SB000: 2020-05-09 21:00:16Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6103 | Trainin, Solomon | 0 | 5 | AB | 787 | 7 | T | No | 787 | 7 | AB |  | V | Solomon |  | 658 | Annex AB "The extended wireless network is intended to complement the sometimes limited signal range of a DMG STA" In any of the known WiFi networks the signal range is limited. The introduction does not provide any justification that solution different from the ESS is needed to provide the expected functionality | Remove the annex | REVISED (SB000: 2020-05-09 21:00:12Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6104 | Trainin, Solomon | 0 | 5 | AB | 787 | 11 | T | No | 787 | 11 | AB |  | V | Solomon |  | 658 | Annex AB "The extended wireless network described in this annex is similar to a mesh network. However, DMG STAs are not mesh STAs and cannot form mesh BSS. This annex describes an alternative approach of extended wireless network formation utilizing multiple BSSs." It is completely unclear what is similarity and difference between the introduced network and the mesh network. In no place, the spec is limited to adapt the mesh network to the DMG STA and vice versa. Unclear and not explained in the Annex why an alternative approach is needed and how it is different. From the other side the 802.11 spec provides means of multiple BSS interconnection by DS and ESS (Extended Service Set) that are applicable for the DMG STA by definition. The referred sentence is misleading. | Remove the annex | REVISED (SB000: 2020-05-09 21:00:07Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6105 | Trainin, Solomon | 0 | 5 | AB | 787 | 14 | T | No | 787 | 14 | AB |  | V | Solomon |  | 658 | Annex AB "Figure AB1 shows an example of an extended wireless network formation by devices that implement DMG STA functionality." There is no explanation of the Figure AB1 that makes the figure useless. | Remove the annex | REVISED (SB000: 2020-05-09 21:00:04Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6106 | Trainin, Solomon | 0 | 5 | AB | 787 | 20 | T | No | 787 | 20 | AB |  | V | Solomon |  | 658 | "AB.2 Layer 3 network consists of multiple BSSs" The sentence wrongfully mixes different layers. The most popular L3 network is IP network built around routers. Below IP, the architecture allows for arbitrarily many different network technologies, ranging from Ethernet to wireless to single point-to-point links. The L3 network does not need and is not aware of the BSS and vice versa. | Remove the annex | REVISED (SB000: 2020-05-09 20:59:58Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6107 | Trainin, Solomon | 0 | 5 | AB | 787 | 21 | T | No | 787 | 21 | AB |  | V | Solomon |  | 658 | Annex AB "DMG STAs can form either an infrastructure BSS or a PBSS." It is not true - the DMG STAs can participate in the IBSS as well. The DMG STAs establish infrastructure BSS and IBSS same as non-DMG STAs. | Remove the annex | REVISED (SB000: 2020-05-09 20:59:55Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6108 | Trainin, Solomon | 0 | 5 | AB | 787 | 22 | T | No | 787 | 22 | AB |  | V | Solomon |  | 658 | Annex AB "Neither DMG BSS nor PBSS is intended to form mesh topology network by itself." By definition "Mesh topology is a type of networking where all nodes cooperate to distribute data amongst each other" so, indeed the Infrastructure BSS and PBSS are not mesh networks with no relation to is it DMG BSS or not. From the other side the 802.11 introduces and defines mesh basic service set (MBSS). From the data delivery point of view, it appears as if all STAs in a mesh BSS are directly connected at the MAC layer even if the STAs are not within range of each other. The multi-hop capability enhances the range of the STAs and benefits wireless LAN deployments. Further, using the multi-hop capability, MSDUs and Management frames can be transferred between STAs that are not in direct communication with each other over a single instance of the wireless medium. There is no reason presented that the mesh BSS is not relevant and does not provide a benefit to the DMG STAs. | Remove the annex | REVISED (SB000: 2020-05-09 20:59:51Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6109 | Trainin, Solomon | 0 | 5 | AB | 788 | 4 | T | No | 788 | 4 | AB |  | V | Solomon |  | 658 | Annex AB "Multiple STA instances inside a device can be managed by a single SME using either MM-SME (see 4.9.3) or cochannel coordinated management (see 4.9.5). The SME can manage multiple DMG STA instances in a device so that each STA is bridged from a higher layer perspective." Misconception of layering - SME has nothing to do with the bridging. The bridging belongs to the data path that the SME is not involved. | Remove the annex | REVISED (SB000: 2020-05-09 21:00:19Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0611-00-00ay-sb000-annex-ab-cids.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6110 | Trainin, Solomon | 0 | 5 | 11.37.3 | 386 | 24 | T | No | 386 | 24 | 11.37.3 |  | V | Solomon |  | 643 | "Issue an MLME-TDD-SECTOR-SWITCH.indication primitive" The ResultCode is not defined for the case | Define value of the ResultCode | REVISED (SB000: 2020-02-05 17:50:00Z) Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0157-01-00ay-sa-ballot-comment-resolution-cids-6113-6114-6110-6111-6112.docx | SB000 | [6 empty] | 2020-02-05 17:50 | SB000
6111 | Trainin, Solomon | 0 | 5 | 9.2.4.5.4 | 94 | 1 | T | No | 94 | 1 | 9.2.4.5.4 |  | A | Solomon |  | 643 | Wrong term "non-MPDU" | Replace by "non-A-MPDU" | ACCEPTED (SB000: 2020-02-05 17:49:12Z) | SB000 | [6 empty] | 2020-02-05 17:49 | SB000
6112 | Trainin, Solomon | 0 | 5 | 9.4.2.142.6 | 131 | 28 | T | No | 131 | 28 | 9.4.2.142.6 |  | V | Solomon |  | 643 | "This statistic is reset when the reset condition defined below in this subclause is met." The sentence and the following text that defines the reset conditions are not suitable for the Frame formats clause and shall be moved to the behavioral clause. | P130L23, P130L35, P131L5, P131L28, P131L53, P131L40, P132L24, P132L28. Remove sentence that starts with "This statistic is reset when the reset condition..." P132L7 change as follows: "The reset condition of the statistics is defined as follows:" Move the text from P132L7 till end of the subclause to the subclause 10.44.5 TDD link maintenance on P354L3. | REVISED (SB000: 2020-02-05 17:49:31Z) Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0157-01-00ay-sa-ballot-comment-resolution-cids-6113-6114-6110-6111-6112.docx | SB000 | [6 empty] | 2020-02-05 17:50 | SB000
6113 | Trainin, Solomon | 0 | 5 | 10.26.11.5 | 245 | 14 | T | No | 245 | 14 | 10.26.11.5 |  | V | Solomon |  | 643 | Text that starts with "For each unsolicited block ack extension agreement, the recipient..." and ends with "... the NextExpectedSequenceNumber for that unsolicited block ack extension agreement, then the MPDU shall be passed up to the next MAC process." is not needed. The NextExpectedSequenceNumber was formerly used in the IEEE Std 802.11-2016 and is not used anymore. The normative behavior of unsolicited block ack is fully defined in the current text and another variable is not needed. The commented text contains a lot of errors like "MSDU Starting Sequence Number subfield of the BAR Information field of the ADDBA Request frame that established the unsolicited block ack extension agreement." There is no such subfield, and the ADDBA request is not used to establish the unsolicited block ack extension agreement. I propose to remove the text. | Remove the text | REVISED (SB000: 2020-02-05 17:49:52Z) Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0157-01-00ay-sa-ballot-comment-resolution-cids-6113-6114-6110-6111-6112.docx | SB000 | [6 empty] | 2020-02-05 17:50 | SB000
6114 | Trainin, Solomon | 0 | 5 | 11.1.7 | 364 | 10 | T | No | 364 | 10 | 11.1.7 |  | A | Solomon |  | 643 | "The Clock Attributes field in the TDD Synchronization element of that frame scores better than .." it is unclear which of the two frames this applies to. | Change as follows: "The Clock Attributes field in the TDD Synchronization element of that last frame scores better than ..." | ACCEPTED (SB000: 2020-02-05 17:49:23Z) | SB000 | [6 empty] | 2020-02-05 17:49 | SB000
6115 | Trainin, Solomon | 0 | 5 | 9.7.1 | 210 | 6 | T | No | 210 | 6 | 9.7.1 |  | V | Solomon |  | 653 | The MPDU size field in the MPDU delimiter is 13 bit, which does not allow placing a Jumbo frame. | Extend the MPDU size field in the MPDU delimiter. Make the extension optional. | REVISED (SB000: 2020-05-09 21:02:20Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0242-03-00ay-msdu-size-extension-cid-6115-6234.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6116 | Da Silva, Claudio | 0 | 5 | 10.42.7 | 288 | 48 | T | No | 288 | 48 | 10.42.7 |  | V | Claudio |  | 646 | Feedback of training performed with an EDMG BRP-RX/TX PPDU uses AWV Feedback IDs; thus, it must be carried within an EDMG Channel Measurement Feedback element. | Substitute "Channel Measurement Feedback element" with "EDMG Channel Measurement Feedback element". | REVISED (SB000: 2020-05-09 21:03:57Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0327-01-00ay-initial-sa-ballot-comment-resolution.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6117 | Rannow, R K | 0 | 5 | 6.3.122.4.4 | 77 | 22 | E | No | 77 | 22 | 6.3.122.4.4 |  | V | Solomon |  | 666 | Phase, "if any" is ambiguous as sentence starts with "If" | Remove "if any" from the line, and change to: ... MAC entity. Receipt of this ... | REVISED (SB000: 2020-07-22 23:53:44Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0916-02-00ay-resolution-to-sa-ballot-cids-6146-6117-6190-and-6205.docx | SB000 | [6 empty] | 2020-07-22 23:54 | SB000
6118 | Rannow, R K | 0 | 5 | 9.4.2.278 | 171 | 24 | T | No | 171 | 24 | 9.4.2.278 |  | V | Solomon |  | 645 | Instances of "if any" that should be removed as this creates ambiguity. | remove ambiguous "if any" statements. Perhaps 12 instances. | REVISED (SB000: 2020-05-09 21:02:10Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0267-01-00ay-resolution-of-sb000-cids-6118-6119-6202-6210-6221-6224.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6119 | Rannow, R K | 0 | 5 | 10.25.11.5 | 245 | 35 | T | No | 245 | 35 | 10.25.11.5 |  | V | Solomon |  | 645 | If, after an MPDU is received, the receive buffer is full, the complete MSDU or A-MSDU with the earliest If, after an MPDU is received, the receive buffer is not full, but the sequence number of the complete MSDU | Ambiguous or confusing wording in line 35 & 37. Suggest change to: When the receive buffer is full, and after an MPDU is received ... | REVISED (SB000: 2020-05-09 21:02:36Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0267-01-00ay-resolution-of-sb000-cids-6118-6119-6202-6210-6221-6224.docx | SB000 | [6 empty] | 2020-05-09 21:03 | SB000
6120 | Alessi, Julie | 0 | 5 |  |  |  | E | No |  |  |  |  | A | Carlos |  | 642 | Draft meets all editorial requirements. |  | ACCEPTED (SB000: 2020-01-13 19:32:10Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:50:08Z |  | 2020-01-30 02:50 | SB000
6121 | Sakoda, Kazuyuki | 0 | 5 | 11.32.7 | 377 | 21 | T | Yes | 377 | 21 | 11.32.7 |  | V | Sakoda-san |  | 654 | The current draft standard lacks a tool for the distribution network bootstrapping, particularly when applications are expecting low latency communication. DMG discovery assistance should enable neighbor DMG/EDMG STA discovery beyond an AP to ease implementation of the distribution network leveraging 802.11ay. In particular, the standard should provide a tool for the AP that serves discovery assistance to propagate discovery assistance request to neighbor STAs. | Add a container that allows AP to transmit discovery asssitance request to STAs in the BSS. Also, allow AP to propagate the discovery assistance request. | REVISED (SB000: 2020-05-09 21:04:22Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0209-05-00ay-suggested-resolution-to-cid-6121-6122-and-6123.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6122 | Sakoda, Kazuyuki | 0 | 5 | 4.3.22 | 25 | 9 | E | Yes | 25 | 9 | 4.3.22 |  | V | Sakoda-san |  | 654 | "TDD channel access" has been introduced to 802.11ay specification. TDD is not the appropriate term to describe single directional transmission mode. The naming TDD in this context should be reconsidered. | Replace TDD with something more appropriate. | REVISED (SB000: 2020-05-09 21:01:31Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0209-05-00ay-suggested-resolution-to-cid-6121-6122-and-6123.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6123 | Sakoda, Kazuyuki | 0 | 5 | 4.3.30 | 25 | 19 | G | Yes | 25 | 19 | 4.3.30 |  | V | Sakoda-san |  | 654 | There is a list of new PHY features for EDMG STAs, but not for MAC. We should have a list of new MAC features for EDMG STAs. | The commenter is willing to provide a suggested text. | REVISED (SB000: 2020-05-09 21:01:28Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0209-05-00ay-suggested-resolution-to-cid-6121-6122-and-6123.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6124 | Banavara, Madhusudan | 0 | 5 |  |  | 6 | E | Yes |  | 6 |  |  | A | Carlos |  | 642 | Assitance | Assistance | ACCEPTED (SB000: 2020-01-13 19:32:43Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:53:33Z |  | 2020-01-30 02:54 | SB000
6125 | Banavara, Madhusudan | 0 | 5 |  |  | 29 | E | Yes |  | 29 |  |  | A | Carlos |  | 642 | FIgue | Figure | ACCEPTED (SB000: 2020-01-13 19:32:32Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:54:16Z |  | 2020-01-30 02:54 | SB000
6126 | Banavara, Madhusudan | 0 | 5 |  |  | 48 | E | Yes |  | 48 |  |  | A | Carlos |  | 642 | Examplary | Exemplary | ACCEPTED (SB000: 2020-01-14 16:17:35Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:54:56Z |  | 2020-01-30 02:55 | SB000
6127 | Banavara, Madhusudan | 0 | 5 |  | 47 | 1 | E | Yes | 47 | 1 |  |  | A | Carlos |  | 652 | adverstised | advertised | ACCEPTED (SB000: 2020-03-18 02:02:05Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6128 | Banavara, Madhusudan | 0 | 5 |  | 67 | 14 | E | Yes | 67 | 14 |  |  | A | Carlos |  | 652 | entitity | entity | ACCEPTED (SB000: 2020-03-18 02:02:10Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6130 | Banavara, Madhusudan | 0 | 5 |  | 99 | 25 | E | Yes | 99 | 25 |  |  | A | Carlos |  | 652 | subfield is is encoded as | subfield is encoded as | ACCEPTED (SB000: 2020-03-18 02:02:26Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6131 | Banavara, Madhusudan | 0 | 5 |  | 102 | 9 | E | Yes | 102 | 9 |  |  | A | Carlos |  | 652 | beamfroming | beamforming | ACCEPTED (SB000: 2020-03-18 02:00:50Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6132 | Banavara, Madhusudan | 0 | 5 |  | 139 | 5 | E | Yes | 139 | 5 |  |  | A | Carlos |  | 652 | characterstics | characteristics | ACCEPTED (SB000: 2020-03-18 02:00:57Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6133 | Banavara, Madhusudan | 0 | 5 |  | 199 | 8 | E | Yes | 199 | 8 |  |  | A | Carlos |  | 652 | MID Extention | MID Extension | ACCEPTED (SB000: 2020-03-18 02:02:40Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6134 | Banavara, Madhusudan | 0 | 5 |  | 200 | 26 | E | Yes | 200 | 26 |  |  | A | Carlos |  | 652 | Feeback | Feedback | ACCEPTED (SB000: 2020-03-18 02:02:45Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6135 | Banavara, Madhusudan | 0 | 5 |  | 215 | 39 | E | Yes | 215 | 39 |  |  | A | Carlos |  | 652 | paramter | parameter | ACCEPTED (SB000: 2020-03-18 02:02:54Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6136 | Banavara, Madhusudan | 0 | 5 |  | 229 | 41 | E | Yes | 229 | 41 |  |  | A | Carlos |  | 652 | segmengation | segmentation | ACCEPTED (SB000: 2020-03-18 02:03:00Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6137 | Banavara, Madhusudan | 0 | 5 |  | 230 | 10 | E | Yes | 230 | 10 |  |  | A | Carlos |  | 652 | recipeint | recipient | ACCEPTED (SB000: 2020-03-18 02:03:03Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6138 | Banavara, Madhusudan | 0 | 5 |  | 230 | 33 | E | Yes | 230 | 33 |  |  | A | Carlos |  | 652 | coresponding | corresponding | ACCEPTED (SB000: 2020-03-18 02:03:06Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6139 | Banavara, Madhusudan | 0 | 5 |  | 233 | 17 | E | Yes | 233 | 17 |  |  | A | Carlos |  | 652 | sublement | subelement | ACCEPTED (SB000: 2020-03-18 02:03:10Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6140 | Banavara, Madhusudan | 0 | 5 |  | 242 | 4 | E | Yes | 242 | 4 |  |  | A | Carlos |  | 652 | aggregaton | aggregation | ACCEPTED (SB000: 2020-03-18 02:03:14Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6141 | Banavara, Madhusudan | 0 | 5 |  | 243 | 5 | E | Yes | 243 | 5 |  |  | A | Carlos |  | 652 | deacresed | decreased | ACCEPTED (SB000: 2020-03-18 02:03:18Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6143 | Banavara, Madhusudan | 0 | 5 |  | 246234 | 26 | E | Yes | 246234 | 26 |  |  | A | Carlos |  | 652 | unsolicted | unsolicited | ACCEPTED (SB000: 2020-03-18 02:06:09Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6144 | Banavara, Madhusudan | 0 | 5 |  | 261 | 9 | E | Yes | 261 | 9 |  |  | A | Carlos |  | 652 | perfoming | performing | ACCEPTED (SB000: 2020-03-18 02:03:33Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6145 | Banavara, Madhusudan | 0 | 5 |  | 0 | 0 | G | Yes | 0 | 0 |  |  | J | Carlos |  | 642 | It appears that the document has been put together in a hurried manner. A simple spell check threw up more than the above errors. I suspect this will not pass muster otherwise too... |  | REJECTED (SB000: 2020-01-14 16:13:56Z) The commenter does not provide a proposed change that would satisfy the comment. With that said, the Editor is continuously reviewing the draft to correct editorial errors. | SB000 |  |  |  | I | SB000: 2020-01-30 02:55:04Z |  | 2020-01-30 02:55 | SB000
6146 | Hansen, Christopher | 0 | 5 | 4.3.22 | 25 | 6 | E | Yes | 25 | 6 | 4.3.22 |  | V | Solomon |  | 666 | The sentence "A DMG STA has MAC features that include frame aggregation, block ack features, service periods,..." is awkward because "features" is used twice and is also used in the previous sentence. | Change to "These features include frame aggregation, block acknowdgement, service periods,..." | REVISED (SB000: 2020-07-22 23:53:41Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0916-02-00ay-resolution-to-sa-ballot-cids-6146-6117-6190-and-6205.docx | SB000 | [6 empty] | 2020-07-22 23:54 | SB000
6147 | Hansen, Christopher | 0 | 5 | 4.3.30 | 25 | 21 | T | Yes | 25 | 21 | 4.3.30 |  | J | Chris |  | 659 | Mandatory support of 4.32 GHz channel width will slow adoption of 802.11ay. | Change to Optional support of 4.32 GHz. | REJECTED (SB000: 2020-04-22 18:28:59Z) Commenter withdrew comment. | SB000 | [6 empty] | 2020-05-09 18:09 | SB000
6148 | Hansen, Christopher | 0 | 5 | 4.3.30 | 26 | 1 | E | Yes | 26 | 1 | 4.3.30 |  | A | Carlos |  | 652 | This statement is awkward because a STA would never be without at least one antenna. "An EDMG STA can be equipped with one or more DMG antennas." | Change to "An EDMG STA is equipped with one or more DMG antennas." | ACCEPTED (SB000: 2020-03-18 02:01:53Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6149 | Hansen, Christopher | 0 | 5 | 4.3.30 | 26 | 2 | E | Yes | 26 | 2 | 4.3.30 |  | A | Carlos |  | 652 | "When equipped with more than one 1 DMG antenna" should specify that it is the STA that is equipped. | Change to "When the STA is equipped" | ACCEPTED (SB000: 2020-03-18 02:01:21Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6150 | Hansen, Christopher | 0 | 5 | 4.3.30 | 26 | 3 | E | Yes | 26 | 3 | 4.3.30 |  | V | Carlos |  | 663 | Grammar errors. "Therefore, transmissions from different DMG antennas can reach different set of STAs." | Change to "Therefore, transmissions from different DMG antennas may reach different sets of STAs." | REVISED (SB000: 2020-05-09 18:20:00Z) Normative verbs like "may" are not used in clause 4, which is not normative. As such, propose to change it to: "Therefore, transmissions from different DMG antennas can reach different sets of STAs." | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6151 | Hansen, Christopher | 0 | 5 | 4.9.4 | 26 | 12 | E | Yes | 26 | 12 | 4.9.4 |  | A | Carlos |  | 642 | Grammar errors. "trigger one of its MLME to" here and on line 15. | Make MLME plural, i.e. MLMEs. | ACCEPTED (SB000: 2020-01-14 16:22:58Z) | SB000 |  |  |  | I | SB000: 2020-01-30 03:00:27Z |  | 2020-01-30 03:00 | SB000
6152 | Hansen, Christopher | 0 | 5 | 4.9.4 | 26 | 12 | E | Yes | 26 | 12 | 4.9.4 |  | A | Carlos |  | 642 | Grammar errors here and on line 16 - "discovery assistance procedure at its operating band" | Change to "discovery assistance procedure for its operating band" | ACCEPTED (SB000: 2020-01-14 16:19:48Z) | SB000 |  |  |  | I | SB000: 2020-01-30 03:01:47Z |  | 2020-01-30 03:02 | SB000
6153 | Hansen, Christopher | 0 | 5 | 4.9.5 | 26 | 24 | E | Yes | 26 | 24 | 4.9.5 |  | A | Carlos |  | 642 | Grammar - "reference model of a device" | Change to "reference model for a device" | ACCEPTED (SB000: 2020-01-14 16:19:30Z) | SB000 |  |  |  | I | SB000: 2020-01-30 03:02:14Z |  | 2020-01-30 03:02 | SB000
6154 | Hansen, Christopher | 0 | 5 | C.3 | 777 | 9 | T | Yes | 777 | 9 | C.3 |  | V | Chris |  | 647 | Need to add additional MIB settings for dot11UnsolicitedBAActivated. | Contribution to be provided. | REVISED (SB000: 2020-05-09 20:59:23Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0347-00-00ay-resolution-to-cid-6154.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6155 | Petrick, Albert | 0 | 5 | 10.39.6.2.2 | 254 | 12 | E | No | 254 | 12 | 10.39.6.2.2 |  | A | Carlos |  | 652 | Spelling error | Change "FIgue" to "Figure" | ACCEPTED (SB000: 2020-03-18 02:03:23Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6156 | Petrick, Albert | 0 | 5 | 10.39.6.2.2 | 254 | 17 | E | No | 254 | 17 | 10.39.6.2.2 |  | A | Carlos |  | 652 | Spelling error in Figure 10-57a | Change "FIgue" to "Figure" | ACCEPTED (SB000: 2020-03-18 02:03:29Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6157 | Petrick, Albert | 0 | 5 | 10.42.7 | 290 | 20 | E | No | 290 | 20 | 10.42.7 |  | A | Carlos |  | 652 | Spelling error | Change "PPDUpacket" to "PPDU" | ACCEPTED (SB000: 2020-03-18 02:03:47Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6158 | Petrick, Albert | 0 | 5 | 10.3.2.3 | 213 | 21 | E | No | 213 | 21 | 10.3.2.3 |  | A | Carlos |  | 652 | Missing period after the clause number | Change "10.23.2" to "10.23.2." | ACCEPTED (SB000: 2020-03-18 02:02:50Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6159 | Petrick, Albert | 0 | 5 | 10.42.7 | 290 | 10 | E | No | 290 | 10 | 10.42.7 |  | A | Carlos |  | 663 | Sentence should read simular to the text on pg 290, line 5 | Change "responder to" to "responder that the responder" | ACCEPTED (SB000: 2020-05-09 18:38:51Z) | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6160 | Petrick, Albert | 0 | 5 | 10.42.10.2.2.3.3 | 299 | 38 | T | No | 299 | 38 | 10.42.10.2.2.3.3 |  | V | Lei Huang |  | 644 | The paragraph discribes the 3 subphases in Figure 10-94b. It states "Each subphase shall be separated by an MBIFS". The MBIFS is missing in Figure 10-94b. | Add MBIFS in Figure 10-94b to illustrate where the MBIFS aligns between the suphases. | REVISED (SB000: 2020-05-09 21:04:04Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0271-01-00ay-sa-ballot-cr-on-cid-6160-6209-6212.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6161 | YANG, RUI | 0 | 5 | 28.1.1 | 397 | 11 | E | No | 397 | 11 | 28.1.1 |  | V | Solomon |  | 665 | It is grammarly inaccurate by saying "multiple channel widths PPDU transmissions." | Change the first sentence of this paragraph to "The EDMG PHY adds support for multiple space-time streams, downlink multi-user (MU) transmissions and PPDU transmissions with multiple channel widths, including 4.32 GHz, 6.48 GHz, 8.64 GHz, 2.16+2.16 GHz, and 4.32+4.32 GHz 11." | REVISED (SB000: 2020-07-22 23:53:23Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6162 | YANG, RUI | 0 | 5 | 28.1.1 | 397 | 14 | E | Yes | 397 | 14 | 28.1.1 |  | V | Solomon |  | 665 | It is not clear what "each channel" means in the last sentence, | Change to "For 2.16+2.16 GHz and 4.32+4.32 GHz transmissions, the maximum number of spatial streams in each 2.16 GHz channel and 4.32 GHz channel, respectively, is four. | REVISED (SB000: 2020-07-22 23:53:25Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6163 | YANG, RUI | 0 | 5 | 28.1.1 | 398 | 17 | E | Yes | 398 | 17 | 28.1.1 |  | V | Solomon |  | 665 | It is not clear if short GI type is supported means the long GI type must also be supported. | If both types must be supported as long as one of them is supported, change this line to "Both short and long GI types"; otherwise, change the line to "Short GI type or long GI type or both" | REVISED (SB000: 2020-07-22 23:53:27Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6164 | YANG, RUI | 0 | 5 | 28.1.2 | 398 | 26 | E | No | 398 | 26 | 28.1.2 |  | J | Carlos |  | 663 | "framing format" is a confusing term. | Just remove "framing format". Change the sentence to "function that defines a method of mapping the PSDUs into a PPDU..." | REJECTED (SB000: 2020-05-09 18:36:08Z) The same wording is used for other PHYs. See (21.1.2 Scope of VHT PHY services) as an example. | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6165 | YANG, RUI | 0 | 5 | 28.2.4.2 | 422 | 1 | E | Yes | 422 | 1 | 28.2.4.2 |  | A | Carlos |  | 652 | "Clause 29" in Figure 28-1 should be changed to "Clause 28". | See Comment | ACCEPTED (SB000: 2020-03-18 02:04:46Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6166 | YANG, RUI | 0 | 5 | 28.2.4.3 | 423 | 6 | E | Yes | 423 | 6 | 28.2.4.3 |  | A | Carlos |  | 652 | "Clause 29" in Figure 28-2 should be changed to "Clause 28". | See Comment | ACCEPTED (SB000: 2020-03-18 02:04:51Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6167 | YANG, RUI | 0 | 5 | 28.2.4.4 | 424 | 21 | E | Yes | 424 | 21 | 28.2.4.4 |  | A | Carlos |  | 652 | "Clause 29" in Figure 28-2 should be changed to "Clause 28". | See Comment | ACCEPTED (SB000: 2020-03-18 02:04:53Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6168 | YANG, RUI | 0 | 5 | 28.3.1 | 427 | 1 | E | No | 427 | 1 | 28.3.1 |  | V | Solomon |  | 665 | In Table 28-2, N_up is defined as Upsampling parameter. The commonly used term is Upsampling factor. | Change Upsamping parameter to Updampling factor. | REVISED (SB000: 2020-07-22 23:53:30Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:54 | SB000
6169 | YANG, RUI | 0 | 5 | 28.3.2.1 | 430 | 6 | E | No | 430 | 6 | 28.3.2.1 |  | J | Carlos |  | 663 | "The Data field carries the PSDU(s)" is better to be changed to "The Data field carrying the PSDU(s)" | See Comment | REJECTED (SB000: 2020-05-09 18:22:24Z) The existing wording is correct. Note that this defines the field. | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6170 | YANG, RUI | 0 | 5 | 28.3.2.1 | 430 | 6 | E | No | 430 | 6 | 28.3.2.1 |  | V | Carlos |  | 663 | "Training sequences field" is better to be changed to "Training sequence field" or simply "Training field" | See Comment | REVISED (SB000: 2020-05-09 18:23:32Z) Use "Training sequence field" | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6171 | YANG, RUI | 0 | 5 | 28.3.3.2.4.1 | 434 | 3 | E | Yes | 434 | 3 | 28.3.3.2.4.1 |  | V | Solomon |  | 665 | The description in some of cells in the last column of Table 28-6 should have "Any one of", similar to the first row. For example, the text in the second row (last column) is better to be "Any one of (1 and 2), (3 and 4), (5 and 6), (7 and 8)" | See Comment | REVISED (SB000: 2020-07-22 23:53:32Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:54 | SB000
6172 | YANG, RUI | 0 | 5 | 28.3.3.2.4.1 | 434 | 3 | E | Yes | 434 | 3 | 28.3.3.2.4.1 |  | V | Carlos |  | 663 | In the last cell of Table 28-6, "28 - 2 and 4 - 6" appears an error. Is it "1-2 and 5-6"? | See Comment | REVISED (SB000: 2020-05-09 18:44:50Z) Replace it with "3-4 and 6-7" | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6173 | YANG, RUI | 0 | 5 | 28.3.3.2.4.1 | 434 | 3 | E | No | 434 | 3 | 28.3.3.2.4.1 |  | V | Carlos |  | 663 | In the last cell of the title row of Table 28-6, "channle(s)" should be "channel number(s)" | See Comment | REVISED (SB000: 2020-05-09 18:47:10Z) In the table heading (last column), replace "channel(s)" with "channel number(s)" | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6174 | YANG, RUI | 0 | 5 | 28.3.3.3.1 | 437 | 18 | E | No | 437 | 18 | 28.3.3.3.1 |  | V | Claudio |  | 646 | It is not clear what " The EDMG-Header-A field is defined at the SC chip rate Fc." means. Does it mean "The EDMG-Header-A field is transmitted using SC modulation at chip rate Fc"? | Change "The EDMG-Header-A field is defined at the SC chip rate Fc." to "The EDMG-Header-A field is transmitted using SC modulation at chip rate Fc." or "The EDMG-Header-A field is modulated in SC at chip rate Fc" | REVISED (SB000: 2020-05-09 20:58:59Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0327-01-00ay-initial-sa-ballot-comment-resolution.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6175 | YANG, RUI | 0 | 5 | 28.3.3.3.1 | 437 | 21 | E | Yes | 437 | 21 | 28.3.3.3.1 |  | V | Claudio |  | 646 | The sentence "Reserved bits shall be set to 0 by the transmitter and shall be ignored by the receiver." it is not clear which reserved bits belong to. | Change the sentence to indicate the field those bits are in. | REVISED (SB000: 2020-05-09 20:59:04Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0327-01-00ay-initial-sa-ballot-comment-resolution.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6176 | YANG, RUI | 0 | 5 | 28.3.3.3.2.2 | 438 | 7 | E | Yes | 438 | 7 | 28.3.3.3.2.2 |  | V | Claudio |  | 646 | In the first row of Table 28-11, the following statements should be conditioned under the EDMG TRN Length Field is non-zero: "If this field set to 0, the BW field specifies that the TRN field of the PPDU is appended on a 2.16 GHz, 4.32 GHz, 6.48 GHz or 8.64 GHz channel. If this field set to 1, the BW field specifies that the TRN field is transmitted over a 2.16+2.16 GHz or 4.32+4.32 GHz channel." | Change "If this field set to 0 ..." to "If this field set to 0 and the EDMG TRN Length Field is non-zero ..." and change "If this field set to 0 ..." to "If this field set to 1 and the EDMG TRN Length Field is non-zero ...". | REVISED (SB000: 2020-05-09 20:59:08Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0327-01-00ay-initial-sa-ballot-comment-resolution.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6177 | YANG, RUI | 0 | 5 | 28.3.3.3.2.4 | 448 | 18 | E | Yes | 448 | 18 | 28.3.3.3.2.4 |  | A | Carlos |  | 652 | Change "Remove zero bits" to "Remove zero-valued bits" | See Comment | ACCEPTED (SB000: 2020-03-18 02:05:50Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6178 | YANG, RUI | 0 | 5 | 28.3.3.3.2.4 | 448 | 20 | E | Yes | 448 | 20 | 28.3.3.3.2.4 |  | A | Carlos |  | 652 | Change "Remove zero bits" to "Remove zero-valued bits" | See Comment | ACCEPTED (SB000: 2020-03-18 02:05:55Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6179 | YANG, RUI | 0 | 5 | 28.3.3.4.2 | 451 | 17 | T | Yes | 451 | 17 | 28.3.3.4.2 |  | V | Claudio |  | 646 | This subclause applies to two channel aggregation cases: 2.16+2.16 GHz PPDU and 4.32+4.32 GHz PPDU, but there is no text mention the first case explicitly. Suggest make them explicitly. | Change Line 21-22 to "The lower half NTX/2 transmit chains (i.e., those with lower indices) are used for transmissions in the primary channel for a 2.16+2.16 GHz PPDU transmission, or primary and secondary channels for a 4.32+4.32 GHz PPDU transmission. Change Line 23-24 to "The upper half NTX/2 transmit chains (i.e., those with higher indices) are used for transmissions in the secondary channel for a 2.16+2.16 GHz PPDU transmission, or secondary1 and secondary2 channels for a 4.32+4.32 GHz PPDU transmission. Similar changes can be applied to Line 28-31. | REVISED (SB000: 2020-05-09 20:59:14Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0327-01-00ay-initial-sa-ballot-comment-resolution.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6180 | YANG, RUI | 0 | 5 | 28.4.7.3.2 | 484 | 16 | E | Yes | 484 | 16 | 28.4.7.3.2 |  | A | Carlos |  | 652 | "The preamble and Data field" should be "The preamble and Data fields" | See Comment | ACCEPTED (SB000: 2020-03-18 02:06:03Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6181 | YANG, RUI | 0 | 5 | 28.6.2.2 | 546 | 9 | E | Yes | 546 | 9 | 28.6.2.2 |  | V | Claudio |  | 649 | The unit of "length" should be given for "short guard interval length", "normal guard interval length" and "long guard interval length". | See Comment | REVISED (SB000: 2020-05-09 20:59:19Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0327-01-00ay-initial-sa-ballot-comment-resolution.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6182 | Eitan, Alecsander | 0 | 5 | 20.3.9 | 395 | 9 | T | No | 395 | 9 | 20.3.9 |  | V | Assaf |  | 648 | The text suggested might be misleading since there are some restrictions on the bits selection when MCS belongs to the set {9.1, 12.1, 12.2, 12.3, 12.4, 12.5, 12.6} - see end of section 20.5.3.1.1 in REVmd Draft 3.0. Text should at least note this. | Add a note that when Extended SC MCS is used additional rules apply see 20.5.3.1.1 | REVISED (SB000: 2020-05-09 21:04:27Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0353-01-00ay-resolution-to-some-tgay-sb000-cids-v1.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6183 | Eitan, Alecsander | 0 | 5 | 20.9.1 | 395 | 18 | T | No | 395 | 18 | 20.9.1 |  | V | Alecs |  | 661 | The text "For a STA that does not support TDD SPs" is not adequate. Just the fact that an STA supprts or not TDD SPs is not the issue. The requirement is for the actual operation mode. An STA may have many elements and RF modules and use them per mode. | Suggest to replace with "For a STA operation in non- TDD SPs"... | REVISED (SB000: 2020-07-22 23:52:51Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0344-00-00ay-resolution-to-cid-6183-and-6208.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6184 | Eitan, Alecsander | 0 | 5 | 9.4.2.142.3 | 129 | 20 | T | No | 129 | 20 | 9.4.2.142.3 |  | V | Alecs |  | 661 | Inconsistency: In section 9.4.2.142.3 the text is "If the value of this subfield is greater than 0, the MCS, Link Margin and SNR fields in the DMG Link Margin element are reserved.". However in section 9.4.2.142.1 suggested changes are: "The SNR field is reserved when the value of the Number of Space-Time Streams Reported (NSTS) subfield within the Rate Adaptation Control/Extended TPC field is greater than 1." | I suggest to remove the issue by deleting in section 9.4.2.142.3 the text is "If the value of this subfield is greater than 0, the MCS, Link Margin and SNR fields in the DMG Link Margin element are reserved.". | REVISED (SB000: 2020-07-22 23:52:30Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0343-01-00ay-resolution-to-cid-6184-9.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6185 | Eitan, Alecsander | 0 | 5 | 9.4.2.142.5 | 130 | 34 | T | No | 130 | 34 | 9.4.2.142.5 |  | V | Alecs |  | 661 | The text doesn't provide rules for the case when Number of PPDUs is 0, as in other cases (e.g. MCS field). | Suggest to copy from MCS case. Add "If the Number of PPDUs subfield within the Rate Adaptation Control/Extended TPC field is 0, the SNRi subfield is set to 255" (add this before the last sentence in the paragraph - line 35) | REVISED (SB000: 2020-07-22 23:52:35Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0343-01-00ay-resolution-to-cid-6184-9.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6186 | Eitan, Alecsander | 0 | 5 | 9.4.2.142.6 | 131 | 29 | T | No | 131 | 29 | 9.4.2.142.6 |  | V | Alecs |  | 661 | The text states that the Max Iterationi subfield presents the maximum of iterations over codewords and PSDUs, where one iteration is processing all rows. However the fiels has a resolution of 0.1. This can be confusion since it is not clear how one can get a non integer number. | Suggest to add a comment sentence that non integer numbers can reflect stop before all rows are processed. | REVISED (SB000: 2020-07-22 23:52:38Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0343-01-00ay-resolution-to-cid-6184-9.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6187 | Eitan, Alecsander | 0 | 5 | 9.4.2.142.8 | 133 | 4 | T | No | 133 | 4 | 9.4.2.142.8 |  | V | Alecs |  | 661 | The text in lines 4-12 is not clear (there is too much freedom) and no Activity codes are reserved for other purpouses (and no real reson for it). It should be noted that there is an Activity field in REVmd Table 9-266 | Suggest to remove options and specify only what is currently defined. All other values to be reserved: Change to: If the Activityi subfield is 1, ...., where NSTS is the value of the Number of Space-Time Streams Reported subfield within the Rate Adaptation Control/Extended TPC field, the Link Margini subfield contains the new requested MCS for space-time stream i. If the Activityi subfield is 2 (delete: or 3), the Link Margini subfield contains the amount of transmit power change, in units of dB, for space-time stream i in 2s complement format and in steps of 0.25 dB. If the Activityi subfield is 3, the Link Margini field contains the measured link margin of the space-time stream i received from the peer STA indicated in the RA field of the Link Measurement Report frame and is coded as a 2s complement signed integer in units of decibels. A value of -128 indicates that no link margin is provided. All other values are reserved. The method used to measure the link margin is beyond the scope of this standard. l also suggest to add that if field is zero do nothing. I suggest to rewrite this paragraph as a table. | REVISED (SB000: 2020-07-22 23:52:43Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0343-01-00ay-resolution-to-cid-6184-9.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6188 | Eitan, Alecsander | 0 | 5 | 9.4.2.142.8 | 133 | 2 | T | No | 133 | 2 | 9.4.2.142.8 |  | V | Alecs |  | 661 | The text says: "The Activity field is defined in 9.4.2.142.2." This is not so good. First the Activity field values in 9.4.2.142.2 are very basic and not efficient (e.g. Increase power is just a bit, but without any value associated). Second we have a better definition in the next paragraph (page 133 lines 4-12). Better to use this one. | Suggested to remove the sentence "The Activity field is defined in 9.4.2.142.2.". There is no need for it and causes confusion with next paragraph. | REVISED (SB000: 2020-07-22 23:52:46Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0343-01-00ay-resolution-to-cid-6184-9.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6189 | Eitan, Alecsander | 0 | 5 | 9.4.2.143 | 133 | 30 | T | No | 133 | 30 | 9.4.2.143 |  | V | Alecs |  | 661 | Better to use the text in 9.4.2.142.8. Better options, more coherent and in sync with 9.4.2.142 | Replace "Activity field is defined in 9.4.2.142.2." with "Activity field is defined in 9.4.2.142.8." | REVISED (SB000: 2020-07-22 23:52:49Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0343-01-00ay-resolution-to-cid-6184-9.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6190 | Eitan, Alecsander | 0 | 5 | 9.4.2.265 | 147 | 29 | E | No | 147 | 29 | 9.4.2.265 |  | V | Solomon |  | 666 | Text points: "The Allocation subfield is defined in Figure 9-517". There is no such figure in this doc and the one in REVmd is "Figure 9-517--MCCAOP Teardown element format", with a different number of bits. | Need fix! | REVISED (SB000: 2020-07-22 23:53:46Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0916-02-00ay-resolution-to-sa-ballot-cids-6146-6117-6190-and-6205.docx | SB000 | [6 empty] | 2020-07-22 23:54 | SB000
6191 | Kasher, Assaf | 0 | 5 | 10.42.2.3.1 | 273 | 7 | T | No | 273 | 7 | 10.42.2.3.1 |  | V | Assaf |  | 648 | The discussion of which frame/packet to use for RSS ignores the case of RSS after BT (in the A-BFT) | Add a reference to 10.42.5.2 for the case the ISS was performed in the BTI. Add | REVISED (SB000: 2020-05-09 21:03:54Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0353-01-00ay-resolution-to-some-tgay-sb000-cids-v1.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6192 | Kasher, Assaf | 0 | 5 | 10.42.2.2.2 | 272 | 23 | T | No | 272 | 23 | 10.42.2.2.2 |  | V | Assaf |  | 648 | If it is an RSS, why is this discussed in the Initiator TXSS subclause? | Move the text the 10.42.2.3 | REVISED (SB000: 2020-05-09 21:03:50Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0353-01-00ay-resolution-to-some-tgay-sb000-cids-v1.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6193 | Wang, Xiaofei | 0 | 5 | 3.2 | 23 | 26 | T | Yes | 23 | 26 | 3.2 |  | V | Cheng |  | 655 | the definition for secondary1 channel is not clear. The phrase "associated with a primary and second channel" is at least missing an "a' in front of "secondary channel". In addition, the term secondary1 may imply that it is a part of secondar channel. In addition, when a 2.16+2.16GHz channel is formed by primary and secondary1 channel, the secondary channel is not involved and the definition of the secondary1 channel should be revised to reflect that.; Suggest to clearly define secondary1 channel. It may also be beneficial to add the reference to figure 8-6. | as in comment | REVISED (SB000: 2020-05-09 21:01:16Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0544-02-00ay-resolutions-to-sa-ballot-cids.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6194 | Wang, Xiaofei | 0 | 5 | 3.2 | 23 | 29 | T | Yes | 23 | 29 | 3.2 |  | V | Cheng |  | 655 | the definition for secondary2 channel is not clear. The phrase "associated with a primary, second channel and secondary1 channel" is at least missing an "a' in front of "secondary channel" and "secondary1 channel". In addition, the term secondary2 may imply that it is a part of secondary channel. In addition, when a 2.16+2.16GHz channel is formed by primary and secondary2 channel, the secondary and secondary1 channel is not involved and the definition of the secondary1 channel should be revised to be more precise to reflect that.; Suggest to clearly define secondary2 channel. It may also be beneficial to add the reference to figure 8-6. | as in comment | REVISED (SB000: 2020-05-09 21:01:12Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0544-02-00ay-resolutions-to-sa-ballot-cids.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6195 | Wang, Xiaofei | 0 | 5 | 10.42.5.1 | 321 | 33 | T | Yes | 321 | 33 | 10.42.5.1 |  | V | Claudio |  | 649 | The sentence is garbled and has grammer errors. "Beam refinement protocol transmit sector sweep (BRP TXSS) is a procedure that makes use of BRP frames 33 to perform transmit sector sweep and receive training and determine improved antenna configuration(s) for 34 transmission and reception." | suggest to change the sentence to "Beam refinement protocol transmit sector sweep (BRP TXSS) is a procedure using BRP frames to perform transmit sector sweep and to determine improved antenna configuration(s) for transmission and reception." | REVISED (SB000: 2020-05-09 21:04:10Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0327-01-00ay-initial-sa-ballot-comment-resolution.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6196 | Hamilton, Mark | 0 | 5 | 3.2 | 23 | 32 | E | Yes | 23 | 32 | 3.2 |  | V | Solomon |  | 665 | The word "packet" is agreed to only be used when dictated by external specifications, by convention. IEEE Std 802.11 uses "frame", for both MAC and PHY structures. | Change all uses of "SSW packet" to "SSW frame" throughout. Change the field name "Packet Type" to "PPDU Type", throughout. Change "TXSS-PACKETS" to "TXSS-PPDUS" throughout. Change "EDMG_PACKET_TYPE" to "EDMG_PPDU_TYPE" and similarly modify its enumerated values, throughout. Change "L_PACKET_TYPE" to "L_PPDU_TYPE" in Table 28-1 and throughout. In text (such as P151.28) and figures (such as Figuer 10-94k) change "packet" to "PPDU" or "frame". | REVISED (SB000: 2020-07-22 23:53:16Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6197 | Hamilton, Mark | 0 | 5 | 10.42.4 | 277 | 26 | T | Yes | 277 | 26 | 10.42.4 |  | V | Solomon |  | 665 | Since the word "packet" has restricted use, the terms "PACKET-TYPE", "TRN-R-PACKET" and "TRN-T-PACKET" have been changed in REVmd. | Update draft to match REVmd's terminology. | REVISED (SB000: 2020-07-22 23:53:19Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6198 | Hamilton, Mark | 0 | 5 | 10.42.7 | 288 | 12 | T | Yes | 288 | 12 | 10.42.7 |  | V | Solomon |  | 665 | There are numerous inconsistencies with the baseline in this paragraph (assuming REVmd D3.0 is the baseline, as stated at the top of the draft). This has significant impact on the wording of the new/modified text, to match the baseline style. This appears to continue in subsequent paragraphs. I didn't check other places in the Draft. | Check that the draft has correct baseline (unchanged) text, and adjust modified text to match the correct baseline. | REVISED (SB000: 2020-07-22 23:53:21Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0811-01-00ay-resolution-to-some-tgay-sb000-editorial-cids-v1.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6199 | Motozuka, Hiroyuki | 0 | 5 | 28.2.2 | 401 | 1 | E | No | 401 | 1 | 28.2.2 |  | A | Carlos |  | 663 | There is unnecessary white space between the table and the title. In P401(Table 28-1), P427(Table 28-2), P441(Table 28-12) | Remove unnecessary white spaces between the table and the title. | ACCEPTED (SB000: 2020-05-09 18:36:49Z) | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6200 | Motozuka, Hiroyuki | 0 | 5 | 28.2.2 | 404 |  | E | No | 404 |  | 28.2.2 |  | A | Carlos |  | 652 | "See Turnaround entry in Table 20-1." | Replace "Turnaround" with "TURNAROUND" | ACCEPTED (SB000: 2020-03-18 02:04:16Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6201 | Motozuka, Hiroyuki | 0 | 5 | 28.3.3.2.4.1 | 432 | 28 | E | No | 432 | 28 | 28.3.3.2.4.1 |  | A | Carlos |  | 663 | Reference inconsisnent to REVmd | Replace "(see Table 20-17)" with "(see Table 20-13)" at P432L28 and P433L10. | ACCEPTED (SB000: 2020-05-09 18:24:05Z) | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6202 | Motozuka, Hiroyuki | 0 | 5 | 10.25.2 | 229 | 8 | E | No | 229 | 8 | 10.25.2 |  | V | Solomon |  | 645 | On the instruction to the editor: "Change the sixth paragraph and insert a new one as follows" Now it's 11th paragraph in REVmd D3.0. | Replace "sixth paragraph" with "eleventh paragraph" | REVISED (SB000: 2020-05-09 21:02:25Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0267-01-00ay-resolution-of-sb000-cids-6118-6119-6202-6210-6221-6224.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6203 | Motozuka, Hiroyuki | 0 | 5 | 28.2.4 | 422 |  | E | No | 422 |  | 28.2.4 |  | A | Carlos |  | 652 | Clause numbers haven't updated in the figures and are inconsistent with REVmd. | Replace "Clause 29(.*)" with "Clause 28(.*)" in Figure 28-1, 28-2, 28-3. Replace Clause 29.4.6.2 with Clause 28.4.7.2 in NON_EDMG_DUP_C_MODE box. | ACCEPTED (SB000: 2020-03-18 02:04:31Z) | SB000 | [6 empty] | 2020-05-09 18:01 | SB000
6204 | Motozuka, Hiroyuki | 0 | 5 | 28.3.3.2.4.1 | 434 | 2 | E | Yes | 434 | 2 | 28.3.3.2.4.1 |  | A | Carlos |  | 663 | There is a broken text or editorial error in the last row on Table 28-6. | Replace "28 - 2 and 4 - 6" with "3 - 4 and 6 - 7" | ACCEPTED (SB000: 2020-05-09 18:44:22Z) | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6205 | Sun, Li-Hsiang | 0 | 5 | 9.4.2.273 | 162 | 1 | E | Yes | 162 | 1 | 9.4.2.273 |  | V | Solomon |  | 666 | In the last row column "meaning" If the Feedback Type subfield is 1 and the Grouping subfield is less than 3, Nsc is determined by 0. What does it mean by "determined by 0"? | Nsc is determined by Table9-321ac | REVISED (SB000: 2020-07-22 23:53:48Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0916-02-00ay-resolution-to-sa-ballot-cids-6146-6117-6190-and-6205.docx | SB000 | [6 empty] | 2020-07-22 23:54 | SB000
6206 | Sun, Li-Hsiang | 0 | 5 | 9.4.2.273 | 162 | 1 | T | Yes | 162 | 1 | 9.4.2.273 |  | V | Li-Hsiang |  | 656 | In the last row column "meaning" If the Feedback Type subfield is 1 and the Grouping subfield is 3, Nsc specifies the number of subcarriers present in the Digital Beamforming Feedback Information field of the Digital BF Feedback element minus one. | Nsc is later used in Table9-321z as the actaul number of subcarriers present in the Digital Beamforming Feedback Information field. It should say "Nsc specifies the number of subcarriers present in the Digital Beamforming Feedback Information field of the Digital BF Feedback element. This field is set to Nsc-1". | REVISED (SB000: 2020-05-09 21:02:02Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0554-02-00ay-proposed-comment-resolutions-for-cid-6206-6207.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6207 | Sun, Li-Hsiang | 0 | 5 | 9.4.2.282 | 180 | 1 | T | Yes | 180 | 1 | 9.4.2.282 |  | V | Li-Hsiang |  | 656 | The Differential Subcarrier Index Field should have Nsc-1 rows, not Nsc rows | In the last row of Differential Subcarrier Index Field "Size" and "Meaning" columns, replace "Nsc-1" with "Nsc-2", replace "Nsc" with "Nsc-1" | REVISED (SB000: 2020-05-09 21:02:14Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0554-02-00ay-proposed-comment-resolutions-for-cid-6206-6207.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6208 | Sun, Li-Hsiang | 0 | 5 | 9.4.2.142.6 | 131 | 16 | T | No | 131 | 16 | 9.4.2.142.6 |  | V | Alecs |  | 661 | In cluase 28, a LDPC CW is stream parsed to multiple sptial streams, It is not clear LDPC Statistics could have different values for different spatial streams. | Revise the field definition | REVISED (SB000: 2020-07-22 23:52:40Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0344-00-00ay-resolution-to-cid-6183-and-6208.docx | SB000 | [6 empty] | 2020-07-22 23:53 | SB000
6209 | Sun, Li-Hsiang | 0 | 5 | 9.4.2.274 | 164 | 1 | T | No | 164 | 1 | 9.4.2.274 |  | V | Lei Huang |  | 644 | For MU-MIMO BF traning, it is not clear the NTX in this table is referring to the 'Number of TX Antennas' each STA specified in the MIMO BF feedback, which could be different for different STAs, or the 'Number of concurrent RF chains' in the AP's PHY Capabilities. Furthermore, for MU MIMO BF training there is no MIMO BF feedback indicating number of TX antennas | Specify NTX corresponds to the 'Number of concurrent RF chains' in the AP's PHY Capabilities | REVISED (SB000: 2020-05-09 21:02:06Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0271-01-00ay-sa-ballot-cr-on-cid-6160-6209-6212.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6210 | Sun, Li-Hsiang | 0 | 5 | 9.3.1.8.9 | 97 | 11 | T | No | 97 | 11 | 9.3.1.8.9 |  | V | Solomon |  | 645 | It is not clear in all ack context, which TID/TID group is asscoaited with the BUFCAP in a multi-TID BA with ack Type 2. | Clarify the setting or the presence of RBUFCAP for ack Type 2 | REVISED (SB000: 2020-05-09 21:01:49Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0267-01-00ay-resolution-of-sb000-cids-6118-6119-6202-6210-6221-6224.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6211 | Sun, Li-Hsiang | 0 | 5 | 10.39.12.4.4 | 267 | 15 | T | No | 267 | 15 | 10.39.12.4.4 |  | V | Cheng |  | 655 | What is the group address used in TA for the CTS-to-self? According to rev.md, "For DMG CTS-to-self frames, the TA field is set to the individual address of the recipient or the group address of the recipients of the frame that the DMG STA intends to transmit after the DMG CTS-to-self frame." | Specify TA for the CTS-to-self the broadcast MAC address | REVISED (SB000: 2020-05-09 21:03:46Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0544-02-00ay-resolutions-to-sa-ballot-cids.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6212 | Sun, Li-Hsiang | 0 | 5 | 10.42.10.2.3.3.2 | 307 | 11 | T | No | 307 | 11 | 10.42.10.2.3.3.2 |  | V | Lei Huang |  | 644 | "The EDMG group ID corresponding to the MU group shall be indicated in the EDMG Group ID field" Is the EDMG group ID in the MIMO Selection Control element the one newly assigned in the EDMG group ID set element, or the group ID used in setup? If it is the newly assigned one, then there could be potentially multiple MIMO selection Control elements in one MIMO BF selection frame. If a STA is assigned a new group ID in MIMO BF selection frame, does it mean the STA no longer has the membership of an old group ID? | Clarifiy the EDMG Group ID and Group User mask in the MIMO selection control element corresponds to to the newly assigned group ID in the EDMG Group ID Set element later in the frame. In Table 9-487e, specify one or more MIMO Selection Control element | REVISED (SB000: 2020-05-09 21:04:07Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0271-01-00ay-sa-ballot-cr-on-cid-6160-6209-6212.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6213 | Levy, Joseph | 0 | 5 | 11.2.6 | 364 | 33 | T | Yes | 364 | 33 | 11.2.6 |  | V | Cheng |  | 655 | The seems to be a missing word in the sentence which obscures its meeting. | Change: ".... while the EDMG STA enables its multiple receive chains only when the frame it receives indicates the following transmission requires the activation of multiple receive chains." To be: ".... while the EDMG STA enables its multiple receive chains only when the frame it receives indicates that the following transmission requires the activation of multiple receive chains." | REVISED (SB000: 2020-05-09 21:04:14Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0544-02-00ay-resolutions-to-sa-ballot-cids.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6214 | Levy, Joseph | 0 | 5 | 11.2.6 | 365 | 3 | T | Yes | 365 | 3 | 11.2.6 |  | V | Cheng |  | 655 | This sentence is awarkard and not very clear. As "switches back" is not presice language. | Change: "... the EDMG STA switches back immediately when the frame exchange sequence ends." To be: "... when the frame exchange sequence ends the EDMG STA immediately disables the multiple recieve chains, enabled durring the frame exchange, returning to single receive chain operation." | REVISED (SB000: 2020-05-09 21:04:18Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0544-02-00ay-resolutions-to-sa-ballot-cids.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6215 | Levy, Joseph | 0 | 5 | 11.2.7.4 | 38 | 38 | T | Yes | 38 | 38 | 11.2.7.4 |  | V | Cheng |  | 655 | Stating that the STA may enter the doze state, is not the best way to specify that once the ATIM frame exchange has commpleted that there will be no additional transmissions to the STA, and hence the STA may go into doze state. It is critical that all the involved STAs are aware that no additional transmissions are allowed durring the awake window. | Change: "An EDMG STA that receives from, or transmits to, a peer EDMG STA an ATIM frame during an awake window may enter the doze state when it has successfully transmitted to and received from all corresponding peer STAs for this allocation a QoS Data frame with the EOSP subfield set to 1; otherwise it shall remain active until the end of the allocation." To; ""Durring an awake window an EDMG STA that receives from, or transmits to, a peer EDMG STA an ATIM frame will transmit and receive until it has received from all corresponding peer STAs for this allocation a QoS Data frame with the EOSP subfield set to 1 or until the end of the allocation." | REVISED (SB000: 2020-05-09 21:01:42Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0544-02-00ay-resolutions-to-sa-ballot-cids.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6216 | Levy, Joseph | 0 | 5 | 3.2 | 22 | 36 | T | Yes | 22 | 36 | 3.2 |  | V | Motozuka-san |  | 657 | The definition of DMG A-PPDU and EDMG A-PPDU are very confusing. A DMG PPDU is defined as a clause 20 PPDU. Hence, a DMG A-PPDU is defined to cognatian only DMG PPDUs (which are non-EDMG PPDUs) and an EDMG A-PPDU to contain only EDMG PPDUs. But DMG is defined to include all operation in a frequency band with a channel greater than 45 GHz, hence both non-EDMG (clause 20) and EDMG (clause 28). To me this is inconsistant. | Fix the definitions to remove the inconsistancy and confusion. | REVISED (SB000: 2020-05-09 21:01:04Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0542-00-00ay-sb000-comment-resolution-cid-6216.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6217 | Levy, Joseph | 0 | 5 | AA | 786 | 27 | T | Yes | 786 | 27 | AA |  | V | Assaf |  | 648 | If the intent is to say that a STA may transmit an SSW frame with both the RA and TA set to its own MAC address it should be clearly that the STA MAC address is that of the transmitting STA. | Change: "A STA may transmit an SSW frame with both the RA field and the TA field set to the MAC address of the STA may to implement radar functionality." To: "A STA may transmit an SSW frame with both the RA field and the TA field set to the MAC address of the transmitting STA, to indicate radar functionality." | REVISED (SB000: 2020-05-09 20:59:26Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0353-01-00ay-resolution-to-some-tgay-sb000-cids-v1.docx | SB000 | [6 empty] | 2020-05-09 20:59 | SB000
6218 | Levy, Joseph | 0 | 5 | AA | 786 | 31 | T | Yes | 786 | 31 | AA |  | V | Assaf |  | 648 | If the intent is to say that a STA may transmit a short SSW packet with both the TXVECTOR parameter SSW_SOURCE_AID and SSW_DESTINATION_AID set to the AID of the transmitting SAT it should clearly say so. | Change: "A non-PCP and non-AP EDMG STA may transmit a Short SSW packet with both the TXVECTOR parameter SSW_SOURCE_AID and SSW_DESTINATION_AID set to the AID of the STA to implement radar functionality" To: "A non-PCP and non-AP EDMG STA may transmit a Short SSW packet with both the TXVECTOR parameter SSW_SOURCE_AID and SSW_DESTINATION_AID set to the AID of the transmitting STA, to indicate radar functionality" | REVISED (SB000: 2020-05-09 20:59:30Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0353-01-00ay-resolution-to-some-tgay-sb000-cids-v1.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6219 | Levy, Joseph | 0 | 5 | AA | 787 | 32 | T | Yes | 787 | 32 | AA |  | V | Assaf |  | 648 | If the intent is to say that a EDMG PCP STA or EDMG AP STA may transmit a short SSW packet with both the TXVECTOR parameter SSW_SOURCE_AID and SSW_DESTINATION_AID set to the BSS AID of the transmitting SAT it should clearly say so. | Change: "An EDMG PCP STA or an EDMG AP STA may transmit a Short SSW packet with both the TXVECTOR parameter SSW_SOURCE_AID and SSW_DESTINATION_AID set to BSS AID of the STA to implement radar functionality." To: "An EDMG PCP STA or an EDMG AP STA may transmit a Short SSW packet with both the TXVECTOR parameter SSW_SOURCE_AID and SSW_DESTINATION_AID set to BSS AID of the transmitting STA, to indicate radar functionality" | REVISED (SB000: 2020-05-09 20:59:36Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0353-01-00ay-resolution-to-some-tgay-sb000-cids-v1.docx | SB000 | [6 empty] | 2020-05-09 21:00 | SB000
6220 | Levy, Joseph | 0 | 5 | 10.39.6.2 | 253 | 5 | E | No | 253 | 5 | 10.39.6.2 |  | J | Carlos |  | 663 | There is no following subclause provided. Either delete 10.39.6.2 and the editoral instructions or provide the subcaluse to be inserted. | Delete lines 4 an 5: "10.39.6.2 Service Period (SP) allocation 'Insert the following subclause heading before the first paragraph" | REJECTED (SB000: 2020-05-09 18:41:28Z) The instruction is to insert the **heading**: "Insert the following subclause heading before the first paragraph" Basically, this instruction is creating a subclause in the existing text, and then inserting a new subclause below it. | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6221 | Yee, James | 0 | 5 | 10.25.2 | 229 | 21 | T | Yes | 229 | 21 | 10.25.2 |  | V | Solomon |  | 645 | The EDMG PHY supports peak rate of 37,917.00 Mbps. This is a significant improvement but we think the MAC efficiency still has a problem. It is not very clear if the current TGay draft meets the PAR throughput requirement (i.e., supporting a maximum throughput of at least 20 gigabits per second (measured at the MAC data service access point)). Although the EDMG STA can use 1024 bits BlockAck Bitmap, for fully utilizing the PHY improvements, the BlockAck Bitmap should be extended to a larger size. Also, the Sequence Number space should be extended to more than 12 bits. | Increase the BlockAck Bitmap size and the Sequence Number space. If the CRC thinks that 1024 bits BlockAck Bitmap and 12 bit Sequence Number space are already sufficient for meeting the PAR throughput requirement at the maximum PHY rate, please provide how the MAC SAP throughput can be achieved. | REVISED (SB000: 2020-05-09 21:02:28Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0267-01-00ay-resolution-of-sb000-cids-6118-6119-6202-6210-6221-6224.docx | SB000 | [6 empty] | 2020-05-09 21:02 | SB000
6222 | Torab, Payam | 0 | 5 | 3.1 | 21 | 4 | E | Yes | 21 | 4 | 3.1 |  | A | Carlos |  | 642 | MPDUs mentioned in the pragraph were never combined before reassembly. | Change "recombining" to "combining". | ACCEPTED (SB000: 2020-01-14 16:18:22Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:56:03Z |  | 2020-01-30 02:56 | SB000
6223 | Torab, Payam | 0 | 5 | 3.1 | 21 | 8 | E | Yes | 21 | 8 | 3.1 |  | A | Carlos |  | 642 | MPDUs mentioned in the pragraph were never combined before reassembly. | Change "recombining" to "combining". | ACCEPTED (SB000: 2020-01-14 16:18:03Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:56:13Z |  | 2020-01-30 02:56 | SB000
6224 | Torab, Payam | 0 | 5 | 3.1 | 21 | 7 | T | Yes | 21 | 7 | 3.1 |  | V | Solomon |  | 645 | MPDU sizes should not be restricted to maximum size; MPDU size may be selected based on link adaptation, also last segment can be smaller | Remove "maximum size". | REVISED (SB000: 2020-05-09 21:01:00Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0267-01-00ay-resolution-of-sb000-cids-6118-6119-6202-6210-6221-6224.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6225 | Torab, Payam | 0 | 5 | 3.1 | 21 | 26 | E | Yes | 21 | 26 | 3.1 |  | A | Carlos |  | 642 | Capitalize the beginning of the sentence. | As described. | ACCEPTED (SB000: 2020-01-14 16:18:11Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:59:39Z |  | 2020-01-30 03:00 | SB000
6226 | Torab, Payam | 0 | 5 | 3.1 | 21 | 29 | E | Yes | 21 | 29 | 3.1 |  | A | Carlos |  | 642 | Capitalize the beginning of the sentence. | As described. | ACCEPTED (SB000: 2020-01-14 16:18:16Z) | SB000 |  |  |  | I | SB000: 2020-01-30 02:59:46Z |  | 2020-01-30 03:00 | SB000
6227 | Torab, Payam | 0 | 5 | 3.1 | 21 | 35 | E | Yes | 21 | 35 | 3.1 |  | A | Carlos |  | 663 | Follow the style of other definitions in this section (not using a full sentence) | Change "A SISO ID subset is a tuple comprising ..." to "A tuple comprising ..." | ACCEPTED (SB000: 2020-05-09 18:33:06Z) Note that this is in P23, not P21 | SB000 | [6 empty] | 2020-07-22 17:14 | SB000
6228 | Torab, Payam | 0 | 5 | 3.1 | 23 | 37 | T | Yes | 23 | 37 | 3.1 |  | V | Cheng |  | 660 | TDD SP should be defined independenty of its channe access. Once a TDD SP is defined, its channel access scheme can be specified. Test has a better definition of TDD SP, use that one. | Remove the NOTE on line 38, and change the definition to "An SP that has the TDD Applicable SP subfield in an Allocation field within an Extended Schedule element equal to 1." There is another comment that proposes to use the Allocation Type field in DMG Extended Schedule Element to designate a TDD SP. If the proposed resolution for that comment is accepted, the definition here should be "A DMG allocation with Allocation Type subfield set to 4." | REVISED (SB000: 2020-05-09 21:01:08Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0620-02-00ay-resolutions-to-cid-6228-6229-6230.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6229 | Torab, Payam | 0 | 5 | 3.1 | 24 | 2 | T | Yes | 24 | 2 | 3.1 |  | V | Cheng |  | 660 | Desination DMG STA is a STA that is expected to receive during (not at the start of) a TDD slot (not TDD SP). Language can be improved too. | Change the definition to "A DMG STA that is expected to receive during a time division duplex (TDD) slot, or a DMG STA identified by the destination association identifier (AID) field in a Grant frame or in an Extended Schedule element that defines a service period (SP) or a contention based access period (CBAP). | REVISED (SB000: 2020-05-09 21:01:22Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0620-02-00ay-resolutions-to-cid-6228-6229-6230.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6230 | Torab, Payam | 0 | 5 | 3.1 | 24 | 16 | T | Yes | 24 | 16 | 3.1 |  | V | Cheng |  | 660 | Source DMG STA is a STA that is expected to transmit during (not at the start of) a TDD slot (not TDD SP). Language can be improved too. | Change the definition to "A DMG STA that is expected to transmit during a time division duplex (TDD) slot, or a DMG STA identified by the source association identifier (AID) field in a Grant frame or in an Extended Schedule element that defines a service period (SP) or a contention based access period (CBAP). | REVISED (SB000: 2020-05-09 21:01:19Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0620-02-00ay-resolutions-to-cid-6228-6229-6230.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6231 | Torab, Payam | 0 | 5 | 10.39.6.2 | 253 | 8 | T | No | 253 | 8 | 10.39.6.2 |  | V | Cheng |  | 655 | An SP with TDD channel access (TDD SP) is a DMG allocation type of its own, not a variation of DMG SP. | Consider adding | REVISED (SB000: 2020-05-09 21:03:39Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0544-02-00ay-resolutions-to-sa-ballot-cids.docx | SB000 | [6 empty] | 2020-05-09 21:04 | SB000
6232 | Torab, Payam | 0 | 5 |  |  |  | T | Yes |  |  |  |  | V | Payam |  | 668 | DMG devices with mostly fixed directions of transmission, regardless of channel access they use, should send a DMG frame to help other DMG STAs (those not in BSS, although usage is not limited to this case) identify the possible inerference and perform inference mitigation. This is a different flow from discovery (beacons), which can use different MCS and different beams. | Define a public frame to describe the transmit power and channel usage information in the direction of transmit activity. Refer to https://mentor.ieee.org/802.11/dcn/19/11-19-1514-00-00ay-dmg-sta-directional-transmit-activity-report-frame.pptx for details. | REVISED (SB000: 2020-08-05 17:13:58Z) Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0859-04-00ay-dmg-sta-directional-transmit-activity-report-frame.docx | SB000 | [6 empty] | 2020-08-05 17:15 | SB000
6233 | Torab, Payam | 0 | 5 | 9.4.2.281 | 177 | 14 | T | Yes | 177 | 14 | 9.4.2.281 |  | J | Payam |  | 669 | Details of beamforming operation for CNs (non-AP STAs) that do not havee access to management lane (network controller) is undefined. It is unclear how these devices can be instructed by DN/AP to select certain beams for transmit or receive training. | Define the details of using TDD Sector Config, as described in https://mentor.ieee.org/802.11/dcn/19/11-19-1517-00-00ay-tdd-beamforming-configuration.pptx | REJECTED (SB000: 2020-08-12 14:36:43Z) - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | SB000 | [6 empty] | 2020-08-12 14:37 | SB000
6234 | Torab, Payam | 0 | 5 |  |  |  | T | Yes |  |  |  |  | V | Solomon |  | 653 | 11ay MSDU size is small for jumbo frame support I mmWave distribution (fixed wireless) use case. | Extend the relevant fields to accomadate ~16KB MSDUs. | REVISED (SB000: 2020-05-09 21:00:49Z) - Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-0242-03-00ay-msdu-size-extension-cid-6115-6234.docx | SB000 | [6 empty] | 2020-05-09 21:01 | SB000
6235 | Torab, Payam | 0 | 5 |  |  |  | T | Yes |  |  |  |  | V | Payam |  | 671 | Network entry (including association and initial TDD slot structure/schedue establishment) following initial beamforming is not clear, in particulr, (1) there is a need for periodic transmit oppportunity to retru transmission, and (2) initial frame from the DN/iitiator should be Probe Response (avoiding Class 0 Announce for mmWave use case) | Define the operation and applicable frames. | REVISED (SB000: 2020-08-12 14:28:17Z) Resolve as in https://mentor.ieee.org/802.11/dcn/20/11-20-1113-03-00ay-tdd-network-entry.docx | SB000 | [6 empty] | 2020-08-12 14:30 | SB000
6236 | Torab, Payam | 0 | 5 |  |  |  | T | Yes |  |  |  |  | J | Payam |  | 669 | 11ad unprotected Announce frame as a Class 1 frame is a threat to Millimeter wave distribution (fixed wireless) networks, as devices need to be open to these frames before and after association/ authentication. | Define a robust version of Annouce frame as a regular (Class 2) frame that can be protected if needed. Exchenge the initial configuration information after initial beamforming trough Probe Response, which is the correct architectural choice (Class 1), and also has many relevant IEs (ccountry, time zone, power, and other operation information). | REJECTED (SB000: 2020-08-12 14:36:33Z) - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | SB000 | [6 empty] | 2020-08-12 14:37 | SB000
6237 | Torab, Payam | 0 | 5 |  |  |  | T | Yes |  |  |  |  | J | Payam |  | 669 | Rename Unscheduled beamforming to Initial beamforming, as it is only exercised once at the beginning. |  | REJECTED (SB000: 2020-08-12 14:36:39Z) - The comment fails to identify changes in sufficient detail so that the specific wording of the changes that will satisfy the commenter can be determined. | SB000 | [6 empty] | 2020-08-12 14:37 | SB000