## Slide 1: Status of the comments-on-fcc19-138-nprm-revisiting-use-of-the-5-850-5-925-ghz-band
Date: 2020-03-17
Authors:

## Slide 2: Abstract
This document provides are review of the status of the development of the 802 comments on the fcc19-138 NPRM revisiting the use of the 5.850-5.925 GHz band
r1: updated as of close of 802 EC Ballot (02 Mar 2020) for TGbd Teleconference 03 Mar 2020.
r2: updated for the TGbd Teleconference 17 Mar 2020.

## Slide 3: Background
21 November 2019 – the FCC announces the intent to propose a NPRM for the 5.9 GHz band at the December 2019 Open Commission Meeting (12 Dec 2019) [1]
5 December 2019 – A discussion thread was started on the 802.11 TGbd reflector [2]
12 December 2019 – at the Open Commission Meeting, the FCC commissioners unanimously approve the proposed NPRM. [3]
06 February 2020 - Publication of the NPRM in the Federal Register [4]
09 March 2020 - Comments on the NPRM are due on or before [4]
06 April 2020 – Reply comments are due on or before [4]

## Slide 4: 802.11 TGbd Activity
During the January 802.11 TGbd session:
Discussed on the pending publication of the NPRM
Initial draft of comments on the NPRM [5]
Additional proposed text was contributed and editorial changes [6 (r0)-(r7)]
TGbd agreed the following motion:
Approve TGbd to develop comment document responding to FCC NPRM on 5.9 GHz band
  - Joseph Levy leads the developing of comments with 11-20/0104 as the comment document.
and run a WG ballot to approve the completed comment document and for the WG Chair to decide to send to FCC after EC review or forward to 802.18 for LMSC process
Note this motion was not agreed at the closing plenary of the 802.11 January meeting, the WG decided that working with 802.18 to generate comments from 802 was the preferred way to proceed.
Additional contribution and editing continued until the NPRM was published (6 Feb) at which time the draft [7,8] and the work transferred to 802.18 (10 Feb)

## Slide 5: 802.18 Comment Activity/Status
Prior to the NPRM being published (6 Feb) 802.18 was monitoring and commenting on the 802.11 TGbd draft contribution 11-20/0104
After the NPRM was published (6 Feb) 802.18 transferred 11-20/0104 [7,8] to become 18-20/0020 [9,10] respectively (10 Feb).
802.18 has set up a very aggressive teleconference plan to complete the comments document and allow for 802 EC review/approval prior to the 9 March 2020 submission due date. Meeting dates (past and planned)
  Ad Hoc meetings 11, 14, 18, 19 Feb (2 hours, 15:00-17:00 EST)
  Regular 802.18 weekly meeting 23, 30 Mar; 06, 13, 20 Feb (1 hour, 15:00-16:00 EST)
The draft 18-20/0020r14 [11] was approved during the 802.18 20 Feb teleconference
The approved document was submitted to the 802 EC (10 day e-mail ballot)
  The ballot closed 02 Mar 2020 at Midnight EST.
  Discussions/proposals by 802 EC and .18 members on the EC reflector and at the 802.18 27 Feb teleconference were considered and the draft was updated several times r15, 16 and 17.
18-20/0020r19 [12] was approved and forwarded to the FCC IEEE 802 LAN/MAN Standards Committee [13]
  8/2/3 Y/N/DNV, 77% response (50% req), 80% approval (67% req)

## Slide 6: 802.18 Reply Comment Activity/Status
The “Comment” period for the FCC 19-38 NPRM has ended
The “Reply Comments” period is on going until 6 April 2020
802.18 has started a “Reply Comments” document
  The scope of the reply comments have been proposed to be limited to the following:
  Correction or support of comments made about DSRC
  Correction or support of comments made about C-V2X
Comment summary review: 18-20/0038r2
Reply Comments time line:
  802.18 Ad Hoc Meetings: 13, 16, 17, and 18 March @ 3:00 PM EDT
  802.18 approval of Reply Comments document: Thursday 19 March @ 3:00 PM EDT
  802 EC approval by: 802 EC teleconference Friday 20 March or by 10 day 802 EC e-ballot.
  Current working draft document: 18-20/0045r0 [14]
  Note: the 19 March approval date was chosen as a 26 March 802.18 approval date was too risky, given the required EC 10 day ballot followed by document submission and the 6 April deadline.

## Slide 7: References
[1] – Office of Engineering and Technology Opens ET Docket No. 19-138, and associated FCC “FACT SHEET”, 21 Nov 2019.
[2] – [STDS-802-11-TGBD] Discussion on: FCC NPRM impacting the 5.9 GHz Band, Joseph Levy, 5 Dec 2019
[3] – FCC Seeks to Promote Innovation in the 5.9 GHz Band – News Release, 12 Dec 2019, Bureau of Engineering and Technology
[4] - “FEDERAL COMMUNICATIONS COMMISSION, 47 CFR Parts 2, 15, 90, and 95, [ET Docket No. 19–138; FCC 19–129; FRS 16447], Use of the 5.850–5.925 GHz Band” as published in the Federal Register/ Vol. 85, No. 25/ Thursday, February 6, 2020 / proposed Rules, starting on page 6841. https://www.govinfo.gov/content/pkg/FR-2020-02-06/pdf/2020-02086.pdf
[5] – “Draft TGbd Comments on FCC NPRM Docket 19-138”, 11-20/0104r1
[6] – “Draft TGbd Comments on FCC NPRM Docket 19-138”, 11-20/0104r13
[7] – “Draft TGbd Comments on FCC NPRM Docket 19-138”, 11-20/0104r14
[8] – “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r0
[9] – “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r1
[10] – “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r5
[11] - “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r14
[12] - “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0020r19
[13] - “Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, https://ecfsapi.fcc.gov/file/103050191209354/18-20-0020-19-0000-comments-on-fcc19-138-nprm-revisiting-use-of-the-5-850-5-925-ghz-band.pdf
[14] – “Reply Comments on FCC19-138 NPRM Revisiting Use of the 5.850-5.925 GHz Band”, 18-20/0045r0