## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-20/1198r5
Venue Date: | September 2020
First Author: | Stephen McCann
Subject: | Comments on P802.11bc/D0.1 - McCann
Full Date: | 2020-09-15
Author(s): | Stephen McCann
| Company: | Self
Address
Phone:
Fax:
email: stephen.mccann@ieee.org
Abstract:
Comments on P802.11bc/D0.1 - McCann

## Revision History
Revision | Date | Description
0 | 2020-08-11 | Initial version
1 | 2020-08-18 | update to CID 310. Addition of CIDs 3 and 316
2 | 2020-08-21 | Additional comments and tetx added following TGbc teleconference on August 18th 2020. Also added some additional CIDS 310, 343, 345, 349, 350 to consider
3 | 2020-09-11 | Additional CIDS 130, 314, 317, 344 and 348 to consider
4 | 2020-09-15 | Updates from the September 14th 2020 teleconference
5 | 2020-09-15 | Updates from the September 15th 2020 teleconference

## All Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
309 | Stephan Sand | 32 | 0.1 | 1.2 | 16 | 14 | E | N | 16.14 | 14 | 1.2 |  |  | Stephen McCann |  |  | the second "to enable" after IEEE 802.11 stations is redunant in line 14 | remove 2nd "to enable" after IEEE 802.11 stations | Accept | [7 empty] | 2020-08-03 13:19
323 | Xiaofei Wang | 32 | 0.1 | 1.2 | 16 | 15 | E | N | 16.15 | 15 | 1.2 | 309 |  |  |  |  | the word of "enable" is used in the same sentence | change the first part of the sentence into"Define a mechanism to enable IEEE 802.11 stations for enhanced transmission and reception of of broadcast data" | Accept | [7 empty] | 2020-08-03 13:19
324 | Xiaofei Wang | 32 | 0.1 | 1.2 | 16 | 15 | G | N | 16.15 | 15 | 1.2 |  |  | Stephen McCann |  |  | In revMD D3.3, Clause 1.3 is supplementary information on purpose, which I suspect is where the added sentence starting at P16L15 belongs. Please change the clause number to 1.3 accordingly. | Please change the clause number to 1.3 accordingly. | Accept | [7 empty] | 2020-08-03 13:19
310 | Stephan Sand | 32 | 0.1 | 1.2 | 16 | 16 | T | N | 16.16 | 16 | 1.2 | [5 empty] | "in cases where there is no association between transmitter(s) and receiver(s)" Does this include OCB? | add after "and receiver(s)" "including STAs operating OCB". | Reject: TGbc discussed the proposed change and decided that there are many modes of IEEE 802.11 STAs operating without an association. Therefore it is not appropriate to single out OCB within clause 1.2. |  |  |  | I think the answer is yes, it does include OCB. However, I'm not sure if OCB need to be specifically mentioned. There are other IEEE 802.11 "modes" of operation (in addition to OCB) between STAs that are un-associated and these are not specifically mentioned in clause 1.3. |  |  |  | 2020-08-03 13:19
322 | Xiaofei Wang | 32 | 0.1 | 1.2 | 16 | 16 | E | N | 16.16 | 16 | 1.2 | [5 empty] | a period is missing at the end of line 16 | add a period at the end | Accept | [7 empty] | 2020-08-03 13:19
325 | Xiaofei Wang | 32 | 0.1 | 1.3 | 16 | 17 | G | N | 16.17 | 17 | 1.3 |  |  | Stephen McCann |  |  | Did Clause 1.3 word usage change under 802.11bc? If not, suggest to remove this clause to avoid confusing readers of the this amendment | as in comment | Accept | [7 empty] | 2020-08-03 13:19
1 | Abhishek Patil | 32 | 0.1 | 3.2 | 17 | 12 | E | N | 17.12 | 12 | 3.2 |  |  | Stephen McCann |  |  | Fix typo "An STA" | "A STA". Same change on line 15 | Accept | [7 empty] | 2020-08-03 13:19
51 | Hitoshi Morioka | 32 | 0.1 | 3.2 | 17 | 12 | T | N | 17.12 | 12 | 3.2 |  |  | Stephen McCann | 11-20-1197 |  | Enhanced Broadcast Service frames should be defined. | Enhanced Broadcast Service (eBCS) frame: eBCS Info frame, eBCS UL frame and Data frame for eBCS. | Revised: Only enhanced broadcast services need to be defined, as IEEE 802.11 frames are not typically defined in clause 3.2. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
125 | Mark RISON | 32 | 0.1 | 3.2 | 17 |  | E | N | 17 |  | 3.2 |  |  | Stephen McCann |  |  | I think terms being defined should be lowercase | Change "Enhanced Broadcast Service (eBCS)" to "enhanced broadcast service (eBCS)" | Accept | [7 empty] | 2020-08-03 13:19
127 | Mark RISON | 32 | 0.1 | 3.4 | 17 |  | E | N | 17 |  | 3.4 |  |  | Stephen McCann |  |  | I think abbreviations being defined should be lowercase | Change "Enhanced Broadcast Service" to "enhanced broadcast service" | Accept | [7 empty] | 2020-08-03 13:19
39 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5 | 24 | 25 | T | N | 24.25 | 25 | 9.4.5 |  |  | Stephen McCann | 11-20-1197 |  | The subclause is not written as spec text, more of an outline of what needs to be included in the spec text. | Contribution required to rewrite the section. | Revised: The subclause is superfluous. The text from Page 24 Line 27 to Page 24 Line 51 can be deleted. | [7 empty] | 2020-08-03 13:19
5 | Abhishek Patil | 32 | 0.1 | 9.4.5 | 24 | 27 | G | N | 24.27 | 27 | 9.4.5 |  |  | Stephen McCann |  |  | Incorrect format - Make entry in Table 9-332 (ANQP-element definition) and add corresponding subclause for each element. | As in comment | Revised: The table entries are on Page 25 Line 5. However, the correct table reference is Table 9-331 (REVmd D4.0). | [7 empty] | 2020-08-03 13:19
157 | Mark RISON | 32 | 0.1 |  | 24 |  | E | N | 24 |  |  |  |  | Stephen McCann |  |  | "to the remote" is missing "destination" | As it says in the comment (or change to "destination") | Revised: Similar change at Page 24 Line 6 and Page 24 Line 10 | [7 empty] | 2020-08-03 13:19
6 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 25 | 9 | T | N | 25.09 | 9 | 9.4.5.bc |  |  | Stephen McCann |  |  | what does 'from a peer STA' mean? - is it services available from the transmitting STA or for a peer STA? I suppose this IE is indicating the service provided by the transmitter. | Change 'from a peer STA' to 'from the STA transmitting this element' | Accept | [7 empty] | 2020-08-03 13:19
41 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5.bc | 25 | 9 | T | N | 25.09 | 9 | 9.4.5.bc | 6 |  | Stephen McCann |  |  | It is unclear what is meant by "peer STA" given that broadcast services are either UL or DL.. the relationship is between STA and AP.. the use of "peer STA" make it sound like a non-AP STA can broadcast for other non-AP STAs. | Either clarify the intention of use of "peer STA" for broadcast services or replace w/ more clear term | Revised: Change the text from 'from a peer STA' to 'from the STA transmitting this element' | [7 empty] | 2020-08-03 13:19
316 | Stephen McCann | 32 | 0.1 | 9.4.2.1 | 20 | 10 | T | N | 20.1 | 10 | 9.4.2.1 |  |  | Abhishek Patil | 11-20-1197 |  | Why does the uplink (UP) case have a capabilities element, but not the downlink case. I think the capabiltiies element should be generic and not dependant on the direction of traffic flow. | Change "eBCS UL Capabilities" to "eBCS Capabilities" | Revised. See submission 11-20-1385r2 | [7 empty] | 2020-08-03 13:19
345 | Antonio DeLaOlivaDelgado | 31 | 0.1 |  |  |  | T | N | 22 | 9 | 9.4.2bc.1 |  |  |  | 11-20-1197 |  | The phrase "An eBCS non-AP STA can include the eBCS UL Capabilities element in an eBCS UL frame if it intends to provide its capabilities to an AP that forwards its data to a remote destination" is not clear | I think what the STA tries to do is to tell the AP what are its requirements in terms of encapsulation, location etc.. It is not giving capabilities supported by the STA but requirements from the STA. Need to revise the phrase imho. | Revised: The comment is correct and the cited text has been re-written. See submission for suggested changes. | CHAIR | Unassigned Comments | [5 empty] | 2020-08-18 19:14 | CHAIR
3 | Abhishek Patil | 32 | 0.1 | 9.4.2.bc.248 | 24 | 18 | T | N | 24.18 | 18 | 9.4.2.bc.248 |  |  | Abhishek Patil | 11-20-1197 |  | Where is this IE used? The eBCS UL Capabilities IE can be made more generic to carry additional information that applies to both UL and DL case. The name can be updated accordingly. | Rename eBCS UL Capabilities element to EBCS Capabilities element. Rename clause 9.4.2.bc.2 from eBCS AP UL Capabilities to EBCS AP Capabilities. Rename UL AP Control field to AP Control field. Append UL to the names of the existing fields in UL AP Control field (e.g., UL Authentication Mode). Add new fields corresponding to the ones described in eBCS Parameters (9.4.2.bc.248) | Revised: The following items have been renamed: 1) eBCS UL Capabilities 2) eBCS AP UL Capabilities 3) UL AP Control 4) UL non-AP STA Control. See submission 11-20-1197r6 | [7 empty] | 2020-08-03 13:19
160 | Mark RISON | 32 | 0.1 | 9.4.2.bc.3 | 25 | 14 | E | N | 25.14 | 14 | 9.4.2.bc.3 |  |  | Stephen McCann | 11-20-1197 |  | Don't show fields as bits in tables, show them as usual figures | Fix Table 9-bc9 - Broadcast field values accordingly | Revised: The comment is corrrect and the Table has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
164 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 25 | 14 | T | N | 25.14 | 14 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | The descriptions in Table 9-bc9 - Broadcast field values are not clear. E.g. "Transmit" -- who has to transmit? "Registration" -- of whom with whom? Ditto in bc.1 and bc.2 | As it says in the comment | Revised: The comment is corrrect and the Table has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
7 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 25 | 15 | T | N | 25.15 | 15 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | Broadcast field is 8 bits long - which bit is it referring to? I think the title of this column should say 'Value' | As in comment | Revised: The comment is corrrect and the Table has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
8 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 25 | 15 | T | N | 25.15 | 15 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | What does 'when bit set to 1' mean here? [This comment also applies to the Request and Response element] | As in comment | Revised: The comment is corrrect and the Table has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
9 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 25 | 15 | T | N | 25.15 | 15 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | Under what conditions is the value 0 useful? As the name and description suggests, this element provides information about the broadcast services provided by the transmitting STA and the column title says when bit set to 1 (which I suppose means when the Broadcast field has a value of 1) | As in comment | Revised: The table and cited text have been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
165 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 25 | 15 | T | N | 25.15 | 15 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | Presumably the Enhanced Broadcast Services Tuples field is not present unless b1 is 1? | As it says in the comment | Revised: The comment is corrrect and the table with b1 has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
167 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 25 | 15 | T | N | 25.15 | 15 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | Presumably the other bits have to be 0 if b0 is 1? | As it says in the comment | Revised: The comment is corrrect and the table with b0 has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
10 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 26 | 3 | T | N | 26.03 | 3 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | Suggest changing the name of this field (Length field) to 'Tuple Length' to differentiate from the Length field carried in the initial portion of the header that describes the length of the Information portion of the element | As in comment | Revised: The length field has been changed to a control field, so this no comment no longer applies. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
11 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 26 | 3 | T | N | 26.03 | 3 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | There are many optional fields (with different lengths) in a tuple, we need a Control field to identify which fields are present or absent. | As in comment | Revised: Agree with comment and the fields and associated text have been changed. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
12 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 26 | 3 | T | N | 26.03 | 3 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | What is the length of the Broadcast Stream Information field? Without a length field, a receiving STA would not know when this field has ended and the next field has started? | As in comment | Revised: The field and associated text have been changed. A control subfield has been added, so that the length of the Broadcast Stream Information field can be determined. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
42 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5bc | 26 | 4 | E | N | 26.04 | 4 | 9.4.5bc |  |  | Stephen McCann | 11-20-1197 |  | in Figure 9-bc10, the size for the last two sub-fields is missing | Add the size of the last two subfields in the figure | Revised: The sub-fields and associated text have been changed. A control subfield has been added, so that the lengths of the sub-fields can be determined. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
43 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5bc | 26 | 4 | T | N | 26.04 | 4 | 9.4.5bc |  |  | Stephen McCann | 11-20-1197 |  | With the current format, it is not clear to the receiver which optional fields are present. | The format needs to be updated, probably w/ addition of a control field, to indicate which fields are present and which are not. | Revised: The sub-fields and associated text have been changed. A control subfield has been added, so that the receiver can determined the fields that are present. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
44 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5bc | 26 | 4 | T | N | 26.04 | 4 | 9.4.5bc |  |  | Stephen McCann | 11-20-1197 |  | How is the length of broadcast Stream Information subfield known? | Please add description of how the length of the broadcast stream information is known? probably need to add a length field prior to the field itself? | Revised: The field and associated text have been changed. A control subfield has been added, so that the length of the Broadcast Stream Information field can be determined. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
168 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 5 | T | N | 26.05 | 5 | 9.4.5.bc |  |  | Stephen McCann |  |  | "set to the total length of the optional fields. " is weird because all the fields are optional | Delete "optional" | Accept | [7 empty] | 2020-08-03 13:19
169 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 5 | T | N | 26.05 | 5 | 9.4.5.bc |  |  | Stephen McCann |  |  | If the field is optional, then the length isn't fixed | Change "6" to "0 or 6" etc. | Revised: Change "6" to "0 or 1" | [7 empty] | 2020-08-03 13:19
170 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 5 | T | N | 26.05 | 5 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | Missing some field lengths | As it says in the comment | Revised: The sub-fields and associated text have been changed. A control subfield has been added, so that the receiver can determined the field that are present. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
171 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 5 | T | N | 26.05 | 5 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | How does the receiver know which fields are present, if all of them are optional, especially if some have variable length? Is this some kind of weird logic puzzle? | As it says in the comment | Revised: The sub-fields and associated text have been changed. A control subfield has been added, so that the receiver can determined the field that are present. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
172 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 6 | T | N | 26.06 | 6 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | "optionally indicates" -- no, if the field is present it indicates | Delete "optionally" and add ", if present". Ditto for the other fields | Revised: The sub-fields and associated text have been changed. A control subfield has been added, so that the receiver can determined the field that are present. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
13 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 26 | 7 | T | N | 26.07 | 7 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | What does multi-STA setup mean? Is this multiple BSSID case with different APs providing different service? | As in comment | Revised: change "multi STA" to "multi AP". | [7 empty] | 2020-08-03 13:19
173 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 8 | T | N | 26.08 | 8 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | "The Broadcast Stream Information field is used to identify the source" -- great! What does it actually contain, and in what format, though? | As it says in the comment | Revised: The definition of the Broadcast Stream Information field has been re-phrased. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
45 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5.bc | 26 | 9 | T | N | 26.09 | 9 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | The OFDMA subchannel is not the source of the broadcast stream.. | Remove "OFDMA sub-channel [TBD - check name]" | Accept. | [7 empty] | 2020-08-03 13:19
174 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 11 | E | N | 26.11 | 11 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | "who value" should be "whose value". Also a few lines down | As it says in the comment | Revised: The comment is correct. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
176 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 13 | T | N | 26.13 | 13 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | So it sounds as if you have to have the Broadcast Stream Information field if you have the Broadcast Time field | Make this requirement explicit | Revised: the comment is correct, although presence of the Broadcast Time field does not imply that the Broadcast Stream Information field is also present. The text has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
175 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 14 | T | N | 26.14 | 14 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | "in terms of real time" -- what does this mean? | As it says in the comment | Revised: the phrase "real time" has been removed from the draft and the text re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
46 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5.bc | 26 | 18 | E | N | 26.18 | 18 | 9.4.5.bc |  |  | Stephen McCann |  |  | Change "Broadcast Time Duration" to "Broadcast Duration Length' | as in the comment | Reject: There is no "Broadcast Time Duration" | [7 empty] | 2020-08-03 13:19
47 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5.bc | 26 | 21 | E | N | 26.21 | 21 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | "in terms of duration" is redundant at the end of the sentence. Remove | as in the comment | Accept. | [7 empty] | 2020-08-03 13:19
177 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 26 | 22 | T | N | 26.22 | 22 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | "The Broadcast Duration field is only present, when there is a Broadcast Time field also present. " but can a Time field be present without a Duration? | As it says in the comment | Revised: the comment is correct, although presence of the Broadcast Time field does not imply that the Broadcast Stream Information field is also present. The text has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
14 | Abhishek Patil | 32 | 0.1 | 9.4.5.bc | 26 | 23 | T | N | 26.23 | 23 | 9.4.5.bc |  |  | Stephen McCann |  |  | There are 3 pieces here - duration of broadcast service (indication of termination), periodicity of advertisement and duration of broadcast. For example: transmitter announces that for the next 1 hr, it will be providing a certain service. The frames carrying information of this service will be advertised every 2 mins at 100ms intervals at most 5 frames. | As in comment | Revised: Delete the note at P26L23. | [7 empty] | 2020-08-03 13:19
48 | Bahareh Sadeghi | 32 | 0.1 | 9.4.5.bc | 26 | 23 | E | N | 26.23 | 23 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | Remove the note | as in the comment | Revised: The comment is correct. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
178 | Mark RISON | 32 | 0.1 | 9.4.5.bc.1 | 27 | 2 | T | N | 27.02 | 2 | 9.4.5.bc.1 |  |  | Stephen McCann | 11-20-1197 |  | "The Enhanced Broadcast Request ANQP-element provides a list of one or more enhanced broadcast 2 services" -- then the field in Figure 9-bc11 - Enhanced Broadcast Request ANQP-element format can't be optional. Ditto in 9-bc12 | As it says in the comment | Revised: the comment is correct and the Enhanced Broadcast Request ANQP-element definition text has be re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
161 | Mark RISON | 32 | 0.1 | 9.4.5.bc | 27 | 10 | E | N | 27.1 | 10 | 9.4.5.bc |  |  | Stephen McCann | 11-20-1197 |  | "Enhanced Broadcast Services Tuples", not "Enhanced Broadcast Services Tuple", for bit 5 | As it says in the comment | Revised: the comment is correct. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
179 | Mark RISON | 32 | 0.1 | 9.4.5.bc.2 | 28 | 7 | T | N | 28.07 | 7 | 9.4.5.bc.2 |  |  | Stephen McCann | 11-20-1197 |  | This is weird. You can set both the success and the failure bit, or neither? | As it says in the comment | Revised: the comment is correct. The text has been re-written. See submission 11-20-1197r6. | [7 empty] | 2020-08-03 13:19
317 | Stephen McCann | 31 | 0.1 | 11.bc | 42 | 6 | T | N | 42.06 | 6 | 11.bc |  |  | Stephen McCann |  |  | The document describes two technical solutions, one for uplink from a non-AP STA to an AP and the other for downlink from an AP to a non-AP STA. Unfortuantely the new frames and much of the behaviour also follow these two solutions. The document clearly shows that it has been written by two separate teams of people. Therefore, it would be much better if many of the frames and behaviour could be defined in a more generic manner and only those apsects which have to be either uplink or downlink are singled out. | Probably a re-write of quite a lot of material. A starting point would be to remove the repeated use of the "UL" term in clause titles and frame definitions. | Revised. The submission proposes the re-writing of a lot of material in the document. The submission proposes a merge of some uplink and downlink frames, so that a single frame can be used in both link directions. See submission 11-20-1197r6.
130 | Mark RISON | 31 | 0.1 | 4.3.31 | 18 | 5 | T | N | 18.05 | 5 | 4.3.31 |  |  | Stephen McCann |  |  | What is "local information"? Surely EBS could broadcast news generated at the other side of the world? | Change "efficient distribution of local information" to "efficient local distribution of information" | Accept
314 | Stephen McCann | 31 | 0.1 | 4.3.31 | 18 | 15 | T | N | 18.15 | 15 | 4.3.31 |  |  | Stephen McCann |  |  | Change the TBD to text. This should correspond to the objectives defined in the PAR. | As an example, change TBD to: eBCS capability advertisments eBCS frames eBCS procedures | Accept
344 | Antonio DeLaOlivaDelgado | 31 | 0.1 |  |  |  | T | Y | 22 | 7 | 9.4.2bc.1 |  |  | Stephen McCann |  |  | In the text the AP only declares capabilities in broadcast Probe Response frames, I think direct unicast Probe Response should also carry this information | remove broadcast | Accept
348 | Antonio DeLaOlivaDelgado | 31 | 0.1 |  |  |  | T | Y | 24 | 19 | 9.4.2.bc.248 |  |  | Stephen McCann | 11-20-1197 |  | eBCS Parameters seem to have the same informaiton as sent in the eBCS Info frame, which is quite long. | I do not think we should have parameters, which is an element, including information about the services being broadcasted in the network, this will be a huge overhead if transmitted in beacons, for example. Unless this element definition is to have one single structure that can be used by all frames including the eBCS Info | Revised: Deleted the cited clause. See submission 11-20-1197r6.

## 2 CIDs
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
350 | Antonio DeLaOlivaDelgado | 31 | 0.1 |  |  |  | T | Y | 28 | 6 | 9.4.5.bc.2 | [5 empty] | The Broadcast Action Response field cannot be included without an Enhanced Broadcast Services Tuples unless the request only had one. If multiple tuples were included in the request, you need some way to specify the one being a success or failure | redo the frame format so we have a Broadcast Action Response together with a Content ID, in this way you can minimise overhead and answer multiple requests. | Discuss: TGbc discussion required. Need to re-encode success/failure for each tuple | CHAIR | Unassigned Comments | [5 empty] | 2020-08-18 19:14 | CHAIR
349 | Antonio DeLaOlivaDelgado | 31 | 0.1 |  |  |  | T | Y | 26 | 3 | 9.4.5.bc (figure 9-bc10) | [5 empty] | The ANQP element lacks of the Content ID per service which is used in the Info frame and Termination notice frames. | I think the ANQP element needs to be aligned in format and elements with the per service information carried in the Info frame and Termination notice frame, for example a title or human readable description is missing, which is required to present the service to the user | Revised: Add a Content ID and an optional Title. [update] | CHAIR | Unassigned Comments | [5 empty] | 2020-08-18 19:14 | CHAIR