## Summary Stats
CID RESOLUTION STATUS 2020-08-05
Comment Type | Ballot Total | JAN | MAY | JUN | JUL | TOTAL Motioned | TODO | TODO Detail
Technical | 460 | 70 | 85 | 47 | 3 | 205 | 255
Editorial | 546 | 0 | 434 | 0 | 0 | 434 | 112 | 80 (RW - Ready) + 23 (reassigned Tech) + 9 (TODO)
General | 16 | 0 | 0 | 0 | 0 |  | 16
TOTAL | 1022
PLAN for D3.0? | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
Proposed number of CIDs | 1022 AUG: 85; 1022 SEP: 85; 1022 OCT: 85; 1022 NOV: D3.0 Recirc Ballot Mid Nov
Based on Doc 20-11/17r4 | 1022 AUG: TECHNICAL; 1022 SEP: Technical; 1022 NOV: TECHNICAL
TOTAL CIDS | 1022 AUG: Assignments; 1022 SEP: NOT ASSIGNED; 1022 NOV: Assigned but NOT DONE
1022 | 1022 AUG: 339; 1022 SEP: 121; 1022 NOV: 134
T | 1022 AUG: (Editor will Transfer) 23

## CID Leaderboard
TECH CID Resolver | JAN | MAY | JUN | JUL | TOTAL
Christian Berger | 14 | 32 |  |  | 46
Ganesh Venkatesan | 36 |  |  | 2 | 38
Assaf Kasher | 19 | 15 |  | 1 | 35
Dibakar Das | 0 |  | 27 |  | 27
Niranjan Grandhe | 0 | 23 |  |  | 23
Nehru Bhandaru | 0 |  | 19 |  | 19
Jonathan Segev | 0 | 15 |  |  | 15
Ali Rasissini | 1 |  |  |  | 1
Feng Jiang | 0 |  | 1 |  | 1
Qinghua Li | 0 |  |  |  | 0
Erik Lindskog | 0 |  |  |  | 0
Qi Wang | 0 |  |  |  | 0
Yongho Seok | 0 |  |  |  | 0
Girish Madpuwar | 0 |  |  |  | 0
Jerome Henry | 0 |  |  |  | 0
Yongho Seok | 0 |  |  |  | 0
ChaoChun | 0 |  |  |  | 0
Roy Want | 0 |  |  |  | 0
TOTAL TECH CIDS | 70 | 85 | 47 | 3 | 205

## Motions MAY-JUL
MOTION | Ed | DOC # | AUTHORS | NOTES | #Ed CIDs | #Tech CIDs | CIDs
202005-01 |  | 140r0 | Assaf Kasher | Interim Meeting MInutes 13-17th Jan (Irvine) | 0 | 0 | N/A
202005-02 |  | 249r0 | Assaf Kasher | Telecon MInutes 8th Jan | 0 | 0 | N/A
202005-03 |  | 251r0 | Assaf Kasher | Telecon MInutes Jan-Feb | 0 | 0 | N/A
202005-04 |  | 419r1 | Roy Want | Ad Hoc Meeting Minutes March | 0 | 0 | N/A
202005-05 |  | 592r0 | Assaf Kasher | Telecon MInutes April | 0 | 0 | N/A
202005-06 |  | 159r1 | Jonathan Segev |  | 0 | 9 | 3862, 3878, 3892, 3854, 3489, (3511), 3533, 3535, 3566 and 3592
202005-07 |  | 256r1 | Jonathan Segev | Use 3511 (2nd occurrence), from this motion, as final. | 0 | 6 | 3829, 3511, 3630, 3708, 3709 and 3716
202005-08 |  | 388r2 | Assaf Kasher |  | 0 | 15 | 3648, 3026, 3027, 3262, 3573, 3574, 3575, 3028, 3029, 3638, 3916, 3918, 4002, 3042 and 4003
202005-09 |  | 379r1 | Niranjan Grandhe |  | 0 | 23 | 3722, 3727, 3728, 3730, 3731, 3732, 3733, 3735, 3738, 3739, 3908, 3255, 3256, 3257, 3258, 3742, 3743, 3745, 3746, 3467, 3259, 3747 and 3260
202005-10 |  | 366r2 | Christian Berger |  | 0 | 13 | 3503, 3504, 3193, 3009, 3101, 3192, 3848, 3894, 3010, 3011, 3222, 3431 and 3710,
202005-11 |  | 368r2 | Christian Berger | Removed 3242 as no resolution in 368r2 | 0 | 19 | 3115, (3242), 3719, 3701, 3702, 3906, 3703, 3705, 3706, 3707, 3711, 3712, 3685, 3686, 3713, 3657, 3714, 3715, 3247 and 3907
202006-01 |  | 255r1 | Nehru Bhandaru |  | 0 | 14 | 3517, 3514, 3515, 3522, 3406, 3519, 3407, 3408, 3536, 3409, 3414, 3833, 3448 and 3521
202006-02 |  | 530r0 | Nehru Bhandaru |  | 0 | 3 | 3524, 3525 and 3526
202006-03 |  | 607r1 | Dibakar Das |  | 0 | 6 | 3676, 3677, 3678, 3680, 3811 and 3126
202006-04 | CCW | 642r0 | ChaoChun / Roy Want |  | 434 | 0 | <CCW Editorial Batch from January>
202006-05 |  | 641r0 | Dibakar Das |  | 0 | 1 | 3679
202006-06 |  | 707r3 | Christian Berger | New Tech Contribution | 0 | 0 | N/A
202006-07 |  | 759r1 | Feng Jiang |  | 0 | 1 | 3129
202006-08 |  | 759r3 | Dibakar Das |  | 0 | 2 | 3629 and 3271
202006-09 |  | 788r2 | Dibakar Das |  | 0 | 18 | 3013, 3014, 3015, 3102, 3283, 3355, 3389, 3016, 3017, 3827, 3888, 3324, 3434, 3962, 3287, 3435, 4004 and 4005
202006-10 |  | 806r1 | Nehru Bhandaru |  | 0 | 2 | 3357 and 3523
202007-01 |  | 1043r0 | Assaf Kasher / Roy Want | Telecon Minutes May-July | 0 | 0 | N/A
202007-02 |  | 800r1 | Ganesh Vankatesan |  | 0 | 2 | 3232 and 3440
202007-03 |  | 889r3 | Nehru Bhandaru | New Tech Contribution: Note r4 exists | 0 | 0 | N/A
202007-04 |  | 698r2 | Assaf Kasher |  | 0 | 1 | 3940
TOTAL |  |  |  |  | 434 | 135