## Summary Stats
CID RESOLUTION STATUS 2020-11-03
Comment Type | Ballot Total | JAN | MAY | JUN | JUL | AUG | SEP | OCT | NOV | TOTAL Motioned
Technical | 460 | 70 | 85 | 45 | 3 | 1 | 80 | 87 |  | 371
Editorial | 546 | 0 | 434 | 2 | 0 | 0 | 8 | 84 | 14 | 542
General | 16 | 0 | 0 | 0 | 0 | 0 | 4 | 7 |  | 11
TOTAL | 1022 | [8 empty] | 924
PLAN for D3.0 | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
Proposed number of Tech CIDs | 1022 OCT: T:62 G:2 E:20; 1022 NOV: D3.0 R. Ballot by 11/20
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | MOTION DUPs | STRAW ONLY | STRAW DUPs | NOT MOTIONED - STRAW | WITHDRAWN | TODO
Technical CIDS | 11 | 449 | 404 | 63 | 7 | 0 | 1 | 64 | 3 | 61
Editorial CIDs | 0 | 546 | 542 | 4 | 0 | 0 | 2 | 6 | 0 | 6
General CIDs | 0 | 16 | 14 | 2 | 0 | 0 | 0 | 2 | 0 | 2
Note on E14: Roy Want: Added the duplicate motions.
Note on F14: Roy Want: 5 CIDs were remotioned: CB(3011) JS(3854, 3862) GV(3440) ELmGV(3165) EL(3052, 3053) SP
Note on H14: Roy Want: 2 CIDs were Sped on existing motion: AK(3209)
Note on C15: Microsoft Office User: 18 of these are really technical and have been assigned to others.

## CID Leaderboard
TECH CID Resolver | JAN | MAY | JUN | JUL | AUG | SEP | OCT | NOV | TOTAL Motions | Total Assigned | Total Outstanding | Strawpolled | TODO | Explanation: Additions to Outstanding [motions only] | Explanation: Additions to TODO [motions + SPs]
Assaf Kasher | JAN: 19; MAY: 15; JUL: 1; OCT: 29 | 64 | 76 | 10 | 10 | 1 |  | Add 1: SP already motioned 3209
Christian Berger | JAN: 14; MAY: 32; SEP: 12; OCT: 1 | 59 | 63 | 10 | 5 | 6 | Add 1: CB remotioned CID 3011 from 366r2 later in 1219r3, Sub 1 O 3020 assigned GV but motion EL; #3245(W); #3772 reassigned to CB | Add 1: 3226 is assigned to DD so does not count against CB assignment
Dibakar Das | JAN: 0; JUN: 27; SEP: 8; OCT: 18 | 53 | 61 | 8 | 0 | 5 |  | Sub 2: 3238 &3239 assigned to DD, motioned by JS; Sub 1: 3236 assigneed to DD, motioned by CB
Jonathan Segev | JAN: 0; MAY: 15; SEP: 18; OCT: 10 | 43 | 39 | 7 | 12 | 7 | Add 2: JS remotioned his own CIDs 3854, 3862 in 1257r1 motioned earlier in 159r1 | Add 10: SPing ten of YS's CIDs; Add 2: for SPing two (3238, 3239) of DD's CIDs
Erik Lindskog | JAN: 0; SEP: 29; OCT: 13 | 42 | 46 | 7 | 3 | 6 | Add 2 EL: Motioned 3020(C. Berger) & 3165 (G Vankatesan). But Add another 1: duplicate motion of 3165 in GV. | Add 2: CIDs (3052 & 3053) that had aready been motioned by EL
Ganesh Venkatesan | JAN: 36; JUL: 2 | 38 | 44 | 6 |  | 6 | Add 1: GV remotioned CID 3440: Sub 1 O: 3165 assigned to GV, but motioned by EL
Nehru Bhandaru | JAN: 0; JUN: 17; AUG: 1; SEP: 13 | 31 | 31 | 0 |  | 0
Niranjan Grandhe | JAN: 0; MAY: 23 | 23 | 24 | 0 |  | 0 | 1 reassigned to UNASSIGNED
Girish Madpuwar | JAN: 0; OCT: 16 | 16 | 20 | 5 | 0 | 5 | 1 reassigned to Girish from Assaf
Feng Jiang | JAN: 0; JUN: 1 | 1 | 1 | 0 |  | 0
Ali Rasissini | [8 empty] | 1 | 1 | 0 |  | 0 | bar: JAN
ChaoChun | JAN: 0 | 0 | 0 | 0 |  | 0
Roy Want | JAN: 0 | 0 | 0 | 0 |  | 0
Jerome Henry | JAN: 0 | 0 | 1 | 1 |  | 1
Qi Wang | JAN: 0 | 0 | 2 | 4 | 3 | 1
Qinghua Li | JAN: 0 | 0 | 16 | 0 |  | 0 | 10 reassigned to UNASSIGNED; 6 reassigned to CB.
Yongho Seok | JAN: 0 | 0 | 23 | 23 | 0 | 13 |  | Sub 10: because 10 CIDs motioned by JS/RW
UNASSIGNED | [9 empty] | 11 | 11 | 0 | 11
WITHDRAWN | [12 empty] | 2
TOTAL TECH CIDS | 70 | 85 | 45 | 3 | 1 | 80 | 87 | 0 | 371 | 459 | 81 | 33 | 64
NAME | JAN: T#; MAY: G#; JUN: E#; JUL: G&E List TODO |  | T-CIDs List TODO
Nehru Bhandaru | JAN: 0; MAY: 0; JUN: 0
Feng Jiang | JAN: 0; MAY: 0; JUN: 0
ChaoChun | JAN: 0; MAY: 0; JUN: 0
Roy Want | JAN: 0; MAY: 0; JUN: 0
Niranjan Grandhe | JAN: 0; MAY: 0; JUN: 0
Qinghua Li | JAN: 0; MAY: 0; JUN: 0
Ali Raissinia | JAN: 1; MAY: 0; JUN: 1; JUL: 3099E |  | 3128
Assaf Kasher | JAN: 1; MAY: 0; JUN: 0 |  | 3635
Jerome Henry | JAN: 1; MAY: 0; JUN: 0 |  | 3356
Qi Wang | JAN: 1; MAY: 0; JUN: 0 |  | 3911
WITHDRAWN | JAN: 3; MAY: 0; JUN: 0 |  | 3909(QW), 3245(CB), 3106(AR)
Girish Madpuwar | JAN: 5; MAY: 0; JUN: 0 |  | 3123, 3124, 3450, 3754, 3775
Dibakar Das | JAN: 5; MAY: 1; JUN: 0; JUL: 3886G |  | 3606, 3607, 3616, 3620, 3700
Ganesh Venkatesan | JAN: 6; MAY: 0; JUN: 1; JUL: 3376E |  | 3134, 3442, 3578, 3579, 3611, 3828 |  |  |  |  | 14 | 5
Erik Lindskog | JAN: 6; MAY: 0; JUN: 0 |  | 3273, 3277, 3278, 3279, 3280, 3311
Christian Berger | JAN: 6; MAY: 0; JUN: 0 |  | 3118, 3717, 3718, 3883, 4014, 4018
Jonathan Segev | JAN: 6; MAY: 1; JUN: 4; JUL: 3214(G), 3375E, 3885E, 3995E, 4008E |  | 3276, 3282, 3411, 3412, 3424, 3921
UNASSIGNED | JAN: 10; MAY: 0; JUN: 0 |  | 3074, 3122, 3131, 3215, 3269, 3270, 3354, 3893, 3900, 3920
Yongho Seok | JAN: 13; MAY: 0; JUN: 0 |  | 3457, 3458, 3507, 3614, 3615, 3627, 3761, 3847, 3868, 3869, 3901, 3902, 3910
TOTAL | JAN: 64; MAY: 2; JUN: 6 | TODO TOTAL | 72
TOTAL-WITHDRAWN | JAN: 61; MAY: 2; JUN: 6 | TODO-WITHDRAWN | 69

## Motions
Action | MOTION | Ed | DOC # | AUTHORS | NOTES | #Ed CIDs | #Gen CIDs | #Tech CIDs | #STR Ed | #STR Gen | #STR Tech | CIDs
JAN | [11 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Superceds corresponding red.
N/A | 202001-01 |  | 1898r0 |  | November Ad Hoc Minutes | 0 |  | 0
N/A | 202001-02 |  | 2005r0 |  | November Minutes | 0 |  | 0
DONE | 202001-03 |  | 121r0 | Ali Raissinia |  | 0 |  | 1 |  |  |  | 3130
DONE | 202001-04 |  | 118r1 | Assaf Kasher |  | 0 |  | 11 |  |  |  | 3079, 3080, 3208, 3081, 3210, 3082, 3089, 3090, 3091, 3092 and 3093
DONE | 202001-05 |  | 137r3 | Assaf Kasher |  | 0 |  | 5 |  |  |  | 3067, 3068, 3181, 3186 and 3938
DONE | 202001-06 |  | 126r2 | Ganesh Venkatesan |  | 0 |  | 13 |  |  |  | 3163, 3164, 3561, 3563, 3564, 3165, 3166, 3167, 3565, 3572, 3577, 3583 and 3439
DONE | 202001-07 |  | 167r1 | Assaf Kasher |  | 0 |  | 3 |  |  |  | 3823, 3832, 3936
DONE | 202001-08 |  | 183r1 | Ganesh Venkatesan |  | 0 |  | 16 |  |  |  | 3580, 3581, 3585, 3169, 3586, 3314, 3483, 3915, 3984, 3425, 3853, 3032, 3033, 3436, 3437 and 3438
N/A | 202001-09 |  |  |  | Ad hoc scheduling | 0 |  | 0
DONE | 202001-10 |  | 198r2 | Ganesh Venkatesan |  | 0 |  | 7 |  |  |  | 3440, 3441, 3490, 3034, 3035, 3231 and 3840
DONE | 202001-11 |  | 154r2 | Christian Berger |  | 0 |  | 14 |  |  |  | 3664, 3985, 3669, 3672, 3675, 3688, 3689, 3692, 3693, 3695, 3697, 3698, 3699 and 3470
MAY
N/A | 202005-01 |  | 140r0 | Assaf Kasher | Interim Meeting MInutes 13-17th Jan (Irvine) | 0 |  | 0 |  |  |  | N/A
N/A | 202005-02 |  | 249r0 | Assaf Kasher | Telecon MInutes 8th Jan | 0 |  | 0 |  |  |  | N/A
N/A | 202005-03 |  | 251r0 | Assaf Kasher | Telecon MInutes Jan-Feb | 0 |  | 0 |  |  |  | N/A
N/A | 202005-04 |  | 419r1 | Roy Want | Ad Hoc Meeting Minutes March | 0 |  | 0 |  |  |  | N/A
N/A | 202005-05 |  | 592r0 | Assaf Kasher | Telecon MInutes April | 0 |  | 0 |  |  |  | N/A
DONE | 202005-06 |  | 159r1 | Jonathan Segev |  | 0 |  | 9 |  |  |  | 3862, 3878, 3892, 3854, 3489, (3511), 3533, 3535, 3566 and 3592 | DBv7 assign 3892 from Qinghua to Jonathan Segev ( motioned)
DONE | 202005-07 |  | 256r1 | Jonathan Segev | Use 3511 (2nd occurrence), from this motion, as final. | 0 |  | 6 |  |  |  | 3829, 3511, 3630, 3708, 3709 and 3716
DONE | 202005-08 |  | 388r2 | Assaf Kasher |  | 0 |  | 15 |  |  |  | 3648, 3026, 3027, 3262, 3573, 3574, 3575, 3028, 3029, 3638, 3916, 3918, 4002, 3042 and 4003
DONE | 202005-09 |  | 379r1 | Niranjan Grandhe |  | 0 |  | 23 |  |  |  | 3722, 3727, 3728, 3730, 3731, 3732, 3733, 3735, 3738, 3739, 3908, 3255, 3256, 3257, 3258, 3742, 3743, 3745, 3746, 3467, 3259, 3747 and 3260
DONE | 202005-10 |  | 366r2 | Christian Berger |  | 0 |  | 13 |  |  |  | 3503, 3504, 3193, 3009, 3101, 3192, 3848, 3894, 3010, 3011, 3222, 3431 and 3710, | DBv7 assign 3011 to Christian Berger (motioned)
DONE | 202005-11 |  | 368r2 | Christian Berger | Removed 3242 as no resolution in 368r2 | 0 |  | 19 |  |  |  | 3115, (3242), 3719, 3701, 3702, 3906, 3703, 3705, 3706, 3707, 3711, 3712, 3685, 3686, 3713, 3657, 3714, 3715, 3247 and 3907
JUNE
DONE | 202006-01 |  | 255r1 | Nehru Bhandaru |  | 0 |  | 14 |  |  |  | 3517, 3514, 3515, 3522, 3406, 3519, 3407, 3408, 3536, 3409, 3414, 3833, 3448 and 3521
DONE | 202006-02 |  | 530r0 | Nehru Bhandaru |  | 0 |  | 3 |  |  |  | 3524, 3525 and 3526
DONE | 202006-03 |  | 607r1 | Dibakar Das |  | 0 |  | 6 |  |  |  | 3676, 3677, 3678, 3680, 3811 and 3126
DONE | 202006-04 | CCW | 642r0 | ChaoChun / Roy Want | Editorials x 434 | 434 |  | 0 |  |  |  | <CCW 434 CID Editorial Batch from January>
DONE | 202006-05 |  | 641r0 | Dibakar Das |  | 0 |  | 1 |  |  |  | 3679
DONE | 202006-06 |  | 707r3 | Christian Berger | New Tech Contribution | 0 |  | 0 |  |  |  | TECH
DONE | 202006-07 |  | 759r1 | Feng Jiang |  | 0 |  | 1 |  |  |  | 3129
DONE | 202006-08 |  | 759r3 | Dibakar Das |  | 0 |  | 2 |  |  |  | 3629 and 3271
DONE | 202006-09 |  | 788r2 | Dibakar Das |  | 0 |  | 18 |  |  |  | 3013, 3014, 3015, 3102, 3283, 3355, 3389, 3016, 3017, 3827, 3888, 3324, 3434, 3962, 3287, 3435, 4004 and 4005
DONE | 202006-10 |  | 806r1 | Nehru Bhandaru | Editorials -> Tech CIDS | 2 |  | 0 |  |  |  | 3357(E) and 3523(E) | CID 3357, 3523 are Editorial
JULY
N/A | 202007-01 |  | 1043r0 | Assaf Kasher / Roy Want | Telecon Minutes May-July | 0 |  | 0 |  |  |  | N/A
DONE | 202007-02 |  | 800r1 | Ganesh Vankatesan |  | 0 |  | 2 |  |  |  | 3232 and 3440
DONE | 202007-03 |  | 889r3 | Nehru Bhandaru | New Tech Contribution: Note r4 exists | 0 |  | 0 |  |  |  | TECH
DONE | 202007-04 |  | 698r2 | Assaf Kasher |  | 0 |  | 1 |  |  |  | 3940
AUG
N/A | 202008-01 |  | 847r0 | Assaf Kasher | Minutes Plenary Meetings May - July | 0 |  | 0 |  |  |  | N/A
N/A | 202008-02 |  | 1195r0 | Roy Want | Minutes Telecon July 15th | 0 |  | 0 |  |  |  | N/A
DONE | 202008-03 |  | 963r2 | Nehru Bhandaru |  | 0 |  | 1 |  |  |  | 3880
DONE | 202008-04 |  | 1106r0 | Nehru Bhandaru | New Technical Contribution | 0 |  | 0 |  |  |  | TECH
SEPT
DONE | 202009-01 |  | 1186r0 | Nehru Bhandaru | New Technical Contribution | 0 |  | 0 |  |  |  | TECH
DONE | 202009-02 |  | 1189r3 | Jonathan Segev |  | 0 |  | 8 |  |  |  | 3094,3095, 3212, 3941, 3618, 3762, 3764, and 3825
DONE | 202009-03 |  | 1257r1 | Jonathan Segev | Duplicates: 3854T, 3862T | 0 |  | 8 |  |  |  | 3758, 3844, 3854, 3855, 3860, 3862, 3863, and 3867 | 3854 is a redo of a CID in 202005-06 and 3862 is a redo of 202005-06
DONE | 202009-04 |  | 1143r1 | Assaf Kasher |  | 2 |  | 0 |  |  |  | 3510(E) and 3361(E)
DONE | 202009-05 |  | 1196r2 | Jonathan Segev |  | 0 |  | 2 |  |  |  | 3281 and 3387
DONE | 202009-06 |  | 1208r1 | Christian Berger | New Technical Contribution | 0 |  | 0 |  |  |  | TECH
DONE | 202009-07 |  | 1219r3 | Christian Berger |  | 1 | 1 | 11 |  |  |  | 3008(E), 3884(G), 3011, 3019, 3105, 3242, 3671, 3119, 4019, 3267, 3268, 3986 and 3987
DONE | 202009-08 |  | 1225r4 | Nehru Bhandaru |  | 0 | 2 | 13 |  |  |  | 3132(G), 3304, 3319, 3388, 3399, 3404, 3453, 3460, 3461, 3520, 3650(G), 3839, 3974, 3975 and 3988
N/A | 202009-09 |  |  |  | Vice Chair affirmation | [6 empty] | N/A
DONE | 202009-10 |  | 1020r8 | Erik Lindskog |  | 1 |  | 7 |  |  |  | 3103(E), 3020, 3830, 3336, 3045, 3143, 3857 and 3337
N/A | 202009-11 |  |  |  | Timeline commit | 0 |  | 0 |  |  |  | N/A
DONE | 202009-12 |  | 1487r4 | Erik Lindskog |  | 3 | 1 | 22 |  |  |  | 3858, 3307, 3052, 3053, 3874(E), 3558, 3554, 3555, 3556, 3655, 3654, 3659, 3800, 3801, 3808, 3165, 3166, 3890(E), 3891(E), 3308(G), 3309, 3547, 3548, 3789, 3790 and 3791
new | 202009-13 |  | 1308r0 | Nehru Bhandaru | New Technical Contribution | 0 |  | 0 |  |  |  | TECH
DONE | 202009-14 |  | 1209r3 | Christian Berger |  | 1 |  | 1 |  |  |  | 3266(E) and 3895
DONE | 202009-15 |  | 1394r1 | Dibakar Das |  | 0 |  | 8 |  |  |  | 3127, 3299, 3814, 3816, 3116, 3543, 3544, and 3537
OCTOBER
N/A | 202010-01 |  | 1335r0 | Assaf Kasher | Minutes Aug 19th Telecos
N/A | 202010-02 |  | 1442r0 | Assaf Kasher | Minutes July-Sept Telecons
| 202010-03 |  | 1393r1 | Dibakar Das |  |  |  | 2 |  |  |  | 3896, and 3999
| 202010-04 |  | 1410r0 | Roy Want | Editorial CIDs x 80 | 80 | [5 empty] | <80 Editorials - see doc>
| 202010-05 |  | 1392r2 | Dibakar Das |  |  |  | 16 |  |  |  | 3594, 3599, 3600, 3904, 3601, 3603, 3605, 3608, 3621, 3622, 3624, 3628, 3683, 3813, 3815, and 3861
FAILED | STRAWPOLL |  | 1245r3 | Christian Berger |  |  |  | 0 |  |  |  | 3883
| 202010-06 |  | 1502r3 | Erik Lindskog | Duplicates: 3052T, 3053T, 3874E | 2 |  | 8 |  |  |  | 3052, 3053, 3874(E), 3557, 3656, 3804, 3301(E), 3152, 3841, and 3310
| 202010-07 |  | 340r8 | Girish Madpuwar |  |  |  | 16 |  |  |  | 3066, 3760, 3842, 3843, 3912, 3913, 3914, 3771, 3777, 3778, 3779, 3780, 3782, 3783, 3625, and 3768
| 202010-08 |  | 1553r1 | Assaf Kasher |  |  |  | 13 |  |  |  | 3000, 3018, 3054, 3055, 3056, 3057, 3058, 3059, 3060, 3061, 3153, 3154, and 3175
| 202010-09 |  | 1501r2 | Erik Lindskog |  |  |  | 4 |  |  |  | 3274, 3047, 3275, 3234
| 202010-10 |  | 1581r2 | Erik Lindskog |  |  |  | 1 |  |  |  | 3658
| 202010-11 |  | 1437r2 | J Segev / R Want |  | 1 | 6 | 10 |  |  |  | 3328(G), 3036(E), 3341, 3365, 3451, 3477(G), 3482, 3529(G), 3570(G), 3643, 3826(G), 3864, 3889(G), 3898, 3108, 3238, and 3239 | 3108 was assigned to JS anyway, 3238 and 3239 were originally assigned to Dibakar
| 202010-12 |  | 1590r2 | Assaf Kasher | Duplicate: 3510E | 1 | 1 | 16 |  |  |  | 3178, 3644, 3645, 3646, 3649, 3652, 3653, 3206, 3207, 3510(E), 3562(G), 3478, 3209, 3939, 4000, 4001, 3919, and 3532
| 202010-13 |  | 1603r2 | Christian Berger |  |  |  | 1 |  |  |  | 3236 | 3236 reassigned from Dibakar to Christian
NOV
N/A | 202011-01 |  | 1482r0 | Assaf Kasher | Minutes September Electronic Meeting Week | [6 empty] | N/A
| 202011-02 |  | 1654r1 | Qi Wang |  |  |  | 3 |  |  |  | 3850, 3851, 3852
| 202011-03 |  | 1683r3 | J Segev / R Want |  |  | 1 | 12 |  |  |  | 3006, 3007, 3899, 3990, 4012(G), 3264, 3265, 3317, 3320, 3321, 3322, 3455, 3456
| 202011-04 |  | 1684r3 | Christian Berger |  |  | 1 | 1 |  |  |  | 3772 and 3882(G) (2 CIDs total)
| 202011-05 |  | 1687r3 | Assaf Kasher | Duplicate: 3209 |  | 1 | 10 |  |  |  | 3204, 3639, 3937, 3534, 3170, 3634, 3773, 3368(G), 3870, 3905, 3209 ( 11 CIDs total)
| 202011-06 |  | 1717r1 | Erik Lindskog |  |  |  | 3 |  |  |  | 3289, 3272 and 3306 (3 CIDs total)
| 202011-07 |  | 1718r1 | Christian Berger |  |  |  | 4 |  |  |  | 4013, 4015, 4016, 4017 (4 CIDs total)
| 202011-08 |  | 1745r0 | Roy Want | 14-Editorials | 14 | [5 empty] | 3049, 3069, 3073, 3075, 3096, 3205, 3297, 3298, 3486, 3487, 3542, 3769, 3781, 3953 (14 E-CIDs total)
| TOTAL |  |  |  |  | 542 | 14 | 404 | 0 | 0 | 0
20
14

## New + changed CID Requests
NEW | 2020-08-11 | 2020-08-13 | 2020-08-19 | 2020-08-19 | 2020-08-25 | 2020-08-26 | 2020-10-08 | 2020-10-08
Count | Christian Berger | Nehru Bhandaru | Jonathan Segev | Yongho Seok | Yongho Seok | Assaf Kasher | Qi Wang | JS/RW
1 | 3011 | 3132 | 3106 | 3317 | 3321 | 3643 | 3850 | 3328(G)
2 | 3019 | 3304 | 3108 | 3320 | 3322 | 3457 | 3851 | 3036(E)
3 | 3020 | 3319 | 3214 |  | 3455 |  | 3852 | 3341
4 | 3105 | 3388 | 3276 |  | 3456 |  |  | 3365
5 | 3267 | 3399 | 3282 |  | 3457 |  |  | 3451
6 | 3268 | 3404 | 3411 |  | 3458 |  |  | 3477(G)
7 | 3986 | 3453 | 3412 |  | 3507 |  |  | 3482
8 | 3987 | 3460 | 3424 |  | 3614 |  |  | 3529(G)
9 | 4019 | 3461 |  |  | 3615 |  |  | 3570(G)
10 |  | 3520 | [5 empty] | 3643
11 |  | 3650 | [5 empty] | 3826(G)
12 |  | 3839 | [5 empty] | 3864
13 |  | 3974 | [5 empty] | 3889(G)
14 |  | 3975 | [5 empty] | 3898
15 |  | 3988 | [5 empty] | 3108
3238
CORRECT OR REASSIGN | [7 empty] | 3239
CID | FROM | TO | STATUS
3011 | n/a | Christian Berger | Motioned
3892 | Qinghua Li | Jonathan Segev | Motioned
3271 | Feng Jiang | Dibakar Das | Motioned
3130 | Feng Jiang | Ali Raissina | Motioned
3269 | Feng Jiang | Qinghua Li | Not Motioned
3889 | Erik Lindskog | n/a | Not Motioned
3328 | Erik Lindskog | n/a | Not Motioned
3565 | N/A | Ganesh Venkatesan | Motioned 202001-06
3310, 3311 | Dibajar Das | Erik Lindskog | Not Motioned
3658 | Editor | Erik Lindskog | STRAWPOLLED
3643 | Assaf Kasher | JS/RW | STRAWPOLLED
3236 | Dibakar Das | Christian Berger | STRAWPOLLED
3775 | Assaf Kasher | Girsh Madupar
3772 | Assaf Kasher | Christian Berger