## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-20/1397r3
Venue Date: | Septembeer 2020
First Author: | Marc Emmelmann
Subject: | Proposed resolutions for TGbc CC31 comments assigned to Marc
Full Date: | 2020-09-14
Author(s): | Marc Emmelmann
| Company: | Koden-TI
Address
Phone:
Fax:
email:
Abstract:
Proposed resolutions for TGbc CC31 comments assigned to Marc

## Revision History
Revision | Date | Description
0 | 2020-09-01 | Initial version
1 | 2020-09-14 | Updated resolutons
2 | 2020-09-14 | Updated resolutons
3 | 2020-09-14 | Marked agreed resolutions green = ready for motion

## Marc Emmelmann
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
140 | Mark RISON | 31 | 0.1 |  |  |  | G | N | [5 empty] | Marc Emmelmann |  |  | AAAARGH! Make the logical and physical page numbers match next time, please! | As it says in the comment | Revised. Start the Draft on its first page wth "1" and do not restart after the openng sectoins. Note -- this was suggested by the 802.11 Editor, i.e. to not follow the style guideline n which the first pages of the draft are numbered in roman numbers and then the numbering is restarted at arabic 1,. The page numering can be fixed by the IEEE editor during the final publicatioin process | CHAIR | [6 empty] | 2020-08-18 19:11 | CHAIR
128 | Mark RISON | 31 | 0.1 |  |  |  | G | N | [5 empty] | Marc Emmelmann |  |  | TBDs need to be Ded. Also "Describe" needs to be replaced by descriptions. Also the [Note:s | As it says in the comment | Revised. Editor to remove TBDs from the draft. Also remove all sentences "Descibe .." without a descriptoin following it. | CHAIR | [6 empty] | 2020-08-18 19:11 | CHAIR
342 | Xiaofei Wang | 31 | 0.1 | 11.22.6.bc | 48 | 52 | E | N | 48.52 | 52 | 11.22.6.bc |  |  | Marc Emmelmann |  |  | The page number shown on the page doesn't match the page number shown for the PDF document. Please make sure tat the numbers match to prevent confusion to which a comment is referring to. For example, page 47 (as printed on the page) is shown as page 42 as indicated by PDF. | as in comment | Revised. Start the Draft on its first page wth "1" and do not restart after the openng sectoins. Note -- this was suggested by the 802.11 Editor, i.e. to not follow the style guideline n which the first pages of the draft are numbered in roman numbers and then the numbering is restarted at arabic 1,. The page numering can be fixed by the IEEE editor during the final publicatioin process | CHAIR | [6 empty] | 2020-09-02 10:14 | CHAIR