## Slide 1: Release Guidelines: An Overview
Date: 2019-07-01
Authors:
Alfred Asterjadhi, et. al.

## Slide 2: Introduction
TGbe agreed to adopt a release-based approach during Jan’20 F2F
  “Move to agree to define releases of features, and to prioritize contributions and decisions related to release in the agenda, as summarized below, starting with Release 1
    Release 1 Features are: 320 MHz, 4KQAM, Multiple RUs per STA, Multi-link operation and a low complexity AP coordination feature
    Candidate Release 2 Features: 16 spatial streams, HARQ, Additional multi-AP features (e.g. C-BF, JT), any other potential features in the scope of PAR (e.g. features for Time-sensitive networks)
  Notes:
    The specification of release 1 features needs to be ready and stable in 11be D1.0/D2.0 at the target dates.
    The specification of release 2 features needs to be ready and stable in 11be D3.0/D4.0 at the target dates.
    The discussion on release 2 features is still allowed during release 1 phase.
    ­All releases target increasing throughput and/or reducing worst case latency and/or improving power efficiency, as defined in the PAR”

## Slide 3: Projected TGbe Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 Letter Ballot May 2021
D2.0 LB Mar 2022
D3.0 LB Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024
* Short terms/intermediate targets: D0.2 in Dec 2020, D0.3 in Jan 2020, D0.4 in Mar 2021
We are here*
Stable Release 1 Features
Stable Release 2 Features

## Slide 4: 802.11be Selection Procedure Flow Chart
Flow chart below shows how technical contributions advance to spec text
  Taken from 11-19/559r1
Functional Requirements Document
Spec Framework text
Technical Contribution
75%
75%
Spec Framework document
Add to Spec
Framework?
Y
Spec
Text Contribution
Adopt into
Draft?
Y
Detailed
Spec
text
75%
Y
TG or WG Letter Ballot
Spec Addresses
Spec Framework
And Ready for LB?

## Slide 5: TGbe Documents: Status and Plan (1)
Specification Framework Document (1262r12)
  Status: Contains all technical concepts motioned to date (list of motions tracked by 1755r12)
    Motions on concepts for Release 1 tagged with R1 & motions on concepts for Release 2 tagged with R2
    Several Motions do not have explicit tags (tagging (R1 vs. R2) is being addressed in 997r63)
  Plan: Continue tracking all technical concepts with respective tags.
Compendium of SPs and potential changes to the SFD (566r12)
  Status: Built on top of SFD and additionally contains all SPs that have RXed majority support
    These SPs are then converted to motions in pre-designated Joint conf calls (see guidelines)
    SPs on concepts for R1 are tagged with R1 and SPs on concepts for R2 are tagged with R2
  Plan: Continue tracking all technical concepts with respective tags.
TGbe Spec text volunteers and status (997r63)
  Status: Contains a table with the spec text volunteers, status updates, etc.
    Lists point of contacts (POCs) for each topic/subject, list of motions, R1/R2 classification, status, etc.
    Tracks proposed draft texts (PDTs) for populating the TGbe drafts
      PDTs related to R1 topics have been included in TGbe D0.1 and expected to be included in subsequent drafts
      No time is currently dedicated to PDTs for R2 features so they are on hold (see next slides)
  Plan: Continue tracking all topics and status, with respective tags.

## Slide 6: TGbe Documents: Status and Plan (2)
Towards TGbe D1.0 (next major milestone) - May 21 as in the approved TGbe Timeline
  D0.3: Undergo a WG comment collection on D0.3 (start mid-Jan’21)
    Comments to target issues with existing draft (except for TBDs), i.e., no new feature request, etc.
    Comment resolution expected to end with delivery of D1.0
      Comments that are unresolved/unexamined by May 13 will be automatically rejected and can be submitted again later
    There shall be no motions to add to TGbe SFD for R1 after D0.3 is released
      I.e., work only on draft spec text for R1 concepts after D0.3
  D1.0: Complete all TBDs that are present in the TGbe draft (usual process, PDTs, etc.)
  D1.0: Approve coexistence assurance document (need a volunteer)
Towards TGbe D2.0 - March 22 as in the approved TGbe Timeline
  Undergo a WG LB (so far everything is pertinent to R1)
    30-day LB and subsequent comment resolution
  Discuss contributions and eventually PDTs for R2 (expect to start around Oct-Nov’21)
    PDTs may be kept in a compendium of PDTs document (will not be part of D2.0, see next)
      POCs and TTTs responsible to stabilize their respective subclauses
    Guidelines/prioritization for discussing these documents are TBD
    ~5-6 months timeframe for working on these docs prior to next phase (see next)

## Slide 7: TGbe Documents: Status and Plan (3)
IEEE802.11be Drafts (pertinent to Release 2)
  Towards D3.0 - Nov’22 as in the approved TGbe Timeline
    WG LB followed by comment resolution
      Targeting R1 topics since there are no R2 features yet on this draft
      Possible to submit comments that pertain to R2 features (PDTs and such)
        Contents from PDTs on R2 features start to be added
    Comment resolution is expected to last 8 months
      Expect R1 features to be stable by now (WG LB & comment resolution)
      Expect R2 features and maintained in compendium of PDTs document
    Draft 3.0 is expected to contain both R1 and R2 features
  Towards D4.0, May 23 as in the approved TGbe Timeline
    Usual process

## Slide 8: 802.11be Selection Procedure Flow Chart
Flow chart with existing auxiliary steps shown below
  Refer to TGbe guidelines
Future auxiliary steps are shown above
Functional Requirements Document
Spec Framework text
Technical Contribution
75%
75%
Spec Framework document
Add to Spec
Framework?
Y
Adopt into
Draft?
Y
Detailed
Spec
text
75%
Y
TG or WG Letter Ballot
Spec Addresses
Spec Framework
And Ready for LB?
Compendium of SPs (75%)
Spec Text Volunteers And Status
Compendium of PDTs (75%)
75%
Spec
Text Contribution
Spec
Text Contribution
Release 2
Release 1