## Slide 1: Release Guidelines: An Overview
Date: 2021-01-01
Authors:
Alfred Asterjadhi, et. al.

## Slide 2: Introduction
TGbe agreed to a release-based approach during Jan 2020 F2F
  “Move to agree to define releases of features, and to prioritize contributions and decisions related to release in the agenda, as summarized below, starting with Release 1
    Release 1 Features are: 320 MHz, 4KQAM, Multiple RUs per STA, Multi-link operation and a low complexity AP coordination feature
    Candidate Release 2 Features: 16 spatial streams, HARQ, Additional multi-AP features (e.g. C-BF, JT), any other potential features in the scope of PAR (e.g. features for Time-sensitive networks)
  Notes:
    The specification of release 1 features needs to be ready and stable in 11be D1.0/D2.0 at the target dates.
    The specification of release 2 features needs to be ready and stable in 11be D3.0/D4.0 at the target dates.
    The discussion on release 2 features is still allowed during release 1 phase.
    ­All releases target increasing throughput and/or reducing worst case latency and/or improving power efficiency, as defined in the PAR”

## Slide 3: Projected TGbe Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 Letter Ballot May 2021
D2.0 LB Mar 2022
D3.0 LB Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024
* Short terms/intermediate targets: Deliver D0.3 in Jan 2021, and D0.4 in Mar 2021
We are here*
Stable Release 1 Features
Stable Release 2 Features

## Slide 4: 802.11be Selection Procedure Flow Chart
Flow chart below shows how technical contributions advance to spec text
  Taken from 11-19/559r1
Functional Requirements Document
Spec Framework text
Technical Contribution
75%
75%
Spec Framework document
Add to Spec
Framework?
Y
Spec
Text Contribution
Adopt into
Draft?
Y
Detailed
Spec
text
75%
Y
TG or WG Letter Ballot
Spec Addresses
Spec Framework
And Ready for LB?

## Slide 5: TGbe Documents: Status and Plan (1)
Specification Framework Document (1262r21)
  Status: Contains all technical concepts motioned to date (list of motions tracked by 1755r13)
    Motions on concepts for Release 1 tagged with R1 & motions on concepts for Release 2 tagged with R2
    Several Motions do not have explicit tags (tagging (R1 vs. R2) is being addressed in 997r78)
  Plan: Continue tracking all technical concepts with respective tags.
Compendium of SPs and potential changes to the SFD (566r99 & 1935r4)
  Status: Built on top of SFD and additionally contains all SPs that have RXed majority support
    These SPs are then converted to motions in pre-designated Joint conf calls (see guidelines)
    SPs on concepts for R1 are tagged with R1 and SPs on concepts for R2 are tagged with R2
  Plan: Continue tracking all technical concepts with respective tags.
TGbe Spec text volunteers and status (997r77)
  Status: Contains a table with the spec text volunteers, status updates, etc.
    Lists point of contacts (POCs) for each topic/subject, list of motions, R1/R2 classification, status, etc.
    Tracks proposed draft texts (PDTs) for populating the TGbe drafts
      PDTs related to R1 topics have been included in TGbe D0.1 and expected to be included in subsequent drafts
      No time is currently dedicated to PDTs for R2 features so they are on hold (see next slides)
  Plan: Continue tracking all topics and status, with respective tags.

## Slide 6: TGbe Documents: Status and Plan (2)
Towards TGbe D1.0 (next major milestone)–May 2021 [see Timeline]
  Motion for creating TGbe D0.3 scheduled during Joint call of Jan. 14, 2021
  Undergo a 14-day WG comment collection on TGbe D0.3 (start Jan. 20, 2021)
    Comments to target issues with the draft (except for TBDs), i.e., no new feature requests
    Comment discussion & assignment scheduled during Joint call of February 10, 2021
    Comment resolution is expected to end with the delivery of TGbe D1.0
      Unresolved/unexamined comments will be automatically rejected after May 13 2021 and can be submitted again later
    There shall be no motions to add to TGbe SFD for R1 after D0.3 is released
      I.e., work only on proposed draft spec texts (PDTs) for R1 concepts after D0.3
  Complete all TBDs that are present in the TGbe draft (usual process, PDTs, etc.)
    Plan is to have a TGbe D1.0 which does not have any TBDs
  D1.0: Approve coexistence assurance document (Sigurd)
Planned Motion Text for TGbe D1.0 (note that it will not be a letter ballot motion)
  Understanding that development of features for P802.11be is ongoing, are the features defined in P802.11be D1.0 complete?

## Slide 7: TGbe Documents: Status and Plan (3)
Towards TGbe D2.0–March 2022 as in the approved TGbe Timeline
  Undergo a WG comment collection on D1.0 (so far everything pertinent to R1)
    30-day comment collection and subsequent comment resolution
  Discuss contributions and PDTs for R2 (expect to start around Oct–Nov 2021)
    PDTs may be kept in a compendium of PDTs (will not be part of D2.0, see next)
      POCs and TTTs responsible to stabilize their respective subclauses
    Guidelines/prioritization for discussing these documents are TBD
    ~5-6 months timeframe for working on these docs prior to next phase (see next)
Motion for TGbe D2.0 (note that it will not be a letter ballot motion)
  Understanding that development of features for P802.11be is ongoing, are the features defined in P802.11be D2.0 complete?

## Slide 8: TGbe Documents: Status and Plan (4)
IEEE802.11be Drafts (pertinent to Release 2 as well)
  Towards D3.0–Nov 2022 as in the approved TGbe Timeline
    WG comment collection on D2.0 followed by comment resolution
      Targeting R1 topics since there are no R2 features yet on this draft
      Possible to submit comments that pertain to R2 features (PDTs and such)
        Contents from PDTs on R2 features start to be added in this round
    Comment resolution is expected to last 8 months
      Expect R1 features to be stable by now (WG CC & comment resolution)
      Expect R2 features and maintained in compendium of PDTs document
    Draft 3.0 is expected to contain both R1 and R2 features
Motion for D3.0 (note that this will be a letter ballot motion)
  Instruct the editor to generate TGbe Draft 3.0, and approve a 30 day Working Group Technical Letter Ballot asking the question “Should TGbe Draft 3.0 be forwarded to Sponsor Ballot?”

## Slide 9: TGbe Documents: Status and Plan (5)
Towards D4.0, May 2023 (see approved TGbe Timeline)
  Following the usual process

## Slide 10: 802.11be Selection Procedure Flow Chart
Flow chart with existing auxiliary steps shown below
  Refer to TGbe guidelines
Future auxiliary steps are shown above
Functional Requirements Document
Spec Framework text
Technical Contribution
75%
75%
Spec Framework document
Add to Spec
Framework?
Y
Adopt into
Draft?
Y
Detailed
Spec
text
75%
Y
TG or WG Letter Ballot
Spec Addresses
Spec Framework
And Ready for LB?
Compendium of SPs (75%)
Spec Text Volunteers And Status
Compendium of PDTs (75%)
75%
Spec
Text Contribution
Spec
Text Contribution
Release 2
Release 1

## Slide 11: LB vs WG CC Motion
A WG Letter Ballot (LB) Motion will read as follows:
  Instruct the editor to prepare TGbe Draft D1.0
  Approve a 30 day Working Group Technical Letter Ballot asking the question “Should TGbe Draft 1.0 be forwarded to Sponsor Ballot?”
A WC Comment Collection (CC) Motion will read as follows:
  Instruct the editor to prepare TGbe Draft D1.0
  Approve a 30 day Working Group Comment Collection asking the question” Understanding that development of features for P802.11be is ongoing, are the features defined in P802.11be D1.0 complete?”

## Slide 12: WG LB vs. WG CC: Considerations
Similarities
  A passed motion will generate a TGbe Draft 1.0
  Comments will be collected on D1.0 during the 30 day period
    TGbe will follow the same procedure for comment resolution for either LB or CC
  D1.0 will be liaised to external organizations
Differences
  WG members are required to vote on a WG LB
    No such requirement would be in place for a WG CC
  TGbe D1.0 will be available for purchase if WG LB passes (75% support); not available for purchase if WG LB fails
    D1.0 will not be available for purchase in the case of WG CC
  No changes to the TGbe timeline are needed if the motion is a WG LB
    Need to strikethrough “Letter Ballot” entries for TGbe D1.0 and TGbe D2.0 for CC path
    However, in both options the milestones and draft numbers will be unchanged (as they were agreed)
  A WG LB motion implies that the TG believes that the draft is complete
    No such implications for a WG CC

## Slide 13: Why using TGbe D1.0 versions
Comments were received that if WG CC option is followed then
  Instead of using D1.0 and D2.0 versions, the TG should continue using D0.X, such as D0.5, and so on, until TG believes the draft is ready for WG LB ( in which case create D1.0)
Reasons for using current versions plan (i.e., D1.0, D2.0, etc.)
  Integer based numbering is generally assigned to drafts that are considered stable
    Decimal point drafts generally used for intermediate releases (incorporating comment resolutions, etc.)
  Aligns IEEE standardization and Wi-Fi industry releases (see 2153r4)
  Aligns with Motion that the TG passed in January 2020 to create D1.0
    Ruled as a technical motion it passed with the following result:
      Y/N/A: 85/5/19
  There is no requirement that D1.0 must be sent out for a WG LB

## Slide 14: Moving Forward
SP1: Which option do you prefer for TGbe D1.0 and TGbe D2.0:
  Option 1: Run a Working Group Letter Ballot motion
  Option 2 Run a Working Group Comment Collection motion
Result: Option 1 42, Option 2 53, Abstain 18
Plan is to go with Option 2, for which we need to amend the timeline as shown in next slide and the motions for D1.0 and D2.0 be as follows:
  Instruct the editor to prepare TGbe Draft D1.0/D2.0
    Approve a 30-day Working Group Comment Collection* asking the question” Understanding that development of features for P802.11be is ongoing, are the features defined in P802.11be D1.0 complete?”
*The voting result of this WG comment collection (CC) will be one of the parameters considered by the TGbe group to determine the maturity of the TGbe draft

## Slide 15: Amended TGbe Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sept 2020
D1.0 Letter Ballot WG Comment Collection May 2021
D2.0 LB recirculation WG Comment Collection Mar 2022
D3.0 Letter Ballot recirculation Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024