## Slide 1: TGbc Closing Report
Date: 2021-01-15
Authors:

## Slide 2: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for January 2021.

## Slide 3: Meeting Goals & Accomplishments of the week
Goal for the week:
Progress with comment resolution
Accomplishments
Group met 4 times this week
Reviewed 97 comment resolutions
  56 comments resolved (motion passed)
  21 comments resolved (ready for motion)
  20 comments reviewed but need further discussion
D1.01 produced

## Slide 4: Plans for March 2021 & Upcoming Telcos
March 2021 meeting
Comment resolution from WG LB
Weekly Telcos until the March meeting
  Every Tuesday, 10:00h ET, 1 hour
  Already announced with 10-day notice to WG and TG reflector

## Slide 5: TGbc schedule (unchanged)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
May 2021 D2.0 WGLB Recirculation LB
November 2021 Form SB Pool
November 2021 MEC/MDR done
Jan 2022 Initial SB
May 2022 Recirculation SB
July 2022 Final WG/EC approval
September 2022 Revcom/SASB approval

## Slide 6: References
Agenda for this week: 11-20/1916
Meeting / Chair’s Slide Deck: 11-20/1992
Meeting minutes: 11-21/37
Snapshot Slide: 11-20/1993
Closing report: 11-20/1994
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135r0
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268