## Slide 1: IEEE 802.11 Plenary Mar 2021 IEEE 802.11 TGbd
Chair: Bo Sun (ZTE)
Vice Chair: Hongyuan Zhang (NXP),
Joseph Levy (InterDigital)
Secretary: Yan Zhang (NXP)
Tech Editor: Bahar Sadeghi (Intel)

## Slide 2: Closing Slides of TGbd for IEEE 802.11 Mar 2021 Interim
TGbd’s Progress in this week
  4 teleconference sessions were arranged in this week
  Approved TC minutes for TGbd sessions in Jan 2021 802.11 interim week and following TGbd TCs before this week.
  Approved CRs that have been presented since Jan 2021 802.11 interim week that got majority support. Totally 304 tech comments were resolved (including 120 approved in Jan).
  There’re still around 150 CIDs remaining unsolved and some comment resolution documents in the submission list not presented. Therefore the D2.0 milestone will be postponed to May 2021.
Goal for future TCs: complete comment resolutions for LB 251 (11bd D1.0)

## Slide 3: TGbd Progress Documents
TG Documents | Latest Revision
Definition and requirements | 11-19/0202r1
Selection Procedure document | 11-19/0030r6
Functional Requirement document | 11-19/0495r3
Spec Framework document | 11-19/0497r7
Liaison response to IEEE VT/ITS 1609 WG | 11-19/0437r3
Liaison response to ITU-T CITS | 11-19/0843r0
TBbd FRD/SFD Motion Booklet | 11-19/0514r14
TGbd Use Case document | 11-19/1342r1
Teleconference Agenda | 11-20/0774r10, 11-20/1164r7, 11-20/1352r9, 11-20/1561r7, 11-20/1806r2, 11-20/1891r0, 11-20/1923r11, 11-21/0177r2, 11-21/0207r6
Teleconference Minutes | 11-20/0276r11, 11-20/1105r8, 11-20/1489r1, 11-20/1655r3, 11-20/1775r1, 11-20/1907r1, 11-21/0068r0, 11-21/0117r0, 11-21/0327r0
Tech Editor Report | 11-19/2045r9 (D1.0)
Comment Database | 11-20/0701r7 (D0.3), 11-20/1887r5 (LB251)
Coexistence Assurance Document | 11-20/1564r2

## Slide 4: IEEE 802.11 TGbd Timeline
  PAR approved Dec 2018
  First TG meeting Jan 2019
  D0.1 Nov 2019
  D1.0 Letter Ballot Sep 2020  Oct 2020
  D2.0 LB recirculation Mar 2021  May 2021
  Form Sponsor Ballot Pool Jul 2021
  D3.0 LB recirculation Sep 2021
  D3.0 unchanged recirculation Sep 2021
  Initial Sponsor Ballot (D4.0) Nov 2021
  Final 802.11 WG approval Jul 2022
  802 EC approval Jul 2022
  RevCom and SASB approval Sep 2022
Note, the D2.0 LB recirculation is postponed to May 2021 while the future milestones are not changed

## Slide 5: IEEE 802.11 TGbd TC Plan
Mar 23rd, 10:00am ~ 11:59am, EDT; Webex
Mar 30th, 10:00am ~ 11:59am, EDT; Webex
Apr 6th, 10:00am ~ 11:59am, EDT; Webex
Apr 13th, 10:00am ~ 11:59am, EDT; Webex
Apr 20th, 10:00am ~ 11:59am, EDT; Webex
Apr 27th, 10:00am ~ 11:59am, EDT; Webex