## Slide 1: TGaz Next Generation Positioning May Electronic Meeting Closing Report
Date: 2021-05-17
Authors:

## Slide 2: Abstract
This document is the TGaz Next Generation Positioning closing report for the IEEE 802.11 interim electronic meeting, May 2021.

## Slide 3: May Progress and Targets Towards the July Meeting
Work completed:
  Reviewed/approved resolution to 36 CIDs.
Targets toward July:
  Complete LB253 comment resolution.
  Generate P802.11az D3.1 adopting resolutions from March and May meetings.
  Respond to MDR findings (Editors).

## Slide 4: Timeline – updated past May meeting
2021
2020
2019
2017
2018
2022
2023
.11az requirement freeze
5-2017
11az SFD
Amendment text
.11az Draft 2.0 11-2019
Recirculation
D1.0
Jan. 19
.11az D0.1 Mar. 18
5/17-3/21
July 18
Inter.
comment
collection
SFD
Final
Initial
WG ballot
CC28
LB240 CR
Initial WG ballot LB240 Pass
SFD Freeze
LB249
LB240 completion/
recirc. init
LB249 completion/
2nd recirculation
.11az Draft 3.0 01-2021
Recirculation
.11az Draft 4.0 07-2021
Recirculation
.11az MDR and SA ballots
07-2021
Publication
LB253
2nd SA
MDR
1st SA
Next
LB
Clean
No changes made, in preparation to SA ballot
1st SA comp.
2nd SA comp.

## Slide 5: LB253 – Completion Status

## Slide 6: Scheduled telecons
May 26* Wed. 13:00 – 15:00 ET
June 2, 9, 16, 23, 30 Wed. 13:00 – 15:00 ET
June 24 + Thur. 10:00 – 12:00 ET
July 7 Wed. 13:00 – 15:00 ET
*Previously announced.
**WG May meeting is running July 11th – 16th , refer to WG agenda doc.
+ TGaz Plenary (motion) meeting.