## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-21/690
Venue Date: | April 2021
First Author: | Michael Montemurro, Huawei
Subject: | REVme comments for SEC ad-hoc
Full Date: | 2021-04-28
Author(s): | Name(s) | Michael Montemurro
| Company | Huawei
Address
Phone:
Fax:
| email: | montemurro.michael@gmail.com
Abstract:
This document contains comments in the "SEC ad hoc" group, submitted on REVme initial comment collection

## Revision History
Revision | Date | Description
0 | 2021-04-19 | Initial revision
1 | 2021-04-28 | Updated with comment assignents

## All Comments
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
37 | David Goodall | 35 | 0 | 12.5.3.3.2 | 2572 | 38 | T | Y | 2572 | 38 | 12.5.3.3.2 |  |  | Nehru Bhandaru |  |  | The fixed version of PV1 CCMP in REVmd still has a potential security flaw due to CCM nonce reuse. From an email from Jouni: The language we use for enforcing unique PN values for the same TK, Priority pair is using "TID", not "PTID". As such, there might be a case where two different TID values (e.g., 1 and 9) getting mapped to the same PTID value (1). The current language would allow the same PN to be used for frames using those two TIDs and this would result in CCM nonce reuse and loss of CCMP security protection. I hope that no one would be allowing TIDs 9..15 to be used with PV1 QoS Data frames, but if those are allowed, we do need to fix this by modifying the rule on PN reuse to not allow reuse for same TK/PTID instead TK/TID. | As suggested by Jouni, change the sentence: "For PV1 MPDUs, the PN shall never repeat for a series of encrypted MPDUs using the same temporal key and TID/ACI." to: "For PV1 MPDUs, the PN shall never repeat for a series of encrypted MPDUs using the same temporal key and PTID/ACI." |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
45 | David Goodall | 35 | 0 | 12.5.3 | 2569 | 28 | T | Y | 2569 | 28 | 12.5.3 |  |  | Mark Rison |  |  | I'm not sure which section to make this comment. PV1 frame security does not cater for protected QoS management frames for a number of reasons: 1. There doesn't seem to be a default QMF policy for PV1 management frames, but I may have missed it. 2. The Packet Number creation/management for encrypted PV1 frames assumes a 12 bit sequence number. The sequence number for QMF is 10 bits and is a separate number space for each AC. 3. Base packet numbers for PV1 encryption are associated with keyid and PTID/ACI so it appears that two separate sequence number spaces, i.e. PV1 data and PV1 QMF at the same priority, could end up using the same BPN which I assume voids the security properties of the underlying cipher. | We can either address the points raised in the comment or put a note somewhere that PV1 management frames do not support QoS. |  | SEC |  | Submission Required | SEC: 2021-04-20 14:16:36Z - status set to: Submission Required |  |  |  | 2021-04-20 14:17 | SEC
116 | Jouni Malinen | 35 | 0 | 12.4.8.6.5 | 2554 | 14 | E | N | 2554 | 14 | 12.4.8.6.5 |  |  | Dan Harkins |  |  | SAE: "<verify X>. If not, <do Y>. If so, <do Z>" construction can be ambiguous since it is not always clear what "if so" is referring to (something in "verify X" vs. "do Y"). | Replace "If Sync is not greater than dot11RSNASAESync, the protocol instance shall verify that the finite cyclic group is the same as the previously received SAE Commit message. If not, the frame shall be silently discarded. If so, the protocol instance shall increment Sync, increment Sc, and transmit its SAE Commit message and its SAE Confirm message with the new Sc value." with "If Sync is not greater than dot11RSNASAESync, the protocol instance shall verify that the finite cyclic group is the same as the previously received SAE Commit message. If not, the frame shall be silently discarded. Otherwise, the protocol instance shall increment Sync, increment Sc, and transmit its SAE Commit message and its SAE Confirm message with the new Sc value." |  | SEC | [6 empty] | 2021-04-28 15:14 | SEC
117 | Jouni Malinen | 35 | 0 | 12.4.8.6.3 | 2552 | 29 | T | N | 2552 | 29 | 12.4.8.6.3 |  |  | Dan Harkins |  |  | Textual description of the SAE Nothing-to-Confirmed transmission does not match the state machine steps shown in Figure 12-4. The figure indicates that Sc is incremented (to 1) before constructing the Confirm message while the text seems to imply that Sc is only set to zero without incrementing. Figure 12-4 shows this as follows: zero(Sync),zero(Sc),zero(Rc),inc(Sc),1(0),2,set(t0). The text should match that. | Add "increment Sc" before construction of Commit and Confirm messages by replacing "If the group is supported, the protocol instance shall zero the Sc and Rc counters and it shall generate the PWE and the secret values according to 12.4.5.2 (PWE and secret generation). It shall then process the received SAE Commit message (see 12.4.5.4 (Processing of a peer's SAE Commit message)). If validation of the received SAE Commit message fails, the protocol instance shall send a Del event to the parent process; otherwise, it shall construct and transmit an SAE Commit message (see 12.4.5.3 (Construction of an SAE Commit message)) followed by an SAE Confirm message (see 12.4.5.5 (Construction of an SAE Confirm message))." with "If the group is supported, the protocol instance shall zero the Sc and Rc counters and it shall generate the PWE and the secret values according to 12.4.5.2 (PWE and secret generation). It shall then process the received SAE Commit message (see 12.4.5.4 (Processing of a peer's SAE Commit message)). If validation of the received SAE Commit message fails, the protocol instance shall send a Del event to the parent process; otherwise, it shall increment Sc, construct and transmit an SAE Commit message (see 12.4.5.3 (Construction of an SAE Commit message)) followed by an SAE Confirm message (see 12.4.5.5 (Construction of an SAE Confirm message))." |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
156 | Mark Hamilton | 35 | 0 | 12.4.7.4 | 2546 | 38 | T | Y | 2546 | 38 | 12.4.7.4 |  |  | Dan Harkins |  |  | It seems that the "method" is called "hash-to-curve" (per 12.4.4.2.3) or described as "direct hash[ing]", but "SAE hash-to-element" is the name of the capability to use this method. So, places like P2546.38 are using the inappropriate term. | Change "hash-to-element" to "hash-to-curve". Same change at P876.47. |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
163 | Mark RISON | 35 | 0 | 12.5.2.6 |  |  | T | N |  |  | 12.5.2.6 |  |  | Nehru Bhandaru |  |  | "For MSDUs sent using the block ack feature, reordering of received MSDUs according to the block ack receiver operation is performed prior to replay detection." -- TKIP is not allowed in 11n, so this cannot happen, unless this is referring to non-HT block ack, which no longer exists. Ditto "TKIP replay detection takes place after the MIC verification and any reordering required by ack processing." | Delete the cited texts, and change "Thus, a" to "A" |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
165 | Mark RISON | 35 | 0 | 12.6.1.1.1 | 2589 | 53 | T | N | 2589 | 53 | 12.6.1.1.1 |  |  | Dan Harkins |  |  | "The following types of security associations are supported by an RSNA STA:" is missing TPKSA | Add a bullet "TPKSA: A result of a successful TPK handshake" at the end of the list |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
166 | Mark RISON | 35 | 0 | 12.5 |  |  | T | N |  |  | 12.5 |  |  | Dan Harkins |  |  | The replay detection/protection subclauses don't cover TDLS direct links (that use a TPKSA not a PTKSA) | Extend 12.5.3.4.4 PN and replay detection [CCMP] and 12.5.5.4.4 PN and replay detection [GCMP] to mention TPKSA together with PTKSA and GTKSA |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
171 | Mark RISON | 35 | 0 | 12.5.3.4.4 |  |  | T | N |  |  | 12.5.3.4.4 |  |  | Nehru Bhandaru |  |  | It is not clear what replay counter to use for non-QoS Data frames. 5.1.1.3 suggests TID 0: "At QoS STAs associated in a QoS BSS, MSDUs with a priority of Contention are considered equivalent to MSDUs with TID 0." (this is perhaps tx not rx though) | At the end of item b) in 12.5.3.4.4 PN and replay detection and 12.5.5.4.4 PN and replay detection add "For the purposes of replay detection Data frames that have the QoS subfield of the Subtype subfield equal to 0 are treated as having TID 0.". At the start of each subclause change "To effect replay detection," to "To effect replay detection for (QoS) Data frames," |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
175 | Mark RISON | 35 | 0 | 12.4.3 |  |  | T | N |  |  | 12.4.3 |  |  | Dan Harkins |  |  | There are two references to "a non-NULL dot11RSNAConfigPasswordIdentifier" but this term is not defined here or in the MIB | Change each instance to "a dot11RSNAConfigPasswordIdentifier that does not have a zero length" and in C.3 show a DEFVAL of "{ }" for dot11RSNAConfigPasswordIdentifier |  | SEC | [6 empty] | 2021-04-28 17:21 | SEC
179 | Mark RISON | 35 | 0 | 12.7.6.8 | 2648 | 62 | T | N | 2648 | 62 | 12.7.6.8 | 180 |  | Mark Rison |  |  | "Message 3 differs from message 2 by not asserting the Ack bit and from message 4 by asserting the Ack Bit." -- asserting bits is not defined, the field is called Key Ack and Bit has the wrong capitalisation | Change to "Message 3 differs from message 2 by having the Key Ack bit of the Key Information field set to 0 and from message 4 by having the Key Ack bit set to 1." In 12.7.6.6 change "in which the Ack bit is 1" to "in which the Key Ack bit of the Key Information field is 1". In 12.7.10.3 change "have the Ack bit set to 1" to "have the Key Ack bit of the Key Information field set to 1" and "the Ack bit is 0" to "the Key Ack bit is 0" |  | SEC |  | Submission Required | SEC: 2021-04-20 14:25:36Z - status set to: Submission Required The CID is the same comment but CID 179 and CID 180 propose different resolutions. |  |  |  | 2021-04-20 14:26 | SEC
180 | Mark RISON | 35 | 0 | 12.7.6.8 | 2648 | 62 | T | N | 2648 | 62 | 12.7.6.8 | 179 |  | Mark Rison |  |  | "Message 3 differs from message 2 by not asserting the Ack bit and from message 4 by asserting the Ack Bit." -- wait, what, how can M3 differ from M2 by not asserting something and also from M4 by asserting the same thing? | Err, dunno. What is this trying to say? |  | SEC |  | Submission Required | SEC: 2021-04-20 14:24:11Z - status set to: Submission Required The CID is the same comment but CID 179 and CID 180 propose different resolutions. |  |  |  | 2021-04-20 14:26 | SEC
186 | Mark RISON | 35 | 0 | 12 | 2650 | 52 | T | N | 2650 | 52 | 12 |  |  | Mark Rison |  |  | It's not clear what to do in the handshakes if a verification fails. E.g. in 12.7.7.2 Group key handshake message 1 the e) might imply that you respond in any case. Should say ignore the received message if any verification step fails | Add an "Otherwise," at 2641.60, 2644.18, 2644.26. Also add some escape/otherwise words to the lettered list processes at the end of 12.7.6.4, 12.7.6.5, 12.7.7.2, 12.7.7.3 |  | SEC |  | Submission Required | SEC: 2021-04-20 14:25:57Z - status set to: Submission Required |  |  |  | 2021-04-20 14:26 | SEC
188 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Michael Montemurro |  |  | It's not sufficient to construct the message, you have to transmit it too! | Change "onstructs" to "onstructs and sends" at 2640.47, 2642.27. Change "creating" to "constructing" at 2650.52 |  | SEC | [6 empty] | 2021-04-20 15:30 | SEC
189 | Mark RISON | 35 | 0 | 12.7.7.2 | 2650 | 22 | T | N | 2650 | 22 | 12.7.7.2 |  |  | Michael Montemurro |  |  | For group key handshake M1, Key Data is specified to be "encrypted, encapsulated" but this is not done for 4WH M3 or indeed anywhere else | Delete "encrypted, encapsulated" at the referenced location |  | SEC | [6 empty] | 2021-04-20 15:30 | SEC
190 | Mark RISON | 35 | 0 | 12.7.6.5 | 2645 | 31 | T | N | 2645 | 31 | 12.7.6.5 |  |  | Mark Rison |  |  | If the Key Data is empty then the length is 0 and there's no meaning to saying it's encrypted | Either add a NOTE to explain what might be included even though Key Data is "none required" (and that the Encrypted Key Data = 1 is ignored in that case) or change line 17 to say Encrypted Key Data = 0, line 30 to say Key Data Length = 0 and line 31 to say Key Data = none |  | SEC |  | Submission Required | SEC: 2021-04-20 14:23:19Z - status set to: Submission Required |  |  |  | 2021-04-20 14:24 | SEC
191 | Mark RISON | 35 | 0 | 12.5.5.3.6 | 2586 | 40 | E | N | 2586 | 40 | 12.5.5.3.6 |  |  | Mark Rison |  |  | GCMP's version of CCMP's "A transmitter shall not use an IEEE 802.11 MSDU or A-MSDU priority if this would cause the total number of priorities used during the lifetime of the SA to exceed the number of replay counters supported by the receiver (for a pairwise SA) or all the receivers (for a group SA) for that SA. The transmitter shall not reorder CCMP protected frames that are transmitted to the same RA within a replay counter, but may reorder frames across replay counters. One possible reason for reordering frames is the IEEE 802.11 MSDU or A-MSDU priority." isn't as clear | Replace the para at the referenced location with the cited text, changing CCMP to GCMP |  | SEC | [6 empty] | 2021-04-28 15:03 | SEC
192 | Mark RISON | 35 | 0 |  |  |  | E | N | [5 empty] | Mark Rison |  |  | Vast swathes of CCMP and GCMP processing are the same | Extract the common parts, put them separately, and then have just the deltas specific to CCMP and GCMP separately |  | SEC |  | Submission Required | SEC: 2021-04-28 14:58:43Z - status set to: Submission Required |  |  |  | 2021-04-28 14:59 | SEC
193 | Mark RISON | 35 | 0 | 12.5.3.4.1 | 2577 | 30 | T | N | 2577 | 30 | 12.5.3.4.1 |  |  | Michael Montemurro |  |  | "The decryption processing prevents replay of MPDUs by validating that the PN in the MPDU is greater than the replay counter maintained for the session." should be ... "and TID" or "and AC" to allow for reordering across TIDs/ACs, where the receiver has indicated support for multiple replay counters (so maybe better as "(or the replay counter corresponding to the TID, if more than one replay counter is supported)" Or actually, since in 802.11 (unlike WMM) you allocate TIDs up to the max num replay counters supported, maybe just say "replay counter maintained for the session for that TID"?) | Change to "The decryption processing prevents replay of MPDUs by validating that the PN in the MPDU is greater than the replay counter maintained for the session for that TID." Ditto at 2587.36. At 2577.49 change "the PN in the CCMP header is greater than the replay counter maintained for the session and TID/ACI." to "the PN in the MPDU is greater than the replay counter maintained for the session for that TID." |  | SEC | [6 empty] | 2021-04-28 15:02 | SEC
199 | Mark RISON | 35 | 0 | 12.6.3 |  |  | T | N |  |  | 12.6.3 |  |  | Nehru Bhandaru |  |  | There is information on how MFP is negotiated for infrastructure BSS (Table 12-5--Robust management frame selection in an infrastructure BSS) and for IBSS (Table 12-6--Robust management frame selection in an IBSS) but not for TDLS. More generally, the use of MFP on a TDLS direct link is lacking (there's just "After receiving a Deauthentication frame or a Disassociation frame from the AP, a Deauthentication frame with Reason Code LEAVING_NETWORK_DEAUTH shall be transmitted via the direct path to all TDLS peer STAs that are in the awake state, if management frame protection has not been negotiated on the TDLS direct link." buried in 11.20.5 TDLS direct-link teardown) | Change "Table 12-6--Robust management frame selection in an IBSS" to "Table 12-6--Robust management frame selection in an IBSS or between TDLS peer STAs". In that table change "The peer STA shall not" to "The STA shall not". At 2598.50 change "An STA" to "A STA" and after that sentence add "A TDLS STA shall use Table 12-6 and the values of the MFPC and MFPR bits advertised in the RSNEs to determine if it may establish a TDLS link with another a TDLS peer STA." |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
200 | Mark RISON | 35 | 0 | 12.6.19 |  |  | T | N |  |  | 12.6.19 |  |  | Mark Rison |  |  | This subclause talks of "associated STA" but MFP can be used with IBSS and TDLS too | Change "associated STA" to "associated or peer STA" throughout this subclause |  | SEC |  | Submission Required | SEC: 2021-04-20 14:10:54Z - status set to: Submission Required |  |  |  | 2021-04-20 14:11 | SEC
202 | Mark RISON | 35 | 0 | 12.6.15 | 2608 | 49 | T | N | 2608 | 49 | 12.6.15 |  |  | Michael Montemurro |  |  | "If enabled, management frame protection shall only be used as a required feature (MFPR) in an IBSS." -- what does this mean? It might be trying to say that in an IBSS if you're going to do MFP you have to set MFPR, but that's contradicted by Table 12-6--Robust management frame selection in an IBSS. Even with the "only" (a word that always massively increases the risk of ambiguity) it's not clear what it might be trying to say | Delete the cited sentence |  | SEC | [6 empty] | 2021-04-20 15:30 | SEC
206 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Mark Rison |  |  | In some places the spec suggests it's sufficient for PN+nonce to differ, e.g.: CCM requires a fresh temporal key for every session. CCM also requires a unique nonce value for each frame protected by a given temporal key. Reuse of a nonce value with the same temporal key voids all security guarantees. increment the base PN so that the PN never repeats for the same temporal key and TID/ACI the PN shall never repeat for a series of encrypted MPDUs using the same temporal key and TID/ACI. but in other places it suggests the PN must never be reused, e.g.: Each transmitter shall maintain a single PN (48-bit counter) for each PTKSA and GTKSA(#59). Increment the PN, to obtain a fresh PN for each MPDU, so that the PN never repeats for the same temporal key. Is it just PN+nonce (or PN+nonce+AAD) that have to be unique, or strictly the PN itself? The former would allow a PN per UP on tx, for example, since the nonce contains the UP. | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:08:44Z - status set to: Submission Required |  |  |  | 2021-04-20 14:09 | SEC
208 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Mark Rison |  |  | Why is the UP in both the AAD and the nonce? See e.g. 12.5.3.3.3 Construct AAD and 12.5.3.3.4 Construct CCM nonce | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:08:23Z - status set to: Submission Required |  |  |  | 2021-04-20 14:08 | SEC
212 | Mark RISON | 35 | 0 | 12.5.3.3.4 | 2575 | 16 | T | N | 2575 | 16 | 12.5.3.3.4 |  |  | Michael Montemurro |  |  | "The Priority subfield shall be set to the priority value of the MPDU" is not clear (if the MPDU is a non-QoS Data frame or a Management frame) | Append "(see 12.5.3.3.1)" since this defines what is meant by "the priority value of the MPDU" |  | SEC | [6 empty] | 2021-04-28 15:01 | SEC
213 | Mark RISON | 35 | 0 | 12.7.2 | 2633 | 3 | T | N | 2633 | 3 | 12.7.2 |  |  | Mark Rison |  |  | The Length field in Figure 12-36--GTK KDE format is not defined. I suspect it's the Length in Figure 12-35--KDE format but then the formula doesn't work, because the OUI and Data Type fields already consume 4 octets from the Length | Change - 4 to -6 in F12-36, change the hyphen to a minus, and where F12-36 is referred to add " (where Length is the Length field in the KDE)"; ditto where F12-42 is referred to and where Figure 12-47 is referred to (and the hyphen->minus there) |  | SEC |  | Submission Required | SEC: 2021-04-20 14:22:54Z - status set to: Submission Required |  |  |  | 2021-04-20 14:23 | SEC
214 | Mark RISON | 35 | 0 | 12.5 |  |  | T | N |  |  | 12.5 |  |  | Mark Rison |  |  | It's not clear why the CCM nonce includes UP but the GCM nonce doesn't. Maybe it's because "the priority value of the MPDU" as used in CCM is a wide concept that covers e.g. 11ae? But then why isn't the UP needed in GCM too? | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:07:57Z - status set to: Submission Required |  |  |  | 2021-04-20 14:08 | SEC
215 | Mark RISON | 35 | 0 | 12.5 |  |  | T | N |  |  | 12.5 |  |  | Nehru Bhandaru |  |  | There are references to "Nonce field" in F12-21/28 and 12.5.3/5.3.4 but there is no such field, it's just an input to [CG]CM {en¦de}cryption | In 12.5.3.3.4 change "Nonce field" to "CCM nonce" (3x inc. caption). in 12.5.5.3.4 change "Nonce field" to "GCM nonce" (2x inc. caption) |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
217 | Mark RISON | 35 | 0 | 12.5.3.3.3 | 2573 | 47 | T | N | 2573 | 47 | 12.5.3.3.3 |  |  | Nehru Bhandaru |  |  | "QC - QoS Control field contains the MSDU priority, if present. The QC TID is used in the construction of the AAD. When in a non-DMG BSS and both the STA and its peer have their SPP A-MSDU Capable fields equal to 1, bit 7 (the A-MSDU Present field) is used in the construction of the AAD. The remaining QC fields are masked to 0 for the AAD calculation (bits 4 to 6, bits 8 to 15, and bit 7 when either the STA or its peer has the SPP A-MSDU Capable field equal to 0). When in a DMG BSS, the A-MSDU Present bit 7 and A-MSDU Type bit 8 are used in the construction of the AAD, and the remaining QC fields are masked to 0 for the AAD calculation (bits 4 to 6, bits 9 to 15)." is a bit ambiguous. "The remaining QC fields are masked to 0 for the AAD calculation (bits 4 to 6, bits 8 to 15, and bit 7 when either the STA or its peer has the SPP A-MSDU Capable field equal to 0)." only applies to non-DMG | Change to "QC - QoS Control field contains the MSDU priority, if present. The QC TID is used in the construction of the AAD. When in a non-DMG BSS, if both the STA and its peer have their SPP A-MSDU Capable fields equal to 1, the A-MSDU Present field is also used in the construction of the AAD. When in a DMG BSS, the A-MSDU Present field and A-MSDU Type field are also used in the construction of the AAD. The remaining QC fields are not used and are masked to 0 for the AAD calculation (for a non-DMG BSS, bits 4 to 6, bits 8 to 15, and bit 7 when either the STA or its peer has the SPP A-MSDU Capable field equal to 0; for a DMG BSS, bits 4 to 6 and bits 9 to 15)." |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
223 | Mark RISON | 35 | 0 | 12.7.8.2 | 2653 | 29 | T | N | 2653 | 29 | 12.7.8.2 |  |  | Mark Rison |  |  | "b) The AP's RSNE indicates that WEP-40 (OUI 00-0F-AC:1) or WEP-104 (OUI 00-0F-AC:5) are enabled as either pairwise or group cipher suites; [...] Violation of any of these cases would cause the TPK handshake to leak the TPK." -- if the issue is that WEP is no longer secure, then the same is true for TKIP (and indeed TKIP is explicitly banned in 12.7.8.4.2) | Add TKIP (00-0F-AC:2) to the list in b) |  | SEC |  | Submission Required | SEC: 2021-04-20 14:27:32Z - status set to: Submission Required |  |  |  | 2021-04-20 14:28 | SEC
224 | Mark RISON | 35 | 0 | 12.7.8.4 |  |  | T | N |  |  | 12.7.8.4 |  |  | Dan Harkins |  |  | There are no constraints on the cipher to use with TDLS, other than not using WEP or TKIP. Some recommendations should be given, specifically that it should be at least as strong as the cipher used with the AP | After the sentence starting "The pairwise cipher suite list field indicating " in 12.7.8.4.2 TPK handshake message 1 add "A pairwise cipher suite of key size smaller than that used on the connection between the STA and the AP should not be used." and after the sentence starting "If none of the pairwise cipher suites are acceptable" add "The TDLS responder STA should ignore any pairwise cipher suites of key size smaller than that used on the connection between the STA and the AP, and should reject the TDLS Setup Request frame with status code STATUS_INVALID_PAIRWISE_CIPHER if all the pairwise cipher suites are such.". In 12.7.8.4.3 TPK handshake message 2 after the sentence starting "Include a pairwise cipher suite" add "A pairwise cipher suite of key size smaller than that used on the connection between the STA and the AP should not be used." |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
225 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Mark Rison |  |  | Can non-QoS Data frames be encrypted with CCMP/GCMP (and TKIP) and if so what value is used for the priority (e.g. in the nonce/MIC), since at the MA SAP it might be "Contention"? | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:06:29Z - status set to: Submission Required |  |  |  | 2021-04-20 14:07 | SEC
239 | Mark RISON | 35 | 0 | 12.5 |  |  | T | N |  |  | 12.5 |  |  | Mark Rison |  |  | The replay detection/protection subclauses don't cover MBSS links (that use a Mesh TKSA and a Mesh GTKSA rather than a PTKSA and a GTKSA) | Extend 12.5.3.4.4 PN and replay detection [CCMP] and 12.5.5.4.4 PN and replay detection [GCMP] to mention Mesh TKSA and GTKSA together with PTKSA and GTKSA |  | SEC |  | Submission Required | SEC: 2021-04-20 14:06:57Z - status set to: Submission Required |  |  |  | 2021-04-20 14:07 | SEC
240 | Mark RISON | 35 | 0 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | A Mesh TKSA is pairwise and bidirectional, just like a PTKSA. So it would be better to call it a Mesh PTKSA | Change "esh TKSA" to "esh PTKSA" throughout |  | SEC |  | Submission Required | SEC: 2021-04-20 14:07:21Z - status set to: Submission Required |  |  |  | 2021-04-20 14:08 | SEC
260 | Mark RISON | 35 | 0 | 12.6.1.2 | 2594 | 33 | T | N | 2594 | 33 | 12.6.1.2 |  |  | Mark Rison |  |  | "The TPKSA consists of the following: -- MAC addresses of the TDLS initiator STA and the TDLS responder STA -- Pairwise cipher suite selector -- TPK Lifetime -- TPK" but TPK stands for TDLS PeerKey in Clause 3 rather than TDLS peer key, so it's not clear what TPK means here. Jouni has suggested by email that it consists of TPK-KCK and TPK-TK, which means it's a transient key like the PTK (so maybe it should be a TDLS PeerKey transient key = TPTK), but the fact that it's a transient key doesn't seem to be stated anywhere | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:21:04Z - status set to: Submission Required |  |  |  | 2021-04-20 14:21 | SEC
271 | Mark RISON | 35 | 0 | 12.6.1.1.6 | 2592 | 10 | T | N | 2592 | 10 | 12.6.1.1.6 |  |  | Michael Montemurro |  |  | "Authenticator MAC address or BSSID" -- when does the PTKSA include the BSSID rather than the Authenticator MAC address? | Delete "or BSSID", and also "or STA's MAC address" above |  | SEC | [6 empty] | 2021-04-20 15:30 | SEC
308 | Mark RISON | 35 | 0 | 12.3.1 | 2523 | 57 | T | N | 2523 | 57 | 12.3.1 |  |  | Michael Montemurro |  |  | "Open System Authentication and Open System Deauthentication shall not be used between mesh STAs." -- no such thing as OS deauth, and for auth the "A" should be lowercase | Change to "Open System authentication shall not be used between mesh STAs." |  | SEC | [6 empty] | 2021-04-20 15:30 | SEC
331 | Mark RISON | 35 | 0 | 12.4.4.2.3 | 2536 |  | T | N | 2536 |  | 12.4.4.2.3 |  |  | Dan Harkins |  |  | Is it "hash-to-element" or "hash-to-curve"? The former seems more popular | Change "ash-to-curve" to "ash-to-element" (5x on referenced page) |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
335 | Mark RISON | 35 | 0 | 12.11.2.3.3 | 2678 | 8 | T | N | 2678 | 8 | 12.11.2.3.3 |  |  | Mark Rison |  |  | "the EAP-Initiate/Reauth data" is not defined | Add a definition |  | SEC |  | Submission Required | SEC: 2021-04-20 14:27:51Z - status set to: Submission Required |  |  |  | 2021-04-20 14:28 | SEC
354 | Mark RISON | 35 | 0 | 12.5.1 | 2555 | 15 | T | N | 2555 | 15 | 12.5.1 |  |  | Michael Montemurro |  |  | "BIP is used only to protect Management frames within the BSS." -- does this mean "is not used to protect other frames" or "is not used to protect Management frames outside the BSS"? | Change to "BIP is not used to protect Management frames intended for members of the BSS." |  | SEC | [6 empty] | 2021-04-20 15:30 | SEC
355 | Mark RISON | 35 | 0 | 12.4.4.2.2 | 2534 | 23 | T | N | 2534 | 23 | 12.4.4.2.2 |  |  | Dan Harkins |  |  | "support for the SAE hash-to-element" -- for the SAE H2E what? Also in 12.4.4.3.2 | Add " technique" to the end of the cited text in both subclauses mentioned |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
356 | Mark RISON | 35 | 0 | 12.5.5.1 | 2583 | 54 | T | N | 2583 | 54 | 12.5.5.1 |  |  | Mark Rison |  |  | If "GCM also requires a unique nonce value for each frame protected by a given temporal key.", then then how does the GCM nonce achieve this? It just has the A2 and the PN, and doesn't have e.g. the TID+Management bits that ensure uniqueness in the CCM nonce | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:18:47Z - status set to: Submission Required |  |  |  | 2021-04-20 14:19 | SEC
357 | Mark RISON | 35 | 0 | 12.5.5.3.1 | 2585 | 10 | T | N | 2585 | 10 | 12.5.5.3.1 |  |  | Nehru Bhandaru |  |  | "Construct the GCM nonce block as defined in 12.5.3.3.4 (Construct CCM nonce)" -- xref should be to 12.5.5.3.4 | As it says in the comment |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
360 | Mark RISON | 35 | 0 | 12.5 |  |  | T | N |  |  | 12.5 |  |  | Nehru Bhandaru |  |  | For AAD construction, what is the difference between "not modified" and "not masked"? How does "masked to <n>" differ from "set to <n>" anyway? | In 12.5.3.3.3, 12.5.4.3, 12.5.3.3.1, 12.5.3.3.6, 12.5.4.5, 12.5.4.6, 12.5.5.3.1 change "masked to" to "set to" and "unmasked" to "not modified" (case-preservingly) |  | SEC |  | Submission Required | SEC: 2021-04-20 14:13:07Z - status set to: Submission Required |  |  |  | 2021-04-28 14:46 | SEC
364 | Mark RISON | 35 | 0 | 12.5.5.1 | 2583 | 40 | T | N | 2583 | 40 | 12.5.5.1 |  |  | Michael Montemurro |  |  | "A DMG RSNA STA shall support GCMP-128." -- a DMG STA is an RSNA STA, so "RSNA" is superfluous and misleading (suggests a DMG STA might not be an RSNA STA) | Delete "RSNA " |  | SEC | [6 empty] | 2021-04-20 15:30 | SEC
369 | Mark RISON | 35 | 0 | 12.5.4.6 | 2582 |  | T | N | 2582 |  | 12.5.4.6 |  |  | Dan Harkins |  |  | "silently drop" would imply that all the other unadorned "drop"s are to be done noisily | Delete "silently" (2x) |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
384 | Mark RISON | 35 | 0 | 12.6.1.1.10 | 2593 | 41 | T | N | 2593 | 41 | 12.6.1.1.10 |  |  | Nehru Bhandaru |  |  | "a wrapped MGTK" -- there is no reference anywhere else to MGTKs being wrapped | Describe how MGTKs are wrapped, or delete "wrapped" |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
387 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Mark Rison |  |  | REVmd CID 4049 resolution directs use of both 1 and 2 if pairwise is "use group" and group is CCMP. Jouni suggested during teleconf on 2020-06-12 that (a) that combination should not be allowed and (b) the 2 option should not allow "or group cipher" in the condition | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:09:12Z - status set to: Submission Required |  |  |  | 2021-04-20 14:09 | SEC
394 | Mark RISON | 35 | 0 | 12 |  |  | E | N |  |  | 12 |  |  | Mark Rison |  |  | ""The Wrapped Key field contains the encrypted GTK as described in 13.8.5 (FT authentication sequence: contents of fourth message)." v "The Wrapped Key field contains the wrapped IGTK being distributed."/" The Wrapped Key field contains the wrapped BIGTK being distributed." inconsistency | Make consistent |  | SEC | [6 empty] | 2021-04-28 14:58 | SEC
395 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Mark Rison |  |  | Is the MIC really always 16 octets for GCMP? For CCMP it's "variable" (compare the "Encapsulated GCMP/CCMP MPDU" figures) | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:09:31Z - status set to: Submission Required |  |  |  | 2021-04-20 14:10 | SEC
406 | Mark RISON | 35 | 0 | 12.7.2 | 2629 | 1 | T | N | 2629 | 1 | 12.7.2 |  |  | Mark Rison |  |  | "i) The value 1 shall be used for all EAPOL-Key frames to a STA when the negotiated AKM is 00-0F-AC:1 or 00-0F-AC:2 and the pairwise cipher is TKIP or "Use group cipher suite". In this case, the "Deprecated" row in Table 12-10 (Integrity and key wrap algo- rithms) is used. ii) The value 2 shall be used for all EAPOL-Key frames to a STA when the negotiated AKM is 00-0F-AC:1 or 00-0F-AC:2 and either the pairwise or the group cipher is an enhanced data cryptographic encapsulation mechanism other than TKIP. In this case, the matching row in Table 12-10 (Integrity and key wrap algorithms) is used." means you have to use both value 1 and value 2 if pairwise = "use group" and group = CCMP | Add a statement to say that the pairwise = "use group" and group = CCMP combination is not allowed |  | SEC |  | Submission Required | SEC: 2021-04-20 14:22:04Z - status set to: Submission Required |  |  |  | 2021-04-20 14:22 | SEC
408 | Mark RISON | 35 | 0 | 12.7.2 |  |  | E | N |  |  | 12.7.2 |  |  | Michael Montemurro |  |  | "into its IEEE 802.11 MAC" doesn't make sense, since an 802.1X component doesn't have an 802.11 MAC per se | Change to "into the IEEE 802.11 MAC" (3x) as in all the other locations |  | SEC | [6 empty] | 2021-04-28 14:59 | SEC
415 | Mark RISON | 35 | 0 | 12.6.1.1 |  |  | E | N |  |  | 12.6.1.1 |  |  | Mark Rison |  |  | 12.6.1.1.8: "The GTKSA results from a successful 4-way handshake, FT 4-way handshake, FT protocol, FT resource request protocol, (11ai)group key handshake, or FILS authentication(11ai)" but 12.6.1.1.1: "GTKSA: A result of a successful group key handshake, 4-way handshake, FT 4-way handshake, (11ai)FT authentication sequence, or FILS authentication(11ai)." -- the two sets differ (" FT protocol, FT resource request protocol" v. "FT authentication sequence" | Excise the spec rot, and stop it from reoccurring by removing the duplication |  | SEC |  | Submission Required | SEC: 2021-04-28 14:57:14Z - status set to: Submission Required |  |  |  | 2021-04-28 14:57 | SEC
418 | Mark RISON | 35 | 0 | 13.5.2 | 2698 | 45 | T | N | 2698 | 45 | 13.5.2 |  |  | Mark Rison |  |  | "The PTKSA is used to protect the subsequent reassociation transaction, including the optional RIC-Request." is not clear. Is it suggesting that the Reassociation Request/Response frames are encrypted or MICked? That's not possible, because they're not robust and they don't carry an MME either | Clarify what "protect" means here |  | SEC |  | Submission Required | SEC: 2021-04-20 14:28:19Z - status set to: Submission Required |  |  |  | 2021-04-20 14:28 | SEC
432 | Mark RISON | 35 | 0 |  |  |  | T | N | [5 empty] | Mark Rison |  |  | There are references to "enhanced data cryptographic encapsulation mechanisms" but this term is never actually defined. The examples seem to suggest it means "non-WEP". If so, just say that. If not, define | Change "enhanced data cryptographic encapsulation" case-insensitively to "RSNA" (4x in C4, 8x in C12) |  | SEC |  | Submission Required | SEC: 2021-04-20 14:14:29Z - status set to: Submission Required |  |  |  | 2021-04-20 14:15 | SEC
486 | Mark RISON | 35 | 0 | 12.5.3.3.3 | 2573 | 26 | T | N | 2573 | 26 | 12.5.3.3.3 |  |  | Nehru Bhandaru |  |  | "Subtype subfield (bits 4 5 6) in a Data frame masked to 0" is confusing because the Subtype subfield is b4-b7 | Change to "The 3 LSBs of the Subtype subfield (bits 4 5 6) in a Data frame masked to 0" |  | SEC | [6 empty] | 2021-04-28 14:46 | SEC
507 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Mark Rison |  |  | Message 1 uses the following values for each of the EAPOL-Key frame fields:" -- "Key Data = PMKID for the PMK being used during PTK generation" -- Jouni said in Vienna that it can contain other stuff, and that it should be referring to PMKID KDE. Also, should have general statement for all the Key Data = lines to say this is the minimum set of things that need to be included in the message, but other stuff (e.g. VS) may also be included | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:06:01Z - status set to: Submission Required |  |  |  | 2021-04-20 14:06 | SEC
535 | Mark RISON | 35 | 0 | 12 |  |  | T | N |  |  | 12 |  |  | Mark Rison |  |  | It is not clear whether the SME picks the Key ID for transmission of encrypted frames (using the Key ID parameter of the MLME-SETKEYS.request) or whether the MAC does so | As it says in the comment |  | SEC |  | Submission Required | SEC: 2021-04-20 14:05:16Z - status set to: Submission Required |  |  |  | 2021-04-20 14:05 | SEC
548 | Michael Montemurro | 35 | 0 | 12.7.6.1 | 2369 | 62 | T | Y | 2369 | 62 | 12.7.6.1 |  |  | Michael Montemurro |  |  | The notation used to describe the contents of the Key Data field in the 4-way handshake, group-key handshake, and FT protocol is cumbersome and poorly depicts the optional fields in the key data element. | Update the key data field description (i.e. notation) for EAPoL frames for the 4-way handshake, group-key handshake, and FT protocol. The commenter will provide a submission with a detailed resolution to this comment. |  | SEC |  | Submission Required | SEC: 2021-04-20 17:15:00Z - status set to: Submission Required |  |  |  | 2021-04-20 17:15 | SEC
587 | Thomas Derham | 35 | 0 | 12.6.3 | 2622 |  | T | Y | 2622 |  | 12.6.3 |  |  | Mark Rison |  |  | Unlike "AP MFPR", the value of "STA MFPR" (in RSNE sent by non-AP STA) does not affect the peer (AP) behavior if STA MFPC is 1. Clarify since it is a frequent source of confusion. | See comment |  | SEC |  | Submission Required | SEC: 2021-04-27 13:09:27Z - From email conversation: In 12.6.19 Protection of robust Management frames change “a STA that advertised MFPC = 1” to “any STA that advertised MFPC = 1” (for consistency with the other occurrences). In 12.6.20 Robust management frame selection procedure delete the first paragraph, “A STA with dot11RSNAProtectedManagementFramesActivated equal to true shall negotiate management frame protection with a STA that advertised MFPC = 1.”. Proposed resolution: REVISED Make the changes shown under “Proposed changes” for CID 587 in <this document>, which clarify the negotiation of MFP in an infrastructure BSS, including interoperation with pre-11w devices. Note to the commenter: yes, given the valid combinations of settings at the AP and the non-AP STA, the setting of the MFPR bit at the non-AP does not affect the AP behaviour. The changes make this clearer. |  |  |  | 2021-04-27 13:10 | SEC
588 | Thomas Derham | 35 | 0 | 12.4.8.6.2 | 2575 |  | T | Y | 2575 |  | 12.4.8.6.2 |  |  | Dan Harkins |  |  | In SAE (also FILS unless bound to rMSK lifetime), the maximum PMK lifetime (dot11RSNAConfigPMKLifetime) is not communicated to the peer. This can cause inefficiencies if STA attempts use of a cached PMK that has expired | Provide a (protected) way for the PMK lifetime to be indicated, at least for communication of AP's lifetime to the STA - e.g. using TIE with Key Lifetime |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
589 | Thomas Derham | 35 | 0 | 12.7.2 | 2621 |  | T | Y | 2621 |  | 12.7.2 |  |  | Dan Harkins |  |  | Key Data field in M1 and M2 "need not be encrypted" - be more precise about conditions under which it can be, or must be, encrypted | See comment |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
590 | Thomas Derham | 35 | 0 | 12.7.1.3 | 2641 |  | T | Y | 2641 |  | 12.7.1.3 |  |  | Dan Harkins |  |  | AKM 20 is PSK SHA-384 per Table 9-151. However per 12.7.1.3, it seems PMK_bits is 256. Should it be 384? | If intent is for PMK_bits to be 384 for this AKM, add the AKM to the corresponding sentence in 12.7.1.3. (Also check PTK length in 12.7.1.6.5) |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC
595 | Thomas Derham | 35 | 0 | 12.4.8.6.3 |  |  | T | Y |  |  | 12.4.8.6.3 |  |  | Dan Harkins |  |  | It is unclear whether the first Send Confirm value should be 0 or 1. 12.4.8.6.3 says Sc is reset and confirm is sent. 12.4.5.5 says message is constructed using current Sc (i.e. 0), but Figure 12-4 shows Inc(Sc) in transition from Nothing to Confirmed. | Clarify language and, to avoid making existing implementations non-compliant, allow either |  | SEC | [6 empty] | 2021-04-19 21:14 | SEC