## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-21/0724r2
Venue Date: | May 2021
First Author: | Nancy Lee, Signify
Subject: | Comments on P802.11bb/D0.4
Full Date: | 2021-05-10
Author(s): | Nancy Lee, Matthias Wendt
Signify
Address
Phone:
Fax:
nancy.lee@signify.com, matthias.wendt@signify.com
Abstract:
This submission contains comments on draft D0.4.
r2 adds additional comments and renumbers the comments to be in page order.

## comments against D0.4
CCI | Date | SA PIN | Name | Comment | Category | Page Number | Subclause | Line Number | Proposed Change | MBS | TG Decision | TE suggested action | Changes in the draft | Assigned to
1 |  |  | Matthias Wendt | Page numbers are missing | Editorial | 1 | all |  | add page numbers |  | accept | accept | done
2 |  |  | Matthias Wendt | line 2, "P802.11bb/D0.3, Draft" should be "P802.11bb/D0.4, Draft" | Editorial | 8 | Intoduction |  | correct in next draft |  | accept | accept | done, check again later as this field does not update with the rest of the document
3 |  |  | Nancy Lee | title "Amendment 6: Light Communicationsht Communications" is corrupted | Editorial | 10 | title | 2 | delete "ht Communications" |  | accept | accept | done
4 |  |  | Nancy Lee | I think red bold italics are intended for TGbb technical editor's notes, so no need for this statement in blue. | Editorial | 10 | Editorial Notes | 37 | delete note in blue and globally change all TGbb technical editor's notes (e.g., page 14 line 1) to use standard format (red bold italics and start with "Editor's Note:") |  | accept | accept | done
5 |  |  | Nancy Lee | This is an editing instruction (see p. 10 lines 5-12) incorrectly shown as an editorial note (see p. 10 lines 13-18) | Editorial | 12 | 2 | 2 | delete "Editor's Note:" and change to black bold italic |  | accept | accept | done
6 |  |  | Nancy Lee | This is an editing instruction incorrectly shown as an editorial note | Editorial | 12 | 3.1 | 7 | delete "Editor's Note:" and change to black bold italic |  | accept | accept | done
7 |  |  | Nancy Lee | This is an editing instruction incorrectly shown as an editorial note | Editorial | 12 | 3.2 | 13 | delete "Editor's Note:" and change to black bold italic |  | accept | accept | done
8 |  |  | Nancy Lee | This is an editing instruction incorrectly shown as an editorial note | Editorial | 12 | 3.4 | 20 | delete "Editor's Note:" and change to black bold italic |  | accept | accept | done
9 |  |  | Nancy Lee | This is an editing instruction incorrectly shown as an editorial note | Editorial | 13 | 4.3 | 3 | delete "Editor's Note:" and change to black bold italic |  | accept | accept | done
10 |  |  | Nancy Lee | LCO abbreviation is missing in list | Editorial | 14 | 31.3 | 5 | add to list on page 12, section 3.4 |  | accept | accept | done
11 |  |  | Nancy Lee | CM abbreviation is missing in list | Editorial | 14 | 31.3 | 3 | add to list on page 12, section 3.4 |  | accept | accept | done
12 |  |  | Nancy Lee | awkward wording (sounds a bit like there are three versions plus two options). "Options" is redundant here because optionality is covered in 32.1.1. | Editorial | 14 | 32.1 | 8 | change to "There are three versions of the LC PHY: the LC Common mode (CM) PHY, the LC High Efficiency (HE) PHY, and the LC Optimized mode PHY." |  | accept | accept | done
13 |  |  | Nancy Lee | IM/DD abbreviation is missing in list | Editorial | 14 | 32.1 | 10 | add to list on page 12, section 3.4 |  | accept | accept | done
14 |  |  | Nancy Lee | DL MU-MIMO is out of scope for LC (page 19 line 13 excludes MU-MIMO) | Editorial | 15 | 32.3.1 | 20 | change as shown: "a PSDU (in the SU case) or one or multiple PSDUs (in the MU-MIMO downlink) are processed" |  | accept | accept | done
15 |  |  | Nancy Lee | wavelength range of 800-1000 nm for LC CM and LC HE modes, but 380-1000 nm for LCO mode (see p. 16 line 1) | Technical | 15 | 32.3.2 | 26 | Consider harmonizing or adding text to explain the reason for the difference |  | reject | not actionable at this time
16 |  |  | Nancy Lee | Unnecessary restriction to BPSK and code rate 1/2. This might be acceptable if CM PHY was restricted to the initial association phase, but there's no such restriction. This restriction could lead to excessive occupation of the medium. Better to allow all modulation and coding supported by the OFDM PHY and let implementations decide on the best tradeoff between reliability and speed. | Technical | 15 | 32.3.2 | 27 | Refer LC Common mode to Clause 17 (OFDM) to enable other modulation and coding; a basic LC implementing LC CM should be similar to a Wi-Fi device implementing OFDM PHY (802.11a) |  | revise, replace P15L26-29 in the draft D0.4 by P2L17-20 in 11-21-0905-02 | replace P15L26-29 in the draft D0.4 by P2L17-20 in 11-21-0905-02 | done
17 |  |  | Nancy Lee | 1024-QAM should also be allowed. Per 4.3.15a (High efficiency (HE) STA), support for HE-MCSs 10 and 11 (i.e., 1024-QAM) is optional. The same should apply to LC HE. (A STA reports which HE-MCSs is supports using 9.4.2.248.4 Supported HE-MCS And NSS Set field) | Technical | 15 | 32.3.2 | 32 | change "and 256-QAM" to ", 256-QAM and 1024-QAM" |  | accepted |  | done
18 |  |  | Nancy Lee | Add a note to LC beamforming | Technical | 19 | 32.3.4.2 | 16 | Add after line 16: "Note: LC supporting MIMO with separate spatial streams is out of scope of this specification." |  | accepted |  | done.
19 |  |  | Nancy Lee | use consistent spelling of TBD to allow easy global search for TBDs | Editorial | 19 | 32.3.3.4.5 | 2 | remove highlighting and change "T.B.D." to "TBD" in red |  | accept |  | already resolved by including text from 11-21/0813r1.
20 |  |  | Nancy Lee | It is unclear what is meant by multiple transmitters and receivers in this context; Are they independent data streams or same stream transmitted via several optical front-ends? Are the optical front-ends spatially separated or not? | Technical | 20 | 32.3.5.2.2 | 12 | Fig 3 and 4 are both confusing. Suggest to delete entire 32.3.5.2.2 |  | reject | discuss this in the framework of fronthaul where MIMO makes a lot more sense
21 |  |  | Nancy Lee | I guess it should be "an" and not "and" | Editorial | 20 | 32.3.5.2.2 | 7 | replace with "an" |  | accept | accept | done.
22 |  |  | Nancy Lee | "centre frequencies" spelling | Editorial | 21 | 32.3.5.2.3 | 4 | change to "center frequencies" |  | accept | accept | done.
23 |  |  | Nancy Lee | all previous 802.11 PHYs specify channels using formulas not a table | Technical | 21 | 32.3.5.2.3 | 4 | delete table 2 and replace with a formula similar to 19.3.15.3 (Channel allocation in the 5 GHz band), i.e.,: "the set of valid operating channel numbers is defined in Annex E." allocation for each band is defined as follows: channel center frequency = channel starting frequency + 5 * nch (MHz) where nch = 1, …, 61 channel starting frequency = 21 MHz" this resolves the Word comments on p. 50 and the Editor's note on p. 50 line 7, so these can be deleted |  | accepted |  | done.
24 |  |  | Nancy Lee | row for channel number 31 in Table 2 is incomplete | Editorial | 22 | 32.3.5.2.3 | 0 | delete the row, since 320 MHz channels are not supported |  | accept | accept | resolved with CID 25 (deleted table 2)
25 |  |  | Nancy Lee | editor's note doesn't apply here and is not needed because it's already done in Annex E | Editorial | 22 | 35.3.5.2.3 | 2 | delete lines 2-6 |  | accept | accept | done
26 |  |  | Nancy Lee | "The LC HE PMLE is should be the same as section 27.4 except the following changes." | Technical | 22 | 32.3.5.3 | 17 | change as shown |  | revise, change sentence to: "The LC HE PLME shall be the same as section 27.4 except the following changes." |  | done
27 |  |  | Nancy Lee | txt calls for a new value of dot11PHYType but this is not defined yet. | Editorial | 23 | 32.3.5.3 | 1 | add an editor's note with TBD |  | accept | accept | done
28 |  |  | Nancy Lee | Having a single PHY dot11PHYType for 3 different modes will not work. | Technical | 23 | 32.3.5.3 | 1 | have separate dot11PHYType values for each LC PHY mode. |  | revise, replace P22L19--P23L2 by P2L35-37 in 11-21-0905-02 | replace P22L19--P23L2 by P2L35-37 in 11-21-0905-02 | needs clarification, what is meant by P22L19-P23L1
29 |  |  | Nancy Lee | second initialization procedure is rendered meaningless by saying the initialization bits "may be" set to the value of SI. Compare to G.9960 7.1.3.1 (Scrambling). | Technical | 25 | 32.3.6.2 | 3 | change to "For the second initialization, the first four bits of the LFSR (C1 to C4) shall be set to the value of the SI (scrambler initialization) field, while all other bits C5 to C23 shall be initialized to 1. The value of SI = C4C3C2C1 is communicated in the header as described in 32.3.6.11.2. The first bit to be scrambled..." |  | reject | withdrawn by commenter
30 |  |  | Nancy Lee | the value "016" for SI doesn't make sense for a 4-bit field. | Technical | 25 | 32.3.6.2 | 6 | change to "0000" |  | accepted | check against latest version of G.9960 (Volker) | done, is own text anyway
31 |  |  | Nancy Lee | editor's note not needed because it's already done in Table 12 | Editorial | 40 | 32.3.6.11.2 | 15 | delete "Editor’s Note: Please, insert the highlighted reference in the last row, right column of Table 12. It is linked to Clause 15.3.3.7 in 802.11REVmd/D5.0." |  | accept | accept | done
32 |  |  | Nancy Lee | B4-B25 is not 20 bits | Editorial | 41 | 32.3.6.11.2 | Table 12, B4-B25 | Delete "20" or change to "22" in column "Number of bits" |  | accept | accept | done
33 |  |  | Nancy Lee | 802.11 style doesn't use quotes around values | Editorial | 41 | 32.3.6.11.2 | Table 12, B26 | change to: "If EHI=0, the PHY header contains PHYH information bits. If EHI=1, the PHY header contains 2×PHYH information bits." |  | accept | accept | done
34 |  |  | Nancy Lee | For HSE, Header Segmentation Indication should be abbreviated HSI | Editorial | 41 | 32.3.6.11.2 | Table 12, B27 | change HSE to HSI |  | accept | accept | done
35 |  |  | Nancy Lee | For HSE, number of bits is missing | Editorial | 41 | 32.3.6.11.2 | Table 12, B27 | Add "1" in column "Number of bits" |  | accept | accept | done
36 |  |  | Nancy Lee | For HSE, description doesn't specify encoding | Technical | 41 | 32.3.6.11.2 | Table 12, B27 | Change description to: "If HSE="1", Header is spread over two symbols." |  | accepted |  | done
37 |  |  | Nancy Lee | for FEC Rate, number of bits missing in table | Editorial | 41 | 32.3.6.11.2 | Table 12, B50-B52 | add "3" in column "Number of bits" |  | accept | accept | done
38 |  |  | Nancy Lee | For FEC Rate, description doesn't specify encoding. Compare to G.9960 Table 7-12 (Interpretation of the FEC_RATE field). | Technical | 41 | 32.3.6.11.2 | Table 12, B50-B52 | specify coding for the values listed in Table 5 on p. 28 (1/2, 2/3, 5/6, 16/18, 20/21). |  | reject | withdrawn by commenter
39 |  |  | Nancy Lee | for FCF, number of bits missing in table | Editorial | 41 | 32.3.6.11.2 | Table 12, B56-B58 | add "3" in column "Number of bits" |  | accept | accept | done
40 |  |  | Nancy Lee | For FCF, description doesn't specify encoding. Compare to G.9960 Table 7-9 (FEC concatenation factor (FCF) allowed values). | Technical | 41 | 32.3.6.11.2 | Table 12, B56-B58 | Description points to 32.2.6.13.1 but 32.2.6.13.1 doesn't specify encoding for the FCF field. |  | reject | withdrawn by commenter
41 |  |  | Nancy Lee | for SI, number of bits missing in table | Editorial | 41 | 32.3.6.11.2 | Table 12, B59-B62 | add "4" in column "Number of bits" |  | accept | accept | done
42 |  |  | Nancy Lee | For SI, description is incomplete. Compare with G.9960 section 7.1.2.3.2.2.6 (Scrambler initialization (SI)). | Technical | 41 | 32.3.6.11.2 | Table 12, B59-B62 | Change to "If SI = "0000", the scrambler is not re-initialized between the header and payload. Otherwise, the SI field comprises…" |  | reject | withdrawn by commenter
43 |  |  | Nancy Lee | for reserved, number of bits missing in table | Editorial | 41 | 32.3.6.11.2 | Table 12, B63 | add "1" in column "Number of bits" |  | accept | accept | done
44 |  |  | Nancy Lee | not in the style for internal cross-references | Editorial | 42 | 32.3.6.11.2 | 1 | remove yellow highlighting and change "15.3.3.7" to "15.3.3.7 (PHY CRC field)" |  | accept | accept | done
45 |  |  | Nancy Lee | missing Annex C changes for the new value(s) of dot11PHYType | Technical | 49 | Annex D | 1 | as an example (depends on resolution of comments on page 23 line 1) insert Annex C.3 (MIB Detail) that contains: Change dot11PHYType as follows: dot11PHYType OBJECT-TYPE SYNTAX INTEGER { fhss(1), dsss(2), irbaseband(3), ofdm(4), hrdsss(5), erp(6), ht(7) dmg(8), vht(9), tvht(10), s1g(11), cdmg(12), cmmg(13), he (14), lco (15) } MAX-ACCESS read-only STATUS current DESCRIPTION "This is a status variable. It is written by the PHY. This is an 8-bit integer value that identifies the PHY type supported by the attached PLCP and PMD. Currently defined values and their corresponding PHY types are: FHSS 2.4 GHz = 01, DSSS 2.4 GHz = 02, IR Baseband = 03, OFDM = 04, HRDSSS = 05, ERP = 06, HT = 07, DMG = 08, VHT = 09, TVHT = 10, S1G = 11, CDMG = 12, CMMG = 13, HE = 14, LCO = 15" ::= { dot11PhyOperationEntry 1 } |  | revise as "insert Annex C.3 (MIB Detail) that contains: Change dot11PHYType as follows: dot11PHYType OBJECT-TYPE SYNTAX INTEGER { fhss(1), dsss(2), irbaseband(3), ofdm(4), hrdsss(5), erp(6), ht(7) dmg(8), vht(9), tvht(10), s1g(11), cdmg(12), cmmg(13), he (14), lco (15) } MAX-ACCESS read-only STATUS current DESCRIPTION "This is a status variable. It is written by the PHY. This is an 8-bit integer value that identifies the PHY type supported by the attached PLCP and PMD. Currently defined values and their corresponding PHY types are: FHSS 2.4 GHz = 01, DSSS 2.4 GHz = 02, IR Baseband = 03, OFDM = 04, HRDSSS = 05, ERP = 06, HT = 07, DMG = 08, VHT = 09, TVHT = 10, S1G = 11, CDMG = 12, CMMG = 13, HE = 14, LCO = 15" ::= { dot11PhyOperationEntry 1 }" |  | not clear what was the difference to CID46
46 |  |  | Nancy Lee | This is an editing instruction incorrectly shown as an editorial note. Editing instructions are relative to the existing base standard and thus should not specify a draft version of the base standard. | Editorial | 49 | D.1 | 4 | as an example (depends on resolution of comments on page 23 line 1) insert Annex C.3 (MIB Detail) that contains: Change dot11PHYType as follows: dot11PHYType OBJECT-TYPE SYNTAX INTEGER { fhss(1), dsss(2), irbaseband(3), ofdm(4), hrdsss(5), erp(6), ht(7) dmg(8), vht(9), tvht(10), s1g(11), cdmg(12), cmmg(13), he (14), lc (15) } MAX-ACCESS read-only STATUS current DESCRIPTION "This is a status variable. It is written by the PHY. This is an 8-bit integer value that identifies the PHY type supported by the attached PLCP and PMD. Currently defined values and their corresponding PHY types are: FHSS 2.4 GHz = 01, DSSS 2.4 GHz = 02, IR Baseband = 03, OFDM = 04, HRDSSS = 05, ERP = 06, HT = 07, DMG = 08, VHT = 09, TVHT = 10, S1G = 11, CDMG = 12, CMMG = 13, HE = 14, LC = 15" ::= { dot11PhyOperationEntry 1 } |  | accept | accept | done. verify chainges versus REVme005 on p.4159, as yellow marked entries are different.
47 |  |  | Nancy Lee | This is an editing instruction incorrectly shown as an editorial note. Editing instructions are relative to the existing base standard and thus should not specify a draft version of the base standard. | Editorial | 50 | E.1 | 4 | delete "Editor's Note:" and change to black bold italic. Also delete "of 802.11me/D0.0" |  | accept |  | done
48 |  |  | Nancy Lee | last row (320 MHz) is not yet supported | Editorial | 50 | E.1 | 6 | in last row, delete "0.021, 320, 31" and change "Near Infrared" to "Reserved for Near Infrared" |  | accept | accept | done