## Summary Stats
CID RESOLUTION STATUS 2021-04-29: Based on LB253 Database Snapshot 11-21/286r3
Comment Type | Ballot Total | MAR | APR | MAY | JUN | JUL | AUG | OCT | NOV | JAN | TOTAL Motioned
Technical | 256 | MAR: 63 | 63
General | 2 | [9 empty] | 0
Editorial | 218 | MAR: 10 | 10
TOTAL | 476 | MAR: 73 | 73
PLAN for D4.0 | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Goal | 476 JUL: D4.0: Ballot by end Aug
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | MOTION DUPs | STRAW ONLY | STRAW DUPs | TODO
Technical CIDS | 53 | 203 | 63 | 193 | 0 | 0 | 0 | 193
General CIDs | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2
Editorial CIDs | 208 | 10 | 10 | 208 | 0 | 0 | 0 | 208
Includes Withdrawn CIDs as Rejects
Note on H14: Roy Want: 2 CIDs were Sped on existing motion: AK(3209)

## CID Leaderboard
TECH CID Resolver | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Nehru Bhandaru | MAR: 33 | 33 | 38 | 5 | 0 | 0 | 0 | 5
Assaf Kasher | MAR: 15 | 15 | 19 | 4 | 0 | 9 | 0 | -5
Christian Berger | MAR: 15 | 15 | 21 | 6 | 0 | 1 | 0 | 5
Jonathan Segev | [10 empty] | 9 | 9 | 0 | 7 | 0 | 2
Steve Shellhammer | [10 empty] | 6 | 6 | 0 | 0 | 0 | 6
Qi Wang | [10 empty] | 7 | 7 | 0 | 0 | 0 | 7
Tianyu Wu | [10 empty] | 10 | 10 | 0 | 0 | 0 | 10
Ali Rasissini | [10 empty] | 26 | 26 | 0 | 27 | 0 | -1
Erik Lindskog | [10 empty] | 32 | 32 | 0 | 0 | 0 | 32
Dibakar Das | [10 empty] | 35 | 35 | 0 | 0 | 0 | 35
Ganesh Venkatesan | [11 empty] | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [11 empty] | 0 | 0 | 0 | 0 | 0
Girish Madpuwar | [11 empty] | 0 | 0 | 0 | 0 | 0
Yongho Seok | [11 empty] | 0 | 0 | 0 | 0 | 0
Feng Jiang | [11 empty] | 0 | 0 | 0 | 0 | 0
ChaoChun | [11 empty] | 0 | 0 | 0 | 0 | 0
Roy Want | [11 empty] | 0 | 0 | 0 | 0 | 0
Qinghua Li | [11 empty] | 0 | 0 | 0 | 0 | 0
Jerome Henry | [11 empty] | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 203 | 140 | 0 | 44 | 0 | 96
[10 empty] | UNASSIGNED | 53 |  |  |  | NET TODO= | 149
USE TABLE BELOW IN FINAL PHASE OF COMMENT RESOLUTION | [14 empty] | MONTHLY | 37.25 | bar: MAR to SEP
NAME | MAR: T#; APR: E#; MAY: G#; JUN: G&E List TODO |  | T-CIDs List TODO
Nehru Bhandaru | MAR: 0; APR: 0; MAY: 0
Feng Jiang | MAR: 0; APR: 0; MAY: 0
ChaoChun | MAR: 0; APR: 0; MAY: 0
Roy Want | MAR: 0; APR: 0; MAY: 0
Niranjan Grandhe | MAR: 0; APR: 0; MAY: 0
Qinghua Li | MAR: 0; APR: 0; MAY: 0
Jonathan Segev | MAR: 0; APR: 0; MAY: 0
Yongho Seok | MAR: 0; APR: 0; MAY: 0
Ali Raissinia | MAR: 0; APR: 0; MAY: 0
Assaf Kasher | MAR: 0; APR: 0; MAY: 0
Girish Madpuwar | MAR: 0; APR: 0; MAY: 0
Dibakar Das | MAR: 0; APR: 0; MAY: 0
Erik Lindskog | MAR: 0; APR: 0; MAY: 0
Jerome Henry | MAR: 0; APR: 0; MAY: 0 | [8 empty] | 14 | 5
Ganesh Venkatesan | MAR: 0; APR: 0; MAY: 0
Qi Wang | MAR: 0; APR: 0; MAY: 0
Christian Berger | MAR: 0; APR: 0; MAY: 0
Steve Shellhammer | MAR: 0; APR: 0; MAY: 0
Tianyu Wu | MAR: 0; APR: 0; MAY: 0
WITHDRAWN | MAR: 0; APR: 0; MAY: 0
UNASSIGNED | MAR: 0; APR: 0; MAY: 0
TOTAL | MAR: 0; APR: 0; MAY: 0
TOTAL-WITHDRAWN | MAR: 0; APR: 0; MAY: 0

## Motions
DB Action | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | #STR Ed | #STR Gen | #STR Tech | CIDs
MAR | [14 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
N/A | 202101-01 | 2021-03-09 | 72r0 | Assaf Kasher | November Ad Hoc Minutes |  |  |  | 0 | 0 | 0 |  |  |  | TGaz January 2021 interim minutes
N/A | 202001-02 | 2021-03-09 | 1986r1 | Assaf Kasher | November Minutes |  |  |  | 0 | 0 | 0 |  |  |  | TGaz Nov 2020 - Jan 2021 minutes
| 202101-03 | 2021-03-09 | 291r4 | Nehru Bhandaru |  |  |  |  | 33 | 0 | 10 |  |  |  | 5018, 5019, 5030, 5031, 5085, 5086, 5144E, 5263, 5268, 5276, 5292E, 5299, 5300, 5301, 5302, 5303, 5304, 5305E, 5306, 5307, 5308, 5337E, 5338E, 5339E, 5340E, 5357E, 5358, 5359, 5360, 5362, 5363, 5370, 5371E, 5372E, 5374, 5394, 5398, 5401, 5403, 5445, 5453, 5455, and 5456 ( 43 CIDs total)
| 202001-04 | 2021-03-09 | 346r2 | Assaf Kasher |  |  |  |  | 15 | 0 | 0 |  |  |  | 5109, 5111, 5440, 5441, 5442, 5443, 5114, 5115, 5395, 5281, 5286, 5397, 5402, 5136, 5149 (15 CIDs total)
| 202101-05 | 2021-03-10 | 307r3 | Christian Berger |  |  |  |  | 4 | 0 | 0 |  |  |  | 5088, 5454, 5193, and 5175 (4 CIDs total)
| 202001-06 | 2021-03-10 | 318r2 | Christian Berger |  |  |  |  | 11 | 0 | 0 |  |  |  | 5204, 5072, 5205, 5207, 5404, 5405, 5214, 5215, 5216, 5217 and 5151 (11 CIDs total)
APR
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
| TOTAL |  |  |  |  | 0 | 0 | 0 | 63 | 0 | 10 | 0 | 0 | 0
20
14