## Summary Stats
CID RESOLUTION STATUS 2021-07-19: Based on LB253 Database Snapshot 11-21/286r6 + July Motions
Comment Type | Ballot Total | MAR | APR | MAY | JUN | JUL | AUG | OCT | NOV | JAN | TOTAL Motioned
Technical | 256 | MAR: 63; APR: 40; MAY: 32; JUN: 3; JUL: 120 | 258 | (2 DUPLICATES)
General | 2 | JUL: 2 | 2
Editorial | 218 | MAR: 10; APR: 4; MAY: 13; JUN: 9; JUL: 182 | 218
TOTAL | 476 | MAR: 73; APR: 44; MAY: 45; JUN: 12 | 478
PLAN for D4.0 | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Goal | JUL: D4.0: Ballot out of July meeting
SUMMARY | NOT ASSIGNED | ASSIGNED | MOTIONED | NOT MOTIONED | TODO
Technical CIDS | 0 | 256 | 256 | 0 | 0
General CIDs | 0 | 2 | 2 | 0 | 0
Editorial CIDs | 0 | 218 | 218 | 0 | 0
Includes Withdrawn CIDs as Rejects

## CID Leaderboard
TECH CID Resolver | MAR | APR | MAY | JUN | JUL | AUG | SEP | TOTAL Motions | Total Assigned | Total Outstanding | Duplicates | Strawpolled | Withdrawn | TODO | Explanation: Additions to Outstanding [motions only]
Assaf Kasher | MAR: 15; APR: 8; JUL: 22 | 45 | 45 | 0 | 0 | 0 | 0 | 0
Nehru Bhandaru | MAR: 32; MAY: 4; JUL: 4 | 40 | 40 | 0 | 0 | 0 | 0 | 0
Erik Lindskog | JUL: 34 | 34 | 34 | 0 | 0 | 0 | 0 | 0
Dibakar Das | MAY: 9; JUL: 23 | 32 | 32 | 0 | 0 | 0 | 0 | 0
Ali Rasissini | APR: 27; MAY: 3; JUL: 1 | 31 | 31 | 0 | 0 | 0 | 0 | 0
Christian Berger | MAR: 15; APR: 1; MAY: 2; JUL: 2 | 20 | 20 | 0 | 0 | 0 | 0 | 0
Jonathan Segev | APR: 3; JUL: 15 | 18 | 18 | 0 | 0 | 0 | 0 | 0
Tianyu Wu | JUN: 2; JUL: 10 | 12 | 12 | 0 | 0 | 0 | 0 | 0
Youhan Kim | MAY: 9; JUL: 1 | 10 | 10 | 0 | 0 | 0 | 0 | 0
Qi Wang | JUL: 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
Steve Shellhammer | MAY: 5; JUN: 1 | 6 | 6 | 0 | 0 | 0 | 0 | 0
Ganesh Venkatesan | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Niranjan Grandhe | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Girish Madpuwar | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Yongho Seok | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Feng Jiang | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
ChaoChun | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Roy Want | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Qinghua Li | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
Jerome Henry | [7 empty] | 0 |  | 0 | 0 | 0 | 0 | 0
TOTAL TECH CIDS | 62 | 39 | 32 | 3 | 120 | 0 | 0 | 256 | 256 | 0 | 0 | 0 | 0 | 0
[8 empty] | UNASSIGNED | 0 |  |  |  | NET TODO= | 0
Negative likely indicates a duplicate resolution

## Motions
DB Action | MOTION | Date | DOC # | AUTHORS | NOTES | #Tech SP | #Gen SP | #Ed SP | #Tech CIDs | #Gen CIDs | #Ed CIDs | CIDs
MAR | [11 empty] | KEY: Blue: indicates duplicates, Red Removed, Green: Supersedes corresponding red.
N/A | 202101-01 | 2021-03-09 | 72r0 | Assaf Kasher | November Ad Hoc Minutes |  |  |  | 0 | 0 | 0 | TGaz January 2021 interim minutes
N/A | 202001-02 | 2021-03-09 | 1986r1 | Assaf Kasher | November Minutes |  |  |  | 0 | 0 | 0 | TGaz Nov 2020 - Jan 2021 minutes
| 202101-03 | 2021-03-09 | 291r4 | Nehru Bhandaru |  |  |  |  | 32 | 0 | 10 | 5018, 5019, 5030, 5031, 5085, 5086, 5144E, 5263, 5268, 5276, 5292E, 5299, 5300, 5301, 5302, 5303, 5304, 5305E, 5306, 5307, 5308, 5337E, 5338E, 5339E, 5340E, 5357E, 5358, 5359, 5360, 5362, 5363, 5370, 5371E, 5372E, 5374, 5394, 5398, 5401, 5403, 5445, 5453, 5455 and 5456 (43 CIDs total)
| 202001-04 | 2021-03-09 | 346r2 | Assaf Kasher |  |  |  |  | 15 | 0 | 0 | 5109, 5111, 5440, 5441, 5442, 5443, 5114, 5115, 5395, 5281, 5286, 5397, 5402, 5136 and 5149 (15 CIDs total)
| 202101-05 | 2021-03-10 | 307r3 | Christian Berger |  |  |  |  | 4 | 0 | 0 | 5088, 5454, 5193, and 5175 (4 CIDs total)
| 202001-06 | 2021-03-10 | 318r2 | Christian Berger |  |  |  |  | 11 | 0 | 0 | 5204, 5072, 5205, 5207, 5404, 5405, 5214, 5215, 5216, 5217 and 5151 (11 CIDs total)
APR
| 202104-01 | 2021-04-29 | 478r2 | Ali Raissinia |  |  |  |  | 21 |  |  | 5045, 5046, 5047, 5049, 5050, 5051, 5052, 5053, 5056, 5057, 5058, 5059, 5060, 5062, 5063, 5064, 5067, 5068, 5069, 5070 and 5071 (21 CIDs total)
| 202104-02 | 2021-04-29 | 505r1 | Ali Raissinia |  |  |  |  | 6 |  |  | 5061, 5066, 5198, 5222, 5224, and 5230 (6 CIDs total)
N/A | 202104-03 | 2021-04-29 | 532r0 | Dibarkar Das |  |  |  |  | 0 |  |  | Technical Contribution TC532r0
| 202104-04 | 2021-04-29 | 533r2 | Johnathan Segev |  |  |  |  | 3 |  | 4 | 5000, 5003E, 5004E, 5005, 5006E, 5009, and 5237E (7 CIDs total),
| 202104-05 | 2021-04-29 | 564r2 | Assaf Kasher |  |  |  |  | 8 |  |  | 5219, 5029, 5400, 5139, 5152, 5097, 5098, 5429, 5260 (9 CIDs total)
| 202104-06 | 2021-04-29 | 519r3 | Christian Berger |  |  |  |  | 1 |  |  | 5014 (1 CIDs total)
MAY
| 202105-01 | 2021-05-10 | 422r0 | Assaf Kasher | [7 empty] | TGaz meeting minutes Feb-Apr 2021
| 202105-02 | 2021-05-10 | 777r0 | Assaf Kasher | [7 empty] | TGaz Telecon meinutes Feb-Apr 2021
| 202105-03 | 2021-05-10 | 708r0 | Nehru Bhandaru |  |  |  |  | 4 |  |  | 5260, 5351, 5364, and 5385 (4 CIDs total)
| 202105-04 | 2021-05-10 | 536r1 | Steve Shellhammer |  |  |  |  | 5 |  |  | 5413, 5414, 5415, 5416 and 5417 (5 CIDs total)
| 202105-05 | 2021-05-12 | 761r3 | Christian Berger |  |  |  |  | 2 |  |  | 5190 and 5191 (2 CIDs total)
| 202105-06 | 2021-05-12 | 811r1 | Youhan Kim |  |  |  |  | 9 |  |  | 5473, 5460, 5461, 5463, 5467, 5468, 5474, 5469, and 5471 (9 CIDs total)
N/A | 202105-07 | 2021-05-17 | 750r2 | Jon Rosdahl | [7 empty] | PAR Extension
| 202105-08 | 2021-05-17 | 810r2 | Ali Raissinia |  |  |  |  | 3 |  |  | 5016, 5027 and 5036 (3 CIDs total)
| 202105-09 | 2021-05-17 | 815r1 | Dibarkar Das |  |  |  |  | 9 |  | 4 | 5007, 5008, 5010E, 5037, 5041, 5048E, 5132, 5141E, 5162E, 5164, 5165, 5167, 5168 (13 CIDs total)
JUNE
| 202106-01 | 2021-06-24 | 835r2 | Jonathan Segev | [6 empty] | 8 | 5203E, 5254E, 5261E, 5294E, 5348E, 5353E, 5378E, 5381E, 5444E (9 CIDs total)
N/A | 202106-02 | 2021-06-24 | 864r1 | Steve Shellhammer |  |  |  |  | 1 |  |  | 5090 (1 CIDs total)
| 202106-03 | 2021-06-24 | 901r0 | Christian Berger | [7 empty] | Technical Contribution
| 202106-04 | 2021-06-24 | 917r0 | Tianyu Wu |  |  |  |  | 2 |  |  | 5189, 5192 (2 CIDs)
JULY | [11 empty] | TGaz D3.2
N/A | 202107-01 | 2021-07-12 | 807r0 | Assaf Kasher | [7 empty] | Minutes
| 202107-02 | 2021-07-12 | 928r1 | Erik Lindskog |  |  |  |  | 11 |  | 6 | 5235E, 5252E, 5253E, 5020, 5021, 5026, 5032, 5033E, 5367E, 5391, 5034, 5035, 5043, 5073, 5074, 5076, 5242E (17 CIDs)
| 202107-03 | 2021-07-12 | 978r1 | Erik Lindskog |  |  |  |  | 9 |  | 5 | 5077, 5243E, 5078, 5246E, 5075, 5244E, 5245E, 5079, 5080, 5083, 5084, 5082, 5081 and 5143E (14 CIDs)
| 202107-04 | 2021-07-12 | 967r2 | Dibarkar Das |  |  |  |  | 17 |  |  | 5451, 5450, 5449, 5428, 5427, 5396, 5393, 5234, 5218, 5194, 5180, 5172, 5171, 5170, 5169, 5135 and 5042 (17 CIDs).
| 202107-05 | 2021-07-12 | 911r2 | Christian Berger |  |  |  |  | 1 |  |  | 5377 (1 CID)
| 202107-06 | 2021-07-12 | 929r3 | Erik Lindskog |  |  |  |  | 3 |  |  | 5220, 5221, and 5223 (3 CIDs) NOTE 5028 was dropped from the motion but in the SP
N/A | 202107-07 | 2021-07-12 | 968r0 | Youhan kim | [7 empty] | Technical Contribution
| 202107-08 | 2021-07-12 | 1021r2 | Eric Lindskog |  |  |  |  | 2 |  | 4 | 5283E, 5022E, 5023E, 5025E, 5055, and 5028 (6 CIDS)
| 202107-09 | 2021-07-12 | 1034r1 | Tianyu Wu |  |  |  |  | 10 |  |  | 5001, 5002, 5103, 5106, 5160, 5423, 5432, 5433, 5434, 5436 (10 CIDS)
| 202107-10 | 2021-07-12 | 1007r1 | Tianyu Wu | [7 empty] | Technical Contribution
| 202107-11 | 2021-07-12 | 1038r1 | Assaf Kasher |  |  |  |  | 4 |  |  | 5138, 5093, 5356, 5095 (4 CIDs total)
| 202107-12 | 2021-07-12 | 969r1 | Nehru Bhandaru |  |  |  |  | 4 |  |  | 5181, 5187, 5228, 5439 (4 CIDs total) NOTE: Doc also contains 5093 and 5095 but not part of motion
| 202107-13 | 2021-07-12 | 1043r1 | Assaf Kasher |  |  |  |  | 5 |  |  | 5101, 5438, 5110, 5269, 5446 (5 CIDs total)
| 202107-14 | 2021-07-12 | 1030r1 | Dibarkar Das | [7 empty] | Technical Contribution
| 202107-15 | 2021-07-12 | 1045r1 | Qi Wang |  |  |  |  | 2 |  | 1 | 5437, 5447 and 5444E (3 CIDs total)
| 202107-16 | 2021-07-12 | 1061r0 | Roy Want | [5 empty] | 0 | 172 | All unassigned Editorials x173 and 2x General CIDs ( 2 Generals were remotioned, and CID 5024E remotioned)
| 202107-17 | 2021-07-13 | 989r0 | Ali Raissinia |  |  |  |  | 1 |  |  | 5044 (1 CID total)
| 202107-18 | 2021-07-13 | 1027r4 | Dibarkar Das |  |  |  |  | 6 |  | 3 | 5196, 5195, 5229, 5174, 5039, 5040, 5209E, 5210E, 5211E (9 CIDs total)
| 202107-19 | 2021-07-13 | 1063r1 | Qi Wang |  |  |  |  | 1 |  |  | 5453 (1 CID total)
| 202107-20 | 2021-07-13 | 1080r0 | Qi Wang |  |  |  |  | 1 |  |  | 5457 (1 CID total)
| 202107-21 | 2021-07-13 | 1079r0 | Qi Wang |  |  |  |  | 2 | 1 |  | 5435, 5452, 5376G (3 CIDs total)
| 202107-22 | 2021-07-13 | 1070r1 | Assaf Kasher |  |  |  |  | 4 |  |  | 5399, 5361, 5466, 5089 (4 CIDs total)
| 202107-23 | 2021-07-14 | 1139r3 | Jonathan Segev |  |  |  |  | 10 |  |  | 5431, 5265, 5380, 5206, 5208, 5173, 5366, 5389, 5390, 5448 (10 CIDs total)
| 202107-24 | 2021-07-14 | 1155r3 | Youhan Kim |  |  |  |  | 1 |  |  | 5465 (1 CID total)
| 202107-25 | 2021-07-14 | 1075r0 | Christian Berger |  |  |  |  | 1 |  |  | 5213 (1 CID total)
| 202107-26 | 2021-07-14 | 1161r0 | Qi Wang |  |  |  |  | 2 |  |  | 5424, 5425 (2 CIDs total)
| 202107-27 | 2021-07-15 | 1156r3 | Assaf Kasher |  |  |  |  | 5 |  |  | 5148, 5464, 5408, 5418 and 5150 (5 CIDs total)
| 202107-28 | 2021-07-16 | 329r7 | Roy Want | [7 empty] | MDR Report for TGaz
| 202107-29 | 2021-07-16 | 1113r2 | Erik Lindskog |  |  |  |  | 6 |  | 1 | 5011, 5024E, 5258, 5257, 5255, 5256, and 5232 (7 CIDs total)
| 202107-30 | 2021-07-16 | 1162r1 | Jonathan Segev |  |  |  |  | 5 | 1 |  | 5410G, 5475, 5349, 5373, 5386, and 5387 (6 CIDs total)
| 202107-31 | 2021-07-16 | 1118r1 | Assaf Kasher |  |  |  |  | 4 |  |  | 5470, 5472, 5375, and 5419W (4 CIDs total)
| 202107-32 | 2021-07-16 | 1112r3 | Erik Lindskog |  |  |  |  | 1 |  |  | 5233 (1 CID total)
| 202107-33 | 2021-07-19 | 1160r3 | Erik Lindskog |  |  |  |  | 2 |  |  | 5231 and 5271 (2 CIDs)
| 202107-34 | 2021-07-19 | 258r8 | Jonathan Segev | [7 empty] | Ballot Approval for D4.0
NOTE: E=Editorial, G=General, W=Withdrawn&Technical (No label is Technical)
| TOTAL |  |  |  |  | 0 | 0 | 0 | 256 | 2 | 218
20
14

## ToDo Per Member
TODO
NAME | TOTAL | TECH CIDS
GRAND TOTAL | 0