## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-21/0830r1
Venue Date: | May 2021
First Author: | Chong Han, pureLiFi
Subject: | Comments on D0.4
Full Date: | 2021-05-12
Author(s): | Chong Han, pureLiFi. Nikola Serafimovski, pureLiFi.
Address
Phone:
Fax:
chong.han@purelifi.com, nikola.serafimovski@purelifi.com
Abstract:
This submission contains some comments against draft D0.4.

## comments against D0.4
CCI | Date | SA PIN | Name | Comment | Category | Page Number | Subclause | Line Number | Proposed Change | MBS | TG Decision | TE suggested action | Changes in the draft | Assigned to
1 |  |  | Chong Han | 31.3 PHY mode selection is embedded in the MAC clause. Reconsider the best place for the sub-clause. | Editorial | 14 | 31.3 | 2 | It seems the Chapter 31 and 32 are not suitable for this sub-clause. Perhaps 4.3.30 is more suitable. |  | revise, move P14L3-5 to P13L14 , delete subclause heading 31.3 |  | done
2 |  |  | Chong Han | 31.1, 31.2 both have ‘LC MAC’ in the sub-clause headlines; while 32.1 does not have ‘LC PHY’ in the headline. Please consider the consistency of the headline. | Editorial | 13 | 31.1, 31.2, 32.1 | 16 | Either use ‘LC MAC/PHY’ in the headlines or not. |  | revise, remove "specification" from P13L15, remove "LC MAC" from P13L16 and P13L23 |  | done
3 |  |  | Chong Han | Add texts in doc. 11-21/0545r2 to the draft | Technical | 13 | 26.5 | 14 | Add texts in doc. 11-21/0545r2 to the draft |  | reject | withdrawn by commenter
4 |  |  | Chong Han | Add texts in doc. 11-20/1772r4 to the draft | Technical | 14 | 31.2 | 1 | Add texts in doc. 11-20/1772r4 to the draft |  | revise, add texts in doc. 11-20/1772r5 to the draft |  | done, needs clarification on why the second sentence is needed "The subclause shall be the same as 26 (High Efficiency (HE) MAC specification). "
5 |  |  | Chong Han | Incorporate the texts in doc. 11-21/0280r5 to 32.3.3.3. | Technical | 18 | 32.3.3.3 | 5 | Incorporate the texts in doc. 11-21/0280r5 to 32.3.3.3. |  | reject | already incorporated in 11-21-0813-01
6 |  |  | Chong Han | the definition for light antenna is missing in the 4.3 | Technical | 12 | 3.1 | 11 | add the following text after line 11: 'antenna connector: The measurement point of reference for radio frequency (RF) measurements in a station (STA). The antenna connector is the point in the STA architecture representing the input of the receiver (output of the antenna) for radio reception and the input of the antenna (output of the transmitter) for radio transmission. In systems using multiple antennas or antenna arrays, the antenna connector is a virtual point representing the aggregate output of (or input to) the multiple antennas. In systems using active antenna arrays with processing, the antenna connector is the output of the active array, which includes any processing gain of the active antenna subsystem. In systems using light communications, the antenna connector is a virtual point representing the aggregate output of (or input to) the optical front-end, which includes any processing gain of the optical front-end subsystem. ' |  | revise, add after line 6, underlining the highlighted text "Change the following definitions: antenna connector: The measurement point of reference for radio frequency (RF) measurements in a station (STA). The antenna connector is the point in the STA architecture representing the input of the receiver (output of the antenna) for radio reception and the input of the antenna (output of the transmitter) for radio transmission. In systems using multiple antennas or antenna arrays, the antenna connector is a virtual point representing the aggregate output of (or input to) the multiple antennas. In systems using active antenna arrays with processing, the antenna connector is the output of the active array, which includes any processing gain of the active antenna subsystem. In systems using light communications, the antenna connector is a virtual point representing the aggregate output of (or input to) the optical front-end, which includes any processing gain of the optical front-end subsystem. '" |  | done
7 |  |  | Chong Han | Add texts in doc. 11-21/0813r0 to the draft | Technical | 13 | 17 | 14 | Add texts in doc. 11-21/0813r0 to the draft |  | rejected | was already added via Motion