## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-21/997r2
Venue Date: | July 2021
First Author: | Xiaofei Wang
Subject: | CR for CIDs assigned to Xiaofei Part 3
Full Date: | 2021-07-05
Author(s): | Xiaofei Wang
| Company: | InterDigital
Address
Phone:
Fax:
email:
Abstract:
CR for LB252 Comments on P802.11bc/D1.0

## Xiaofei Wang
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
1221 | Kazuto Yano | 252 | 1 | 11.100.4 | 56 | 30 | E | N | 56 | 30 | 11.100.4 |  |  | Xiaofei Wang |  |  | "Time of Termination field" should be "Time Of Termination filed". | Please revise according to the comment. | revised; change "Time Of Termination" to "Time To Termination". TGbc editor: the change has already been included in TGbc D1.03 and no furher changes are needed. | CHAIR | [6 empty] | 2021-01-06 07:58 | CHAIR
1123 | Hitoshi Morioka | 252 | 1 | 9.6.50.1 | 47 | 1 | T | N | 47 | 1 | 9.6.50.1 |  |  | Xiaofei Wang |  |  | The name of the eBCS Request/Response frame should be eBCS Negotiation Request/Response frame. The original name does not specify the function and MLME SAP interfaces for them are MLME-EBCNEGOTIATION.request/response. | As commented. | EBCS Streams Request/response | CHAIR | [6 empty] | 2021-01-15 15:46 | CHAIR
1124 | Hitoshi Morioka | 252 | 1 |  |  |  | T | Y | [5 empty] | Xiaofei Wang |  |  | Why is association required to use the eBCS Request/Response frame? As the frames are not protected, they are easily spoofed. | The eBCS Request/Response should be able to be used by unassociated STAs, too. Or protect the frames by using RSNA. | revised: EBCS Request/Response frames are action frames and are protected. Add clarification | CHAIR | [6 empty] | 2021-05-17 15:03 | CHAIR
1140 | Hitoshi Morioka | 252 | 1 | 9.6.7.102 | 43 | 6 | T | N | 43 | 6 | 9.6.7.102 |  |  | Xiaofei Wang |  |  | Transmitted one is not eBCS, it is content. | Replace "eBCSs" with "eBCS contents" or "eBCS streams". | revised: agree with the comment. Change "eBCSs" to "EBCS traffic streams" TGbc editor: this change is already included in TGbc D1.03, no further change is needed. | CHAIR | [6 empty] | 2021-01-15 15:46 | CHAIR
1145 | Hitoshi Morioka | 252 | 1 | 9.6.50.1 | 46 | 17 | T | N | 46 | 17 | 9.6.50.1 |  |  | Xiaofei Wang |  |  | Replace "Several" with "Two". | As commented. | accepted | CHAIR | [6 empty] | 2021-01-15 15:46 | CHAIR
1214 | Kazuto Yano | 252 | 1 | 9.4.2.302 | 28 | 5 | E | N | 28 | 5 | 9.4.2.302 |  |  | Xiaofei Wang | 11-21/123r2 |  | Figure 9-bc11 include "Time to Termination Present". On the other hand, it is represented as "Time To Termination Present" (i.e., "To" begins with capital) in the main text. | Please make consistent the notation of the subfield. | revised:the cited text has been deleted TGbc editor: no further changes are needed. | CHAIR |  |  | CHAIR: 2021-01-27 20:17:19Z - Discussed in telco 2021-01-26. Deferred.. CHAIR: 2021-01-19 17:37:05Z - discussed in telco and reassigned to Xiafei.. |  |  |  | 2021-01-27 20:17 | CHAIR
1561 | Tomoko Adachi | 252 | 1 | 11.100.4 | 56 | 27 | T | Y | 56 | 27 | 11.100.4 |  |  | Xiaofei Wang |  |  | Shouldn't Time To Termination field included in the eBCS Request frame be Request Time To Termination? | As in comment. | Revised: change "Time To Termination" to "Requested Time To Termination". TGbc editor: the change is already included in TGbc D1.03 and no further changes are needed. | CHAIR | [6 empty] | 2021-01-06 07:58 | CHAIR
1340 | Mark RISON | 252 | 1 | 11.100.4 | 56 | 24 | E | Y | 56 | 24 | 11.100.4 |  |  | Xiaofei Wang |  |  | "to request one or more of such eBCSs" should be just "to request these eBCSs" |  | revised: the sentence has been cleaned up. TGbc editor: please incorporate changes in 11-21/1065r1 under tag 1340. | CHAIR | [6 empty] | 2021-01-06 07:58 | CHAIR
1341 | Mark RISON | 252 | 1 | 11.100.4 | 56 | 21 | E | Y | 56 | 21 | 11.100.4 |  |  | Xiaofei Wang |  |  | "An eBCS STA may transmit an eBCS Request frame to its associated eBCS AP to request one or more 21 eBCSs provided by the eBCS AP." could be misread | Change to "To request one or more eBCSs provided by the eBCS AP an eBCS non-AP STA is associated with, the STA shall transmit an eBCS Request frame to the AP." | Revised: the sentence has been revised following the spirit of the proposed change. TGbc editor: please incorporate changes in 11-21/1065r1 under tag 1341. | CHAIR | [6 empty] | 2021-01-06 07:58 | CHAIR
1342 | Mark RISON | 252 | 1 | 11.100.4 | 56 | 27 | T | Y | 56 | 27 | 11.100.4 |  |  | Xiaofei Wang |  |  | "in Time To Termination field included in the eBCS Request frame" -- no such field (and missing article) | Change to "in the Requested Time To Termination field included in the eBCS Request frame" | Revised: change "Time To Termination" to "the Requested Time To Termination". TGbc editor: the change is already included in TGbc D1.03 and no further changes are needed. | CHAIR | [6 empty] | 2021-01-06 07:58 | CHAIR
1213 | Kazuto Yano | 252 | 1 | 9.4.2.301 | 27 | 1 | E | N | 27 | 1 | 9.4.2.301 |  |  | Xiaofei Wang | 11-21/123r2 |  | The notation of Request Time "To" Termination subfield is different between Figures 9-bc7 and 9-bc8. ("To" begins with capital in Figure 9-bc8, but does not in Figure 9-bc7). | Please make consistent the notation of the subfield. | revised: the cited contents are deleted and in the new section added covering the same material (9.4.1.68) in TGbc D1.03, the notations are consistent. TGbc editor: no further changes are needed. | CHAIR |  |  | CHAIR: 2021-01-27 20:17:19Z - Discussed in telco 2021-01-26. Deferred.. CHAIR: 2021-01-19 17:37:05Z - discussed in telco and reassigned to Xiafei.. |  |  |  | 2021-01-27 20:17 | CHAIR