## Slide 1: IEEE 802.11 Interim Sep 2021 IEEE 802.11 TGbd Closing Report
Chair: Bo Sun (ZTE)
Vice Chair: Hongyuan Zhang (NXP),
Joseph Levy (InterDigital)
Secretary: Yan Zhang (NXP)
Tech Editor: Yujin Noh (Senscomm)

## Slide 2: TGbd’s Progress during the Sep 802.11 interim week
4 TGbd sessions were held during the week
Approved TG minutes for Jul plenary week and following TCs before Sep interim week.
Presented and discussed CRs and approved CRs for totally 184 comments (65% of total comments) for LB 254.
Approved TGbd tech editor to generate IEEE P802.11bd D2.1 to incorporate approved CRs.
Approved TGbd teleconference plan as in following slides.
TGbd agenda and preliminary minutes documents for this week:
  https://mentor.ieee.org/802.11/dcn/21/11-21-1326-07-00bd-tgbd-teleconference-agenda-for-sep-2021.pptx
  https://mentor.ieee.org/802.11/dcn/21/11-21-1544-00-00bd-tgbd-september-interim-2021-teleconference-minutes.docx
Goal for future TCs: proceeding comments collected during LB 254 (11bd D2.0)

## Slide 3: TGbd Progress Documents
TG Documents | Latest Revision
Definition and requirements | 11-19/0202r1
Selection Procedure document | 11-19/0030r6
Functional Requirement document | 11-19/0495r3
Spec Framework document | 11-19/0497r7
Liaison response to IEEE VT/ITS 1609 WG | 11-19/0437r3
Liaison response to ITU-T CITS | 11-19/0843r0
TBbd FRD/SFD Motion Booklet | 11-19/0514r14
TGbd Use Case document | 11-19/1342r1
Teleconference Agenda | 11-20/0774r10, 11-20/1164r7, 11-20/1352r9, 11-20/1561r7, 11-20/1806r2, 11-20/1891r0, 11-20/1923r11, 11-21/0177r2, 11-21/0207r8, 11-21/0595r3, 11-21/0597r7, 11-21/0904r1, 11-21/0941r2, 11-21/1303r4, 11-21/1326r7
Teleconference Minutes | 11-20/0276r11, 11-20/1105r8, 11-20/1489r1, 11-20/1655r3, 11-20/1775r1, 11-20/1907r1, 11-21/0068r0, 11-21/0117r0, 11-21/0327r0, 11-21/0453r0, 11-21/0454r0, 11-21/0565r0, 11-21/0655r0, 11-21/0806r0, 11-21/0889r0, 11-21/1138r0, 11-21/1468r0, 11-21/1544r0
Tech Editor Report | 11-19/2045r13 (D2.0)
Comment Database | 11-20/0701r7 (D0.3), 11-20/1887r10 (LB251), 11-21/1296r3 (LB254)
Coexistence Assurance Document | 11-20/1564r2

## Slide 4: IEEE 802.11 TGbd Timeline
  PAR approved Dec 2018
  First TG meeting Jan 2019
  D0.1 Nov 2019
  D1.0 Letter Ballot Oct 2020
  D2.0 LB recirculation Jul 2021
  Form SA Ballot Pool Nov 2021 (Try Sep 2021)
  D3.0 LB recirculation Jan 2022 (Try Nov 2021)
  D3.0 unchanged recirculation Jan 2022
  Initial SA Ballot (D4.0) Mar 2022
  Final 802.11 WG approval Sep 2022
  802 EC approval Oct 2022
  RevCom and SASB approval Dec 2022

## Slide 5: IEEE 802.11 TGbd TC Plan
Sep 28th, 10:00am ~ 11:59am, ET; Webex (existing TC)
Oct 12th, 10:00am ~ 11:59am, ET; Webex
Oct 19th, 10:00am ~ 11:59am, ET; Webex
Oct 22nd, 10:00am ~ 11:59am, ET; Webex
Oct 26th, 10:00am ~ 11:59am, ET; Webex
Nov 2nd, 10:00am ~ 11:59am, ET; Webex (Daylight Time)
Nov 9th, 10:00am ~ 11:00am, ET; Webex (Standard Time)