## Abhishek Patil
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2043 | Abhishek Patil | 257 | 2 | 11.55.3.3 | 82 | 7 | T | N | 82.07 | 7 | 11.55.3.3 |  |  | Abhishek Patil |  |  | While it is clear from clause 4.3.31 that the EBCS transmitter and receiver can be in unassociated state. Add a NOTE in this subclause to clarify that the transmitting non-AP STA can be unassociated with the EBCS AP that provided relaying service. | As in comment | Revised Agree with the comment. Added a NOTE to clause 11.55.3.2 to clarify that the EBCS AP that provided relaying service may be unassociated with the EBCS STA that transmitted the EBCS UL frame. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2043 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2154 | Joseph Levy | 257 | 2 | 11.55.3.3 | 66 | 7 | T | Y | 66.07 | 7 | 11.55.3.3 |  |  | Abhishek Patil |  |  | As stated in the draft "An EBCS non-AP STA is not required to monitor the WM and may transmit an EBCS UL frame without discovering nearby EBCS APs that provide access to the relaying service." This statement should be clearly stated at the beginning of this clause not at the end. | Delete: "An EBCS non-AP STA is not required to monitor the WM and may transmit an EBCS UL frame without discovering nearby EBCS APs that provide access to the relaying service." Add the following to the be the first sentence of clause 11.55.3.3: "An EBCS non-AP STA may transmit an EBCS UL frame at any time. NOTE: the STA is not required to monitor the WM and the STA is not required to have received a Beacon frame with dot11EBSCSRelayingSeriviceSuupported equal to true." | Revised Agree with the comment. The cited was updated and moved to the beginning of the subclause. Instead of adding a NOTE, the behavior is specified as normative text for emphasising that the STA is not required to discover any APs in its neighborhood that provide relaying service. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2154 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2155 | Joseph Levy | 257 | 2 | 11.55.3.3 | 65 | 45 | T | Y | 65.45 | 45 | 11.55.3.3 |  |  | Abhishek Patil |  |  | The statement that an EBCS non-AP STA may request relaying of an HLP payload to a specific destination by transmitting an EBCS UL frame provides no requirement. A statement that an EBCS UL frame shall contain an HLP payload and that Address 1 and Address 3 of the frame shall be the broadcast address is much more meaningful. | Replace: "An EBCS non-AP STA may request relaying of an HLP payload to a specific destination by transmitting an EBCS UL frame. The frame carries the URI of the intended destination. The Address 1 and Address 3 fields of the frame shall be set to the broadcast address." With: "An EBCS UL frame transmitted by a EBCS non-AP STA shall contain an HLP payload and shall have the Address 1 and Address 3 fields set to the broadcast address." | Revised Agree with the comment. The sentence related to 'requesting relaying service' is deleted. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2155 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2156 | Joseph Levy | 257 | 2 | 11.55.3.3 | 65 | 50 | T | Y | 65.5 | 50 | 11.55.3.3 |  |  | Abhishek Patil |  |  | The requirement that an EBCS non-AP STA should include a STA certificate in an EBCS UL frame is adequate. The reason it is included may be provided as a note and should not be included in the normative text. | Replace: "An EBCS non-AP STA should include a STA certificate in an EBCS UL frame to help authenticate it (see 12.14.2.6 (Authentication of an EBCS UL frame))." With: "An EBCS non-AP STA should include a STA certificate in an EBCS UL frame. NOTE: The STA certificate is included to help authenticate the EBCS UL frame (see 12.14.2.6 (Authentication of an EBCS UL frame))." | Revised Agree with the comment. However, this aspect was discussed and debated in the past and TGbc members felt it was necessary to provide the recommendation as normative text for emphasising on security. The text in the cited paragraph was also modified as a resolution to CID 2133 TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2156 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2133 | John Wullert | 257 | 2 | 11.55.3.3 | 65 | 50 | T | N | 65.5 | 50 | 11.55.3.3 |  |  | Abhishek Patil |  |  | The phase "help authenticate it" is vague. | Rephrase as "...in an EBCS UL frame to allow the EBCS Proxy to authenticate the EBCS non-AP STA." | Revised Agree with the comment. The text in the cited paragraph was modified as proposed by the comment. In addition, replaced 'a STA certificate' with 'its certificate' to avoid any ambiguity with respect to the field STA Certificate. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2133 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2042 | Abhishek Patil | 257 | 2 | 11.55.3.3 | 81 | 54 | T | N | 81.54 | 54 | 11.55.3.3 |  |  | Abhishek Patil |  |  | The setting of the 'presence' bits in the Control field of the EBCS UL frame is described in clause 9.6.53. It doesn't need to be duplicated in this paragraph. | Simplify the text in the cited paragraph (P81L54) by focusing on the behavior and the value carried in the Frame Tx Time field and the Frame Count field. | Revised Agree with the comment. The text in the cited paragraph is updated to focus on the behavioral aspect rather than how the presence bits are set in the Control field of the EBCS UL frame. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2042 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2157 | Joseph Levy | 257 | 2 | 11.55.3.3. | 65 | 54 | T | Y | 65.54 | 54 | 11.55.3.3. |  |  | Abhishek Patil |  |  | The requirement related to including the Frame Count field should be provided, but the reason it should be provided is not normative and should be a note. | As in comment. | Revised Agree with the comment. TGbc had discussed and debated on the topic in the past and members felt it is necessary to cite the reason (for including the field) be kept as normative text to emphasis on security. The rest of the text was revised as proposed by the comment. In addition, the cited text was modified as a resolution to CID 2042 TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2157 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2158 | Joseph Levy | 257 | 2 | 11.55.3.3 | 65 | 55 | T | Y | 65.55 | 55 | 11.55.3.3 |  |  | Abhishek Patil |  |  | The requirement that a EBCS non-AP STA that has time information shall set the time present subfield to 1 and indicate the time the frame queued for transmission in the Frame TX Time field is very confusing. What is meant by "has time information". It is simpler to state that a EBCS non-AP STA may set the time present subfield to 1 and include the time the transmission was queued for transmission in the Time field | Replace: "When the STA has time information, the Frame Tx Time Present subfield in the Control field shall be set to 1 and the Frame Tx Time field shall indicate the time when the frame is queued for transmission; otherwise the Frame Tx Time Present subfield of the Control field shall be set to 0 and the Frame Tx Time field is not present in the frame." With: "A EBCS non-AP STA may set the Frame Tx Time Present subfield in the Control field to 1 and set the Frame Tx Time field to the time when the frame is queued for transmission; otherwise the Frame Tx Time Present subfield of the Control field shall be set to 0 and the Frame Tx Time field is not present in the frame." | Revised It is possible that the non-AP STA that transmits an EBCS UL frame is in unassociated state and as a result does not have accurate time information. Therefore, inclusion of Tx Time field is conditional. The NOTE was updated to capture this point. In addition, the cited text was modified as a resolution to CID 2042 TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2158 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2134 | John Wullert | 257 | 2 | 11.55.3.3 | 66 | 3 | E | N | 66.03 | 3 | 11.55.3.3 |  |  | Abhishek Patil |  |  | Extra word "carry" | Remove "carry" in "shall carry be computed" | Accepted | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2048 | Abhishek Patil | 257 | 2 | 12.14.2.5 | 87 | 13 | G | Y | 87.13 | 13 | 12.14.2.5 |  |  | Abhishek Patil |  |  | Reorganize the text in this subclause. 1. Move the paragraph on line 33 as the 1st paragraph. 2. Delete the last sentence (line 46) in this clause 3. For the paragraph (in D2.0) on line 15, clarify the public key algorithms described in this subclause apply when the Frame Signature Type subfield is nonzero; Otherwise, the authentication of the HLP payload is provided by higher layer and is out-of-scope of this standard. | As in comment | Revised The text in this subclause was revised as proposed by the comment. A few fixes were made along the way - such as updating the text for computing the signature and in the paragraph describing Frame Signature field in EBCS UL frame format. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2048 | CHAIR | [6 empty] | 2021-11-02 07:52 | CHAIR
2001 | Abhishek Patil | 257 | 2 | 4.3.31 | 25 | 17 | T | N | 25.17 | 17 | 4.3.31 |  |  | Abhishek Patil |  |  | The relaying embedding of additional information is performed by an EBCS proxy (as described in 4.5.12.2). | Revise the sentence on P25L17 as: "Further, EBCS provides a service in which an EBCS proxy affiliated with an EBCS AP can relay the contents of a higher layer payload, received from an EBCS non-AP STA, to a destination typically within an external network. The EBCS proxy can embed additional information if requested by the STA and supported by it." | Revised Agree with the comment. The text was revised as proposed by the comment. Deleted the text related to request for embedding additional information since the embedding is not requested by the transmitting STA. Rather it is based on the relationship between the relaying proxy and the specified destination. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2001 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2108 | John Wullert | 257 | 2 | 4.5.12.2 | 10 | 7 | E | N | 10.07 | 7 | 4.5.12.2 |  |  | Abhishek Patil |  |  | This parapgraph covers two separate topics. It would be clearer to separate into two | Break paragraph after first sentence: "different criteria. An EBCS proxy can also embed..." | Accepted | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2105 | John Wullert | 257 | 2 | 4.5.12.1 | 9 | 51 | T | N | 9.51 | 51 | 4.5.12.1 |  |  | Abhishek Patil |  |  | The abbreviation HLP is not defined prior to be used. | Rephrase as "... for an EBCS non-AP STA to send an higher-layer protocol (HLP) payload to a...". Note: this is used often enough it might warrant a definition. | Rejected The term HLP is defined in the baseline spec. Please see REVme D0.4 pg 254 line 60 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2215 | Michael Montemurro | 257 | 2 | 4.5.12.1 | 25 | 51 | E | N | 25.51 | 51 | 4.5.12.1 |  |  | Abhishek Patil |  |  | HLP (Higher Layer Protocol) acronym should be expanded on first use. | Expand the acronym at the cited location. | Rejected The term HLP is defined in the baseline spec. Please see REVme D0.4 pg 254 line 60 | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2110 | John Wullert | 257 | 2 | 4.5.12.3 | 10 | 37 | E | N | 10.37 | 37 | 4.5.12.3 |  |  | Abhishek Patil |  |  | In figure caption, reference should be to "EBCS APs" (plural) rather than singular "an EBCS AP" | As in comment | Accepted | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2233 | Stephan Sand | 257 | 2 | 4.5.12.2 | 10 | 15 | E | N | 10.15 | 15 | 4.5.12.2 |  |  | Abhishek Patil |  |  | The article "the" is missing before scope | Add "the" before scope | Rejected The text 'out of scope' is consistent with the usage in baseline. Please see REVme D0.4 P867L33, P1340L4, P1413L25, P2066L5 to list a few instances. | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2234 | Stephan Sand | 257 | 2 | 4.5.12.3 | 11 | 31 | E | N | 11.31 | 31 | 4.5.12.3 |  |  | Abhishek Patil |  |  | The article "the" is missing before scope | Add "the" before scope | Rejected The text 'out of scope' is consistent with the usage in baseline. Please see REVme D0.4 P867L33, P1340L4, P1413L25, P2066L5 to list a few instances. | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2003 | Abhishek Patil | 257 | 2 | 4.5.12.3 | 26 | 43 | T | N | 26.43 | 43 | 4.5.12.3 |  |  | Abhishek Patil |  |  | The main difference between Figure 4-20a and Figure 4-20b is whether the proxy is collocated with an EBCS AP. Update the sentence on P26L43 to clarify that the proxy is collocated with respective APs. | Update the sentence on P26L43 as: "In the figure, EBCS proxies P1, P2 and P3 are collocated with EBCS APs A1, A2 and A3 respectively. EBCS proxy P1 and EBCS proxy P3 have established ...". Add "(P2)" in the sentence on L54 as shown here: "... its collocated proxy (P2) ..." | Revised Agree with the commenter. The text was updated as proposed by the comment to clarify that the three proxies described in the example are collocated with their respective EBCS APs. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2003 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2111 | John Wullert | 257 | 2 | 4.5.12.3 | 10 | 50 | T | N | 10.5 | 50 | 4.5.12.3 |  |  | Abhishek Patil |  |  | The phrase "then each of P1 and P# does not send..." is difficult to follow. Plus, this text raises the question of how P1 and P3 make their decisions (e.g., independently or in concert) | Rephrase as "...then P1 and P3 determine whether or not to forward their receive HLP payloads to D, based on whether or not prior transmissisions have reached the limit." Further, move note from page 12, line 27 to here. | Revised Agree with the commenter. The text was updated as proposed by the comment. The NOTE (from the end of the subclause) is moved to be after the cited paragraph TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2111 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2112 | John Wullert | 257 | 2 | 4.5.12.3 | 10 | 54 | E | N | 10.54 | 54 | 4.5.12.3 |  |  | Abhishek Patil |  |  | Phrasing of final sentence is hard to follow | rephrase as "This could be for any number of reasons such as that the AP does not provide a relaying service, the AP's collocated proxy has not established a relationship with D, or that one or more criteria for relaying has not been satisfied." | Revised Agree with the commenter. The text was updated (w/ minor tweaks) as proposed by the comment. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2112 | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2161 | Jouni Malinen | 257 | 2 | 9.6.7.53 | 44 | 25 | T | N | 44.25 | 25 | 9.6.7.53 |  |  | Abhishek Patil |  |  | Including the full Destination URI element in the Destination URI field of the EBCS UL frame makes the frame two octets longer without providing any real value since the Element ID field will have a fixed value and the ESS Detection Interval field is reserved in this frame. | Add a Destination URI Length field into Figure 9-909ah between the Control and Destination URI fields. On page 45 line 28, replace "The Destination URI field contains a Destination URI element as defined in 9.4.2.89" with "The Destination URI field specifies the destination URI using the format defined in IETF RFC 3986". Add "The Destination URI Length field indicates the length of the Destination URI field in octets." immediately before this paragraph. Revert the changes to 9.4.2.89. | Revised Agree with the commenter. The proposed resolution reverts all changes to clause 9.4.2.69 and deletes it from TGbc draft. Furthermore, the resolution updates description text related to Destination URI in clause 9.6.7.53 and clause 6. TGbe editor, please make changes as shown in https://mentor.ieee.org/802.11/dcn/21/11-21-1798-02-00bc-cids-assigned-to-abhi-part-1.docx tagged 2161 | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
2055 | Abhishek Patil | 257 | 2 | 9.6.7.53 | 60 | 55 | E | N | 60.55 | 55 | 9.6.7.53 |  |  | Abhishek Patil |  |  | F in 'field' must be lower case | As in comment | Accepted | CHAIR | [6 empty] | 2021-11-02 07:53 | CHAIR
2174 | Kazuto Yano | 257 | 2 | 9.6.7.53 | 44 | 40 | T | Y | 44.4 | 40 | 9.6.7.53 |  |  | Abhishek Patil |  |  | In Figure 9-909ai, the Control field has only 7 bits. (B6 is missing.) | Please give two (B6-B7) Reserved bits to the Control field. | Accepted | CHAIR | [6 empty] | 2021-11-02 07:51 | CHAIR
|  | 257 | 2 |  |  |  |  | Y | [5 empty] | Abhishek Patil
|  | 257 | 2 |  |  |  |  | Y | [5 empty] | Abhishek Patil
|  | 257 | 2 |  |  |  |  | Y | [5 empty] | Abhishek Patil