## Title
IEEE P802.11 Wireless LANs
Submission
Designator: | doc.: IEEE 802.11-21/1835r0
Venue Date: | November 2021
First Author: | Stephen McCann
Subject: | LB257 Comments on P802.11bc/D2.0
Full Date: | 2021-11-12
Author(s): | Stephen McCann
| Company: | Huawei Technologies Co., Ltd
Address
Phone:
Fax:
email:
Abstract:
LB257 Comments on P802.11bc/D2.0

## Revision History
Revision | Date | Description
0 | 2021-11-12 | Initial version

## Stephen McCann
CID | Commenter | LB | Draft | Clause Number(C) | Page(C) | Line(C) | Type of Comment | Part of No Vote | Page | Line | Clause | Duplicate of CID | Resn Status | Assignee | Submission | Motion Number | Comment | Proposed Change | Resolution | Owning Ad-hoc | Comment Group | Ad-hoc Status | Ad-hoc Notes | Edit Status | Edit Notes | Edited in Draft | Last Updated | Last Updated By
2212 | Michael Montemurro | 257 | 2 | 1.3 | 21 | 46 | T | N | 21.46 | 46 | 1.3 |  |  | Stephen McCann |  |  | An infrastructure AP operates the EBCS service. The service itself isn't part of the BSS although an AP is involved. | Change "to transmit and receive broadcast data in an infrastructure BSS" to "to transmit and receive broadcast data from an AP operating in an infrastructure BSS" | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2227 | Rojan Chitrakar | 257 | 2 | 3.2 | 22 | 29 | T | Y | 22.29 | 29 | 3.2 |  |  | Stephen McCann |  |  | Definitions are supposed to describe what a term means, but not to provide details of the feature. The second sentence "It additionally provides means for protecting broadcast traffic, protecting the privacy of the stations receiving that traffic, and verifying the authenticity of the origin of the traffic." should not be part of the definition. | Delete "It additionally provides means for protecting broadcast traffic, protecting the privacy of the stations receiving that traffic, and verifying the authenticity of the origin of the traffic." | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2102 | John Wullert | 257 | 2 | 4.3.31 | 9 | 15 | T | N | 9.15 | 15 | 4.3.31 |  |  | Stephen McCann |  |  | The phrasing of the first sentence seems to suggest that IBSS is only needed for when there is an association between transmitter and receiver, and thus not required when there is no association | Rephrase as "...transmission and reception of broadcast data in an infrastructure BSS, both in cases where there is an association between the transmitter and the receiver(s) and in cases where there is no association between transmitter and receiver(s)." | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2103 | John Wullert | 257 | 2 | 4.3.31 | 9 | 19 | T | N | 9.19 | 19 | 4.3.31 |  |  | Stephen McCann |  |  | In the phrase "The relaying EBCS AP can embed additional information...", it is not clear where this additional information can be embedded. | Rephrase as "The relaying EBCS AP can embed additional information into the higher layer payload..." | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2099 | Hitoshi Morioka | 257 | 2 | C.3 | 85 | 58 | T | Y | 85.58 | 58 | C.3 |  |  | Stephen McCann |  |  | "dot11EBCSComplianceGroup" should be located in the "Groups" part in the baseline. | Move "dot11EBCSComplianceGroup" to the end of the "Groups" part (e.g. P5764L51 in REVmeD0.4). Add the group description at the end of the "dot11Compliance" (e.g. P5770L39). Add "-- dot11EBCSComplianceGroup" to "--OPTIONAL-GROUPS" in "dot11Compliance" (e.g. P5771L9). | Submission required. Although the proposed change is correct, a submission is required to show the editorial instructions within the 11bc draft itself. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2087 | Hitoshi Morioka | 257 | 2 | 4.3.31 | 9 | 22 | T | Y | 9.22 | 22 | 4.3.31 |  |  | Stephen McCann |  |  | EBCS provides additional means for protecting broadcast traffic and the privacy of the stations receiving that traffic, including data origin authenticity even if there is not an association. | Remove "When there is an association,". | Revised: Change the first sentence of the paragraph at P9L14 to "Enhanced broadcast services (EBCS) provides transmission and reception of broadcast data in an infrastructure BSS, both in cases where there is an association between the transmitter and the receiver(s) and in cases where there is no association between transmitter and receiver(s)." | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2096 | Hitoshi Morioka | 257 | 2 | B.4 | 80 | 1 | T | Y | 80.01 | 1 | B.4 |  |  | Stephen McCann |  |  | PICS does not reflect the approved resolutions for LB252. | Please incorporate the changes in https://mentor.ieee.org/802.11/dcn/21/11-21-1234-03-00bc-clause-11-and-pics-annex-b-comment-resolutions.docx | Accepted. Note: The cited submission was not incorporated into D2.0 | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2250 | Tomoko Adachi | 257 | 2 | 1.3 | 5 | 46 | T | Y | 5.46 | 46 | 1.3 |  |  | Stephen McCann |  |  | "Defines a mechanism to enable IEEE 802.11 stations to transmit and receive broadcast data in an infrastructure BSS, both in cases where the transmitter(s) and the receiver(s) are associated and when they are not; ..." Non-AP STAs, even when each of them are associated to an AP, are not associated to each other and can be categorized as a "when they are not" case. Is it expected at a non-AP STA to receive and process broadcast data transmitted from another non-AP STA? (This is related to my previous comment, CID 1537.) I don't think so. | Change it to read "Defines a mechanism to enable IEEE 802.11 stations to transmit and receive broadcast data in an infrastructure BSS, in both cases where a transmitter is an access point (AP) and receivers are either associated or non-associated non-AP stations (STAs) and where a transmitter is a non-AP STA and receivers are APs; ..." Change also the abstract in p.3 to read "Abstract: This amendment specifies modifications to the IEEE 802.11 medium access control (MAC) specifications that enable enhanced transmission and reception of broadcast data in an infrastructure BSS in both cases where a transmitter is an access point (AP) and receviers are either associated or non-associated non-AP stations (STAs) and where a transmitter is a non-AP STA and receivers are APs." Change also the first sentence in 4.3.31 to read "Enhanced broadcast services (EBCS) provides enhanced transmission and reception of broadcast data in both cases where a transmitter is an access point (AP) and receviers are either associated or non-associated non-AP stations (STAs) and where a transmitter is a non-AP STA and receivers are APs." Or, if these changes are not accepted or taken into account, please clarify that a non-AP STA associated with an AP is expected to also receive and process broadcast data transmitted from another non-AP STA, at least in the resolution. | Discussion required. I would prefer not to make the supplementary purpose (1.3) so specific. Using the terminology "802.11 stations" should be sufficient rather than listing specific uplink and downlink cases. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2000 | Abhishek Patil | 257 | 2 | 4.3.31 | 25 | 16 | T | N | 25.16 | 16 | 4.3.31 |  |  | Stephen McCann |  |  | From P25L16: "... and in cases where there is no association between transmitter and receiver(s)." From the text it looks like EBCS allows non-infrastructure BSS operation in unassociated state. Update the text to clarify that it is still infrastructure BSS even when the transmitter and receiver are in unassociated state. | Update the sentence to be similar to the one on page 3 (Abstract): " ... that enable enhanced transmission and reception of broadcast data in an infrastructure BSS both where there is an association between the transmitter(s) and the receiver(s) and in cases where there is no association between transmitter(s) and receiver(s)." | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2207 | Mark RISON | 257 | 2 |  |  |  | T | Y | [5 empty] | Stephen McCann |  |  | The term "unassociated STA" is ambiguous, as a STA that is associated in one BSS is unassociated from the perspective of another BSS | Change to wording like "and where an AP is transmitting to or receiving from an unassociated non-AP STA" | Rejected: There are 44 occurances of the term "unassociated STA" within the baseline (REVme D0.4). This change is not required. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2213 | Michael Montemurro | 257 | 2 | 1.3 | 21 | 47 | T | N | 21.47 | 47 | 1.3 |  |  | Stephen McCann |  |  | "when they are associated or not" could be worded better. | Change "are associated and when they are not" to "the non-AP STAs are not required to be members of a BSS" | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2217 | Michael Montemurro | 257 | 2 | 9.3.2.1.4 | 23 | 39 | T | N | 23.39 | 39 | 9.3.2.1.4 |  |  | Stephen McCann |  |  | Given that EBCS frames are available to STAs beyond the BSS and may be transmitted by multiple APs, they should be addressed independently of the BSS. | Provide an L2 addressing scheme that will allow EBCS traffic to be differentiated from WLAN BSS traffic. Consider the proposal in https://mentor.ieee.org/802.11/dcn/21/11-21-1540-00-00bc-topology-and-address-mapping.pptx. .The commenter is willing to collaborate to create a submission to address this comment. | Submission required. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2268 | Xiaofei Wang | 257 | 2 | 9.4.5.1 | 46 | 52 | T | N | 46.52 | 52 | 9.4.5.1 |  |  | Stephen McCann |  |  | Change "Enhanced Broadcast Services Request" to "Enhanced Broadcast Services Content Request" as agreed in LB252 | Change "Enhanced Broadcast Services Request" to "Enhanced Broadcast Services Content Request" throughout the spec | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2269 | Xiaofei Wang | 257 | 2 | 9.4.5.1 | 46 | 52 | T | N | 46.52 | 52 | 9.4.5.1 |  |  | Stephen McCann |  |  | Change "Enhanced Broadcast Services Request" to "Enhanced Broadcast Services Content Response" as agreed in LB252 | Change "Enhanced Broadcast Services Request" to "Enhanced Broadcast Services Content Response" throughout the spec | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2270 | Xiaofei Wang | 257 | 2 | 9.4.5.1 | 50 | 46 | T | N | 50.46 | 46 | 9.4.5.1 |  |  | Stephen McCann |  |  | PHY type and detailed TX parameters may provide additional information, however,not quite sure what value is added to provide this information. Please clarify. If no value is added, suggest to remvoe. | as in comment, suggest to remove all PHY spec related to PHY type, data rate if no value is added. | Discussion required. I need to understand a little more about the comment. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2203 | Mark RISON | 257 | 2 |  |  |  | T | Y | [5 empty] | Stephen McCann |  |  | What is the difference between "content stream" and "EBCS content stream"? | Add "EBCS " before "content stream" where not present | Revised. Replace "content stream" and also "EBCS content stream" with "EBCS traffic stream". | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2204 | Mark RISON | 257 | 2 |  |  |  | T | Y | [5 empty] | Stephen McCann |  |  | What is an "[EBCS] content stream"? | Add a definition | Revised. Replace "content stream" and also "EBCS content stream" with "EBCS traffic stream". | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR
2239 | Stephen McCann | 257 | 2 | 9.4.5.1 | 46 | 48 | T | N | 46.48 | 48 | 9.4.5.1 |  |  | Stephen McCann |  |  | The ANQP-elements titles should use the acronym "EBCS". | Change all occurances of "Enhanced Broadcast Services...." ANQP-element to "EBCS...." ANQP-element throughout the draft. | Accepted. | CHAIR | [6 empty] | 2021-11-02 15:10 | CHAIR