## Slide 1: TGbh Closing Report
Date: 2021-11-15
Authors:

## Slide 2: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
November 2021 Plenary Session (virtual)

## Slide 3: Work Completed
Agenda is here: 11-21/1628r6
Continued review of tracking document: 11-21/0332r24
  Contributions:
    11-21/1585r10: Identifiable Random MAC address
    11-21/1853r0: ID Query analysis
    11-21/1839r0: Transient STA ID
    11-21/1634r0-00bh-private-identifier-requirements-for-tgbh.docx Private identifier requirements for TGbh (still pending)
  Clarifying group agreements on requirements
Review of liaison from WBA (11-21/0703r0) is completed, analysis in: 11-21/1141r0, and tracking document.
  Still working on response
Missed target for D0.1 out of this session, timeline update needed

## Slide 4: Next steps
Complete review of requirements/metrics for proposed solutions
Consider proposed solutions for impacted features/functions, and incorporate into D0.1
WBA liaison response

## Slide 5: Timeline
  PAR approved Feb 2021
  First TG meeting Mar 2021
  D0.1 Nov 2021
  Initial Letter Ballot (D1.0) Mar 2022
  Recirculation LB (D2.0) Jul 2022
  Initial SA Ballot (D3.0) Nov 2022
  Final 802.11 WG approval Mar 2023
  802 EC approval May 2023
  RevCom and SASB approval May 2023

## Slide 6: Teleconference(s)
Tuesday, Dec 7, 9:00-11:00 ET
Thursday, Dec 16, 19:00-21:00 ET
Thursday, Jan 6, 19:00-21:00 ET
Tuesday, Jan 11, 9:00-11:00 ET

## Slide 7: January 2022 Plans
Four meeting slots planned
Consider “solutions” to use cases that are in 802.11 scope to resolve
Formulate D0.1