## Slide 1: 802.11 WG January 2022 Session Report
Date: 2022-01-24
Authors:

## Slide 2: Abstract
This document is a digest of the closing reports of all 802.11 sub-groups for presentation at the January 2022 closing plenary meeting. Liaison reports (including liaison reports from the opening plenary) are also included.

## Slide 3: Attendance data

## Slide 6: Attendees by affiliation (attended at least one meeting November to January)

## Slide 7: Attendance by subgroup (November to January)

## Slide 8: Closing Reports

## Slide 9: 802.11 WG Editor’s Meeting (January 2022)
Date: 2022-01-23
Authors:

## Slide 10: Volunteer Editor Contacts
  WG – Robert Stacey – robert.stacey@intel.com, Peter Ecclesine - pecclesi@cisco.com
  TGaz – Roy Want RoyWant@google.com , Chao Chun Wang – chaochun.wang@mediatek.com
  TGbb – Volker Jungnickel – volker.jungnickel@hhi.fraunhofer.de , Harry Bims harrybims@me.com
  TGbc – Carol Ansley – carol@ansley.com
  TGbd – Yujin Noh – Yujin.Noh@senscomm.com
  TGbe – Edward Au – edward.ks.au@huawei.com
  TGbf – Claudio da Silva – claudiodasilva@fb.com
  TGbh – Carol Ansley – carol@ansley.com
  TGbi – Po-kai Huang – po-kai.huang@intel.com
  REVme – Emily Qi – emily.h.qi@intel.com, Edward Au – edward.ks.au@huawei.com,

## Slide 11: MDR Status
802.11 Working Group Mandatory Draft Review
  802.11-11/615r6 documents the process. MDR now in the 802.11 Operating Manual 802.11-14/0629r8. The process causes some changes to the draft, so the report is done after the editing is done.
REVmd on Draft 2.1 was started out of February 2019 (Robert Stacey, Joseph Levy, Carol Ansley, Menzo Wentink, Bahar Sadeghi, Mark Hamilton, Yongho Seok, Emily Qi, Edward Au, Peter Ecclesine) 19/260r15 – IEEE SA staff - mixing normative and informative, see 19/1444r4 MDR complete
P802.11ay was started on D3.1 out of March 2019 (Robert Stacey, Solomon Trainin, Edward Au, Emily Qi, Yongho Seok, Peter Ecclesine) 19/681r6 MDR complete
P802.11ax was started on D4.1 out of May 2019 (Robert Stacey, Edward Au, Yongho Seok, Naveen Kakani, Perry Correll, Peter Ecclesine, Po-Kai Huang) 19/1015r4 MDR complete
P802.11ba was started on D4.0 out of September 2019 (Robert Stacey, Po-Kai Huang, Rojan Chitrakar, Yunsong Yang, Yongho Seok, Mark Hamilton ) 19/1765r6 MDR complete
P802.11az was started on D3.0 out of January 2021 (Robert Stacey, Emily Qi, Edward Au, Carol Ansley, Peter Ecclesine, Yongho Seok, Mark Hamilton) 21/0329r7 July 15, 2021 MDR complete
P802.11bd was started on D3.0 out of November 2021 (Robert Stacey, Emily Qi, Peter Ecclesine, Joseph Levy, Edward Au, Carol Ansley, Yongho Seok, Yujin Noh) MDR Report 11-22/0021. There will be a final MDR meeting in the March 7 Editors meeting itself. This allows the TG knows what all the MDR changes are.

## Slide 12: 802.11 Style Guide
See 11-09-1034-19-0000-802-11-editorial-style-guide.docx
We update 802.11 Style Guide based on IEEE Standards Style Manual and consistency changes in final publication of the 802.11 standard
Editor’s responsibility includes checking the 2020 IEEE Standards Style Manual when creating or updating drafts. https://mentor.ieee.org/myproject/Public/mytools/draft/styleman.pdf
Submissions with draft text should conform to both the WG11 Style Guide and IEEE Standards Style Manual
Note that the 802.11 Style Guide evolves with our practice, we’ve added the particular use of “Tail” and explained our practice in acronyms.
We may revisit numbering of MAC addresses and their form of expression

## Slide 13: MIB Style, Visio and Frame Practices
11-15/355r13 MIB TruthValue usage patterns
MIB Style: We use a single style with appropriately set tabs, and use leading Tabs to distinguish the syntax and description parts. (Adrian Stephens Feb 9, 2010)
Two ways to format a figure & its caption in frame:
  Insert a table. Insert anchored frame inside table cell to hold graphics. Use table caption as figure caption.
  Insert an anchored frame. Insert caption inside a text frame inside the anchored frame. Insert graphics inside the anchored frame.
Do not reference other clauses in Visio figures, it is very hard to maintain the references in figures
Keep embedded figures using Visio as long as possible (not in Word)
  Near the end of sponsor ballot, turn these all into .emf (windows meta file) format files (you can do this from visio using “save as”).
  Keep separate files for the .vsd source and the .emf file that is linked to from frame. There is high likelihood we should use .emf
  Use the figure number or a short version of the figure title (shown in your final draft) for the name of the Visio and emf file.
  One figure, one Visio file. Don’t store multiple figures in one Visio file.
Frame format figures are tables
The MathML editor for equations may be applicable

## Slide 14: Editor Amendment Ordering
Data as of Jan 2022
See http://grouper.ieee.org/groups/802/11/Reports/802.11_Timelines.htm
We will revisit the running order in March, 2022. Changes are usually based on MDR suitability.
Amendment Number | Task Group | Projected REVCOM Date
802.11-2020 Amendment 4 802.11-2020 Amendment 5 | TGaz – 282 TGbd – 146 | Dec 2022 Dec 2022
802.11-2020 Amendment 6 | TGbc - 106 | Mar 2023
802.11-2020 Amendment 7 | TGbb – 27 | Dec 2022
REVme 802.11-2024 Amendment 1 | TGm – 6095 TGbe – 765 | Sep 2024 May 2024

## Slide 15: Draft Development Snapshot
TG | Published or Draft Baseline Document |  |  |  |  |  |  |  |  | Source | MDR | Editor | Snapshot Date
 | Published | az | bd | bc | bb | me | be |  |  |  |  |  | 
az | Y | 4.0 |  |  |  |  |  |  |  | Word | Yes | Roy Want, Chao Chun Wang | 13-Jan
bd | N | 4.0 | 3.0 |  |  |  |  |  |  | FrameMaker 2020 release | No | Yujin Noh | 17-Jan
bc | N | 4.0 |  | 2.1 |  |  |  |  |  | FrameMaker 2020 release | No | Carol Ansley | 17-Jan
bb | N | 4.0 | 2.1 | 2..0 | 1.0 |  |  |  |  | Word | No | Volker Jungnickel, Harry Bims | 17-Jan
me | Y |  |  |  |  | 1.0 |  |  |  | FrameMaker 2020 release | No | Emily Qi, Edward Au | 13-Jan
be | N | 4.0 | 2.1 | 2.0 | 0.7 | 0.4 | 1.31 |  |  | FrameMaker (old) | No | Edward Au | 16-Jan
Most current doc shaded green.
Jan 2022
Changes from last report shown in red.

## Slide 16: ARC Closing Report
Date: 2022-01-21
Authors:

## Slide 17: Abstract
This document is the closing report for ARC SC,
January 2022 Plenary Session (virtual)

## Slide 18: Work Completed
Agenda is here: 11-21/1994r5
Annex G, Part 2 (Part 1 is completed, and in REVme D1.0):
  Part 2: Create a new and more useable Annex G with a friendly notation/style and cross-references to main body text for technical details:
    Considered: The need for Frame Exchange Sequences: 11-22/0101r0 – Harry Bims
    Will resume on teleconferences
IEEE Std 802 revision:
  Reviewed proposal for PAR/scope of work in (note 802.1 document): https://mentor.ieee.org/802.1/dcn/21/1-21-0076-08-ICne-draft-ella-report.pdf
  No comments at this time. Will continue to monitor Nendica work on this.

## Slide 19: Work Completed
Clause 6
  Reviewed: 11-21/1822r1 – Graham Smith
  Started brainstorming on a potentially better (more clear, more concise) approach to specifying MLME SAP.
  Will apply ideas generated to some examples in subclause 6.3, and consider on teleconferences.
Consider TGbe/MLO informative annex
  Deferred

## Slide 20: Monitoring/future activities
    Other items being tracked (but not actively worked unless/until contributions):
    “What is a STA?” (per REVmd discussion: 11-19/0106r0)
    Off-channel TDLS architecture
    MLME-RESET, versus MLME-JOIN, MLME-START, MLME-SCAN and MLME-END
      One aspect is how MAC address is set/controlled – related to IEEE 1609/TGbd activities
    Nendica’s/TGbe’s discussion on 802.11 in a Deterministic Network/Time-Sensitive Networking

## Slide 21: Plans
Ongoing work:
Annex G replacement
Status updates on IEEE Std 802 revision, technical work if/as appropriate
Consider the purpose and value of Clause 6
TGbe MLO informative annex consideration
Other monitoring/future activities
Teleconferences
  Feb 7 (Monday): 13:00 ET, 2 hours
  Feb 24 (Thursday): 19:00 ET, 2 hours
Two meeting slots requested in March

## Slide 22: IEEE 802.11 Coexistence SC Jan 2022 (virtual) closing report
Date: 20220125
Authors:

## Slide 23: IEEE 802.11 Coexistence SC achieved its goals as a discussion forum for coexistence issues
802.11 Coex SC summary for Jan 2022 (11-22-1997)
  Coex issues with LAA are real today and coex is not a solved problem
    Coex with NR-U is likely to have similar issues, but potentially worse
    More actual measurements are required to understand scope of the issues!
  EN 301 893 (5 GHz) is progressing well, with a compromise in place
    But it is likely to cause potential 802.11be/ax coex issues in Europe …
    … with more work in Coex SC/TGbe/ETSI BRAN/WFA required to understand and resolve
  EN 303 687 (6 GHz) is progressing well, with a compromise in place
    But with the ultimate NB FH resolution likely to be delayed until next revision …
    .. and C2C becoming more contentious
    Spec work in TGbe/TGme may be required to optimise coex in Europe
  There is ongoing competition for access to 6 GHz (licensed vs unlicenced)
  3GPP RAN is starting work on SL-U (Side Link) that will require monitoring

## Slide 24: IEEE 802.11 Coexistence SC will continue promoting good coexistence in Mar 2022
IEEE 802.11 Coexistence SC will meet virtually in Mar 2022
  Review latest Wi-Fi/LAA coexistence measurements
  Review results of BRAN #113 (Feb 2022)
    … particularly progress of the NB FH & C2C for 6 GHz in Europe
  Discuss need to refine 802.11ax/be standard for optimal operation in 6 GHz in Europe
    ie, are IEEE 802.11 changes needed to account for EDT @ -72 dBm constraint in 6 GHz?
  Discuss mitigation of EN 301 893 compromise on 802.11be operation in 5 GHz in Europe
    ie, is 802.11be operation adversely impacted by the compromise compared to 802.11ax operation?
  Discuss results of possible coex presentation in Mar 2022 to TGbe or WG
    A draft is available in 11-22-0180-00; comments welcome
  Discuss possible LS to WFA about market drivers of coex work
    Some draft questions are in 11-22-0180-00; comments welcome
  Other issues: 3GPP SL-U, 60 GHz coex , 6 GHz availability, …
Contributions are sought & encouraged!

## Slide 25: PAR Review SC
Did not meet - no report

## Slide 26: WNG SC Closing Report
Date: 2022-01-25
Authors:

## Slide 27: Abstract
Closing report for WNG SC for January 2022 virtual meeting

## Slide 28
Summary
Final Agenda
    https://mentor.ieee.org/802.11/dcn/21/11-21-1970-01-0wng-agenda-for-wng-sc-2022-january.pptx
Presentations at January 2022 meeting
  “Beyond be’” – Rolf de Vegt (Qualcomm) - Document 22/0059r0
  “Next-Gen-After-11be” - Vinko Erceg (Broadcom) – Document 22/0032r0
  “Next generation after 802.11be” – Laurent Cariou (Intel) – Document 22/0046r1
  “Look ahead to next generation” - Ming Gan (Huawei) – Document 22/0030r1
  “Inconsistent STA range and channel support indications” – Amelia Andersdotter, Sean Muir (Sky UK Group) – Document 22/0014r0
Minutes
  https://mentor.ieee.org/802.11/dcn/22/11-22-0106-00-0wng-wng-meeting-minutes-2022-january-electronic-meeting.docx
Plans for March 2022
  TBD – call for presentations will be sent out in February
No motions in the SG, no conference calls

## Slide 29: IEEE 802 JTC1 Standing Committee January 2022 (virtual) closing report
Date: 20220124
Authors:

## Slide 30: The IEEE 802 JTC1 SC reviewed the PSDO process status, including IPR issues holding up 802.11ax/ay/ba
Agenda - 11-21-1866; Minutes - tbd
802.11ax/ay/ba IPR issue
Situation: IPR holding up PSDO process
  Multiple 802.11 submissions into PSDO process are “on hold” due to negative LoAs
Status: some progress
  ISO has informed IEEE that it will reach out to the submitters to try to obtain positive declarations to ISO (under ISO IPR policy) that demonstrate a willingness to license on terms that are either royalty-free or reasonable and non-discriminatory
Next steps: unclear
  The timeline, and any deadlines, for this process are currently unknown …
WG | Completed | In-process
802.1 | 38 | 14
802.3 | 17 | 15
802.11 | 12 | 9
802.15 | 3 | 0
802.16 | 0 | 0
802.19 | 0 | 0
802.21 | 3 | 0
802.22 | 3 | 1
All | 76 | 39

## Slide 31: The SC discussed a possible LS to SC6/WG1 in relation to an PWI on Deterministic Wireless Industrial Network
SC6/WG1 has decided to start discussion on a PWI on Deterministic Wireless Industrial Network in Feb 2022
  Based on assertions that 5G-TSN is not good enough and Wi-Fi 6 (802.11ax) is worse
IEEE 802 JTC1 SC discussed a draft LS in response to a request in SC6/WG1
  See 11-22-0081-00 for proposed LS …
  … and 11-22-0080-00 for referenced ppt
Since the session, there has been more discussion & editing
  In the final version (11-22-0081-06) …
  … the ppt has been dereferenced to keep the message simple
  … language refined, including to (mostly) remove Wi-Fi & Ethernet terminology

## Slide 32: Consensus has been achieved on a LS in relation to an PWI on Deterministic Wireless Industrial Network
The high level summary of the refined proposed LS is
  IEEE 802 is providing comments on the PWI proposal for a Deterministic Wireless Industrial Network project
  Industrial networks are evolving to use TSN over standards based, widely available networks
  The 802.3 and 802.11 standards continue to be refined to meet industrial network requirements for TSN
  IEEE 802 requests that ISO/IEC JTC1/SC6/WG1 assist in developing 802.3 and 802.11 refinements
802.11 WG approval is part of the approval process
  802.1 TSN TG approved the LS, as long as 802.11 WG approves
  802.11 approval is requested at the closing plenary
  802 EC is required next, in time for submission to WG1 by 1 Feb 2022

## Slide 33: The IEEE 802.11 WG are requested to approve the proposed LS to ISO/IEC JTC1/SC6/WG1
Motion
  The IEEE 802.11 WG recommends to the IEEE 802 EC that the material in 11-22-0081r6 be liaised to ISO/IEC JTC1/SC6/WG1 in relation to the Preliminary Work Item (PWI) proposal in SC6/WG1 for a new Deterministic Wireless Industrial Network, with editorial privileges given to the IEEE 802.11 WG Chair
  Moved: Andrew Myles (personal motion)
  Seconded:

## Slide 34: The IEEE 802 JTC1 SC will undertake its usual work at its virtual meeting in Marc 2022
IEEE 802 JTC1 SC plans for the virtual meeting in March 2022
  Execute PSDO process
  Deal with issues arising from IPR related comments on 802.11ax/ay
  Review SC6/WG1 interim meeting discussions
  …

## Slide 35: REVme Closing Report – January 2022
Date: 2022-01-24
Authors:

## Slide 36: Work Completed
Approved remaining CC35 comment resolutions
Initiated comment resolution for comments received in initial LB
  Approved 108 comment resolutions
Timeline change (next slide)

## Slide 37: Updated Timeline
Feb 2021 – PAR Approval
March 2021– Initial meeting, issue comment collection on IEEE Std 802.11-2020
March 2021 – Draft 0.00 available
May 2021 – Process CC input, 11ax, 11ay, 11ba integration begins
Nov 2021 – Initial D1.0 WG Letter ballot
Jul 2022 – D2.0 Recirculation LB
Mar 2023 – D3.0 Recirculation LB (11az + other amendments <11bc, 11bd, 11bb> )
Sep 2023 – D4.0 Recirculation (<other amendments – if Jul>)
Nov 2023 – D5.0 Initial SA Ballot
Mar 2024 – D6.0 Recirculation SA Ballot
May 2024 – D7.0 Recirculation SA Ballot
Jun 2024 – D7.0 Recirculation SA Ballot (clean recirculation)
Sep 2024 – RevCom/SASB Approval

## Slide 38: Plans for March
Teleconferences:
  Next call: Monday 31 January 2022 at 10am ET, 2hrs
  7, 14, 25, 28 Feb – 10am ET, 2hrs
  21 Mar – 10am ET, 2hrs
Request 5 sessions for the March Plenary
Continue comment resolution on initial LB

## Slide 39: TGaz Next Generation Positioning January Electronic Meeting Closing Report
Date: 2022-01-24
Authors:

## Slide 40: Abstract
This document is the TGaz Next Generation Positioning closing report for the IEEE 802.11 plenary electronic meeting, Jan. 2022.

## Slide 41: Jan. Progress and Targets Towards the March Meeting
Status and Work completed this week:
  Continued SA Ballot CR:
    Group resolved 27 comments and adopted additional text changes.
    Resolved ~50% of all technical and general comments.
Targets towards the March meeting:
  Complete review and resolution for 75% of SAB comments received on P802.11 D4.0 SA1 comments.
  Publish P802.11az D4.1 incorporating approved resolutions prior and including the January meeting.
  Resolve majority oof editorial comments.
Chart: P802.11az SA1 CR Status
| Technical | General | Editorial
Received | 166 | 6 | 192
Resolved | 76 | 0 | 0

## Slide 42: Timeline – TG progress update past the Jan. meeting
Clean
2021
2020
2019
2022
2023
.11az Draft 2.0 11-2019
Recirculation
D1.0
Jan. 19
Initial
WG ballot
LB240 CR
Initial WG ballot LB240 Pass
LB249
LB240 completion/
recirc. init
LB249 completion/
2nd recirculation
.11az Draft 3.0 01-2021
Recirculation
.11az Draft 4.0 07-2021
Recirculation
.11az MDR and SA ballots
07-2021
Publication
LB253
SA2
MDR
SA1
LB 255
No changes made, in preparation to SA ballot
LB249 completion/
2nd recirculation
1st SA start
REVcom
SA3
1st SA comp.
05-22
2nd SA comp.
07-22
3rd SA comp.
11-22

## Slide 43: Scheduled telecons
* - newly announced
+ TGaz Plenary (motion) meeting.
** - meeting as part of the IEEE week, refer to WG agenda document for details.
Feb. 3rd Thu. 12:00 – 14:00 ET*
Feb. 9th Wed. 13:00 – 15:00 ET*
Feb. 16th Wed. 13:00 – 15:00 ET*
Feb. 23rd Wed. 13:00 – 15:00 ET*
Mar. 2nd Wed. 13:00 – 15:00 ET*

## Slide 44: Light Communications Task Group (TGbb) January 2022 Closing Report
Date: 2022-01-24
Authors:

## Slide 45: Abstract
This presentation contains the IEEE 802.11 Light Communications Task Group closing report for the January 2022 session.

## Slide 46: TGbb activities at the January 2022 meeting
  Content
  Comment resolution on LB260 against Draft 1.0 (333 comments in total)
    131 Editorial
    183 Technical
    18 General
  Resolved
    116 Technical
    10 Editorial
  Meeting agenda and motions are available in doc. 11-21/1991r4.
  Minutes of the meeting are available in doc. 11-22/0189r0.

## Slide 47: TGbb moving forward
  Comment resolution against D1.0
  Teleconference plans:
    3 Feb. (03:00 EDT) 09:00 CET for 1h
    7 Feb. (11:00 EDT) 17:00 CET for 1h
    10 Feb. (03:00 EDT) 09:00 CET for 1h
    17 Feb. (03:00 EDT) 09:00 CET for 1h
    24 Feb. (03:00 EDT) 09:00 CET for 1h
    3 Mar. (03:00 EDT) 09:00 CET for 1h

## Slide 48: TGbc Closing Report
Date: 2022-01-21
Authors:

## Slide 49: Abstract
Closing report for IEEE 802.11 TGbc (Broadcast Services) for January 2022.

## Slide 50: Meeting Goals & Accomplishments of the week
Goal for the week:
Continue comment resolution process
Revisit Timeline
Accomplishments
Group met 4 times this week
Resolved 101 technical comments
  87 comments resolved and approved
  14 comments resolved and ready for motion
Updated timeline
Owning Ad-hoc | Count of CID
EDITOR | 186
2021-11-11 - approved | 62
2021-11-12 - approved | 4
2021-11-23 - approved | 18
2022-01-04 - approved | 15
2022-01-19 - approved | 70
2022-01-20 - approved | 16
2022-01-20 - motion 144 approved | 1
CHAIR | 108
2022-02-01 - ready for motion | 14
(Leer) | 94
Gesamtergebnis | 294

## Slide 51: Plans for Next Meeting & Upcoming Telcos
Telcos
Continue comment resolution
Upcoming meeting
Finish comment resolution from WG Recirculation LB257 and
Create D3.0 (out of March meeting)
Go to WG recirculation LB (D3.0) out of March meeting
Weekly Telcos
Tuesdays, 10:00h – 11.00h ET (1 hours)

## Slide 52: TGbc schedule (updated)
January 2019 First meeting as a task group
June 2020 Call for comments on D0.1
November 2020 Initial WGLB (D1.0)
September 2021 D2.0 WG Recirculation LB
March 2022 D3.0 WG Recirculation LB
March 2022 Editorial review / MEC/MDR on D3.0
May 2022 D4.0 WG Recirculation LB
May 2022 Form SAB Pool
Jul 2022 D4.0-unchanged WG Recirculation LB
Jul 2022 Initial SAB (4.0)
November 2022 Recirculation SAB
March 2023 Final WG/EC approval
May 2023 Revcom/SASB approval

## Slide 53: References
Agenda for this week: 11-21/1954
Meeting / Chair’s Slide Deck: 11-21/1955
Meeting minutes: 11-22/0050
Snapshot Slide: 11-21/1956
Closing report: 11-21/1957
TGbc Motion Booklet: 11-18/2123
TGbc Selection Procedure: 11-19/0135
TGbc Functional Requirements: 11-19/0151
TGbc UseCase Document: 11-19/268

## Slide 54: IEEE 802.11 Interim Week Jan 2022 IEEE 802.11 TGbd Closing Report
Chair: Bo Sun (ZTE)
Vice Chair: Hongyuan Zhang (NXP),
Joseph Levy (InterDigital)
Secretary: Yan Zhang (NXP)
Tech Editor: Yujin Noh (Senscomm)

## Slide 55: TGbd’s Progress during this interim week
4 TGbd sessions were held during the week
Approved TG minutes for Nov plenary week and following TCs before Jan interim week.
Presented and discussed 12 CR docs and approved CRs for 87 of 107 (81%) comment from LB 259.
Approved 4 teleconferences till Mar plenary week.
TGbd agenda and minutes documents for this week:
  https://mentor.ieee.org/802.11/dcn/21/11-21-2000-04-00bd-tgbd-agenda-for-jan-interim-2022.pptx
  https://mentor.ieee.org/802.11/dcn/22/11-22-0167-00-00bd-ieee-802-11bd-january-2022-interim-meeting-minutes.docx
Goal for future TCs: proceeding the rest comments collected from LB259 and MDR

## Slide 56: TGbd Progress Documents
TG Documents | Latest Revision
Definition and requirements | 11-19/0202r1
Selection Procedure document | 11-19/0030r6
Functional Requirement document | 11-19/0495r3
Spec Framework document | 11-19/0497r7
Liaison response to IEEE VT/ITS 1609 WG | 11-19/0437r3
Liaison response to ITU-T CITS | 11-19/0843r0
TBbd FRD/SFD Motion Booklet | 11-19/0514r14
TGbd Use Case document | 11-19/1342r1
Teleconference Agenda | 11-20/0774r10, 11-20/1164r7, 11-20/1352r9, 11-20/1561r7, 11-20/1806r2, 11-20/1891r0, 11-20/1923r11, 11-21/0177r2, 11-21/0207r8, 11-21/0595r3, 11-21/0597r7, 11-21/0904r1, 11-21/0941r2, 11-21/1303r4, 11-21/1326r8, 11-21/1622r4, 11-21/1623r4, 11-21/1998r2, 11-21/1999r3, 11-2I/2000r4
Teleconference Minutes | 11-20/0276r11, 11-20/1105r8, 11-20/1489r1, 11-20/1655r3, 11-20/1775r1, 11-20/1907r1, 11-21/0068r0, 11-21/0117r0, 11-21/0327r0, 11-21/0453r0, 11-21/0454r0, 11-21/0565r0, 11-21/0655r0, 11-21/0806r0, 11-21/0889r0, 11-21/1138r0, 11-21/1468r0, 11-21/1544r0, 11-21/1769r0, 11-21/1863r0 11-22/0167r0
Tech Editor Report | 11-19/2045r15 (D3.0)
Comment Database | 11-20/0701r7 (D0.3), 11-20/1887r10 (LB251), 11-21/1296r6 (LB254), 11-21/2018r4 (LB259)
Coexistence Assurance Document | 11-20/1564r2

## Slide 57: Motion #1 (approval of Comment Resolutions)
Move to approve the comment resolutions to 87 CIDs which marked as “ready for motion” as in 11-21/2018r4
Moved: Yujin Noh Seconded: Stephan Sand
Result: Approved with unanimous consensus

## Slide 58: TGbd Timeline (no change)
  PAR approved Dec 2018
  First TG meeting Jan 2019
  D0.1 Nov 2019
  D1.0 Letter Ballot Oct 2020
  D2.0 LB recirculation Jul 2021
  Form SA Ballot Pool Nov 1 to Nov 30, 2021
  D3.0 LB recirculation Dec 2021
  D4.0 LB recirculation Mar 2022
  D4.0 LB unchanged recirculation Mar 2022
  Initial SA Ballot (D4.0) Mar 2022
  Final 802.11 WG approval Sep 2022
  802 EC approval Oct 2022
  RevCom and SASB approval Dec 2022

## Slide 59: IEEE 802.11 TGbd TC Plan
Feb 8th, 2022, 9:00am ~ 11:00am, ET
Feb 15th, 2022, 10:00am ~ 11:59am, ET
Feb 22nd, 2022, 9:00am ~ 11:00am, ET
Mar 1st, 2022, 10:00am ~ 11:59am, ET

## Slide 60: TGbe January 2022 Closing Report
Date: 2022-01-24
Authors:

## Slide 61: TGbe (Extremely High Throughput)
TGbe had scheduled 4 conf. calls during the January electronic interim
  Two Joint calls, and two parallel MAC/PHY calls
    Covered comment resolution documents
    Approved the resolution of several technical/editorial comments and PDT submissions
      ~60% of all CC36 comments are now resolved
  Approved the creation of TGbe D1.4
    TGbe D1.4 is expected to be available by end of this month
Agenda is available in 1971r8, with queue statuses available in 0110r0
  Future Teleconference Plan is provided in the next slide
Motions List is available in 1982r59
Distribution of ~4350 CIDs
9%
67%
24%
Resolution Status

## Slide 62: Teleconference Plan
Feb 14 Monday – MAC/PHY 19:00-21:00 ET
Feb 16 Wednesday – Joint** 10:00-12:00 ET
Feb 17 Thursday – MAC 10:00-12:00 ET
Feb 21 Monday – MAC/PHY 19:00-21:00 ET
Feb 23 Wednesday – Joint** 10:00-12:00 ET
Feb 24 Thursday – MAC 10:00-12:00 ET
Feb 28 Monday – MAC/PHY 19:00-21:00 ET
Mar 02 Wednesday – Joint (Motions) 10:00-12:00 ET
Mar 03 Thursday – MAC 10:00-12:00 ET
Mar 07 Monday – MAC/PHY 19:00-21:00 ET
Mar 09 Wednesday – Joint** 10:00-12:00 ET
Mar 10 Thursday – MAC 10:00-12:00 ET
** Can be modified to MAC/PHY on the fly with pre-announcement.
Jan 26 Wednesday – MAC (No SP) 10:00-12:00 ET
Jan 27 Thursday – MAC 10:00-12:00 ET
Jan 31 Monday – No Conf Call Holiday
Feb 02 Wednesday – No Conf Call Holiday
Feb 03 Thursday – No Conf Call Holiday
Feb 07 Monday – MAC/PHY 19:00-21:00 ET
Feb 09 Wednesday – Joint (Motions) 10:00-12:00 ET
Feb 10 Thursday – MAC 10:00-12:00 ET

## Slide 63: Timeline
PAR approved Mar 2019
First TG meeting May 2019
D0.1 Sep 2020
D1.0 WG Comment Collection May 2021
D2.0 WG Comment Collection Mar 2022
D3.0 Letter Ballot Nov 2022
Initial Sponsor Ballot (D4.0) May 2023
Final 802.11 WG approval Mar 2024
802 EC approval Mar 2024
RevCom and SASB approval May 2024

## Slide 64: Task Group BF January 2022 Closing Report
Date: 2022-01-24
Authors:
Name | Affiliation | Address | Phone | Email
Tony Xiao Han | Huawei Technologies Co., Ltd. | F3, Huawei Base, Shenzhen, China |  | Tony.hanxiao@huawei.com

## Slide 65: Abstract
This document is the closing report for Task Group BF for the January 2022 session.

## Slide 66: TGbf (WLAN Sensing) – January 2022
Progress during January 2022 meeting
  4 teleconference calls for TGbf (January 18, 19, 21, 24, 9am - 11:00am ET)
  Presentation of technical submissions (e.g., Feedback type, general protocol and procedure……)
  Developing the SFD and D0.1
Goals for the next two months
  Presentation of technical submissions (e.g., PDT for D0.1, Feedback type, general protocol and procedure ……)
  Speed up the technical discussion and developing the SFD and D0.1 (Requested 3 calls per week)

## Slide 67: TGbf Timeline (Updated)
  PAR approved Sep 2020
  First TG meeting Oct 2020
  Comment Collection (D0.1) Jan 2022Mar 2022
  Initial Letter Ballot (D1.0) Jul 2022 Sep 2022
  Recirculation LB (D2.0) Jan 2023
  Recirculation LB (D3.0) May 2023
  Recirculation LB (D4.0) July 2023
  Initial SA Ballot (D4.0) Sep 2023
  Final 802.11 WG approval July 2024
  802 EC approval July 2024
  RevCom and SASB approval Sep 2024
Timeline for D0.1 (Tentative)
Week of January 3
  Editor provides initial list of topics (and updated SFD revision) (Tuesday)
  Chair issues call for volunteers (Tuesday)
  POCs and volunteers are identified for topics in the initial list (Friday)
January 2128, 2022
  Deadline for baseline document for each topic (in the initial list) to be uploaded
March 2022 IEEE Plenary
  Deadline for contributions to pass motion and be included in D0.1
  Seek TGbf approval to go to comment collection (“Move to Approve a 30-day comment collection on TGbf D0.1?”)
March 28 (Monday, two weeks after March 2022 Plenary)
  Editor releases D0.1
  If the Motion is favorable, the TG chair sends a request to the WG chair (Dorothy) to start the comment collection
  30-day comment collection window opens

## Slide 68: Teleconference Schedule
  Confirmed:
    January Interim
    January 18 (Tuesday), 9am - 11:00am ET January 19 (Wednesday), 9am - 11:00am ET
    January 21 (Friday), 9am - 11:00am ET January 24 (Monday), 9am - 11:00am ET
    (January 28, deadline for baseline document for each topic (in the initial list) to be uploaded)
    February 7 (Monday), 9am - 11:00am ET February 8 (Tuesday), 9am - 11:00am ET
    February 10 (Thursday), 10pm - 12:00am ET
    February 14 (Monday), 9am - 11:00am ET February 15 (Tuesday), 9am - 11:00am ET
    February 17 (Thursday), 10pm - 12:00am ET
    February 22 (Tuesday), 9am - 11:00am ET
    February 24 (Thursday), 10pm - 12:00am ET
    February 28 (Monday), 9am - 11:00am ET March 1 (Tuesday), 9am - 11:00am ET
    March 3 (Thursday), 10pm - 12:00am ET
  To be confirmed:
    March 2022 IEEE Plenary (March 13-18 7-15) (Deadline for contributions to pass motion and be included in D0.1)
    March 8 (Tuesday), 9am - 11:00am ET
    March 9 (Wednesday), 9am - 11:00am ET
    March 9 (Wednesday), 10pm – 11:59pm ET
    March 11 (Friday), 9am - 11:00am ET
    March 14 (Monday), 9am - 11:00am ET
    Seek TGbf approval to go to comment collection (“Move to Approve a 30-day comment collection on TGbf D0.1?”)
  ** Note:
  1. when conflict with CAC, the call will be changed from 9am -11:00am to 10am -11:00am (Jan-March 2022 CAC calls (TBD): Monday February 21 and Thursday March 3 )
  2. Thursday 10pm - 12:00am ET (Thursday 7 PM - 9 PM PT, Friday 11am-1pm in China, Friday 5am-7am in Israel, Friday 4am – 6am in Central Europe), and Sang Kim will help to take the minutes for these slots.

## Slide 69: TGbh Closing Report
Date: 2022-01-21
Authors:

## Slide 70: Abstract
This document is the closing report for TGbh
“Randomized and Changing MAC addresses” (RCM)
January 2022 Plenary Session (virtual)

## Slide 71: Work Completed
Agenda is here: 11-21/1995r6
Latest Issue Tracking document: 11-21/0332r29
Contributions reviewed (solutions direction, some with draft text):
  11-22/0117r0 : Secure Device ID exchange concept
  11-22/0118r0 : IRMA with ID Query
  11-22/0145r0 : STA identifier way forward
  11-22/0154r0 : Opaque device ID
  11-22/0158r0 : STA generated Device ID
  11-22/0157r0 : MAC Address designation MAAD
  11-21/1634r2 : Non-MAC device identifier requirements for TGbh (partially reviewed)
Missed target for D0.1, again, out of this session, timeline update needed

## Slide 72: Next steps
Consider proposed solutions for impacted features/functions, and incorporate into D0.1
Review what items remain open, for a complete D1.0
Still targeting D1.0 out of March – need to consider if that is feasible
WBA liaison response

## Slide 73: Timeline
  PAR approved Feb 2021
  First TG meeting Mar 2021
  D0.1 Jan 2022
  Initial Letter Ballot (D1.0) Mar 2022
  Recirculation LB (D2.0) Jul 2022
  Initial SA Ballot (D3.0) Nov 2022
  Final 802.11 WG approval Mar 2023
  802 EC approval May 2023
  RevCom and SASB approval May 2023

## Slide 74: Teleconference(s)
Feb 8, 9:00-11:00 ET
Feb 17, 17:00-19:00 ET
Feb 22, 9:00-11:00 ET
Mar 3, 17:00-19:00 ET

## Slide 75: March 2022 Plans
Four meeting slots planned
Consider “solutions” to use cases that are in 802.11 scope to resolve
Formulate D1.0

## Slide 76: TGbi Closing Report
Date: 2022-01-21
Authors:
Name | Affiliation | Address | Phone | Email
Carol Ansley | Cox Communications |  | +1 404 229 1672 | carol@ansley.com

## Slide 77: IEEE 802.11 TGbi – January 2022
TGbi met three times during this interim session.
We reviewed 5 technical presentations on proposed requirements based on the use cases and issues in doc 21/641.
We discussed but have not yet approved the Use case and Issue document (21/641). It will be addressed in an upcoming teleconference.
The timeline is unchanged.
Upcoming teleconferences:
  February 10, 9am-10amET
  February 17, 9am-10amET
  February 24, 9am-10amET
  March 3, 9am-10amET

## Slide 78: Timeline
TG use case start: March 2021
Use case completion: January 2022
Features identified: July 2022
LB initial: March 2023
LB re-circ: September 2023
Ballot Pool: May 2024
MDR: May 2024
SA ballot: July 2024
SA re-circ: January 2025
802.11/EC approval: July 2025
RevCom/SASB approval: September 2025

## Slide 79: ITU AHG Closing Report for January 2022 Interim
Date: 2022-01-20
Authors:

## Slide 80
    Had one Session: Thu 01/20 16:00 EST
    IEEE 802 Recommendations on M.1450-5 & M.1801-2 (based on ITU –AHG recommendations) discussed in WP 5A Meeting 2021-11-15 to 2021-11-26
    [ 439 ] Proposed modification to Recommendation ITU-R M.1801-2, IEEE
    [ 438 ] Proposed modification to Recommendation ITU-R M.1450-5, IEEE
  Chair provided an overview update on 12 other contributions submitted to WP 5A Nov 2021 meeting on revising M.1450 & M.1801and went through the two working documents towards the preliminary drafts as the outcome of the meeting captured in the WP 5A Chairman report
    ITU-R M.1450-5 - “Characteristics of broadband radio local area networks” (Annex 15 to Doc. 5A/491)
    ITU-R M.1801-2 – “Radio interface standards for broadband wireless access systems, including mobile and nomadic applications, in the mobile service operating below 6 GHz” (Annex 16 to Doc. 5A/491).
    Next Steps
      To develop two new contributions on M.1450 and M.1801 for submission to the next WP5A meeting
      Working Party 5A Next Meeting Dates
        Monday 2022-05-23 - Friday 2022-06-03
    Next AHG Meeting: Feb 24, 2022, 12-13 ET (9-10AM PT)
    Meeting Minutes: 11-21-1386-00-0itu

## Slide 81: Internal Liaisons

## Slide 82: 802 Technical Plenary Liaison Report
Date: 2022-01-16
Authors:

## Slide 83: 802 Technical Plenaries
802 held virtual Technical Plenaries on Dec 2, 2021 and Jan 13, 2022.
  Agendas:
    https://1.ieee802.org/2021-12-technical-plenary-agenda/
    https://1.ieee802.org/2022-01-technical-plenary-agenda/
Next meeting, March 3
Mark Hamilton, Ruckus/CommScope

## Slide 84: Stated goals
This series of meetings would:
Provide wider awareness for the need to revise IEEE Std 802
Provide an opportunity to discuss the content – notably should it be the same or should it add more architecture
Provide examples of the current 802 architecture (i.e., spread around in 802, .1Q, .1AC, .3, .11, .15.x, …)
Identify gaps in the current architecture
In addition, this would provide the opportunity to discuss technical points across all WGs, for example:
MAC address privacy
Data privacy
Protocol IDs and their encoding – Length/Type and LLC
Attendance is open to all 802 WG participants. WG chairs are invited to identify at least one voting member to attend.

## Slide 85: Major Topics
December 2021:
History of 802
Questions about the IEEE 802 Architecture
Development of IEEE Std 802 revision/update PAR(s) and CSD(s)
802.1 and 802.15 compatibility
January 2022:
Nendica report on options for IEEE Std 802 revision PAR & CSD
Presentation on IEEE Std 802E and P802.1AEdk
Presentation on IEEE P802.11bh
Presentation on IEEE P802.11bi

## Slide 86: Next steps
General agreement for two (or more) projects:
“Simple revision” of IEEE Std 802-2014, rolling in 802c, 802d, and 802f. Limited scope, to stay on quick schedule, and complete revision before 2024 (10 years from 2014) deadline when IEEE Std 802 will become “inactive”.
  Nendica is developing PAR (no CSD needed), and 802.1 will complete the process
  Targets: March 24 (2022) for SASB approval of PAR; September 2024 for RevCom/SASB approval of revision
A comprehensive amendment:
  Consider truly adding an 802 “architecture”, which is not currently present
  Consider work from ELLA (Evolved Link Layer Architecture) in Nendica
  Targets: May/June 2022 agreement on PAR(s) scope, and number of PAR(s); Sept 2022 for SASB approval of PAR(s)
Intention on the above projects is that all 802 active members can participate and vote on the projects

## Slide 87: 802.15
No report

## Slide 88: IEEE 802.18 RR-TAG Electronic Wireless Interim Liaison from 802.18 to 802.11
Date: 17 January 2022
Authors:

## Slide 89: 802.18 Radio Regulatory Technical Advisory Group – RR-TAG
Number of voters: 40 (8 on LMSC); Nearly Voters: 4; Aspirant members: 6
Officers or the RR-TAG / IEEE 802.18:
  Chair is Jay Holcomb (Itron)
  Co-Vice-chair Stuart Kerry (OK-Brit, self)
  Co-Vice-Chair Al Petrick (Skyworks Solutions)
  Secretary is open –
  Schedule this Wireless Interim
    Thursday 20th 15:00et, 1hr, opening
    Thursday 27rd 15:00et, 1hr, closing
    These meetings do require registration with payment of fee and will have voting participation credit.
WEBEX MEETING
See IEEE 802 overall calendar ( & under 802.18 calendar)
Using same call-in as our weekly meetings.

## Slide 90: 802.18 meeting discussion items – EU Standards
Will discuss what members have to share on EU activities in ETSI, CEPT, etc.
ETSI – <BRAN> next call #113, 04-14feb22 (dates are set through 2024.) Many other calls also setup.
  CEPT – <ECC> (and general items) next call, #58 01-04mar22, hybrid/ECO/tbd
  CEPT has reported virtual meetings only till mid-February.
  From their November meeting: https://cept.org/ecc/groups/ecc/news/57th-ecc-plenary-meeting-2-5-november/
    New Work item on WAS/RLAN in 6425-7125 MHz: the ECC agreed on the new WI on the basis that, inter alia, no regulatory measures shall be taken under this WI and that the work in preparation for WRC-23 agenda item 1.2 will run independently from the work conducted under this work item.
  CEPT – ECC <SE45> next call #15, 03-04mar22, web-meeting

## Slide 91: 802.18 meeting discussion items - non-EU stds and USA activities
APAC update: will be doc 18-22/0001r00
Recent consultations / activities:
  India: The Use of Low Power Equipment in the Frequency Band 865-868 MHz for Short Range Devices (Exemption from Licence) Rules, 2021, is published in the Gazette of India on December 13, 2021, and in the DoT website on December 16, 2021:
  Korea MSIT has recently begun two consultations related to the use of 5925 to 6425 MHz band for subway/passenger cars.
    5925 ~ 6425 250mW or less Wireless devices used in subway/passenger cars. Including antenna absolute gain.
    5925 ~ 6425 2dBm/MHz or less The power density including the absolute gain of the antenna should be an average value. Limited to devices installed and operated by being connected to the power source in subway/passenger cars, or devices communicating with this device.
  Hong Kong HKCA’s consultation on lower 6 GHz band for Wi-Fi, including compulsory AP certification, the consultation was closed on December 24, 2021, and the list of submissions is recently posted: https://www.coms-auth.hk/en/policies_regulations/consultations/completed/tele_services/index_id_2362.html

## Slide 92: 802.18 meeting discussion items – ITU-R
Will discuss what members have to share on ITU-R,
802.18 does have standing by for this spring (2022): Additional WP 1A light communications and 2 WP 5A submissions from IEEE 802.

## Slide 93: General Discussion Items
27 January 2022 FCC Open Commission Meeting; 10:30 am – 12:30 pm EST, one of the topics:
Facilitating Better Use of 'White Space' Spectrum; https://www.fcc.gov/document/facilitating-better-use-white-space-spectrum
  Much on the data base operation and working with wireless microphones.

## Slide 94: General Discussion Items – ongoing fyi – will find out what is the latest
1. The WInnforum “6 GHz Committee”, some docs: https://6ghz.wirelessinnovation.org/work-group-products
    https://www.wirelessinnovation.org/6ghz-multistakeholder-committee
    For access to documents from the committee, can request to be an observer from the MSG “Group” below.
    Org: 2 focus areas:
      1) AFC Functional Specification -WG – includes: Interference-TG, Incumbent Info-TG, security and Protocols TG
      2) AFC Test and Certification-WG
    General activity picking up.
    Last week, it was reported this committee is moving forward proposing test bench equipment certifications, while others are looking at using the cloud.
2. From the FCC 6 GHz R&O, an informal MSG (“Group”)
  https://groups.wirelessinnovation.org/wg/6MSG/dashboard.
      Work stream 1 - interference protection and resolution (CableLabs, EPRI, Lake Cty, APCO)
      Work stream 2 - correct incumbent data (ULS) (Comsearch, APCO)
      Work stream 3 - AFC and how it provides protection, etc. (Charter, Google, UTC)
      Overall Co-chairs: NPSTC, UTC, WFA, WISPA.
      General activity picking up.
  General note: reported on 16dec21: A public notice is expected in January about work needed on improving the ULS data.

## Slide 95: General Discussion Items – ongoing fyi – IEEE 802 Wireless Standards Table of Frequency Ranges
General discussions include progress on IEEE 802 Wireless Standards - Table of Frequency Ranges
This is a joint effort by 802.18 and 802.19
  Ad hoc calls, the 4th Tuesday of the month, the next is 22Feb22, 15:00et.
Problem statement
  It is difficult for 802 wireless standards developers to quickly and accurately identify all the frequency bands by the family of 802 wireless standards in a regularly maintained database.
  The primary application is to simplify identification of potential frequency bands for coexistence assessment.
Initial Audiences:
  1) 802 wireless standards developers & 2) 802.19 wireless coexistence working group
The spreadsheet is going, always look for latest:
  https://mentor.ieee.org/802.18/dcn/21/18-21-0036-10-0000-frequency-table-template.xlsx
  Will share the current table and some of the basics.
From ad hoc call on 11jan22
  Moving forward will copy into a new 2022 document rev0 (22/0009r00) and are working on a process to get comment collection on the spreadsheet from other IEEE 802 members.

## Slide 96
Thank You
  Schedule this Wireless Interim
    Thursday 20th 15:00et, 1hr, opening
      Will do an epoll about May’s wireless on how to hold the meeting, electronic, mixed-mode or in-person.
    Thursday 27th 15:00et, 1hr, closing
WEBEX MEETING
See 802.18 webpage or IEEE 802 overall calendar ( & under 802.18 calendar)
or : Join from this meeting link
https://ieeesa.webex.com/ieeesa/j.php?MTID=m91b36f4c80de69b002c6b1e7296833ef
Join by meeting number
Meeting number (access code): 2348 296 5390
Meeting password: rrtag22a
this is the call-in used for the weekly 802.18 call thursday’s at 1500et )
******which btw all are welcomed at the .18 weekly meetings on Thursdays. ******

## Slide 97: January 2022 802.19 Liaison Report
Date: 2022-01-17
Authors:
Notice: This document has been prepared to assist IEEE 802.19. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.

## Slide 98: Voters and Voting Rights
IEEE 802.19 has 50 voting members
This meeting provides attendance credit towards voting rights
You must pay the registration fee in order to attend
If you have not already done so, you can register https://touchpoint.eventsair.com/ieee-802-wireless-interim-session-jan-2022

## Slide 99: Coexistence Assessment Documents
The IEEE 802.19 WG held a letter ballot on the approval of the IEEE 802.11bb Coexistence Assessment (CA) document which closed on January 10
The results were as follows:
  Approve: 22
  Disapprove: 2
  Abstain: 2
  The ballot passed
  Five comments were collected and sent to the 802.11 working group

## Slide 100: March 2022 Working Group Elections
The Working Group will hold elections for the WG Chair and WG Vice Chair at the March 2022 (Electronic) Plenary Session
  The current WC Chair (Steve Shellhammer) plans to run again for WG Chair
  The current WG Vice Chair (Tuncer Baykas) plans to run again for WG Vice Chair
If anyone else is interested in running for either the WG Chair or the WG Vice Chair position, please email the WG Chair (Steve) by March 1

## Slide 101: ePolls Regarding the May Wireless Interim
Current ePoll survey, closing on Monday January 24.
  If the 2022 May 802 Wireless Interim Session is held in Warsaw Poland as an in-person only session, will you attend?
    Yes/No
  If the 2022 May 802 Wireless Interim Session is held in Warsaw Poland as a mixed-mode session, will you attend:
    Attend In-person
    Attend Virtually (remotely)
    Will not attend plenary
The IEEE 802 Wireless Chairs committee will meet on February 2 and at that time will decide if the May Wireless Interim session will be held as a Mixed Mode (combination of in-person and on-line) meeting or as a fully on-line meeting

## Slide 102: IEEE 802 Frequency Tables – Activity
IEEE 802.18 and 802.19 continue to jointly develop a Spreadsheet for IEEE 802 Frequency Table providing information about the Frequency Bands used by various 802 Standards/Amendments
Steve Shellhammer has been the 802.19 representative
The group has agreed on the format of the Frequency Table
Refinements have been made over the last few meetings
Recently Steve S. and Eduard Au providing input on the various 802.11 PHY Amendments
  Detailed Frequency Bands for each PHY is under development
The latest working version of the Frequency Table document is available on Mentor,
  https://mentor.ieee.org/802.18/dcn/21/18-21-0036-07-0000-frequency-table-template.xlsx
Anyone who wants to participate please reach out to Jay or Steve

## Slide 103: Schedule

## Slide 104: External Liaisons